## Sheet1
WEEKLY SCHEDULE
PROJECT JXPXXXX / CONTRACT ID 1XXXXX-XX
SCHEDULE # | 6
START DATE | 2014-06-02 |  | Items in Red must be filled out
END DATE | 2014-06-16
DATE | WORK ACTIVITY W/LOCATIONS | HOLD POINTS | PREACTIVITY MEETINGS | TRAFFIC CONTROL EVENTS | COMMENTS
| Install Storm Line D (Inlet D1 to Inlet D3) | Prior to Backfill of Line D (1PM) | 9AM - RCB wall pour | Inside lanes remain closed 15+00 to 27+00 | Weekly Progress Meeting at 10AM.
| Placing wall steel for 5x5 RCB at 4+00 | PCCP Prepour Check (7AM)
2014-06-02 | Pave 23+34 to 26+00 (NB Inside Lane) |  |  |  | New 2 Week Look Ahead Issued - No. 6
1900-01-01 | Trim Base Rock 0+00 to 3+24 (Rte. BB)
Workhours through end of project 7AM-5PM (M-F)
| Install Storm Line D (Inlet D3 to D5) | Prior to Backfill of Line D (1PM) | 10AM - C&G construction | Inside lanes remain closed 15+00 to 27+00
Placing wall steel for 5x5 RCB at 4+00
2014-06-03
1900-01-02
| Finish Storm Line D (D5 - D9) | Rte. BB Base Rock Review (8AM) |  | Inside lanes remain closed 15+00 to 27+00
| Form C&G - 0+00 to 3+24 RT (Rte. BB) | Prior to Backfill of Line D (1PM)
2014-06-04 | Placing wall steel for 5x5 RCB at 4+00 | C&G Prepour Check- Rte. BB RT (2PM)
1900-01-03
| Finish Steel Placement for 5x5 RCB at 4+00 | Review 5x5 RCB Steel (8AM) | 3PM - Review Rte. BB Intersection Closure | Inside lanes remain closed 15+00 to 27+00
| Form walls 5x5 RCB at 4+00 | C&G Prepour Check- Rte. BB LT (2PM)
2014-06-05 | Install C&G - 0+00 to 3+24 RT (Rte. BB)
1900-01-04 | Form C&G - 0+00 to 3+24 LT (Rte. BB)
| Install Storm Line A (Inlet A1 - Inlet A3) | Rte. BB Int. Closure Traffic Control (7:45AM) | 8AM - Concrete Medians | Close Intersection at Rte. BB for Storm Line A Crossing (Closed 8AM - 12PM)
| Form walls 5x5 RCB at 4+00 | Prior to Backfill of Line A (10AM)
2014-06-06 | Install C&G - 0+00 to 3+24 LT (Rte. BB) |  |  | Inside lanes remain closed 15+00 to 27+00
1900-01-05
| NO WORK |  |  | Inside lanes remain closed 15+00 to 27+00 | Light Poles scheduled for delivery.
2014-06-07
1900-01-06
| NO WORK |  |  | Inside lanes remain closed 15+00 to 27+00
2014-06-08
1900-01-07
| Form walls 5x5 RCB at 4+00 | 5x5 RCB Prepour Check | 11AM - MSE Wall Construction - Subcontractor must be present | Inside lanes remain closed 15+00 to 27+00 | Weekly Progress Meeting at 10AM.
| Form concrete median 25+00 to 26+00 | Concete Median Check
2014-06-09 |  |  | 1PM - Asphalt Pavement Construction | Change CMS Message for 6/16 traffic shift | New Weekly Schedule Issued - No. 7
1900-01-08
Notify Businesses and City of traffic shift on 06/16/14.
| Pour 5x5 RCB at 4+00 | 15+00 to 27+00 Traffic Control |  | Inside lanes remain closed 15+00 to 27+00
Install concrete median 25+00 to 26+00
2014-06-10 | Pour leveling pad for MSE Wall
1900-01-09
| Install SP125B - 0+00 to 3+24 (Rte. BB) | Concete Median Check | 1PM - Seed & Mulch | Inside lanes remain closed 15+00 to 27+00
| Form concrete median 16+00 to 19+00 | Asphalt Laydown Check
2014-06-11
1900-01-10
| Install SP125B - 0+00 to 3+24 (Rte. BB) | Asphalt Laydown Final Check |  | Inside lanes remain closed 15+00 to 27+00
| Install concrete median 16+00 to 19+00 | MSE Wall Material & Pad Accepted
2014-06-12 | Finish Grade Rte. BB
1900-01-11
| Pavement Marking Prep Rte. BB |  | 9AM - Pavement Marking | Inside lanes remain closed 15+00 to 27+00
Seed/Mulch Rte. BB
2014-06-13 | Construct MSE Wall |  | 2PM - Traffic Switch 15+00 to 27+00 Review
1900-01-12 | General Clean-Up
Prep for 6/16 Traffic Switch
| No Work |  |  | Inside lanes remain closed 15+00 to 27+00
2014-06-14
1900-01-13
| No Work |  |  | Inside lanes remain closed 15+00 to 27+00
2014-06-15
1900-01-14
| Traffic Switch | 15+00 to 27+00 Traffic Control | 1PM - Lights/Signals | Open inside lanes remain 15+00 to 27+00 at 9AM | Weekly Progress Meeting at 10AM.
Remove 5X5 RCB Forms
2014-06-16 | Construct MSE Wall |  |  | Close outside lanes from 15+00 to 27+00 at 9AM | New Weekly Schedule Issued - No. 8
1900-01-15
Make sure MoDOT Traffic attends preactivity
Formulas:
DATE = DAY([DATE, row above])