|  | Missouri Department of Transportation Aviation Section Revision 03/15/10 |  |
| --- | --- | --- |

### PREPARATION OF PROJECT PLANS AND SPECIFICATIONS

### STATE AVIATION TRUST FUND PROGRAM

The development requirements of a Sponsor are typically conveyed to prospective bidders through the preparation of plans and specifications. Project plans (drawings) serve to graphically depict the extent of the development requirements in an accurate and concise manner. The project specification in contrast serves to convey technical information for quality acceptance, performance characteristics, and permissible construction methods.

In addition to the plans and specifications, bid documents and contract documents are prepared to convey to prospective contractors all bidding requirements and contractual obligations expected of the successful bidder. The bid documents and contract documents are commonly bound with the project specifications to form a project manual.

It is important to note that the Sponsor is responsible for all matters concerning contract procurement for a project. The Sponsor is also the contractual authority for all matter related to establishing and administering the contract agreement. MoDOT is not a party to such contract agreements.

The Sponsor and their engineering consultant are also responsible for the accuracy, completeness, legal sufficiency and technical content of the contract plans and specifications. Reviews conducted by MoDOT are limited to the purpose of determining State Aviation Trust Fund eligibility and adherence with FAA Standards.

Submittal Requirements

The sponsor shall submit one set of 100% plans and specifications to the MoDOT Aviation Section for review and concurrence. When the Sponsor receives written authorization to advertise for bids from MoDOT, two complete sets of the bidding documents (sealed, signed, and dated by the engineer) shall be submitted to MoDOT.

MoDOT Review and Approval

The approval of plans and specifications is based on a MoDOT cursory review. The review by MoDOT is generally limited to critical project elements such as the safety plan, pavement details, airfield marking details, and airfield lighting details. MoDOT will not typically review detailed engineering and quantity calculations, however such documentation shall be made available if so requested by MoDOT. The primary purpose of MoDOT's review is to verify that applicable FAA standards are being applied as well as to make a determination regarding the limits of State Aviation Trust Fund eligibility.

The sponsor and their consultant shall allow sufficient time for MoDOT to conduct an appropriate review. This may vary per size and type of project. Generally, a review time frame of 4 weeks is requested. Upon receipt of MoDOT review comments, the Sponsor or their consultant shall provide a written response to each comment made by MoDOT that addresses how the comment was resolved. Authorization to advertise for bids will generally not be granted until the plans and specifications are deemed acceptable by MoDOT for State Aviation Trust Fund participation. Sponsors shall note that MoDOT approval in the plans and specifications does not relieve the Sponsor of the responsibility to correct items of work later found to be non-compliant with regards to FAA Standards.

Project Drawings

The project-drawing package serves to graphically depict the extent of the contract requirements in an accurate and concise manner. The project drawings, along with the technical specifications, form a critical part of the Contractor’s contractual obligations. As a legal document, the contract drawings must convey the requirements of the sponsor in a clear and unambiguous manner.

Projects funded under the State Aviation Trust Fund shall be developed in accordance with applicable FAA standards. FAA standards are contained within various Advisory Circulars and engineering briefs and are also supplemented by regional guidance.

Responsibility of Sponsor and Engineer

The sponsor and their consultant assume the responsibility for the accuracy, completeness, and technical content of the contract drawings. The engineer shall apply sound engineering judgment and widely accepted engineering principals when preparing project drawings.

Typical Project Plans

A typical drawing package will generally consist of the following sheets. A suggested outline of items to be addressed on each sheet can be found on the Construction Plans Checklist which is available on the MoDOT Aviation website under MoDOT Construction Specifications. This outline should not be construed as being inclusive of all such necessary drawings and associated details and elements. The engineering consultant shall apply "best practice" judgment in determining the extent of the drawing package for each specific project.

- Cover Sheet

- Project Layout Plan

- Safety and Phasing Plan (see Safety Plan requirements below)

- Typical sections

- Runway Plan and Profile

- Taxiway Plan and Profile

- Grading and Drainage Plan

- Pavement Joint Plan

- Pavement Marking and Signing Plan

- Lighting Plan

- Cross Sections

- Miscellaneous

Safety Plan

Construction activities within the operations areas of an airport have the potential to significantly compromise normal operational safety for aircraft. Careful planning and implementation of mitigating measures will greatly minimize the impact construction activities may have on normal airport operations.

Advisory Circular 150/5370-2E establishes FAA guidelines to assure operational safety on airports during construction activities. Adherence to these guidelines is mandatory for all construction projects funded in whole or in part by the State Aviation Trust Fund.

Airport Operator's Responsibility

The airport operator is ultimately accountable for assuring operational safety at their airport during construction activities. The airport operator fulfills its obligation by several measures such as: preparing a comprehensive safety plan for each project, conducting routine meetings that address airport safety concerns, monitoring the implementation of safety plan measures and informing tenants of construction activities.

Safety Plan

As each project will vary per size and complexity, the required safety plan for each project should be customized for the unique conditions associated with the specific project and airport. It is important to note that while AC 150/5370-2E establishes the FAA standards for operational safety during construction, this Advisory Circular is not intended to serve as the safety plan. Simply incorporating this Advisory Circular into the contract documents does not fulfill the airport operator's responsibility to prepare a safety plan for the specific project.

Minimum Requirements

The Sponsor of the State Aviation Trust Fund project, through their consultant engineer, shall identify minimum requirements for operational safety during construction activities at their airport. This includes but is not limited to acceptable construction sequencing, pavement closures, hazard identification, AOA security concerns, and airfield communication. These requirements are best conveyed to the Contractor by graphical representation on a drawing sheet labeled "Safety Plan". Considering that construction sequencing is an integral element of the safety plan, the project phasing requirements are often combined with the safety plan requirements on a drawing labeled "Safety and Phasing Plan".

Chapter 2 of AC 150/5370-2E provides a recommended checklist that addresses suggested elements of a safety plan. Chapter 3 addresses guidelines for various situations and conditions that would compromise normal operational safety. Appendix 3 provides a sample safety plan template for the benefit of the sponsor.

MoDOT Review

MoDOT will conduct a cursory review of all safety plans to determine if appropriate requirements and measures are incorporated. Sponsors may not proceed with commencing work activities unless approval of the safety plan has been granted. Any changes to the approved safety plan shall be submitted to MoDOT for review and concurrence.

The Safety Plan and the Contractor

The Contractor is obligated to implement the requirements of the "approved" safety plan. By identifying the minimum requirements of the safety plan in the bid package, prospective contractors have a sound basis for estimating the cost of implementing measures associated with the safety. The successful Contractor would then be required to identify how they intend to comply with the requirements of the safety plan.

We strongly discourage the practice of assigning the responsibility of preparing a safety plan to the successful contractor. Such a practice can introduce contract legal issues and create vague and ambiguous safety plan measures. By not identifying minimum safety plan requirements within the bid package; it may be possible for the Contractor to seek additional compensation for required operational safety restrictions that were not clearly identified within the bid package. Sponsor should take into consideration that the project incentive for most Contractor's is based on profit. Furthermore, the Sponsor remains accountable for all construction activities on their airport. It is not prudent for the Sponsor to assign the responsibility of preparing a safety plan to the Contractor while retaining the associated risk.

We strongly recommend identifying minimum safety plan requirements within the bid package. If the contractor proposes construction sequencing that differs from that developed by the Sponsor, the Contractor would then be responsible for identifying acceptable revisions to the approved safety plan at no additional cost to the Sponsor. Such revisions would require approval by the Sponsor and MoDOT.

Project Manual

Typically, engineering consultants combine the bid documents, contract documents and technical specifications of a project into one bound document commonly referred to as the Project Manual. This document serves to convey to the Contractor the contractual and technical requirements of a construction project. The Project Manual also serves a critical role as part of the bid documents.

The Project Manual will generally consist of the following elements:

- Notice to bidders

- Instructions to Bidders

- General Provisions

- Supplementary Provisions

- Technical Specifications

- Advisory Circulars

- Proposal Form

- Performance Bond

- Payment Bond

- Contract Agreement

Suggested Forms for Construction Contracting

For the benefit of the Sponsor, we have prepared a suggested sample project manual boilerplate (State-Preparation of Project Plans and Specifications) that the Sponsor may use as a guide in preparing his or her own specific bid package.

Sponsors and Consultants are cautioned that this suggested sample is not to be considered as being complete and whole and that the provision of such suggested sample contract documents by MoDOT shall not be construed as a guarantee of legal sufficiency. Sponsors are solely responsible for verifying the legal sufficiency of all matters concerning procurement and contracting.

Technical Specifications

Projects funded under the State Aviation Trust Fund must be developed in accordance with FAA established standards.

MoDOT and FAA Standards

FAA Advisory Circular 150/5370-10 contains the FAA standards for specifying construction of airports and airport related development. These standards may be supplemented by various engineering briefs issued by Airport Engineering Division of the Office of Airport Safety and Standards.

The FAA Regional Office may also supplement or amend the FAA standards for purposes of accommodating regional and local conditions that may not be adequately covered by the broader national standard. These modifications to AC 150/5370-10 are available under AIP Sponsor Guide No. 940 (FAA Central Region website).

Sponsors and their consultants must utilize AC 150/5370-10 as a guide specification when preparing a project specification. Sponsors may not modify or deviate from the accepted FAA standard unless expressed written approval is obtained from MoDOT. Sponsors desiring to make such modifications must refer to AIP Sponsor Guide No. 950 (FAA Central Region website) for the required procedure to properly request a sponsor-initiated modification to FAA standards.

While AC 150/5370-10 provides the required technical specifications for construction projects, the FAA does allow MoDOT to modify these standards to incorporate the use of State highway specifications. These modified technical specifications are available on the MoDOT Aviation website and must be utilized in the development of the project specifications. All other technical specifications related to items other than those listed on the MoDOT Aviation website shall be obtained from AC 150/5370-10 on the FAA Central Region website.

The FAA standard and MoDOT modified specifications includes several "notes to engineers" that elaborate on permissible options and modifications an engineer may choose when preparing a project specification. The engineer shall use their sound engineering judgment to make appropriate and permissible decisions that account for project specific materials, site conditions, methods and other requirements.

Procurement Requirements

The technical specifications shall be prepared and issued in a manner that promotes fair and open competition. The technical specification shall convey a clear and accurate description of the desired product, material or item. The technical description shall not contain unnecessary or proprietary requirements that would unduly restrict competition.

The use of "brand name or equal" is permitted when it is impractical to make a clear and accurate description of the technical requirement. However, acceptance shall be based on the salient characteristics of the item and not based simply on providing the named brand. The specific features of the brand name that must be met by the bidder shall be clearly stated.

Industry Standards

In the case of development items for which no FAA standard exists, the sponsor shall rely on accepted industry practice to develop the technical requirements. Such requirements shall promote fair and open competition and shall not unduly restrict competition. MoDOT reserves the right to review and approve such standards for justification and reasonableness.

# BID DOCUMENTS & TECHNICAL SPECIFICATIONS

{Appropriate changes and additions required by the notes must be made.  Where numbers, words, phrases, or sentences are enclosed in brackets {     }, a choice or modification must be made.  Where blank spaces {       } occur in sentences, the appropriate data must be inserted.  Explanatory notes, shown in brackets and bold-type, should be deleted when printed in final form.}

TABLE OF CONTENTS

SECTION 1

NOTICE TO BIDDERS	  2

SECTION 2

INSTRUCTIONS TO BIDDERS	  4

SECTION 3

GENERAL PROVISIONS	  5

SECTION 4

SUPPLEMENTARY PROVISIONS	 60

Part A – STATE REQUIREMENTS	 60

Part B  - LOCAL PROVISIONS	 66

Part C  - STATE WAGE RATES	 67

SECTION 5

TECHNICAL SPECIFICATIONS	 68

APPENDIX

ADVISORY CIRCULARS	 69

PROPOSAL/FORMS

PROPOSAL FORM	 70

PERFORMANCE BOND	 75

PAYMENT BOND	 77

CONTRACT AGREEMENT	 79

SECTION 1

NOTICE TO BIDDERS

{OWNERS NAME}

{AIRPORT NAME}

Project No. {MoDOT PROJECT NUMBER}

Sealed bids subject to the conditions and provisions presented herein will be received until {TIME}, {DATE}, and then publicly opened and read at {LOCATION WHERE BIDS ARE TO BE OPENED}, for furnishing all labor, materials, equipment and performing all work necessary to {BRIEF AND CONCISE DESCRIPTION OF PROJECT}.

Copies of the bid documents including project drawings and technical specifications are on file and may be inspected at:

{OFFICE LOCATIONS FOR VIEWING PLANS AND SPECIFICATIONS}

A complete set of bid documents may be obtained from the {OFFICE LOCATION FOR OBTAINING BID DOCUMENTS} for a fee of $ {REASONABLE VALUE APPROPRIATE FOR THE SIZE OF THE PROJECT AND STATE WHETHER DEPOSIT/FEE IS REFUNDABLE}.

A prebid conference for this project will be held at {TIME, DATE AND LOCATION OF THE PREBID CONFERENCE}.

Contract Work Items.  This project will involve the following work items and estimated quantities. Prospective bidders are hereby advised that the quantities indicated herein are approximate and are subject to change.

| 1. Mobilization | Lump Sum |
| --- | --- |
| 2. Class A Excavation | 42,500 C.Y. |
| 3. Crushed Aggregate Base Course | 5,200 Tons |
| 4. Mineral Aggregate (BP-1 Mix) | 1,625 Tons |
| 5. Asphalt Cement (BP-1 Mix) | 85 tons |
| 6. Bituminous Prime Coat. | 6,000 Gals. |
| 7. Runway Pavement Marking (White) | 5,000 S.F. |
| 8. Seeding | 18 Acres |
| 9. Runway End Identification Light (REIL) System | Lump Sum |

Contract Time.  The owner has established a contract performance time of {NUMBER OF DAYS} calendar days from the date of the Notice-to-Proceed. All project work shall be substantially completed within the stated timeframe. This project is subject to liquidated damages as prescribed in the project manual.

Bid Security.  No bid will be considered unless accompanied by a certified check or cashier’s check on any bank or trust company insured by the Federal Deposit Insurance Corporation, payable to {NAME OF SPONSOR}, for not less than five (5) percent of the total amount of the bid, or by a bid bond secured by an approved surety or sureties, payable to the owner, for not less than five (5) percent of the total amount of the bid.

Bonding Requirements.  The successful bidder will be required to furnish separate performance and payment bonds each in an amount equal to 100% of the contract price at the time of contract execution.

Award of Contract.  All proposals submitted in accordance with the instructions presented herein will be subject to evaluation. Bids may be held by the {NAME OF SPONSOR} for a period not to exceed {NUMBER OF DAYS} from the date of the bid opening for the purpose of conducting the bid evaluation.

Award of contract will be based on the lowest aggregate sum proposal submitted from those bidders that are confirmed as being responsive and responsible. If more than one base bid is listed in the Proposal Form, the bidder may bid on Base Bid No. 1 and/or Base Bid No. 2.  The owner reserves the right to select any one of the combinations of the base bid(s) and alternate bid(s), which in the judgment of the owner, best serves the owner’s interest. The right is reserved, as the {NAME OF SPONSOR} may require, to reject any bid and all bids.

Award of contract is contingent upon the owner receiving State-funding assistance under the State Aviation Trust Fund.

State Wage Requirements.  The contractor will be required to comply with the wage and labor requirements and pay minimum wages in accordance with the schedule of wage rates established by the Missouri Division of Labor Standards included in the Supplementary Provisions.

Additional Provisions.

Modification to the project documents may only be made by written addendum by the Owner or Owner’s authorized Representative.

The proposal must be made on the forms provided within the bound project manual. Bidders must supply all required information prior to the time of bid opening.

SECTION 2

# INSTRUCTIONS TO BIDDERS

# This section contains excerpts of the bidding requirements from Section 20 of the General Provisions. The bidder’s attention is directed to Section 20 for complete details.

1.	THE EXECUTED PROPOSAL FORM MUST BE SUBMITTED IN THE ORIGINAL BOUND PROECT MANUAL.  NO INDIVIDUAL ELEMENTS OF THE PROJECT MANUAL MAY BE REMOVED OR DETACHED.

2.	The apparent low bidder shall submit ``evidence of competency'' and ``evidence of financial responsibility'' to the owner no later than 3 business days after the specified date for opening bids.

3.	Each bidder shall certify in the Proposal Form at the time of bid submittal that they acknowledge receipt of all issued addenda.

4.	No bid will be considered unless accompanied by a certified check or cashier’s check on any bank or trust company insured by the Federal Deposit Insurance Corporation, payable to the owner, for not less than five (5) percent of the amount of the bid, or by a bid bond secured by an approved surety or sureties (licensed to conduct surety business in the state of Missouri), payable to the owner, for not less than five (5) percent of the amount of the bid.

5.	Proposals shall be sent to arrive at the time and date specified in Section 1, Notice to Bidders. Proposals received after the specified time and date will not receive consideration and will be returned unopened.  Prior to submittal, the proposal shall be placed in a sealed opaque envelope and addressed to:

{OFFICE LOCATION IDENTIFIED IN THE NOTICE-TO-BIDDERS}

The upper left hand corner of the envelope should be marked as follows:

Sealed Bid Proposal

Bid of NAME OF BIDDER

For construction improvements at {AIRPORT NAME}

Project No.: {MoDOT PROJECT NUMBER}

To be opened at: {TIME AND DATE FOR RECEIPT OF BIDS}

For a modification to a previously submitted proposal, insert “Modification to Proposal” in place of “Sealed Bid Proposal”.

6.	The Owner reserves the right to reject any or all bids, as determined to be in the best interest of the Owner. Causes for rejection of proposals include but are not limited to:

- Submittal of more than one proposal from the same partnership, firm or corporation;

- Failure by Bidder to submit the bid prior to the stated time and date for receipt of bids;

- Failure by Bidder to furnish satisfactory bid guarantee;

- Failure by Bidder to provide all information required of the bid forms;

- Failure by Bidder to comply with the requirements of bid instructions;

- Determination by the Owner that Bidder is not qualified to accomplish the project work;

- Determination by the Owner that the Bidder has placed conditions on or qualified their proposal;

- Discovery of any alteration, interlineations or erasure of any project requirement by the Bidder;

- Evidence of collusion among bidders.

# {Information regarding State sales tax exemption may be provided in this section}

# SECTION 3

# GENERAL PROVISIONS

# INDEX TO GENERAL PROVISIONS

# SECTION 10	DEFINITION OF TERMS

# SECTION 20	PROPOSAL REQUIREMENTS AND CONDITIONS

# 20-01	Bidder Qualifications

# 20-02	Bid Documents/Project Manual

# 20-03	Modifications to Project Documents

# 20-04	Errors and Discrepancies in Project Documents

# 20-05	Clarifications and Interpretations

# 20-06	Issuance of Proposal Forms

# 20-07	Interpretation of Estimated Proposal Quantities

# 20-08	Examination of Plans, Specification and Site Conditions

# 20-09	Preparation of the Bid Proposal

# 20-10	Bid Guaranty

# Submission of Bid Proposal

# Modification or Withdrawal of Bid Proposal

# Bid Opening

# Disqualification of Bid Proposals

# SECTION 30	AWARD AND EXECUTION OF CONTRACT

# 30-01	Evaluation of Proposals

# 30-02	Cancellation of Award

# 30-03	Notice of Award of Contract

# 30-04	Return of Bid Guaranty

# 30-05	Contract Agreement

# 30-06	Performance and Payment Bonds

# 30-07	Certificate of Insurance

# 30-08	Approval of Contract

# SECTION 40	SCOPE OF WORK

# 40-01	Intent of Contract

# 40-02	Alteration of Work and Quantities

# 40-03	Omitted Items

# 40-04	Extra Work

# 40-05	Maintenance of Traffic

# 40-06	Removal of Existing Structures

# 40-07	Rights In and Use of Materials Found in Work

# 40-08	Not Used

# 40-09	Final Cleaning Up

# SECTION 50	CONTROL OF WORK

# 50-01	Authority of the Engineer

# 50-02	Conformity with Plans and Specifications

# 50-03	Coordination of Contract, Plans and Specifications

# 50-04	Cooperation of Contractor

# 50-05	Cooperation Between Contractors

# 50-06	Construction Layout and Stakes

# 50-07	Automatically Controlled Equipment

# 50-08	Authority and Duties of Inspectors

# 50-09	Inspection of the Work

# 50-10	Removal of Unacceptable and Unauthorized Work

# 50-11	Load Restrictions

# 50-12	Maintenance During Construction

# 50-13	Failure to Maintain the Work

# 50-14	Partial Acceptance

# 50-15	Final Acceptance

# 50-16	Claims for Adjustments and Disputes

# SECTION 60	CONTROL OF MATERIALS

# 60-01	Source of  Supply and Quality Requirements

# 60-02	Samples, Tests and Cited Specifications

# 60-03	Certification of Compliance

# 60-04	Plant Inspection

# 60-05	Engineer’s Field Office

# 60-06	Storage of Materials

# 60-07	Unacceptable Materials

# 60-08	Owner-Furnished Materials

# SECTION 70	LEGAL RELATIONS AND RESPONSIBLITY TO PUBLIC

# 70-01	Laws to be Observed

# 70-02	Permits, Licenses and Taxes

# 70-03	Patented Devices, Materials and Processes

# 70-04	Restoration of Surfaces Disturbed by Others

# 70-05	Sanitary, Health and Safety Provisions

# 70-06	Public Convenience and Safety

# 70-07	Barricades, Warning Signs and Hazard Markings

# 70-08	Use of Explosives

# 70-09	Protection and Restoration of Property and Landscape

# 70-10	Responsibility for Damage Claims

# 70-11	Third Party Beneficiary Clause

# 70-12	Opening Section of the Work to Traffic

# 70-13	Contractor’s Responsibility for Work

# 70-14	Contractor’s Responsibility for Utility Service and Facilities of Others

# 70-15	Furnishing Rights-of-Way

# 70-16	Personal Liability of Public Officials

# 70-17	No Waiver of Legal Rights

# 70-18	Environmental Protection

# 70-19	Archaeological and Historical Findings

# SECTION 80	PROSECUTION AND PROGRESS

# 80-01	Subletting of Contract

# 80-02	Notice to Proceed

# 80-03	Prosecution and Progress

# Limitation of Operations

# 80-04.1	Operational Safety on Airport During Construction

# 80-05	Character of Workman, Methods and Equipment

# 80-06	Temporary Suspension of the Work

# 80-07	Determination and Extension of Contract Time

# 80-08	Failure to Complete on Time

# Default and Termination of Contract

# Termination for National Emergencies

# Work Area, Storage Area and Sequence of Operations

# SECTION 90	MEASUREMENT OF QUANTITIES

# 90-01	Measurement of Quantities

# 90-02	Scope of Payment

# 90-03	Compensation for Altered Quantities

# 90-04	Payment for Omitted Items

# 90-05	Payment for Extra and Force Account Work

# 90-06	Partial Payments

# 90-07	Payment for Materials on Hand

# 90-08	Payment of Withheld Funds

# Acceptance and Final Payment

# General Warranty

# Project Closeout

# SECTION 100	CONTRACTOR QUALITY CONTROL PROGRAM

# 100-01	General

# 100-02	Description of Program

# 100-03	Quality Control Organization

# 100-04	Project Progress Schedule

# 100-05	Submittals Schedule

# 100-06	Inspection Requirements

# 100-07	Quality Control Testing Plan

# 100-08	Documentation

# 100-09	Corrective Action Requirements

# 100-10	Surveillance by the Engineer

# 100-11	Noncompliance

# SECTION 110	METHOD OF ESTIMATING PERCENTAGE OF MATERIAL WITHIN SPECIFICATION LIMITS

# General

# Method of Computing PWL

# SECTION 10

# DEFINITION OF TERMS

Whenever the following terms are used in these specifications, in the contract, or in any documents or other instruments pertaining to construction where these specifications govern, the intent and meaning shall be interpreted as follows:

10-01  AASHTO.  The American Association of State Highway and Transportation Officials, the successor association to AASHO.

10-02  ACCESS ROAD.  The right-of-way, the roadway and all improvements constructed thereon connecting the airport to a public highway.

10-03  ADVERTISEMENT.  A public announcement, as required by local law, inviting bids for work to be performed and materials to be furnished.

10-04  NOT USED.

10-05  AIR OPERATIONS AREA.  For the purpose of these specifications, the term air operations area shall mean any area of the airport used or intended to be used for the landing, takeoff, or surface maneuvering of aircraft.  An air operation area shall include such paved or unpaved areas that are used or intended to be used for the unobstructed movement of aircraft in addition to its associated runway, taxiway, or apron.

10-06  AIRPORT.  Airport means an area of land or water which is used or intended to be used for the landing and takeoff of aircraft; an appurtenant area used or intended to be used for airport buildings or other airport facilities or rights of way; and airport buildings and facilities located in any of these areas, and includes a heliport.

10-07  ASTM.  The American Society for Testing and Materials.

10-08  AWARD.  The acceptance, by the Owner, of the successful bidder's proposal.

10-09  BIDDER.  Any individual, partnership, firm, or corporation, acting directly or through a duly authorized representative, who submits a proposal for the work contemplated.

10-10  BUILDING AREA.  An area on the airport to be used, considered, or intended to be used for airport buildings or other airport facilities or rights-of-way together with all airport buildings and facilities located thereon.

10-11  CALENDAR DAY.  Every day shown on the calendar.

10-12  CHANGE ORDER.  A written order to the Contractor covering changes in the plans, specifications, or proposal quantities and establishing the basis of payment and contract time adjustment, if any, for the work affected by such changes.  The work, covered by a change order, shall be within the scope of the contract.

10-13  CONTRACT.  The written agreement covering the work to be performed.  The awarded contract shall include, but is not limited to:  The Advertisement; The Contract Form; The Proposal; The Performance Bond; The Payment Bond; any required insurance certificates; The Specifications; The Plans, and any addenda issued to bidders.

10-14  CONTRACT ITEM (PAY ITEM).  A specific unit of work for which a price is provided in the contract.

10-15  CONTRACT TIME.  The number of calendar days or working days, stated in the proposal, allowed for completion of the contract, including authorized time extensions.  If a calendar date of completion is stated in the proposal, in lieu of a number of calendar or working days, the contract shall be completed by that date.

10-16  CONTRACTOR.  The individual, partnership, firm, or corporation primarily liable for the acceptable performance of the work contracted and for the payment of all legal debts pertaining to the work who acts directly or through lawful agents or employees to complete the contract work.

10-17  DRAINAGE SYSTEM.  The system of pipes, ditches, and structures by which surface or subsurface waters are collected and conducted from the airport area.

10-18  ENGINEER.  The individual, partnership, firm, or corporation duly authorized by the Owner to be responsible for engineering inspection of the contract work and acting directly or through an authorized representative.

10-19  EQUIPMENT.  All machinery, together with the necessary supplies for upkeep and maintenance, and also all tools and apparatus necessary for the proper construction and acceptable completion of the work.

10-20  EXTRA WORK.  An item of work not provided for in the awarded contract as previously modified by change order or supplemental agreement, but which is found by the Engineer to be necessary to complete the work within the intended scope of the contract as previously modified.

10-21  FAA.  The Federal Aviation Administration of the U.S. Department of Transportation.  When used to designate a person, FAA shall mean the Administrator or his/her duly authorized representative.

10-22  FEDERAL SPECIFICATIONS.  The Federal Specifications and Standards, Commercial Item Descriptions, and supplements, amendments, and indices thereto are prepared and issued by the General Services Administration of the Federal Government.

10-23  FORCE ACCOUNT.  Not used.

10-24  INSPECTOR.  An authorized representative of the Engineer assigned to make all necessary inspections and/or tests of the work performed or being performed, or of the materials furnished or being furnished by the Contractor.

10-25  INTENTION OF TERMS.  Whenever, in these specifications or on the plans, the words ``directed,'' ``required,'' ``permitted,'' ``ordered,'' ``designated,'' ``prescribed,'' or words of like import are used, it shall be understood that the direction, requirement, permission, order, designation, or prescription of the Engineer is intended; and similarly, the words ``approved,'' ``acceptable,'' ``satisfactory,'' or words of like import, shall mean approved by, or acceptable to, or satisfactory to the Engineer, subject in each case to the final determination of the Owner.

Any reference to a specific requirement of a numbered paragraph of the contract specifications or a cited standard shall be interpreted to include all general requirements of the entire section, specification item, or cited standard that may be pertinent to such specific reference.

10-26  LABORATORY.  The official testing laboratories of the Owner or such other laboratories as may be designated by the Engineer.

10-27  LIGHTING.  A system of fixtures providing or controlling the light sources used on or near the airport or within the airport buildings.  The field lighting includes all luminous signals, markers, floodlights, and illuminating devices used on or near the airport or to aid in the operation of aircraft landing at, taking off from, or taxiing on the airport surface.

10-28  MAJOR AND MINOR CONTRACT ITEMS.  A major contract item shall be any item that is listed in the proposal, the total cost of which is equal to or greater than 20 percent of the total amount of the award contract.  All other items shall be considered minor contract items.

10-29  MATERIALS.  Any substance specified for use in the construction of the contract work.

10-30  NOTICE TO PROCEED.  A written notice to the Contractor to begin the actual contract work on a previously agreed to date.  If applicable, the Notice to Proceed shall state the date on which the contract time begins.

10-31  OWNER.  The term “Owner” shall mean the party of the first part or the contracting agency signatory to the contract.  For State contracts, the term “sponsor” shall have the same meaning as the term “Owner.”  Where the term “Owner” is capitalized in this document, it shall mean airport owner or sponsor only.

10-32  PAVEMENT.  The combined surface course, base course, and subbase course, if any, considered as a single unit.

10-33  PAYMENT BOND.  The approved form of security furnished by the Contractor and his/her surety as a guaranty that he will pay in full all bills and accounts for materials and labor used in the construction of the work.

10-34  PERFORMANCE BOND.  The approved form of security furnished by the Contractor and his/her surety as a guaranty that the Contractor will complete the work in accordance with the terms of the contract.

10-35  PLANS.  The official drawings or exact reproductions which show the location, character, dimensions and details of the airport and the work to be done and which are to be considered as a part of the contract, supplementary to the specifications.

10-36  PROJECT.  The agreed scope of work for accomplishing specific airport development with respect to a particular airport.

10-37  PROPOSAL.  The written offer of the bidder (when submitted on the approved proposal form) to perform the contemplated work and furnish the necessary materials in accordance with the provisions of the plans and specifications.

10-38  PROPOSAL GUARANTY.  The security furnished with a proposal to guarantee that the bidder will enter into a contract if his/her proposal is accepted by the Owner.

10-39  RUNWAY.  The area on the airport prepared for the landing and takeoff of aircraft.

10-40  SPECIFICATIONS.  A part of the contract containing the written directions and requirements for completing the contract work.  Standards for specifying materials or testing which are cited in the contract specifications by reference shall have the same force and effect as if included in the contract physically.

10-41  SPONSOR.  See definition above of “Owner.”

10-42  STRUCTURES.  Airport facilities such as bridges; culverts; catch basins, inlets, retaining walls, cribbing; storm and sanitary sewer lines; water lines; underdrains; electrical ducts, manholes, handholes, lighting fixtures and bases; transformers; flexible and rigid pavements; navigational aids; buildings; vaults; and, other manmade features of the airport that may be encountered in the work and not otherwise classified herein.

10-43  SUBGRADE.  The soil that forms the pavement foundation.

10-44  SUPERINTENDENT.  The Contractor's executive representative who is present on the work during progress, authorized to receive and fulfill instructions from the Engineer, and who shall supervise and direct the construction.

10-45  SUPPLEMENTAL AGREEMENT.  A written agreement between the Contractor and the Owner covering  (1) work that would increase or decrease the total amount of the awarded contract, or any major contract item, by more than 25 percent, such increased or decreased work being within the scope of the originally awarded contract; or (2) work that is not within the scope of the originally awarded contract.

10-46  SURETY.  The corporation, partnership, or individual, other than the Contractor, executing payment or performance bonds that are furnished to the Owner by the Contractor.

10-47  TAXIWAY.  For the purpose of this document, the term taxiway means the portion of the air operations area of an airport that has been designated by competent airport authority for movement of aircraft to and from the airport's runways or aircraft parking areas.

10-48  WORK.  The furnishing of all labor, materials, tools, equipment, and incidentals necessary or convenient to the Contractor's performance of all duties and obligations imposed by the contract, plans, and specifications.

10-49  WORKING DAY.  A working day shall be any day other than a legal holiday, Saturday, or Sunday on which the normal working forces of the Contractor may proceed with regular work for at least 6 hours toward completion of the contract. When work is suspended for causes beyond the Contractor's control, it will not be counted as a working day. Saturdays, Sundays and holidays on which the Contractor's forces engage in regular work will be considered a working day.

END OF SECTION 10

# SECTION 20

PROPOSAL REQUIREMENTS AND CONDITIONS

20-01  BIDDER QUALIFICATIONS.  The apparent low bidder shall furnish the owner satisfactory evidence of his/her competency and financial capability to perform the proposed work. The Bidder shall demonstrate that they are a responsible firm that possesses the skills, abilities, and integrity to faithfully perform the project work. Evidence of competency shall consist of statements covering the Bidder’s past experience on similar work, a listing of plant and equipment immediately available for use on the project, and a listing of key personnel that are available for the project.  The listing for plant and equipment shall identify the type, the capacity and the present condition of the item.

Evidence of financial responsibility shall consist of a confidential statement or report of the Bidder’s financial resources and liabilities as of the last calendar year. A public accountant must certify such statements and reports.  If the Bidder is presently pre-qualified with the Missouri Department of Transportation (MoDOT), evidence of this pre-qualification may serve as evidence of financial responsibility in lieu of the certified financial statements and reports.

The apparent low bidder shall submit ``evidence of competency'' and ``evidence of financial responsibility'' to the owner no later than 3 business days after the specified date for opening bids.

20-02  BID DOCUMENTS/PROJECT MANUAL.  The bid documents are comprised of the following; Notice-to-Bidders, Instructions-to-Bidders, General Provisions, Supplementary Provisions, Technical Specifications, Project Drawings, Proposal Form, Performance and Payment Bonds, Form of Contract Agreement, any authorized addenda issued by the Owner and any document incorporated in whole or in part by reference therein.

All documents comprising the Bid Documents are complementary to one another and together establish the complete terms, conditions and obligations of the successful bidder.

Those individual elements of the Contract Documents that are bound together shall also be referred to as the Project Manual. THE EXECUTED PROPOSAL FORM MUST BE SUBMITTED IN THE ORIGINAL BOUND PROECT MANUAL.  NO INDIVIDUAL ELEMENTS OF THE PROJECT MANUAL MAY BE REMOVED OR DETACHED.

Prospective bidders may obtain a copy of the project manual and project drawings from the designated office identified within this Notice-to-Bidders.

20-03  MODIFICATIONS TO PROJECT DOCUMENTS.  Modifications to the project documents may only be made by written addendum issued by the Owner or the Engineer.  Verbal explanations, interpretations or comments made by the Owner or Owner’s representative shall not be binding.  Addenda will be transmitted to all known official plan holders.  Each bidder shall certify in the Proposal Form at the time of bid submittal, that they acknowledge receipt of all issued addenda.

20-04  ERRORS AND DISCREPANCIES IN PROJECT DOCUMENTS.  Should Bidder find an error, discrepancy, ambiguity or omission in the project documents prior to submittal of a proposal, the Bidder is obligated to contact the Owner or Engineer with written notice of the error, discrepancy, ambiguity or omission. The written notice shall identify the nature and location of the error, discrepancy, ambiguity or omission.  Corrections or modifications to the project documents will only be made by written addendum as prescribed herein.  By submittal of a Bid Proposal, Bidder represents that they have thoroughly reviewed the project documents and that they have not identified any error, discrepancy, ambiguity or omission that would affect cost, progress or performance of the project work.

20-05  CLARIFICATIONS AND INTERPRETATIONS.  A bidder requiring a clarification or interpretation of the project documents shall make a written request to the Owner or Engineer.  The Owner or Engineer must receive the written request a minimum of seven (7) calendar days prior to the date of the bid opening.

20-06  ISSUANCE OF PROPOSAL FORMS.  The owner reserves the right to refuse to issue a proposal form to a prospective bidder should such bidder be in default for any of the following reasons:

a.  Failure to comply with any prequalification regulations of the owner, if such regulations are cited, or otherwise included, in the proposal as a requirement for bidding.

b.  Failure to pay, or satisfactorily settle, all bills due for labor and materials on former contracts in force (with the owner) at the time the owner issues the proposal to a prospective bidder.

c.  Contractor default under previous contracts with the owner.

d.  Unsatisfactory work on previous contracts with the owner.

20-07  INTERPRETATION OF ESTIMATED PROPOSAL QUANTITIES.  An estimate of quantities of work to be done and materials to be furnished under these specifications is stated within the project manual.  This estimate is a result of careful calculations and is believed to be correct. The estimated quantities are given only as a basis for comparison of proposals and the award of the contract.  The owner does not expressly or impliedly agree that the actual quantities involved will correspond exactly with the estimated quantities. The bidder shall not plead misunderstanding or deception because of such estimates of quantities, or of the character, location, or other conditions pertaining to the work.  Payment to the Contractor will be made only for the actual quantities of work performed or materials furnished in accordance with the plans and specifications.  It is understood that the quantities may be increased or decreased as hereinafter provided in the subsection titled “Alteration of Work and Quantities” of the general provisions without in any way invalidating the unit bid prices.

20-08  EXAMINATION OF PLANS, SPECIFICATIONS, AND SITE CONDITIONS.  The bidder is expected to carefully examine the site of the proposed work, the proposal, drawings, specifications, terms and conditions of the proposed agreement and the form of agreement.  The Bidder shall satisfy themselves as to the character, quality, and quantities of work to be performed, materials to be furnished, and as to the requirements of the proposed contract.  The submission of a proposal shall be prima facie evidence that the bidder has made such examination and is satisfied as to the conditions to be encountered in performing the work and as to the requirements of the proposed contract, plans, and specifications.

Boring logs and other records of subsurface investigations and tests, as appropriate may be available for inspection by the bidder.  It is understood and agreed that such subsurface information, whether included in the project drawings, specifications, or otherwise made available to the bidder, was obtained and is intended for the owner's design and estimating purposes only.  Such information has been made available for the convenience of all bidders.  It is further understood and agreed that the bidder is solely responsible for all assumptions, deductions, or conclusions which he or she may make or obtain from his or her examination of the boring logs and other records of subsurface investigations and tests that are furnished by the owner.

20-09  PREPARATION OF THE BID PROPOSAL.  All bid proposals shall be made on the forms provided by the owner within the bound Project Manual. No bidder may submit more than one proposal.  Each bidder shall specify in the bid, in figures, a unit price for each of the separate items listed in the bid proposal, except a unit price entry will not be necessary for those items having a quantity of one, and only the amount for that item need be entered.  Zero will be considered a valid bid.  The bidder shall not enter zero in any "Unit Price" field unless zero is the intended bid for that item.  A unit price left blank, with or without an extension, other than items having a quantity of one, will be considered as zero by the owner.  The bidder shall show the products of the respective unit prices and quantities in the amount column provided for that purpose. These extensions shall be totaled and in case of errors or discrepancies in extensions, the unit prices shall govern. All entries in the bid shall be in ink. If, in the sole discretion of the owner, an obvious and apparent clerical error exists in the unit bid price for an item due to a misplaced decimal, but the extension appears to be correct and as intended in all respects, the owner may correct the unit price bid in accordance with the extension listed.  All errors in extensions or totals will be corrected by the owner and such corrected extensions and totals will be used in comparing bids.

Bids shall not contain interlineations, alterations or erasures except a bidder may alter or correct a unit price, lump sum price or extension entered on the Proposal Form by crossing out the figure with ink and entering a new unit price, lump sum bid or extension above or below in ink with his/her initials.

The proposal shall be signed and dated by an authorized representative of the bidder. All signatures shall be made with an ink pen.  The bidder’s representative shall have the legal authority to obligate and bind the bidder to the terms and conditions of the contract. The bidder shall legibly state the name of the bidder’s representative, the legal name of the bidder, the address of the bidder including City, State and Zip Code.

- For bids by corporations, an officer of the corporation shall sign the bid, the State of incorporation shall be identified and the corporate seal affixed.

- For bids submitted by an agent, evidence of the power of attorney shall be attached to the bid.

- For bids submitted by a partnership or joint venture, the proposal shall identify the name of all firms and the authorized parties of all firms. A copy of the partnership/joint agreement shall be provided to the owner as an attachment to the proposal.

20-10  BID GUARANTY.  No bid will be considered unless accompanied by a certified check or cashier’s check on any bank or trust company insured by the Federal Deposit Insurance Corporation, payable to the owner, for not less than five (5) percent of the amount of the bid, or by a bid bond secured by an approved surety or sureties (licensed to conduct surety business in the state of Missouri), payable to the owner, for not less than five (5) percent of the amount of the bid.

20-11  SUBMISSION OF BID PROPOSAL.  Proposals shall be sent to arrive at the time and date specified in Section 1, Notice to Bidders. Proposals received after the specified time and date will not receive consideration and will be returned unopened.  Prior to submittal, the proposal shall be placed in a sealed opaque envelope and addressed as specified in Section 2, Instructions to Bidders, paragraph 5.

20-12  MODIFICATION OR WITHDRAWAL OF BID PROPOSAL.  Bidder may modify or withdraw his/her proposal at any point up to the specified time and date identified for receipt of proposals.  Any request for bid withdrawal or modification by the Bidder that is received after the specified time and date for receipt of proposals will be returned unopened to the sender.

Any modification to a Bidder’s proposal, subject to the time constraint noted herein, must be made on the proposal forms contained in the project manual. The Bidder’s authorized representative must sign the modification. The modification shall be placed in a sealed envelope and the statement “Modification to Proposal” shall be legibly marked in the upper left hand corner. Withdrawal of a proposal may be made, subject to the time constraint noted herein, only with written confirmation under signature of the Bidder.

20-13  BID OPENING.  All proposals submitted prior to the stated time and date for receipt of bids will be publicly opened and read aloud by the Owner or the Owner’s representative. Bidders, their authorized agents, and other interested parties are invited to attend. Proposals submitted after the stated time and date for receipt of bids will be automatically rejected without consideration and will be returned unopened.

20-14 DISQUALIFICATION OF BID PROPOSALS.  The Owner reserves the right to reject any or all bids, as determined to be in the best interest of the Owner.  Causes for rejection of proposals include but are not limited to:

- Submittal of more than one proposal from the same partnership, firm or corporation;

- Failure by Bidder to submit the bid prior to the stated time and date for receipt of bids;

- Failure by Bidder to furnish satisfactory bid guarantee;

- Failure by Bidder to provide all information required of the bid forms;

- Failure by Bidder to comply with the requirements of bid instructions;

- Determination by the Owner that Bidder is not qualified to accomplish the project work;

- Determination by the Owner that the Bidder has placed conditions on or qualified their proposal;

- Discovery of any alteration, interlineations or erasure of any project requirement by the Bidder;

- Evidence of collusion among bidders.

END OF SECTION 20

# SECTION 30

AWARD AND EXECUTION OF CONTRACT

30-01  EVALUATION OF PROPOSALS.  Proposals may be held by the Owner for purposes of review and evaluation by the Owner for a period not to exceed {NUMBER OF DAYS} calendar days from the stated date for receipt of bids.  The Owner will tabulate all bids and verify proper extension of unit costs.  The Bidder shall honor their proposal for the duration of this period of review and evaluation.  The bid guaranty will be held by the Owner until this period of review has expired or a contract has been formally executed.

30-02  CANCELLATION OF AWARD.  At any time prior to execution of a contract agreement, the Owner reserves the right to cancel the award for any reason without liability to the Bidder, with the exception of the return of the bid guaranty, at any time prior to execution of the contract.

30-03  NOTICE OF AWARD OF CONTRACT.  It is the intent of the Owner, after a period of review and evaluation, to award a contract to the responsible bidder that submits the lowest responsive proposal. The successful bidder will be informed their bid has been accepted through the Owner’s issuance of a Notice-of-Award. The Notice-of-Award shall not be construed as a binding agreement. The proper execution of a contract agreement shall serve as the binding agreement.

Award of this contract is conditioned upon MoDOT concurring in award of contract. The issuance of the Notice-of-Award will not be made until MoDOT has concurred in award.

Unless specifically stated, the owner reserves the right to accept alternates in any order or combination, which in the judgment of the Owner, best serves the Owner’s interest.

30-04  RETURN OF BID GUARANTY.  The bid guaranty of the successful Bidder will be returned upon successful execution of the contract documents as specified herein.  Failure by the successful Bidder to execute the contract documents within the specified time shall result in forfeiture of the bid guaranty. The bid guaranty of the second and third lowest responsible bidders will be retained for a period of {NUMBER OF DAYS} days pending the execution of the contract documents by the successful bidder. Except as noted above, the bid guaranty of unsuccessful bidders will be returned at the point their proposal is rejected.

30-05 CONTRACT AGREEMENT.  The successful Bidder shall execute the contract agreement in accordance with the accepted bid proposal within thirty (30) days of the date of the Notice-of-Award.  Failure to execute the contract agreement within the specified time frame may result in the bid being awarded to the next low bidder and shall result in the forfeiture of the Bidder’s bid guarantee as a liquidated damage.

30-06  PERFORMANCE AND PAYMENT BONDS.  The successful Bidder shall furnish separate performance and payment bonds each in the amount of 100% of the contract price.  The bonds shall be made payable to the Owner as security for faithful performance of the contract and for the payment of all persons, firms or corporations to whom the Bidder may become legally indebted for labor, materials, tools, equipment or services in the performance of the project work. The form of the bond shall be that provided within the project manual.  The current power of attorney for the person signing the bond as a representative of the surety shall be attached to the bonds.

The executed bonds shall be delivered to the Owner within fifteen (15) calendar days from the date of contract execution. Bonds should not be executed prior to execution of the contract agreement. The bonds shall be issued by a solvent Surety, which is certified to operate within the State the project work is located and which is listed in the current issue of the U.S. Treasury Circular 570.  If specifically requested by the Owner, the successful Bidder shall obtain and submit information on the surety’s financial strength rating.

30-07  CERTIFICATES OF INSURANCE.  The successful Bidder shall furnish to the Owner all required certificates of insurance as specified within the project manual.

30-08  APPROVAL OF CONTRACT.  Upon receipt of the Contract Agreement, Contract Bonds and Certificate of Insurance as executed by the successful Bidder, the Owner will complete execution of the contract conditioned upon the Owner’s judgment that it remains in their best interest to enter into the Agreement.

Delivery of the fully executed Contract Agreement to the successful Bidder shall constitute the Owner’s approval to be bound by the successful Bidder’s proposal and all terms and conditions of the Contract Agreement.

Upon satisfactory execution of the contract by the successful Bidder and the Owner, all references to “Bidder” in the bid documents become equivalent to the term “Contractor”.

END OF SECTION 30

# SECTION 40

# SCOPE OF WORK

40-01  INTENT OF CONTRACT.  The intent of the contract is to provide for construction and completion, in every detail, of the work described.  It is further intended that the Contractor shall furnish all labor, materials, equipment, tools, transportation, and supplies required to complete the work in accordance with the plans, specifications, and terms of the contract.

40-02  ALTERATION OF WORK AND QUANTITIES.  The owner reserves and shall have the right to make such alterations in the work as may be necessary or desirable to complete the work originally intended in an acceptable manner.  Unless otherwise specified herein, the Engineer shall be and is hereby authorized to make such alterations in the work as may increase or decrease the originally awarded contract quantities, provided that the aggregate of such alterations does not change the total contract cost or the total cost of any major contract item by more than 25 percent (total cost being based on the unit prices and estimated quantities in the awarded contract).  Alterations that do not exceed the 25 percent limitation shall not invalidate the contract nor release the surety, and the Contractor agrees to accept payment for such alterations as if the altered work had been a part of the original contract.  These alterations that are for work within the general scope of the contract shall be covered by ``Change Orders'' issued by the Engineer.  Change orders for altered work shall include extensions of contract time where, in the Engineer's opinion, such extensions are commensurate with the amount and difficulty of added work.

Should the aggregate amount of altered work exceed the 25 percent limitation hereinbefore specified, such excess altered work shall be covered by supplemental agreement.  If the owner and the Contractor are unable to agree on a unit adjustment for any contract item that requires a supplemental agreement, the owner reserves the right to terminate the contract with respect to the item and make other arrangements for its completion.

All supplemental agreements shall be approved by the Missouri Department of Transportation’s Aviation Section and shall require consent of the Contractor's surety and separate performance and payment bonds.

40-03  OMITTED ITEMS.  The Engineer may, in the Owner's best interest, omit from the work any contract item, except major contract items.  Major contract items may be omitted by a supplemental agreement.  Such omission of contract items shall not invalidate any other contract provision or requirement.

Should a contract item be omitted or otherwise ordered to be nonperformed, the Contractor shall be paid for all work performed toward completion of such item prior to the date of the order to omit such item.  Payment for work performed shall be in accordance with the subsection titled PAYMENT FOR OMITTED ITEMS of Section 90.

40-04  EXTRA WORK.  Should acceptable completion of the contract require the Contractor to perform an item of work for which no basis of payment has been provided in the original contract or previously issued change orders or supplemental agreements, the same shall be called “Extra Work.”  Extra Work that is within the general scope of the contract shall be covered by written change order.  Change orders for such Extra Work shall contain agreed unit prices for performing the change order work in accordance with the requirements specified in the order, and shall contain any adjustment to the contract time that, in the Engineer's opinion, is necessary for completion of such Extra Work.

When determined by the Engineer to be in the Owner's best interest, he may order the Contractor to proceed with Extra Work by force account as provided in the subsection titled PAYMENT FOR EXTRA AND FORCE ACCOUNT WORK of Section 90.

Extra Work that is necessary for acceptable completion of the project, but is not within the general scope of the work covered by the original contract shall be covered by a Supplemental Agreement as hereinbefore defined in the subsection titled SUPPLEMENTAL AGREEMENT of Section 10.

Any claim for payment of Extra Work that is not covered by written agreement (change order or supplemental agreement) shall be rejected by the Owner.

40-05  MAINTENANCE OF TRAFFIC.  It is the explicit intention of the contract that the safety of aircraft, as well as the Contractor's equipment and personnel, is the most important consideration.  It is understood and agreed that the Contractor shall provide for the free and unobstructed movement of aircraft in the air operations areas of the airport with respect to his/her own operations and the operations of all his/her subcontractors as specified in the subsection titled LIMITATION OF OPERATIONS of Section 80.  It is further understood and agreed that the Contractor shall provide for the uninterrupted operation of visual and electronic signals (including power supplies thereto) used in the guidance of aircraft while operating to, from, and upon the airport as specified in the subsection titled CONTRACTOR'S RESPONSIBILITY FOR UTILITY SERVICE AND FACILITIES OF OTHERS in Section 70.

With respect to his/her own operations and the operations of all his/her subcontractors, the Contractor shall provide marking, lighting, and other acceptable means of identifying: personnel; equipment; vehicles; storage areas; and any work area or condition that may be hazardous to the operation of aircraft, fire-rescue equipment, or maintenance vehicles at the airport.

When the contract requires the maintenance of vehicular traffic on an existing road, street, or highway during the Contractor's performance of work that is otherwise provided for in the contract, plans, and specifications, the Contractor shall keep such road, street, or highway open to all traffic and shall provide such maintenance as may be required to accommodate traffic.  The Contractor shall furnish erect, and maintain barricades, warning signs, flagperson, and other traffic control devices in reasonable conformity with the manual of Uniform Traffic Control Devices for Streets and Highways (published by the United States Government Printing Office), unless otherwise specified herein.  The Contractor shall also construct and maintain in a safe condition any temporary connections necessary for ingress to and egress from abutting property or intersecting roads, streets or highways.  Unless otherwise specified herein, the Contractor will not be required to furnish snow removal for such existing road, street, or highway.

The Contractor shall make his/her own estimate of all labor, materials, equipment, and incidentals necessary for providing the maintenance of aircraft and vehicular traffic as specified in this subsection.

The cost of maintaining the aircraft and vehicular traffic specified in this subsection shall not be measured or paid for directly, but shall be included in the various contract items.

40-06  REMOVAL OF EXISTING STRUCTURES.  All existing structures encountered within the established lines, grades, or grading sections shall be removed by the Contractor, unless such existing structures are otherwise specified to be relocated, adjusted up or down, salvaged, abandoned in place, reused in the work or to remain in place.  The cost of removing such existing structures shall not be measured or paid for directly, but shall be included in the various contract items.

Should the Contractor encounter an existing structure (above or below ground) in the work for which the disposition is not indicated on the plans, the Engineer shall be notified prior to disturbing such structure.  The disposition of existing structures so encountered shall be immediately determined by the Engineer in accordance with the provisions of the contract.

Except as provided in the subsection titled RIGHTS IN AND USE OF MATERIALS FOUND IN THE WORK of this section, it is intended that all existing materials or structures that may be encountered (within the lines, grades, or grading sections established for completion of the work) shall be utilized in the work as otherwise provided for in the contract and shall remain the property of the Owner when so utilized in the work.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

The removal of large or complicated existing structures such as box-culverts, underground storage tanks, large underground electrical vaults, large reinforced concrete structures or foundations, or similar existing airport facilities should be provided for in separate technical specifications. Contract pay items should also be provided in the contract proposal to cover payment for such work.

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

40-07  RIGHTS IN AND USE OF MATERIALS FOUND IN THE WORK.  Should the Contractor encounter any material such as (but not restricted to) sand, stone, gravel, slag, or concrete slabs within the established lines, grades, or grading sections, the use of which is intended by the terms of the contract to be either embankment or waste, he may at his/her option either:

a.  Use such material in another contract item, providing such use is approved by the Engineer and is in conformance with the contract specifications applicable to such use; or,

b.  Remove such material from the site, upon written approval of the Engineer; or

c.  Use such material for his/her own temporary construction on site; or,

d.  Use such material as intended by the terms of the contract.

Should the Contractor wish to exercise option a., b., or c., he shall request the Engineer's approval in advance of such use.

Should the Engineer approve the Contractor's request to exercise option a., b., or c., the Contractor shall be paid for the excavation or removal of such material at the applicable contract price.  The Contractor shall replace, at his/her own expense, such removed or excavated material with an agreed equal volume of material that is acceptable for use in constructing embankment, backfills, or otherwise to the extent that such replacement material is needed to complete the contract work.  The Contractor shall not be charged for his/her use of such material so used in the work or removed from the site.

Should the Engineer approve the Contractor's exercise of option a., the Contractor shall be paid, at the applicable contract price, for furnishing and installing such material in accordance with requirements of the contract item in which the material is used.

It is understood and agreed that the Contractor shall make no claim for delays by reason of his/her exercise of option a., b., or c.

The Contractor shall not excavate, remove, or otherwise disturb any material, structure, or part of a structure which is located outside the lines, grades, or grading sections established for the work, except where such excavation or removal is provided for in the contract, plans, or specifications.

40-08  (NOT USED)

40-09  FINAL CLEANING UP.  Upon completion of the work and before acceptance and final payment will be made, the Contractor shall remove from the site all machinery, equipment, surplus and discarded materials, rubbish, temporary structures, and stumps or portions of trees.  He shall cut all brush and woods within the limits indicated and shall leave the site in a neat and presentable condition.  Material cleared from the site and deposited on adjacent property will not be considered as having been disposed of satisfactorily, unless the Contractor has obtained the written permission of such property owner.

END OF SECTION 40

# SECTION 50

CONTROL OF WORK

50-01  AUTHORITY OF THE ENGINEER.  The Engineer shall decide any and all questions which may arise as to the quality and acceptability of materials furnished, work performed, and as to the manner of performance and rate of progress of the work.  The Engineer shall decide all questions that may arise as to the interpretation of the specifications or plans relating to the work.  The Engineer shall determine the amount and quality of the several kinds of work performed and materials furnished which are to be paid for the under contract.

The Engineer does not have the authority to accept pavements that do not conform to FAA specification requirements.

50-02  CONFORMITY WITH PLANS AND SPECIFICATIONS.  All work and all materials furnished shall be in reasonably close conformity with the lines, grades, grading sections, cross sections, dimensions, material requirements, and testing requirements that are specified (including specified tolerances) in the contract, plans or specifications.

If the Engineer finds the materials furnished, work performed, or the finished product not within reasonably close conformity with the plans and specifications but that the portion of the work affected will, in his/her opinion, result in a finished product having a level of safety, economy, durability, and workmanship acceptable to the Owner, he will advise the Owner of his/her determination that the affected work be accepted and remain in place.  In this event, the Engineer will document his/her determination and recommend to the Owner a basis of acceptance that will provide for an adjustment in the contract price for the affected portion of the work.  The Engineer's determination and recommended contract price adjustments will be based on good engineering judgment and such tests or retests of the affected work as are, in his/her opinion, needed.  Changes in the contract price shall be covered by contract modifications (change order or supplemental agreement) as applicable.

If the Engineer finds the materials furnished, work performed, or the finished product are not in reasonably close conformity with the plans and specifications and have resulted in an unacceptable finished product, the affected work or materials shall be removed and replaced or otherwise corrected by and at the expense of the Contractor in accordance with the Engineer's written orders.

For the purpose of this subsection, the term ``reasonably close conformity'' shall not be construed as waiving the Contractor's responsibility to complete the work in accordance with the contract, plans, and specifications.  The term shall not be construed as waiving the Engineer's responsibility to insist on strict compliance with the requirements of the contract, plans, and specifications during the Contractor's prosecution of the work, when, in the Engineer's opinion, such compliance is essential to provide an acceptable finished portion of the work.

For the purpose of this subsection, the term ``reasonably close conformity'' is also intended to provide the Engineer with the authority, after consultation with the FAA, to use good engineering judgment in his/her determinations as to acceptance of work that is not in strict conformity but will provide a finished product equal to or better than that intended by the requirements of the contract, plans and specifications.

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

- The Owner should keep MoDOT advised of the Engineer's determinations as to acceptance of work that is not in reasonably close conformity to the contract, plans, and specifications.  Change orders or supplemental agreements must bear the written approval of MoDOT.  The Engineer may consult with MoDOT for the determination to accept materials that are not in strict conformance with the specification requirements.

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

The Engineer will not be responsible for the Contractor’s means, methods, techniques, sequences, or procedures of construction or the safety precautions incident thereto.

50-03  COORDINATION OF CONTRACT, PLANS, AND SPECIFICATIONS.  The contract, plans, specifications, and all referenced standards cited are essential parts of the contract requirements.  A requirement occurring in one is as binding as though occurring in all.  They are intended to be complementary and to describe and provide for a complete work.  In case of discrepancy, calculated dimensions will govern over scaled dimensions; contract technical specifications shall govern over contract general provisions, plans, cited standards for materials or testing, and cited FAA advisory circulars; contract general provisions shall govern over plans, cited standards for materials or testing, and cited FAA advisory circulars; plans shall govern over cited standards for materials or testing and cited FAA advisory circulars.  If any paragraphs contained in the Special Provisions conflict with General Provisions or Technical Specifications, the Special Provisions shall govern.

The Contractor shall not take advantage of any apparent error or omission on the plans or specifications.  In the event the Contractor discovers any apparent error or discrepancy, he shall immediately call upon the Engineer for his/her interpretation and decision, and such decision shall be final.

50-04  COOPERATION OF CONTRACTOR.  The Contractor will be supplied with five copies each of the plans and specifications.  He shall have available on the work at all times one copy each of the plans and specifications.  Additional copies of plans and specifications may be obtained by the Contractor for the cost of reproduction.

The Contractor shall give constant attention to the work to facilitate the progress thereof, and he shall cooperate with the Engineer and his/her inspectors and with other contractors in every way possible.  The Contractor shall have a competent superintendent on the work at all times who is fully authorized as his/her agent on the work.  The superintendent shall be capable of reading and thoroughly understanding the plans and specifications and shall receive and fulfill instructions from the Engineer or his/her authorized representative.

50-05  COOPERATION BETWEEN CONTRACTORS.  The Owner reserves the right to contract for and perform other or additional work on or near the work covered by this contract.

When separate contracts are let within the limits of any one project, each Contractor shall conduct his/her work so as not to interfere with or hinder the progress of completion of the work being performed by other Contractors.  Contractors working on the same project shall cooperate with each other as directed.

Each Contractor involved shall assume all liability, financial or otherwise, in connection with his/her contract and shall protect and save harmless the Owner from any and all damages or claims that may arise because of inconvenience, delays, or loss experienced by him because of the presence and operations of other Contractors working within the limits of the same project.

The Contractor shall arrange his/her work and shall place and dispose of the materials being used so as not to interfere with the operations of the other Contractors within the limits of the same project.  He shall join his/her work with that of the others in an acceptable manner and shall perform it in proper sequence to that of the others.

50-06  CONSTRUCTION LAYOUT AND STAKES.  The Engineer shall establish horizontal and vertical control only.  The Contractor must establish all layout required for the construction of the work.  Such stakes and markings as the Engineer may set for either his/her own or the Contractor's guidance shall be preserved by the Contractor.  In case of negligence on the part of the Contractor, or his/her employees, resulting in the destruction of such stakes or markings, an amount equal to the cost of replacing the same may be deducted from subsequent estimates due the Contractor at the discretion of the Engineer.

The Contractor will be required to furnish all lines, grades and measurements from the control points necessary for the proper prosecution and control of the work contracted for under these specifications.

The Contractor must give weekly copies of the survey notes to the Engineer so that the Engineer may check them as to accuracy and method of staking.  All areas that are staked by the Contractor must be checked by the Engineer prior to beginning any work in the area.  The Engineer will make periodic checks of the grades and alignment set by the Contractor.  In case of error on the part of the Contractor, or his/her employees, resulting in establishing grades and/or alignment that are not in accordance with the plans or established by the Engineer, all construction not in accordance with the established grades and/or alignment shall be replaced without additional cost to the Owner.

No direct payment will be made, unless otherwise specified in contract documents, for this labor, materials, or other expenses therewith.  The cost thereof shall be included in the price of the bid for the various items of the Contract.

Construction Staking and Layout includes but is not limited to:

Clearing and Grubbing perimeter staking.

Rough Grade slope stakes at 100-foot stations.

Drainage Swales slope stakes and flow line blue tops at 50-foot stations.

Subgrade blue tops at 25-foot stations and 25 foot offset distance (max.) for the following section locations:

a.	Runway – minimum 5 per station

b.	Taxiways – minimum 3 per station

c.	Holding apron areas – minimum 3 per station

d.	Roadways – minimum 3 per station

Base Course blue tops at 25-foot stations and 25 foot offset distance (max.) for the following section locations:

- Runway – minimum 5 per station

- Taxiways – minimum 3 per station

- Holding apron areas – minimum 3 per station

Pavement areas:

- Edge of Pavement hubs and tacks (for stringline by Contractor) at 100 foot stations

- Between Lifts at 25 foot stations for the following section locations:

- Runways – each paving lane width

- Taxiways – each paving lane width

- Holding areas – each paving lane width

c. 	After finish paving operations at 50 foot stations

- All paved areas – Edge of each paving lane prior to next paving lot (QA check of as constructed pavement edge)

- Shoulder and safety area blue tops at 50 foot stations and at all break points with maximum of 50 foot offsets

Fence lines at 100-foot stations

Electrical and Communications System locations, lines and grades including but not limited to duct runs, connections, fixtures, signs, lights, VASI’s, PAPI’s, REIL’s, Wind Cones, Distance Markers (signs), pull boxes and manholes.

Drain lines, cut stakes and alignment on 25-foot stations, inlet and manholes.

Painting and Striping Layout (HMA: Pinned with 1.5 inch PK nails; PCC: Layout with Permanent Marker)

Laser, or other automatic control devices, shall be checked with temporary control point or grade hub at a minimum of once per 400 feet per pass (i.e. paving lane).

NOTE: Controls and stakes disturbed or suspect of having been disturbed shall be checked and/or reset as directed by the Engineer without additional cost to the Owner.

50-07  AUTOMATICALLY CONTROLLED EQUIPMENT.  Whenever batching or mixing plant equipment is required to be operated automatically under the contract and a breakdown or malfunction of the automatic controls occurs, the equipment may be operated manually or by other methods for a period 48 hours following the breakdown or malfunction, provided this method of operations will produce results which conform to all other requirements of the contract.

50-08  AUTHORITY AND DUTIES OF INSPECTORS.  Inspectors employed by the Owner shall be authorized to inspect all work done and all material furnished.  Such inspection may extend to all or any part of the work and to the preparation, fabrication, or manufacture of the materials to be used.  Inspectors are not authorized to revoke, alter, or waive any provision of the contract.  Inspectors are not authorized to issue instructions contrary to the plans and specifications or to act as foreman for the Contractor.

Inspectors employed by the Owner are authorized to notify the Contractor or his/her representatives of any failure of the work or materials to conform to the requirements of the contract, plans, or specifications and to reject such nonconforming materials in question until such issues can be referred to the Engineer for his/her decision.

50-09  INSPECTION OF THE WORK.  All materials and each part or detail of the work shall be subject to inspection by the Engineer.  The Engineer shall be allowed access to all parts of the work and shall be furnished with such information and assistance by the Contractor as is required to make a complete and detailed inspection.

If the Engineer requests it, the Contractor, at any time before acceptance of the work, shall remove or uncover such portions of the finished work as may be directed.  After examination, the Contractor shall restore said portions of the work to the standard required by the specifications.  Should the work thus exposed or examined prove acceptable, the uncovering, or removing, and the replacing of the covering or making good of the parts removed will be paid for as extra work; but should the work so exposed or examined prove unacceptable, the uncovering, or removing, and the replacing of the covering or making good of the parts removed will be at the Contractor's expense.

Any work done or materials used without supervision or inspection by an authorized representative of the Owner may be ordered removed and replaced at the Contractor's expense unless the Owner's representative failed to inspect after having been given reasonable notice in writing that the work was to be performed.

Should the contract work include relocation, adjustment, or any other modification to existing facilities, not the property of the (contract) Owner, authorized representatives of the owners of such facilities shall have the right to inspect such work.  Such inspection shall in no sense make any facility owner a party to the contract, and shall in no way interfere with the rights of the parties to this contract.

50-10  REMOVAL OF UNACCEPTABLE AND UNAUTHORIZED WORK.  All work that does not conform to the requirements of the contract, plans, and specifications will be considered unacceptable, unless otherwise determined acceptable by the Engineer as provided in the subsection titled CONFORMITY WITH PLANS AND SPECIFICATIONS of this section.

Unacceptable work, whether the result of poor workmanship, use of defective materials, damage through carelessness, or any other cause found to exist prior to the final acceptance of the work, shall be removed immediately and replaced in an acceptable manner in accordance with the provisions of the subsection titled CONTRACTOR'S RESPONSIBILITY FOR WORK of Section 70.

No removal work made under provision of this subsection shall be done without lines and grades having been given by the Engineer.  Work done contrary to the instructions of the Engineer, work done beyond the lines shown on the plans or as given, except as herein specified, or any extra work done without authority, will be considered as unauthorized and will not be paid for under the provisions of the contract.  Work so done may be ordered removed or replaced at the Contractor's expense.

Upon failure on the part of the Contractor to comply forthwith with any order of the Engineer made under the provisions of this subsection, the Engineer will have authority to cause unacceptable work to be remedied or removed and replaced and unauthorized work to be removed and to deduct the costs (incurred by the Owner) from any monies due or to become due the Contractor.

50-11  LOAD RESTRICTIONS.  The Contractor shall comply with all legal load restrictions in the hauling of materials on public roads beyond the limits of the work.  A special permit will not relieve the Contractor of liability for damage that may result from the moving of material or equipment.

The operation of equipment of such weight or so loaded as to cause damage to structures or to any other type of construction will not be permitted.  Hauling of materials over the base course or surface course under construction shall be limited as directed.  No loads will be permitted on a concrete pavement, base, or structure before the expiration of the curing period.  The Contractor shall be responsible for all damage done by his/her hauling equipment and shall correct such damage at his/her own expense.

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

The Engineer should check to see if the on site project access roads and haul routes will support the construction equipment.  Particular attention should be paid when sections of existing airfield pavements will be used as haul routes to assure that existing pavements are not overloaded.  If questionable, the Engineer should add appropriate provisions to preserve or rehabilitate any access roads or haul routes to the bid documents.  Various measures such as videotape or photographs may be required to document existing conditions prior to start of construction.

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

50-12  MAINTENANCE DURING CONSTRUCTION.  The Contractor shall maintain the work during construction and until the work is accepted.  This maintenance shall constitute continuous and effective work prosecuted day by day, with adequate equipment and forces so that the work is maintained in satisfactory condition at all times.

In the case of a contract for the placing of a course upon a course or subgrade previously constructed, the Contractor shall maintain the previous course or subgrade during all construction operations.

All costs of maintenance work during construction and before the project is accepted shall be included in the unit prices bid on the various contract items, and the Contractor will not be paid an additional amount for such work.

50-13  FAILURE TO MAINTAIN THE WORK.  Should the Contractor at any time fail to maintain the work as provided in the subsection titled MAINTENANCE DURING CONSTRUCTION of this section, the Engineer shall immediately notify the Contractor of such noncompliance.  Such notification shall specify a reasonable time within which the Contractor shall be required to remedy such unsatisfactory maintenance condition.  The time specified will give due consideration to the exigency that exists.

Should the Contractor fail to respond to the Engineer's notification, the Owner may suspend any work necessary for the Owner to correct such unsatisfactory maintenance condition, depending on the exigency that exists.  Any maintenance cost incurred by the Owner, shall be deducted from monies due or to become due the Contractor.

50-14  PARTIAL ACCEPTANCE.  If at any time during the prosecution of the project the Contractor substantially completes a usable unit or portion of the work, the occupancy of which will benefit the Owner, he may request the Engineer to make final inspection of that unit.  If the Engineer finds upon inspection that the unit has been satisfactorily completed in compliance with the contract, he may accept it as being completed, and the Contractor may be relieved of further responsibility for that unit.  Such partial acceptance and beneficial occupancy by the Owner shall not void or alter any provision of the contract.

50-15  FINAL ACCEPTANCE. Upon due notice from the Contractor of presumptive completion of the entire project, the Engineer and Owner will make an inspection.  If all construction provided for and contemplated by the contract is found to be completed in accordance with the contract, plans, and specifications, such inspection shall constitute the final inspection.  The Engineer shall notify the Contractor in writing of final acceptance as of the date of the final inspection.

If, however, the inspection discloses any work, in whole or in part, as being unsatisfactory, the Engineer will give the Contractor the necessary instructions for correction of same and the Contractor shall immediately comply with and execute such instructions.  Upon correction of the work, another inspection will be made which shall constitute the final inspection, provided the work has been satisfactorily completed.  In such event, the Engineer will make the final acceptance and notify the Contractor in writing of this acceptance as of the date of final inspection.

50-16  CLAIMS FOR ADJUSTMENT AND DISPUTES.  If for any reason the Contractor deems that additional compensation is due him for work or materials not clearly provided for in the contract, plans, or specifications or previously authorized as extra work, he shall notify the Engineer in writing of his/her intention to claim such additional compensation before he begins the work on which he bases the claim.  If such notification is not given or the Engineer is not afforded proper opportunity by the Contractor for keeping strict account of actual cost as required, then the Contractor hereby agrees to waive any claim for such additional compensation.  Such notice by the Contractor and the fact that the Engineer has kept account of the cost of the work shall not in any way be construed as proving or substantiating the validity of the claim.  When the work on which the claim for additional compensation is based has been completed, the Contractor shall, within l0 calendar days, submit his/her written claim to the Engineer who will present it to the Owner for consideration in accordance with local laws or ordinances.

Nothing in this subsection shall be construed as a waiver of the Contractor's right to dispute final payment based on differences in measurements or computations.

50-17  COST REDUCTION INCENTIVE.  The provisions of this subsection will apply only to contracts awarded to the lowest bidder pursuant to competitive bidding.

On projects with original contract amounts in excess of $100,000, the Contractor may submit to the Engineer, in writing, proposals for modifying the plans, specifications or other requirements of the contract for the sole purpose of reducing the cost of construction.  The cost reduction proposal shall not impair, in any manner, the essential functions or characteristics of the project, including but not limited to service life, economy of operation, ease of maintenance, desired appearance, design and safety standards.  This provision shall not apply unless the proposal submitted is specifically identified by the Contractor as being presented for consideration as a value-engineering proposal.

Not eligible for cost reduction proposals are changes in the basic design of a pavement type, runway and taxiway lighting, visual aids, hydraulic capacity of drainage facilities, or changes in grade or alignment that reduce the geometric standards of the project.

As a minimum, the following information shall be submitted by the Contractor with each proposal:

a.  A description of both existing contract requirements for performing the work and the proposed changes, with a discussion of the comparative advantages and disadvantages of each;

b.  An itemization of the contract requirements that must be changed if the proposal is adopted;

c.  A detailed estimate of the cost of performing the work under the existing contract and under the proposed changes;

d.  A statement of the time by which a change order adopting the proposal must be issued;

e.  A statement of the effect adoption of the proposal will have on the time for completion of the contract; and

f.  The contract items of work affected by the proposed changes, including any quantity variation attributable to them.

The Contractor may withdraw, in whole or in part, any cost reduction proposal not accepted by the Engineer, within the period specified in the proposal.  The provisions of this subsection shall not be construed to require the Engineer to consider any cost reduction proposal that may be submitted.

The Contractor shall continue to perform the work in accordance with the requirements of the contract until a change order incorporating the cost reduction proposal has been issued.  If a change order has not been issued by the date upon which the Contractor's cost reduction proposal specifies that a decision should be made, or such other date as the Contractor may subsequently have requested in writing, such cost reduction proposal shall be deemed rejected.

The Engineer shall be the sole judge of the acceptability of a cost reduction proposal and of the estimated net savings from the adoption of all or any part of such proposal.  In determining the estimated net savings, the Engineer may disregard the contract bid prices if, in the Engineer's judgment such prices do not represent a fair measure of the value of the work to be performed or deleted.

The Owner may require the Contractor to share in the Owner's costs of investigating a cost reduction proposal submitted by the Contractor as a condition of considering such proposal.  Where such a condition is imposed, the Contractor shall acknowledge acceptance of it in writing.  Such acceptance shall constitute full authority for the Owner to deduct the cost of investigating a cost reduction proposal from amounts payable to the Contractor under the contract.

If the Contractor's cost reduction proposal is accepted in whole or in part, such acceptance will be by a contract change order that shall specifically state that it is executed pursuant to this subsection.  Such change order shall incorporate the changes in the plans and specifications which are necessary to permit the cost reduction proposal or such part of it as has been accepted and shall include any conditions upon which the Engineer's approval is based.  The change order shall also set forth the estimated net savings attributable to the cost reduction proposal.  The net savings shall be determined as the difference in costs between the original contract costs for the involved work items and the costs occurring as a result of the proposed change.  The change order shall also establish the net savings agreed upon and shall provide for adjustment in the contract price that will divide the net savings equally between the Contractor and the Owner.

The Contractor's 50 percent share of the net savings shall constitute full compensation to the Contractor for the cost reduction proposal and the performance of the work.

Acceptance of the cost-reduction proposal and performance of the cost-reduction work shall not extend the time of completion of the contract unless specifically provided for in the contract change order.

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

- Use of this subsection in project specifications is at the option of the Owner/Engineer.

- This subsection should not be incorporated into project specifications if State or local laws prohibit its use or if the project does not lend itself to value engineering.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

END OF SECTION 50

# SECTION 60

CONTROL OF MATERIALS

60-01  SOURCE OF SUPPLY AND QUALITY REQUIREMENTS.  The materials used on the work shall conform to the requirements of the contract, plans, and specifications.  Unless otherwise specified, such materials that are manufactured or processed shall be new (as compared to used or reprocessed).

In order to expedite the inspection and testing of materials, the Contractor shall furnish complete statements to the Engineer as to the origin, composition, and manufacture of all materials to be used in the work.  Such statements shall be furnished promptly after execution of the contract but, in all cases, prior to delivery of such materials.

Note statement of origin should clearly address compliance with Buy American Provisions of Contract.

At the Engineer's option, materials may be approved at the source of supply before delivery is stated.  If it is found after trial that sources of supply for previously approved materials do not produce specified products, the Contractor shall furnish materials from other sources.

The Contractor shall furnish airport lighting equipment that conforms to the requirements of cited materials specifications.  In addition, where an FAA specification for airport lighting equipment is cited in the plans or specifications, the Contractor shall furnish such equipment that is:

a.  Listed in FAA Advisory Circular (AC) 150/5345-53, Airport Lighting Equipment Certification Program, that is in effect on the date of advertisement; and,

b.  Produced by the manufacturer qualified (by FAA) to produce such specified and listed equipment.

The following airport lighting equipment is required for this contract and is to be furnished by the Contractor in accordance with the requirements of this subsection:

EQUIPMENT NAME

CITED FAA SPECIFICATIONS

EFFECTIVE FAA AC OR APPROVAL LETTER FOR EQUIPMENT AND

MANUFACTURER

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

To avoid errors, the design Engineer should furnish the above listing after having conformed the list to those specifications cited on the plans or in the technical specifications.  Both the individual FAA material specifications and the AC 150/5345-53, Airport Lighting Equipment Certification Program, should be listed to indicate the edition that is effective on the date the contract is advertised.

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

60-02  SAMPLES, TESTS, AND CITED SPECIFICATIONS.  Unless otherwise designated, all materials used in the work shall be inspected, tested, and approved by the Engineer before incorporation in the work.  Any work in which untested materials are used without approval or written permission of the Engineer shall be performed at the Contractor's risk.  Materials found to be unacceptable and unauthorized will not be paid for and, if directed by the Engineer, shall be removed at the Contractor's expense.  Unless otherwise designated, tests in accordance with the cited standard methods of ASTM, AASHTO, Federal Specifications, Commercial Item Descriptions, and all other cited methods, which are current on the date of advertisement for bids, will be made by and at the expense of the Engineer.  The testing organizations performing on site field tests shall have copies of all referenced standards on the construction site for use by all technicians and other personnel, including the Contractor's representative at his/her request.  Unless otherwise designated, samples will be taken by a qualified representative of the Engineer.  All materials being used are subject to inspection, test, or rejection at any time prior to or during incorporation into the work.  Copies of all tests will be furnished to the Contractor's representative at his/her request.

The Contractor shall employ a testing organization to perform all Contractor required tests.  The Contractor shall submit to the Engineer resumes on all testing organizations and individual persons who will be performing the tests.  The Engineer will determine if such persons are qualified.  All the test data shall be reported to the Engineer after the results are known.  A legible, handwritten copy of all test data shall be given to the Engineer daily, along with printed reports, in an approved format, on a weekly basis.  After completion of the project, and prior to final payment, the Contractor shall submit a final report to the Engineer showing all test data reports, plus an analysis of all results showing ranges, averages, and corrective action taken on all failing tests.

60-03  CERTIFICATION OF COMPLIANCE.  The Engineer may permit the use, prior to sampling and testing, of certain materials or assemblies when accompanied by manufacturer's certificates of compliance stating that such materials or assemblies fully comply with the requirements of the contract.  The certificate shall be signed by the manufacturer.  Each lot of such materials or assemblies delivered to the work must be accompanied by a certificate of compliance in which the lot is clearly identified.

Materials or assemblies used on the basis of certificates of compliance may be sampled and tested at any time and if found not to be in conformity with contract requirements will be subject to rejection whether in place or not.

The form and distribution of certificates of compliance shall be as approved by the Engineer.

When a material or assembly is specified by ``brand name or equal'' and the Contractor elects to furnish the specified ``brand name,'' the Contractor shall be required to furnish the manufacturer's certificate of compliance for each lot of such material or assembly delivered to the work.  Such certificate of compliance shall clearly identify each lot delivered and shall certify as to:

a.  Conformance to the specified performance, testing, quality or dimensional requirements; and,

b.  Suitability of the material or assembly for the use intended in the contract work.

Should the Contractor propose to furnish an ``or equal'' material or assembly, he shall furnish the manufacturer's certificates of compliance as hereinbefore described for the specified brand name material or assembly.  However, the Engineer shall be the sole judge as to whether the proposed ``or equal'' is suitable for use in the work.

The Engineer reserves the right to refuse permission for use of materials or assemblies on the basis of certificates of compliance.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

When it is necessary to specify a material or assembly by ``brand name or equal,'' the technical requirements (performance, testing, quality, or dimensions) must be accurately described in enough detail to ensure a suitable product while not restricting competition unduly.

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

60-04  PLANT INSPECTION.  The Engineer or his/her authorized representative may inspect, at its source, any specified material or assembly to be used in the work.  Manufacturing plants may be inspected from time to time for the purpose of determining compliance with specified manufacturing methods or materials to be used in the work and to obtain samples required for his/her acceptance of the material or assembly.

Should the Engineer conduct plant inspections, the following conditions shall exist:

a.  The Engineer shall have the cooperation and assistance of the Contractor and the producer with whom he has contracted for materials.

b.  The Engineer shall have full entry at all reasonable times to such parts of the plant that concern the manufacture or production of the materials being furnished.

c.  If required by the Engineer, the Contractor shall arrange for adequate office or working space that may be reasonably needed for conducting plant inspections. Office or working space should be conveniently located with respect to the plant.

It is understood and agreed that the Owner shall have the right to retest any material that has been tested and approved at the source of supply after it has been delivered to the site.  The Engineer shall have the right to reject only material which, when retested, does not meet the requirements of the contract, plans, or specifications.

60-05  ENGINEER'S FIELD OFFICE.  The Contractor shall furnish for the duration of the project one building for the use of the field engineers and inspectors, as a field office.  This facility shall be an approved weatherproof building meeting the current State Highway Specifications (for example, Class I Field Office or Type C Structure).  This building shall be located conveniently near to the construction and shall be separate from any building used by the Contractor.  A landline telephone and answering machine shall be provided.  The Contractor shall be responsible for payment of the basic monthly charge and local calls only.  Any Long Distance Tolls shall be the responsibility of the caller.  The Contractor shall furnish {FAX machine, photocopy machine, water, sanitary facilities, heat, air conditioning, and electricity}.  No direct payment will be made for this building or labor, materials, ground rental, or other expense in connection therewith.  The cost hereof shall be included in the price bid for the various items of the contract.  The Contractor and his/her superintendent shall provide all reasonable facilities to enable to the Engineer to inspect the workmanship and materials entering into the work.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

Requirements for specifying the Engineer's field office should be coordinated with the Owner and the Engineer since such facilities are not needed for all airport construction projects.

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

60-06  STORAGE OF MATERIALS.  Materials shall be so stored as to assure the preservation of their quality and fitness for the work.  Stored materials, even though approved before storage, may again be inspected prior to their use in the work.  Stored materials shall be located so as to facilitate their prompt inspection.  The Contractor shall coordinate the storage of all materials with the Engineer.  Materials to be stored on airport property shall not create an obstruction to air navigation nor shall they interfere with the free and unobstructed movement of aircraft.  Unless otherwise shown on the plans, the storage of materials and the location of the Contractor's plant and parked equipment or vehicles shall be as directed by the Engineer.  Private property shall not be used for storage purposes without written permission of the owner or lessee of such property.  The Contractor shall make all arrangements and bear all expenses for the storage of materials on private property.  Upon request, the Contractor shall furnish the Engineer a copy of the property owner's permission.

All storage sites on private or airport property shall be restored to their original condition by the Contractor at his/her entire expense, except as otherwise agreed to (in writing) by the owner or lessee of the property.

60-07  UNACCEPTABLE MATERIALS.  Any material or assembly that does not conform to the requirements of the contract, plans, or specifications shall be considered unacceptable and shall be rejected.  The Contractor shall remove any rejected material or assembly from the site of the work, unless otherwise instructed by the Engineer.

Rejected material or assembly, the defects of which have been corrected by the Contractor, shall not be returned to the site of the work until such time as the Engineer has approved its used in the work.

60-08  OWNER FURNISHED MATERIALS.  The Contractor shall furnish all materials required to complete the work, except those specified herein (if any) to be furnished by the Owner.  Owner-furnished materials shall be made available to the Contractor at the location specified herein.

All costs of handling, transportation from the specified location to the site of work, storage, and installing Owner-furnished materials shall be included in the unit price bid for the contract item in which such Owner-furnished material is used.

After any Owner-furnished material has been delivered to the location specified, the Contractor shall be responsible for any demurrage, damage, loss, or other deficiencies that may occur during the Contractor's handling, storage, or use of such Owner-furnished material.  The Owner will deduct from any monies due or to become due the Contractor any cost incurred by the Owner in making good such loss due to the Contractor's handling, storage, or use of Owner-furnished materials.

END OF SECTION 60

# SECTION 70

LEGAL REGULATIONS AND RESPONSIBILITY TO PUBLIC

70-01  LAWS TO BE OBSERVED.  The Contractor shall keep fully informed of all Federal and state laws, all local laws, ordinances, and regulations and all orders and decrees of bodies or tribunals having any jurisdiction or authority, which in any manner affect those engaged or employed on the work, or which in any way affect the conduct of the work.  He shall at all times observe and comply with all such laws, ordinances, regulations, orders, and decrees; and shall protect and indemnify the Owner and all his/her officers, agents, or servants against any claim or liability arising from or based on the violation of any such law, ordinance, regulation, order, or decree, whether by himself or his/her employees.

70-02  PERMITS, LICENSES, AND TAXES.  The Contractor shall procure all permits and licenses, pay all charges, fees, and taxes, and give all notices necessary and incidental to the due and lawful prosecution of the work.

70-03  PATENTED DEVICES, MATERIALS, AND PROCESSES.  If the Contractor is required or desires to use any design, device, material, or process covered by letters of patent or copyright, he shall provide for such use by suitable legal agreement with the patentee or owner.  The Contractor and the surety shall indemnify and save harmless the Owner, any third party, or political subdivision from any and all claims for infringement by reason of the use of any such patented design, device, material or process, or any trademark or copyright, and shall indemnify the Owner for any costs, expenses, and damages which it may be obliged to pay by reason of an infringement, at any time during the prosecution or after the completion of the work.

70-04  RESTORATION OF SURFACES DISTURBED BY OTHERS.  The Owner reserves the right to authorize the construction, reconstruction, or maintenance of any public or private utility service, FAA or National Oceanic and Atmospheric Administration (NOAA) facility, or a utility service of another government agency at any time during the progress of the work.  To the extent that such construction, reconstruction, or maintenance has been coordinated with the Owner, such authorized work (by others) is indicated as follows:

Owner (Utility or Other Facility)

Location (See Plan Sheet No.)

Person to Contact (Name, Title, Address and Phone)

Except as listed above, the Contractor shall not permit any individual, firm, or corporation to excavate or otherwise disturb such utility services or facilities located within the limits of the work without the written permission of the Engineer.

Should the owner of public or private utility service, FAA, or NOAA facility, or a utility service of another government agency be authorized to construct, reconstruct, or maintain such utility service or facility during the progress of the work, the Contractor shall cooperate with such owners by arranging and performing the work in this contract so as to facilitate such construction, reconstruction or maintenance by others whether or not such work by others is listed above.  When ordered as extra work by the Engineer, the Contractor shall make all necessary repairs to the work which are due to such authorized work by others, unless otherwise provided for in the contract, plans, or specifications.  It is understood and agreed that the Contractor shall not be entitled to make any claim for damages due to such authorized work by others or for any delay to the work resulting from such authorized work.

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

It is the intention of this subsection to provide for both foreseen and unforeseen work by owners of utility services and other facilities on the airport.  Such owners have legal rights and obligations under some form of easement with the airport Owner.  Every effort should be made, during the initial design phase, to coordinate the proposed contract work with such owners so that their rights and obligations are provided for the in the contract, plans, and specifications.  Where there is conflict between an existing utility service (or facility) and the proposed work or where the owner of the utility or facility must perform work to construct, reconstruct, or maintain his/her utility or facility, such work should be listed in this subsection and provided for in the contract, plans and specifications.  In addition, all known utility services or facilities that are within the limits of the proposed work should be shown on the plans (regardless of whether or not there is a conflict of work to be performed by the owner) with enough detailed information to indicate the lack of conflicts.

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

70-05  SANITARY, HEALTH, AND SAFETY PROVISIONS.  The Contractor shall provide and maintain in a neat, sanitary condition such accommodations for the use of his/her employees as may be necessary to comply with the requirements of the state and local Board of Health, or of other bodies or tribunals having jurisdiction.

Attention is directed to Federal, state, and local laws, rules and regulations concerning construction safety and health standards.  The Contractor shall not require any worker to work in surroundings or under conditions that are unsanitary, hazardous, or dangerous to his/her health or safety.

70-06  PUBLIC CONVENIENCE AND SAFETY.  The Contractor shall control his/her operations and those of his/her subcontractors and all suppliers, to assure the least inconvenience to the traveling public.  Under all circumstances, safety shall be the most important consideration.

The Contractor shall maintain the free and unobstructed movement of aircraft and vehicular traffic with respect to his/her own operations and those of his/her subcontractors and all suppliers in accordance with the subsection titled MAINTENANCE OF TRAFFIC of Section 40 hereinbefore specified and shall limit such operations for the convenience and safety of the traveling public as specified in the subsection titled LIMITATION OF OPERATIONS of Section 80 hereinafter.

70-07  BARRICADES, WARNING SIGNS, AND HAZARD MARKINGS.  The Contractor shall furnish, erect, and maintain all barricades, warning signs, and markings for hazards necessary to protect the public and the work.  When used during periods of darkness, such barricades, warning signs, and hazard markings shall be suitably illuminated.  Unless otherwise specified, barricades, warning signs, and markings for hazards that are in the air operations area shall be a maximum of 18 inches high.  Unless otherwise specified, barricades shall be spaced not more than 25 feet apart.  Barricades, warning signs, and markings shall be paid for under Section 40-05.

For vehicular and pedestrian traffic, the Contractor shall furnish, erect, and maintain barricades, warning signs, lights and other traffic control devices in reasonable conformity with the Manual of Uniform Traffic Control Devices for Streets and Highways (published by the United States Government Printing Office).

When the work requires closing an air operations area of the airport or portion of such area, the Contractor shall furnish, erect, and maintain temporary markings and associated lighting conforming to the requirements of  AC 150/5340-1 (current edition), Standards for Airport Markings.

The Contractor shall furnish, erect, and maintain markings and associated lighting of open trenches, excavations, temporary stockpiles, and his/her parked construction equipment that may be hazardous to the operation of emergency fire-rescue or maintenance vehicles on the airport in reasonable conformance to AC 150/5370-2 (current edition), Operational Safety on Airports During Construction.

The Contractor shall identify each motorized vehicle or piece of construction equipment in reasonable conformance to AC 150/5370-2 (current edition).

The Contractor shall furnish and erect all barricades, warning signs, and markings for hazards prior to commencing work that requires such erection and shall maintain the barricades, warning signs, and markings for hazards until their dismantling is directed by the Engineer.

Open-flame type lights shall not be permitted within the air operations areas of the airport.

70-08  USE OF EXPLOSIVES.  When the use of explosives is necessary for the prosecution of the work, the Contractor shall exercise the utmost care not to endanger life or property, including new work.  The Contractor shall be responsible for all damage resulting from the use of explosives.

All explosives shall be stored in a secure manner in compliance with all laws and ordinances, and all such storage places shall be clearly marked.  Where no local laws or ordinances apply, storage shall be provided satisfactory to the Engineer and, in general, not closer than 1,000 feet (300 m) from the work or from any building, road, or other place of human occupancy.

The Contractor shall notify each property owner and public utility company having structures or facilities in proximity to the site of the work of his/her intention to use explosives.  Such notice shall be given sufficiently in advance to enable them to take such steps as they may deem necessary to protect their property from injury.

The use of electrical blasting caps shall not be permitted on or within 1,000 feet (300 m) of the airport property.

70-09  PROTECTION AND RESTORATION OF PROPERTY AND LANDSCAPE.  The Contractor shall be responsible for the preservation of all public and private property, and shall protect carefully from disturbance or damage all land monuments and property markers until the Engineer has witnessed or otherwise referenced their location and shall not move them until directed.

The Contractor shall be responsible for all damage or injury to property of any character, during the prosecution of the work, resulting from any act, omission, neglect, or misconduct in his/her manner or method of executing the work, or at any time due to defective work or materials, and said responsibility will not be released until the project shall have been completed and accepted.

When or where any direct or indirect damage or injury is done to public or private property by or on account of any act, omission, neglect, or misconduct in the execution of the work, or in consequence of the nonexecution thereof by the Contractor, he shall restore, at his/her own expense, such property to a condition similar or equal to that existing before such damage or injury was done, by repairing, or otherwise restoring as may be directed, or he shall make good such damage or injury in an acceptable manner.

70-10  RESPONSIBILITY FOR DAMAGE CLAIMS.  The Contractor shall indemnify and save harmless the Engineer and the Owner and their officers, and employees from all suits actions, or claims of any character brought because of any injuries or damage received or sustained by any person, persons, or property on account of the operations of the Contractor; or on account of or in consequence of any neglect in safeguarding the work; or through use of unacceptable materials in constructing the work; or because of any act or omission, neglect, or misconduct of said Contractor; or because of any claims or amounts recovered from any infringements of patent, trademark, or copyright; or from any claims or amounts arising or recovered under the ``Workmen's Compensation Act,'' or any other law, ordinance, order, or decree.  Money due the Contractor under and by virtue of his/her contract as may be considered necessary by the Owner for such purpose may be retained for the use of the Owner or, in case no money is due, his/her surety may be held until such suit(s), action(s), or claim(s) for injuries or damages as aforesaid shall have been settled and suitable evidence to that effect furnished to the Owner, except that money due the Contractor will not be withheld when the Contractor produces satisfactory evidence that he is adequately protected by public liability and property damage insurance.

70-11  THIRD PARTY BENEFICIARY CLAUSE.  It is specifically agreed between the parties executing the contract that it is not intended by any of the provisions of any part of the contract to create the public or any member thereof a third party beneficiary or to authorize anyone not a party to the contract to maintain a suit for personal injuries or property damage pursuant to the terms or provisions of the contract.

70-12  OPENING SECTIONS OF THE WORK TO TRAFFIC.  Should it be necessary for the Contractor to complete portions of the contract work for the beneficial occupancy of the Owner prior to completion of the entire contract, such ``phasing'' of the work shall be specified herein and indicated on the plans.  When so specified, the Contractor shall complete such portions of the work on or before the date specified or as otherwise specified.  The Contractor shall make his/her own estimate of the difficulties involved in arranging his/her work to permit such beneficial occupancy by the Owner as described below:

Phase or Description

Required Date or Sequence of Owner's Beneficial Occupancy

Work Shown on Plan Sheet

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

The Owner's requirements for ``phasing'' the work should be coordinated with certain agencies having an interest in operational capability of the airport.  Such coordination must be accomplished at the earliest possible time.  See AC 150/5300-9, Predesign, Prebid, and Preconstruction Conferences for Airport Grant Projects, for more information.

The Engineer should include a section on airport safety in the bid documents that has, as a minimum, the information contained in the appendix of AC150/5370-2, Operational Safety on Airports During Construction.

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

Upon completion of any portion of the work listed above, such portion shall be accepted by the Owner in accordance with the subsection titled PARTIAL ACCEPTANCE of Section 50.

No portion of the work may be opened by the Contractor for public use until ordered by the Engineer in writing.  Should it become necessary to open a portion of the work to public traffic on a temporary or intermittent basis, such openings shall be made when, in the opinion of the Engineer, such portion of the work is in an acceptable condition to support the intended traffic.  Temporary or intermittent openings are considered to be inherent in the work and shall not constitute either acceptance of the portion of the work so opened or a waiver of any provision of the contract.  Any damage to the portion of the work so opened that is not attributable to traffic which is permitted by the Owner shall be repaired by the Contractor at his/her expense.

The Contractor shall make his/her own estimate of the inherent difficulties involved in completing the work under the conditions herein described and shall not claim any added compensation by reason of delay or increased cost due to opening a portion of the contract work.

Contractor shall be required to conform to safety standards contained AC 150/5370-2, Operational Safety on Airports During Construction (See Special Provisions.)

Contractor shall refer to the  approved safety plan to identify barricade requirements and other safety requirements prior to opening up sections of work to traffic.

70-13  CONTRACTOR'S RESPONSIBILITY FOR WORK.  Until the Engineer's final written acceptance of the entire completed work, excepting only those portions of the work accepted in accordance with the subsection titled PARTIAL ACCEPTANCE of Section 50, the Contractor shall have the charge and care thereof and shall take every precaution against injury or damage to any part due to the action of the elements or from any other cause, whether arising from the execution or from the non-execution of the work.  The Contractor shall rebuild, repair, restore, and make good all injuries or damages to any portion of the work occasioned by any of the above causes before final acceptance and shall bear the expense thereof except damage to the work due to unforeseeable causes beyond the control of and without the fault or negligence of the Contractor, including but not restricted to acts of God such as earthquake, tidal wave, tornado, hurricane or other cataclysmic phenomenon of nature, or acts of the public enemy or of government authorities.

If the work is suspended for any cause whatever, the Contractor shall be responsible for the work and shall take such precautions necessary to prevent damage to the work.  The Contractor shall provide for normal drainage and shall erect necessary temporary structures, signs, or other facilities at his/her expense.  During such period of suspension of work, the Contractor shall properly and continuously maintain in an acceptable growing condition all living material in newly established planting, seedings, and soddings furnished under his/her contract, and shall take adequate precautions to protect new tree growth and other important vegetative growth against injury.

70-14  CONTRACTOR'S RESPONSIBILITY FOR UTILITY SERVICE AND FACILITIES OF OTHERS.  As provided in the subsection titled RESTORATION OF SURFACES DISTURBED BY OTHERS of this section, the Contractor shall cooperate with the owner of any public or private utility service, FAA or NOAA, or a utility service of another government agency that may be authorized by the owner to construct, reconstruct or maintain such utility services or facilities during the progress of the work.  In addition, the Contractor shall control his/her operations to prevent the unscheduled interruption of such utility services and facilities.

To the extent that such public or private utility services, FAA, or NOAA facilities, or utility services of another governmental agency are known to exist within the limits of the contract work, the approximate locations have been indicated on the plans and the owners are indicated as follows:

Utility Service or Facility

Person to Contract (Name, Title, Address, & Phone)

Owner's Emergency Contact (Phone)

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

It is intended that the plans will show the approximate location of the utilities or facilities known to exist within the limits of the contract work.  It is also intended that the proposed contract plans and specifications be coordinated with the various owners at the earliest possible time to avoid overlooking utility conflicts in the design and to obtain the best possible information needed to protect such utility services or facilities from damage resulting from the Contractor's operations.  Where conflicts are indicated during the coordination, they should be resolved by the airport Owner and the utility owner, in accordance with existing legal agreements, by providing for work in the proposed contract or by the utility owner.  In such cases of conflict, regardless of how the conflict is resolved, the airport Owner and utility owner should also be advised of the need to furnish the best information possible as to location of the utility service or facility to ensure protection during the proposed contract work.

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

It is understood and agreed that the Owner does not guarantee the accuracy or the completeness of the location information relating to existing utility services, facilities, or structures that may be shown on the plans or encountered in the work.  Any inaccuracy or omission in such information shall not relieve the Contractor of his/her responsibility to protect such existing features from damage or unscheduled interruption of service.

It is further understood and agreed that the Contractor shall, upon execution of the contract, notify the owners of all utility services or other facilities of his/her plan of operations.  Such notification shall be in writing addressed to THE PERSON TO CONTACT as provided hereinbefore in this subsection and the subsection titled RESTORATION OF SURFACES DISTURBED BY OTHERS of this section.  A copy of each notification shall be given to the Engineer.

In addition to the general written notification hereinbefore provided, it shall be the responsibility of the Contractor to keep such individual owners advised of changes in his/her plan of operations that would affect such owners.

Prior to commencing the work in the general vicinity of an existing utility service or facility, the Contractor shall again notify each such owner of his/her plan of operation.  If, in the Contractor's opinion, the owner's assistance is needed to locate the utility service or facility or the presence of a representative of the owner is desirable to observe the work, such advice should be included in the notification.  Such notification shall be given by the most expeditious means to reach the utility owner's PERSON TO CONTACT no later than two normal business days prior to the Contractor's commencement of operations in such general vicinity.  The Contractor shall furnish a written summary of the notification to the Engineer.

The Contractor's failure to give the two day's notice hereinabove provided shall be cause for the Owner to suspend the Contractor's operations in the general vicinity of a utility service or facility.

Where the outside limits of an underground utility service have been located and staked on the ground, the Contractor shall be required to use excavation methods acceptable to the Engineer within 3 feet (90 cm)  of such outside limits at such points as may be required to ensure protection from damage due to the Contractor's operations.

Should the Contractor damage or interrupt the operation of a utility service or facility by accident or otherwise, he shall immediately notify the proper authority and the Engineer and shall take all reasonable measures to prevent further damage or interruption of service.  The Contractor, in such events, shall cooperate with the utility service or facility owner and the Engineer continuously until such damage has been repaired and service restored to the satisfaction of the utility or facility owner.

The Contractor shall bear all costs of damage and restoration of service to any utility service or facility due to his/her operations whether or not due to negligence or accident.  The Owner reserves the right to deduct such costs from any monies due or which may become due the Contractor, or his/her surety.

70-14.1 FAA FACILITIES AND CABLE RUNS.  The Contractor is hereby advised that the construction limits of the project include existing facilities and buried cable runs that are owned, operated and maintained by the FAA.  The Contractor, during the prosecution of the project work, shall comply with the following:

- The Contractor shall permit FAA maintenance personnel the right of access to the project work site for purposes of inspecting and maintaining all existing FAA owned facilities.

- The Contractor shall notify the above named FAA Airway Facilities Point-of-Contact seven (7) calendar days prior to commencement of construction activities in order to permit sufficient time to locate and mark existing buried cables and to schedule any required facility outages.

- If prosecution of the project work requires a facility outage, the Contractor shall contact the above named FAA Point-of-Contact a minimum of 48 hours prior to the time of the required outage.

- If prosecution of the project work results in damages to existing FAA equipment or cables, the Contractor shall repair the damaged item in conformance with FAA Airway Facilities’ standards to the satisfaction of the above named FAA Point-of-Contact.

- If the project work requires the cutting or splicing of FAA owned cables, the above named FAA Point-of-Contact shall be contacted a minimum of 48 hours prior to the time the cable work commences.  The FAA reserves the right to have a FAA Airway Facilities representative on site to observe the splicing of the cables as a condition of acceptance.  All cable splices are to be accomplished in accordance with FAA Airway Facilities’ specifications and require approval by the above named FAA Point-of-Contact as a condition of acceptance by the Owner.  The Contractor is hereby advised that FAA Airway Facilities restricts the location of where splices may be installed.  If a cable splice is required in a location that is not permitted by FAA Airway Facilities, the Contractor shall furnish and install a sufficient length of new cable that eliminates the need for any splice.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

The Engineer should include subsection 70-14.1 when existing FAA owned facilities and/or cable runs are located within the construction limits.

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

70-15  FURNISHING RIGHTS-OF-WAY.  The Owner will be responsible for furnishing all rights-of-way upon which the work is to be constructed in advance of the Contractor's operations.

70-16  PERSONAL LIABILITY OF PUBLIC OFFICIALS.  In carrying out any of the contract provisions or in exercising any power or authority granted to him by this contract, there shall be no liability upon the Engineer, his/her authorized representatives, or any officials of the Owner either personally or as an official of the Owner.  It is understood that in such matters they act solely as agents and representatives of the Owner.

70-17  NO WAIVER OF LEGAL RIGHTS.  Upon completion of the work, the Owner will expeditiously make final inspection and notify the Contractor of final acceptance.  Such final acceptance, however, shall not preclude or stop the Owner from correcting any measurement, estimate, or certificate made before or after completion of the work, nor shall the Owner be precluded or stopped from recovering from the Contractor or his/her surety, or both, such overpayment as may be sustained, or by failure on the part of the Contractor to fulfill his/her obligations under the contract.  A waiver on the part of the Owner of any breach of any part of the contract shall not be held to be a waiver of any other or subsequent breach.

The Contractor, without prejudice to the terms of the contract, shall be liable to the Owner for latent defects, fraud, or such gross mistakes as may amount to fraud, or as regards the owner's rights under any warranty or guaranty.

70-18  ENVIRONMENTAL PROTECTION.  The Contractor shall comply with all Federal, state, and local laws and regulations controlling pollution of the environment.  He shall take necessary precautions to prevent pollution of streams, lakes, ponds, and reservoirs with fuels, oils, bitumens, chemicals, or other harmful materials and to prevent pollution of the atmosphere from particulate and gaseous matter.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

For  state contracts, the contract provisions required to mitigate the environmental consequences of the contract work should be specified in the contract specifications as required generally and specifically by the Environmental Impact Statement or Assessment Report for the particular state project.

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

70-19  ARCHAEOLOGICAL AND HISTORICAL FINDINGS.  Unless otherwise specified in this subsection, the Contractor is advised that the site of the work is not within any property, district, or site, and does not contain any building, structure, or object listed in the current National Register of Historic Places published by the United States Department of Interior.

Should the Contractor encounter, during his/her operations, any building, part of a building, structure, or object that is incongruous with its surroundings, he shall immediately cease operations in that location and notify the Engineer.  The Engineer will immediately investigate the Contractor's finding and the Owner will direct the Contractor to either resume his/her operations or to suspend operations as directed.

Should the Owner order suspension of the Contractor's operations in order to protect an archaeological or historical finding, or order the Contractor to perform extra work, such shall be covered by an appropriate contract modification (change order or supplemental agreement) as provided in the subsection titled EXTRA WORK of Section 40 and the subsection titled PAYMENT FOR EXTRA WORK AND FORCE ACCOUNT WORK of Section 90.  If appropriate, the contract modification shall include an extension of contract time in accordance with the subsection titled  DETERMINATION AND EXTENSION OF CONTRACT TIME of Section 80.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

The contract language suggested in subsection 70-19 is intended to remind Owners of airports that proper planning will prevent construction delays that may be caused when objects of archaeological or historical significance are encountered in the work.  Airport Owners should include in their planning the coordination with state and local planning bodies as may be required by state and local laws pertaining to the National Historic Preservation Act of 1966.

As a general rule, disposition of known archaeological or historic objects that are situated on the site of the work should be covered by a separate contract when such disposition is required as a part of FAA project approval.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

END OF SECTION 70

# SECTION 80

PROSECUTION AND PROGRESS

80-01  SUBLETTING OF CONTRACT.  The Owner will not recognize any subcontractor on the work.  The Contractor shall at all times when work is in progress be represented either in person, by a qualified superintendent, or by other designated, qualified representative who is duly authorized to receive and execute orders of the Engineer.

Should the Contractor elect to assign his/her contract, said assignment shall be concurred in by the surety, shall be presented for the consideration and approval of the Owner, and shall be consummated only on the written approval of the Owner.  In case of approval, the Contractor shall file copies of all subcontracts with the Engineer.

The Contractor shall perform, with his organization, an amount of work equal to at least {      } percent of the total contract cost.

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

The engineer should determine the percentage of work to be performed by the prime contractor on a project basis (typically at least 25 percent).

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

80-02  NOTICE TO PROCEED.  The notice to proceed shall state the date on which it is expected the Contractor will begin the construction and from which date contract time will be charged.  The Contractor shall begin the work to be performed under the contract within 10 days of the date set by the Engineer in the written notice to proceed, but in any event, the Contractor shall notify the Engineer at least 24 hours in advance of the time actual construction operations will begin.

80-03  PROSECUTION AND PROGRESS.  Unless otherwise specified, the Contractor shall submit his/her progress schedule for the Engineer's approval within 10 days after the effective date of the notice to proceed.  The Contractor's progress schedule, when approved by the Engineer, may be used to establish major construction operations and to check on the progress of the work.  The Contractor shall provide sufficient materials, equipment, and labor to guarantee the completion of the project in accordance with the plans and specifications within the time set forth in the proposal.

If the Contractor falls significantly behind the submitted schedule, the Contractor shall, upon the Engineer's request, submit a revised schedule for completion of the work within the contract time and modify his/her operations to provide such additional materials, equipment, and labor necessary to meet the revised schedule.  Should the prosecution of the work be discontinued for any reason, the Contractor shall notify the Engineer at least 24 hours in advance of resuming operations.

For AIP contracts, the Contractor shall not commence any actual construction prior to the date on which the notice to proceed is issued by the Owner.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

It is important that the Owner issue the notice to proceed for state contracts because any actual construction work, performed prior to the execution of a grant agreement, (between the owner and the FAA) would be ineligible for FAA participation in its cost.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

80-04  LIMITATION OF OPERATIONS.  The Contractor shall control his/her operations and the operations of his/her subcontractors and all suppliers so as to provide for the free and unobstructed movement of aircraft in the AIR OPERATIONS AREAS of the airport.

When the work requires the Contractor to conduct his/her operations within an AIR OPERATIONS AREA of the airport, the work shall be coordinated with airport operations (through the Engineer) at least 48 hours prior to commencement of such work.  The Contractor shall not close an AIR OPERATIONS AREA until so authorized by the Engineer and until the necessary temporary marking and associated lighting is in place as provided in the subsection titled BARRICADES, WARNING SIGNS, AND HAZARD MARKINGS of Section 70.

When the contract work requires the Contractor to work within an AIR OPERATIONS AREA (AOA) of the airport on an intermittent basis (intermittent opening and closing of the AIR OPERATIONS AREA), the Contractor shall maintain constant communications as hereinafter specified; immediately obey all instructions to vacate the AIR OPERATIONS AREA; immediately obey all instructions to resume work in such AIR OPERATIONS AREA.  Failure to maintain the specified communications or to obey instructions shall be cause for suspension of the Contractor's operations in the AIR OPERATIONS AREA until the satisfactory conditions are provided.  The following AIR OPERATIONS AREA cannot be closed to operating aircraft to permit the Contractor's operations on a continuous basis and will therefore be closed to aircraft operations intermittently as follows:

AOA

TIME PERIODS AOA CAN BE CLOSED

TYPE OF COMMUNICATIONS REQUIRED WHEN WORKING IN AN AOA

CONTROL AUTHORITY

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

It is intended that the contract provisions which limit the Contractor's operations be specified for all AIR OPERATIONS AREAS of the airport that are not intended to be closed to permit continuous construction operations.  These contract provisions vary widely from airport to airport and require careful coordination (during the early stages of designing the work) with the Owner, FAA, and the users of the airport.  AC 150/5300-9, Predesign, Prebid, and Preconstruction Conferences for Airport Grant Projects, contains additional information on this subject.

The Engineer should include a section on airport safety in the bid documents that has , as a minimum, the information contained in the appendix of AC150/5370-2, Operational Safety on Airports During Construction.

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

Contractor shall be required to conform to safety standards contained in AC 150/5370-2, Operational Safety on Airports During Construction (See Special Provisions).

80-04.1  OPERATIONAL SAFETY ON AIRPORT DURING CONSTRUCTION.  All Contractors’ operations shall be conducted in accordance with the project safety plan and the provisions set forth within the current version of Advisory Circular 150/5370-2.  The safety plan included within the contract documents conveys minimum requirements for operational safety on the airport during construction activities.  The Contractor shall prepare and submit a plan that details how it proposes to comply with the requirements presented within the safety plan.

The Contractor shall implement all necessary safety plan measures prior to commencement of any work activity.  The Contractor shall conduct routine checks of the safety plan measures to assure compliance with the safety plan measures.

The Contractor is responsible to the Owner for the conduct of all subcontractors it employs on the project.  The Contractor shall assure that all subcontractors are made aware of the requirements of the safety plan and that they implement and maintain all necessary measures.

No deviation or modifications may be made to the approved safety plan unless approved in writing by the Owner or Engineer.

80-05  CHARACTER OF WORKERS, METHODS, AND EQUIPMENT.  The Contractor shall, at all times, employ sufficient labor and equipment for prosecuting the work to full completion in the manner and time required by the contract, plans, and specifications.

All workers shall have sufficient skill and experience to perform properly the work assigned to them.  Workers engaged in special work or skilled work shall have sufficient experience in such work and in the operation of the equipment required to perform the work satisfactorily.

Any person employed by the Contractor or by any subcontractor who violates any operational regulations and, in the opinion of the Engineer, does not perform his work in a proper and skillful manner or is intemperate or disorderly shall, at the written request of the Engineer, be removed forthwith by the Contractor or subcontractor employing such person, and shall not be employed again in any portion of the work without approval of the Engineer.

Should the Contractor fail to remove such persons or person, or fail to furnish suitable and sufficient personnel for the proper prosecution of the work, the Engineer may suspend the work by written notice until compliance with such orders.

All equipment that is proposed to be used on the work shall be of sufficient size and in such mechanical condition as to met requirements of the work and to produce a satisfactory quality of work.  Equipment used on any portion of the work shall be such that no injury to previously completed work, adjacent property, or existing airport facilities will result from its use.

When the methods and equipment to be used by the Contractor in accomplishing the work are not prescribed in the contract, the Contractor is free to use any methods or equipment that will accomplish the work in conformity with the requirements of the contract, plans, and specifications.

When the contract specifies the use of certain methods and equipment, such methods and equipment shall be used unless others are authorized by the Engineer.  If the Contractor desires to use a method or type of equipment other than specified in the contract, he may request authority from the Engineer to do so.  The request shall be in writing and shall include a full description of the methods and equipment proposed and of the reasons for desiring to make the change.  If approval is given, it will be on the condition that the Contractor will be fully responsible for producing work in conformity with contract requirements.  If, after trial use of the substituted methods or equipment, the Engineer determines that the work produced does not meet contract requirements, the Contractor shall discontinue the use of the substitute method or equipment and shall complete the remaining work with the specified methods and equipment.  The Contractor shall remove any deficient work and replace it with work of specified quality, or take such other corrective action as the Engineer may direct.  No change will be made in basis of payment for the contract items involved nor in contract time as a result of authorizing a change in methods or equipment under this subsection.

80-06  TEMPORARY SUSPENSION OF THE WORK.  The Owner shall have the authority to suspend the work wholly, or in part, for such period or periods as he may deem necessary, due to unsuitable weather, or such other conditions as are considered unfavorable for the prosecution of the work, or for such time as is necessary due to the failure on the part of the Contractor to carry out orders given or perform any or all provisions of the contract.

In the event that the Contractor is ordered by the Owner, in writing, to suspend work for some unforeseen cause not otherwise provided for in the contract and over which the Contractor has no control, the Contractor may be reimbursed for actual money expended on the work during the period of shutdown.  No allowance will be made for anticipated profits.  The period of shutdown shall be computed from the effective date of the Engineer's order to suspend work to the effective date of the Engineer's order to resume the work.  Claims for such compensation shall be filed with the Engineer within the time period stated in the Engineer's order to resume work.  The Contractor shall submit with his/her claim information substantiating the amount shown on the claim.  The Engineer will forward the Contractor's claim to the Owner for consideration in accordance with local laws or ordinances.  No provision of this article shall be construed as entitling the Contractor to compensation for delays due to inclement weather, for suspensions made at the request of the Owner, or for any other delay provided for in the contract, plans, or specifications.

If it should become necessary to suspend work for an indefinite period, the Contractor shall store all materials in such manner that they will not become an obstruction nor become damaged in any way.  He shall take every precaution to prevent damage or deterioration of the work performed and provide for normal drainage of the work.  The Contractor shall erect temporary structures where necessary to provide for traffic on, to, or from the airport.

80-07  DETERMINATION AND EXTENSION OF CONTRACT TIME.  The number of calendar or working days allowed for completion of the work shall be stated in the proposal and contract and shall be known as the CONTRACT TIME.

Should the contract time require extension for reasons beyond the Contractor's control, it shall be adjusted as follows:

a.  CONTRACT TIME based on WORKING DAYS shall be calculated weekly by the Engineer.  The Engineer will furnish the Contractor a copy of his/her weekly statement of the number of working days charged against the contract time during the week and the number of working days currently specified for completion of the contract (the original contract time plus the number of working days, if any, that have been included in approved CHANGE ORDERS or SUPPLEMENTAL AGREEMENTS covering EXTRA WORK).

The Engineer shall base his/her weekly statement of contract time charged on the following considerations:

(1)  No time shall be charged for days on which the Contractor is unable to proceed with the principal item of work under construction at the time for at least 6 hours with the normal work force employed on such principal item.  Should the normal work force be on a double-shift, 12 hours shall be used.  Should the normal work force be on a triple-shift, 18 hours shall apply.  Conditions beyond the Contractor's control such as strikes, lockouts, unusual delays in transportation, temporary suspension of the principal item of work under construction or temporary suspension of the entire work which have been ordered by the Owner for reasons not the fault of the Contractor, shall not be charged against the contract time.

(2)  The Engineer will not make charges against the contract time prior to the effective date of the notice to proceed.

(3)  The Engineer will begin charges against the contract time on the first working day after the effective date of the notice to proceed.

(4)  The Engineer will not make charges against the contract time after the date of final acceptance as defined in the subsection titled FINAL ACCEPTANCE of Section 50.

(5)  The Contractor will be allowed 1 week in which to file a written protest setting forth his/her objections to the Engineer's weekly statement.  If no objection is filed within such specified time, the weekly statement shall be considered as acceptable to the Contractor.

The contract time (stated in the proposal) is based on the originally estimated quantities as described in the subsection titled INTERPRETATION OF ESTIMATED PROPOSAL QUANTITIES of Section 20.  Should the satisfactory completion of the contract require performance of work in greater quantities than those estimated in the proposal, the contract time shall be increased in the same proportion as the cost of the actually completed quantities bears to the cost of the originally estimated quantities in the proposal.  Such increase in contract time shall not consider either the cost of work or the extension of contract time that has been covered by change order or supplemental agreement and shall be made at the time of final payment.

b.  CONTRACT TIME based on CALENDAR DAYS shall consist of the number of calendar days stated in the contract counting from the effective date of the notice to proceed and including all Saturdays, Sundays, holidays, and nonwork days.  All calendar days elapsing between the effective dates of the Owner's orders to suspend and resume all work, due to causes not the fault of the Contractor, shall be excluded.

At the time of final payment, the contract time shall be increased in the same proportion as the cost of the actually completed quantities bears to the cost of the originally estimated quantities in the proposal.  Such increase in the contract time shall not consider either cost of work or the extension of contract time that has been covered by a change order or supplemental agreement.  Charges against the contract time will cease as of the date of final acceptance.

c.  When the contract time is a specified completion date, it shall be the date on which all contract work shall be substantially completed.

If the Contractor finds it impossible for reasons beyond his/her control to complete the work within the contract time as specified, or as extended in accordance with the provisions of this subsection, he may, at any time prior to the expiration of the contract time as extended, make a written request to the Engineer for an extension of time setting forth the reasons which he believes will justify the granting of his/her request.  Requests for extension of time on calendar day projects, caused by inclement weather, shall be supported with National Weather Bureau data showing the actual amount of inclement weather exceeded which could normally be expected during the contract period.  The Contractor's plea that insufficient time was specified is not a valid reason for extension of time.  If the Engineer finds that the work was delayed because of conditions beyond the control and without the fault of the Contractor, he may extend the time for completion in such amount as the conditions justify.  The extended time for completion shall then be in full force and effect, the same as though it were the original time for completion.

80-08  FAILURE TO COMPLETE ON TIME.  For each calendar day or working day, as specified in the contract, that any work remains uncompleted after the contract time (including all extensions and adjustments as provided in the subsection titled DETERMINATION AND EXTENSION OF CONTRACT TIME of this Section), the sum specified in the contract and proposal as liquidated damages will be deducted from any money due or to become due the Contractor or his/her surety.  Such deducted sums shall not be deducted as a penalty but shall be considered as liquidation of a reasonable portion of damages including but not limited to additional engineering services that will be incurred by the Owner should the Contractor fail to complete the work in the time provided in his/her contract.

| ALTERNATE # | LIQUIDATED DAMAGES COST | ALLOWED CONSTRUCTION TIME |
| --- | --- | --- |

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

The Engineer should list the liquidated damages cost per alternate and allowed construction time per alternate to clarify when more than one alternate of work is bid, or in the event all alternate bids cannot be awarded.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

The maximum construction time allowed for alternates {       } will be the sum of the time allowed for individual alternates but not more than {        } days.  (Note:  this paragraph will be modified for each project.)

Permitting the Contractor to continue and finish the work or any part of it after the time fixed for its completion, or after the date to which the time for completion may have been extended, will in no way operate as a wavier on the part of the Owner of any of its rights under the contract.

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

The contract time is an essential part of each contract for construction on airports and should be considered carefully in the preparation of plans and specifications.

In selecting the method of specifying the contract time (working days, calendar days, or a specified completion date), the primary consideration should be the impact on the operations of the airport should the Contractor be unable to complete the work within the time specified.  These considerations should be coordinated with the airport users as indicated in AC 150/5300-9, Predesign, Prebid, and Preconstruction Conferences for Airport Grant Projects.

The amount of liquidated damages to be specified should be tailored to each contract and should be based on the cost per day incurred by the Owner should the Contractor overrun the contract time.  For large airports (where the impact on airport operations may be great), it is not practical for the Owner to attempt to recover all loss of revenue through liquidated damages.  Consequently, the amount of liquidated damages specified must be balanced somewhere between the cost per day incurred for a time overrun and the cost that bidders would have to add to their bids to cover the contingency of a time overrun.

Generally speaking, contract time is based on working days when completion is not critical to operation of the airport.  As the impact on airport operations increases, the use of calendar days will give more control.  Use of a specified completion date should be used only in cases where the construction operations require long-range rescheduling of airport operations.  Also, generally speaking, the amount of liquidated damages would be greater for a calendar day contract than for a working day contract and would be greatest for a specified completion date contract.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

80-09  DEFAULT AND TERMINATION OF CONTRACT.  The Contractor shall be considered in default of his/her contract and such default will be considered as cause for the Owner to terminate the contract for any of the following reasons if the Contractor:

a.  Fails to begin the work under the contract within the time specified in the ``Notice to Proceed,'' or

b.  Fails to perform the work or fails to provide sufficient workers, equipment or materials to assure completion of work in accordance with the terms of the contract, or

c.  Performs the work unsuitably or neglects or refuses to remove materials or to perform anew such work as may be rejected as unacceptable and unsuitable, or

d.  Discontinues the prosecution of the work, or

e.  Fails to resume work which has been discontinued within a reasonable time after notice to do so, or

f.  Becomes insolvent or is declared bankrupt, or commits any act of bankruptcy or insolvency, or

g.  Allows any final judgment to stand against him unsatisfied for a period of 10 days, or

h.  Makes an assignment for the benefit of creditors, or

i.  For any other cause whatsoever, fails to carry on the work in an acceptable manner.

Should the Engineer consider the Contractor in default of the contract for any reason hereinbefore, he shall immediately give written notice to the Contractor and the Contractor's surety as to the reasons for considering the Contractor in default and the Owner's intentions to terminate the contract.

If the Contractor or surety, within a period of 10 days after such notice, does not proceed in accordance therewith, then the Owner will, upon written notification from the Engineer of the facts of such delay, neglect, or default and the Contractor's failure to comply with such notice, have full power and authority without violating the contract, to take the prosecution of the work out of the hands of the Contractor.  The Owner may appropriate or use any or all materials and equipment that have been mobilized for use in the work and are acceptable and may enter into an agreement for the completion of said contract according to the terms and provisions thereof, or use such other methods as in the opinion of the Engineer will be required for the completion of said contract in an acceptable manner.

All costs and charges incurred by the Owner, together with the cost of completing the work under contract, will be deducted from any monies due or which may become due the Contractor.  If such expense exceeds the sum which would have been payable under the contract, then the Contractor and the surety shall be liable and shall pay to the Owner the amount of such excess.

80-10  TERMINATION FOR NATIONAL EMERGENCIES.  The Owner shall terminate the contract or portion thereof by written notice when the Contractor is prevented from proceeding with the construction contract as a direct result of an Executive Order of the President with respect to the prosecution of war or in the interest of national defense.

When the contract, or any portion thereof, is terminated before completion of all items of work in the contract, payment will be made for the actual number of units or items of work completed at the contract price or as mutually agreed for items of work partially completed or not started.  No claims or loss of anticipated profits shall be considered.

Reimbursement for organization of the work, and other overhead expenses, (when not otherwise included in the contract) and moving equipment and materials to and from the job will be considered, the intent being that an equitable settlement will be made with the Contractor.

Acceptable materials, obtained or ordered by the Contractor for the work and that are not incorporated in the work shall, at the option of the Contractor, be purchased from the Contractor at actual cost as shown by receipted bills and actual cost records at such points of delivery as may be designated by the Engineer.

Termination of the contract or a portion thereof shall neither relieve the Contractor of his/her responsibilities for the completed work nor shall it relieve his/her surety of its obligation for and concerning any just claim arising out of the work performed.

80-11  WORK AREA, STORAGE AREA AND SEQUENCE OF OPERATIONS.  The Contractor shall obtain approval from the Engineer prior to beginning any work in all areas of the airport.  No operating runway, taxiway, or Air Operations Area (AOA) shall be crossed, entered, or obstructed while it is operational.  The Contractor shall plan and coordinate his/her work in such a manner as to insure safety and a minimum of hindrance to flight operations.  All Contractor equipment and material stockpiles shall be stored a minimum or {       } feet from the centerline of an active runway.  No equipment will be allowed to park within the approach area of an active runway at any time.  No equipment shall be within {       } feet of an active runway at any time.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

The Engineer shall insert the appropriate distances per AC 150/5370-2 Operational Safety on Airports During Construction.

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

END OF SECTION 80

SECTION 90

MEASUREMENT AND PAYMENT

90-01  MEASUREMENT OF QUANTITIES.  All work completed under the contract will be measured by the Engineer, or his/her authorized representatives, using United States Customary Units of Measurement or the International System of Units.

The method of measurement and computations to be used in determination of quantities of material furnished and of work performed under the contract will be those methods generally recognized as conforming to good engineering practice.

Unless otherwise specified, longitudinal measurements for area computations will be made horizontally, and no deductions will be made for individual fixtures (or leave-outs) having an area of 9 square feet (0.8 square meter) or less.  Unless otherwise specified, transverse measurements for area computations will be the neat dimensions shown on the plans or ordered in writing by the Engineer.

Structures will be measured according to neat lines shown on the plans or as altered to fit field conditions.

Unless otherwise specified, all contract items which are measured by the linear foot such as electrical ducts, conduits, pipe culverts, underdrains, and similar items shall be measured parallel to the base or foundation upon which such items are placed.

In computing volumes of excavation the average end area method or other acceptable methods will be used.

The thickness of plates and galvanized sheet used in the manufacture of corrugated metal pipe, metal plate pipe culverts and arches, and metal cribbing will be specified and measured in decimal fraction of inches.

The term ``ton'' will mean the short ton consisting of 2,000 pounds (907 kilograms) avoirdupois.  All materials that are measured or proportioned by weights shall be weighed on accurate, approved scales by competent, qualified personnel at locations designed by the Engineer.  If material is shipped by rail, the car weight may be accepted provided that only the actual weight of material is paid for.  However, car weights will not be acceptable for material to be passed through mixing plants.  Trucks used to haul material being paid for by weight shall be weighed empty daily at such times as the Engineer directs, and each truck shall bear a plainly legible identification mark.

Materials to be measured by volume in the hauling vehicle shall be hauled in approved vehicles and measured therein at the point of delivery.  Vehicles for this purpose may be of any size or type acceptable to the Engineer, provided that the body is of such shape that the actual contents may be readily and accurately determined.  All vehicles shall be loaded to at least their water level capacity, and all loads shall be leveled when the vehicles arrive at the point of delivery.

When requested by the Contractor and approved by the Engineer in writing, material specified to be measured by the cubic yard (cubic meter) may be weighed, and such weights will be converted to cubic yards (cubic meters) for payment purposes.  Factors for conversion from weight measurement to volume measurement will be determined by the Engineer and shall be agreed to by the Contractor before such method of measurement of pay quantities is used.

Bituminous materials will be measured by the gallon (liter) or ton (kilogram).  When measured by volume, such volumes will be measured at 60 F (15 C) or will be corrected to the volume at 60 F (15 C) using ASTM D 1250 for asphalts or ASTM D 633 for tars.

Net certified scale weights or weights based on certified volumes in the case of rail shipments will be used as a basis of measurement, subject to correction when bituminous material has been lost from the car or the distributor, wasted, or otherwise not incorporated in the work.

When bituminous materials are shipped by truck or transport, net certified weights by volume, subject to correction for loss or foaming, may be used for computing quantities.

Cement will be measured by the ton (kilogram) or hundredweight (kilogram).

Timber will be measured by the thousand feet board measure (M.F.B.M.) actually incorporated in the structure.  Measurement will be based on nominal widths and thicknesses and the extreme length of each piece.

The term ``lump sum'' when used as an item of payment will mean complete payment for the work described in the contract.

When a complete structure or structural unit (in effect, ``lump sum'' work) is specified as the unit of measurement, the unit will be construed to include all necessary fittings and accessories.

Rental of equipment will be measured by time in hours of actual working time and necessary traveling time of the equipment within the limits of the work.  Special equipment ordered by the Engineer in connection with force account work will be measured as agreed in the change order or supplemental agreement authorizing such force account work as provided in the subsection titled PAYMENT FOR EXTRA AND FORCE ACCOUNT WORK of this section.

When standard manufactured items are specified such as fence, wire, plates, rolled shapes, pipe conduit, etc., and these items are identified by gage, unit weight, section dimensions, etc., such identification will be considered to be nominal weights or dimensions.  Unless more stringently controlled by tolerances in cited specifications, manufacturing tolerances established by the industries involved will be accepted.

Scales for weighing materials which are required to be proportioned or measured and paid for by weight shall be furnished, erected, and maintained by the Contractor, or be certified permanently installed commercial scales.

Scales shall be accurate within one-half percent of the correct weight throughout the range of use.  The Contractor shall have the scales checked under the observation of the inspector before beginning work and at such other times as requested.  The intervals shall be uniform in spacing throughout the graduated or marked length of the beam or dial and shall not exceed one-tenth of 1 percent of the nominal rated capacity of the scale, but not less than 1 pound (454 grams).  The use of spring balances will not be permitted.

Beams, dials, platforms, and other scale equipment shall be so arranged that the operator and the inspector can safely and conveniently view them.

Scale installations shall have available ten standard 50-pound (2.3 kilogram) weights for testing the weighing equipment or suitable weights and devices for other approved equipment.

Scales must be tested for accuracy and serviced before use at a new site.  Platform scales shall be installed and maintained with the platform level and rigid bulkheads at each end.

Scales ``overweighing'' (indicating more than correct weight) will not be permitted to operate, and all materials received subsequent to the last previous correct weighting-accuracy test will be reduced by the percentage of error in excess of one-half of 1 percent.

In the event inspection reveals the scales have been ``underweighing'' (indicating less than correct weight), they shall be adjusted, and no additional payment to the Contractor will be allowed for materials previously weighed and recorded.

All costs in connection with furnishing, installing, certifying, testing, and maintaining scales; for furnishing check weights and scale house; and for all other items specified in this subsection, for the weighing of materials for proportioning or payment, shall be included in the unit contract prices for the various items of the project.

When the estimated quantities for a specific portion of the work are designated as the pay quantities in the contract, they shall be the final quantities for which payment for such specific portion of the work will be made, unless the dimensions of said portions of the work shown on the plans are revised by the Engineer.  If revised dimensions result in an increase or decrease in the quantities of such work, the final quantities for payment will be revised in the amount represented by the authorized changes in the dimensions.

90-02  SCOPE OF PAYMENT.  The Contractor shall receive and accept compensation provided for in the contract as full payment for furnishing all materials, for performing all work under the contract in a complete and acceptable manner, and for all risk, loss, damage, or expense of whatever character arising out of the nature of the work or the prosecution thereof, subject to the provisions of the subsection titled NO WAIVER OF LEGAL RIGHTS of Section 70.

When the ``basis of payment'' subsection of a technical specification requires that the contract price (price bid) include compensation for certain work or material essential to the item, this same work or material will not also be measured for payment under any other contract item which may appear elsewhere in the contract, plans, or specifications.

90-03  COMPENSATION FOR ALTERED QUANTITIES.  When the accepted quantities of work vary from the quantities in the proposal, the Contractor shall accept as payment in full, so far as contract items are concerned, payment at the original contract price for the accepted quantities of work actually completed and accepted.  No allowance, except as provided for in the subsection titled ALTERATION OF WORK AND QUANTITIES of Section 40 will be made for any increased expense, loss of expected reimbursement, or loss of anticipated profits suffered or claimed by the Contractor which results directly from such alterations or indirectly from his/her unbalanced allocation of overhead and profit among the contract items, or from any other cause.

90-04  PAYMENT FOR OMITTED ITEMS.  As specified in the subsection titled OMITTED ITEMS of Section 40, the Engineer shall have the right to omit from the work (order nonperformance) any contract item, except major contract items, in the best interest of the Owner.

Should the Engineer omit or order nonperformance of a contract item or portion of such item from the work, the Contractor shall accept payment in full at the contract prices for any work actually completed and acceptable prior to the Engineer's order to omit or nonperform such contract item.

Acceptable materials ordered by the Contractor or delivered on the work prior to the date of the Engineer's order will be paid for at the actual cost to the Contractor and shall thereupon become the property of the Owner.

In addition to the reimbursement hereinbefore provided, the Contractor shall be reimbursed for all actual costs incurred for the purpose of performing the omitted contract item prior to the date of the Engineer's order.  Such additional costs incurred by the Contractor must be directly related to the deleted contract item and shall be supported by certified statements by the Contractor as to the nature the amount of such costs.

90-05  PAYMENT FOR EXTRA AND FORCE ACCOUNT WORK.  Extra work, performed in accordance with the subsection titled EXTRA WORK of Section 40, will be paid for at the contract prices or agreed prices specified in the change order or supplemental agreement authorizing the extra work.  When the change order or supplemental agreement authorizing the extra work requires that it be done by force account, such force account shall be measured and paid for based on expended labor, equipment, and materials plus a negotiated and agreed upon allowance for overhead and profit.

a.  Miscellaneous.  No additional allowance will be made for general superintendence, the use of small tools, or other costs for which no specific allowance is herein provided.

b.  Comparison of Record.  The Contractor and the Engineer shall compare records of the cost of force account work at the end of each day.  Agreement shall be indicated by signature of the Contractor and the Engineer or their duly authorized representatives.

c.  Statement.  No payment will be made for work performed on a force account basis until the Contractor has furnished the Engineer with duplicate itemized statements of the cost of such force account work detailed as follows:

(1)  Name, classification, date, daily hours, total hours, rate and extension for each laborer and foreman.

(2)  Designation, dates, daily hours, total hours, rental rate, and extension for each unit of machinery and equipment.

(3)  Quantities of materials, prices, and extensions.

(4)  Transportation of materials.

(5)  Cost of property damage, liability and workman's compensation insurance premiums, unemployment insurance contributions, and social security tax.

Statements shall be accompanied and supported by a receipted invoice for all materials used and transportation charges.  However, if materials used on the force account work are not specifically purchased for such work but are taken from the Contractor's stock, then in lieu of the invoices the Contractor shall furnish an affidavit certifying that such materials were taken from his/her stock, that the quantity claimed was actually used, and that the price and transportation claimed represent the actual cost to the Contractor.

90-06  PARTIAL PAYMENTS.  Partial payments will be made at least once each month as the work progresses.  Said payments will be based upon estimates prepared by the Engineer of the value of the work performed and materials  complete in place in accordance with the contract, plans, and specifications.  Such partial payments may also include the delivered actual cost of those materials stockpiled and stored in accordance with the subsection titled PAYMENT FOR MATERIALS ON HAND of this section.

No partial payment will be made when the amount due the Contractor since the last estimate amounts to less than five hundred dollars.

From the total of the amount determined to be payable on a partial payment, 10 percent of such total amount will be deducted and retained by the Owner until the final payment is made, except as may be provided (at the Contractor's option) in the subsection titled PAYMENT OF WITHHELD FUNDS of this section. The balance (90 percent) of the amount payable, less all previous payments, shall be certified for payment.  Should the Contractor exercise his/her option, as provided in the subsection titled PAYMENT OF WITHHELD FUNDS of this section, no such 10 percent retainage shall be deducted.

When not less than 95 percent of the work has been completed, the Engineer may, at the Owner's discretion and with the consent of the surety, prepare an estimate from which will be retained an amount not less than twice the contract value or estimated cost, whichever is greater, of the work remaining to be done.  The remainder, less all previous payments and deductions, will then be certified for payment to the Contractor.

It is understood and agreed that the Contractor shall not be entitled to demand or receive partial payment based on quantities of work in excess of those provided in the proposal or covered by approved change orders or supplemental agreements, except when such excess quantities have been determined by the Engineer to be a part of the final quantity for the item of work in question.

No partial payment shall bind the Owner to the acceptance of any materials or work in place as to quality or quantity.  All partial payments are subject to correction at the time of final payment as provided in the subsection titled ACCEPTANCE AND FINAL PAYMENT of this section.

The Contractor shall deliver to the Owner a complete release of all claims for labor and material arising out of this contract before the final retained percentage or final payment is made.  If any subcontractor or supplier fails to furnish such a release in full, the Contractor may furnish a bond or other collateral satisfactory to the Owner to indemnify the Owner against any potential lien or other such claim.  The bond or collateral shall include all costs, expenses, and attorney fees the Owner may be compelled to pay in discharging any such lien or claim.

- * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

In some areas, release of liens prior to paying the full amount to the prime contractor may void the contract.  In those areas, revise the previous paragraph as required to meet all state and local regulations.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

90-07  PAYMENT FOR MATERIALS ON HAND.  Partial payments may be made to the extent of the delivered cost of materials to be incorporated in the work, provided that such materials meet the requirements of the contract, plans, and specifications and are delivered to acceptable sites on the airport property or at other sites in the vicinity that are acceptable to the Owner.  Such delivered costs of stored or stockpiled materials may be included in the next partial payment after the following conditions are met:

a.  The material has been stored or stockpiled in a manner acceptable to the Engineer at or on an approved site.

b.  The Contractor has furnished the Engineer with acceptable evidence of the quantity and quality of such stored or stockpiled materials.

c.  The Contractor has furnished the Engineer with satisfactory evidence that the material and transportation costs have been paid.

d.  The Contractor has furnished the Owner legal title (free of liens or encumbrances of any kind) to the material so stored or stockpiled.

e.  The Contractor has furnished the Owner evidence that the material so stored or stockpiled is insured against loss by damage to or disappearance of such materials at anytime prior to use in the work.

It is understood and agreed that the transfer of title and the Owner's payment for such stored or stockpiled materials shall in no way relieve the Contractor of his/her responsibility for furnishing and placing such materials in accordance with the requirements of the contract, plans, and specifications.

In no case will the amount of partial payments for materials on hand exceed the contract price for such materials or the contract price for the contract item in which the material is intended to be used.

No partial payment will be made for stored or stockpiled living or perishable plant materials.

The Contractor shall bear all costs associated with the partial payment of stored or stockpiled materials in accordance with the provisions of this subsection.

90-08  PAYMENT OF WITHHELD FUNDS.  At the Contractor's option, he/she may request that the Owner accept (in lieu of the 10 percent retainage on partial payments described in the subsection titled PARTIAL PAYMENTS of this section) the Contractor's deposits in escrow under the following conditions.

a.  The Contractor shall bear all expenses of establishing and maintaining an escrow account and escrow agreement acceptable to the Owner.

b.  The Contractor shall deposit to and maintain in such escrow only those securities or bank certificates of deposit as are acceptable to the Owner and having a value not less than the 10 percent retainage that would otherwise be withheld from partial payment.

c.  The Contractor shall enter into an escrow agreement satisfactory to the Owner.

d.  The Contractor shall obtain the written consent of the surety to such agreement.

90-09  ACCEPTANCE AND FINAL PAYMENT.  When the contract work has been accepted in accordance with the requirements of the subsection titled FINAL ACCEPTANCE of Section 50, the Engineer will prepare the final estimate of the items of work actually performed.  The Contractor shall approve the Engineer's final estimate or advise the Engineer of his/her objections to the final estimate which are based on disputes in measurements or computations of the final quantities to be paid under the contract as amended by change order or supplemental agreement.  The Contractor and the Engineer shall resolve all disputes (if any) in the measurement and computation of final quantities to be paid within 30 calendar days of the Contractor's receipt of the Engineer's final estimate.  If, after such 30-day period, a dispute still exists, the Contractor may approve the Engineer's estimate under protest of the quantities in dispute, and such disputed quantities shall be considered by the Owner as a claim in accordance with the subsection titled CLAIMS FOR ADJUSTMENT AND DISPUTES of Section 50.

After the Contractor has approved, or approved under protest, the Engineer's final estimate, final payment will be processed based on the entire sum, or the undisputed sum in case of approval under protest, determined to be due the Contractor less all previous payments and all amounts to be deducted under the provisions of the contract.  All prior partial estimates and payments shall be subject to correction in the final estimate and payment.

If the Contractor has filed a claim for additional compensation under the provisions of the subsection titled CLAIMS FOR ADJUSTMENTS AND DISPUTES of Section 50 or under the provisions of this subsection, such claims will be considered by the Owner in accordance with local laws or ordinances.  Upon final adjudication of such claims, any additional payment determined to be due the Contractor will be paid pursuant to a supplemental final estimate.

90-10  CONSTRUCTION WARRANTY.  In addition to any other warranties in this contract, the Contractor warrants that work performed under this contract conforms to the contract requirements and is free of any defect in equipment, material, or design furnished, or workmanship performed by the Contractor or any subcontractor or supplier at any tier. This warranty shall continue for a period of 1 year from the date of final acceptance of the work. If the Owner takes possession of any part of the work before final acceptance, this warranty shall continue for a period of 1 year from the date the Owner takes possession.

The Contractor shall remedy at the Contractor's expense any failure to conform, or any defect. In addition, the Contractor shall remedy at the Contractor's expense any damage to Owner real or personal property, when that damage is the result of:

(1) The Contractor's failure to conform to contract requirements; or

(2) Any defect of equipment, material, workmanship, or design furnished by the Contractor.

The Contractor shall restore any work damaged in fulfilling the terms and conditions of this clause. The Contractor's warranty with respect to work repaired or replaced will run for 1 year from the date of repair or replacement.

The Owner will notify the Contractor, in writing, within a reasonable time after the discovery of any failure, defect, or damage. If the Contractor fails to remedy any failure, defect, or damage within a reasonable time after receipt of notice, the Owner shall have the right to replace, repair, or otherwise remedy the failure, defect, or damage at the Contractor's expense.

With respect to all warranties, express or implied, from subcontractors, manufacturers, or suppliers for work performed and materials furnished under this contract, the Contractor shall:

(1) Obtain all warranties that would be given in normal commercial practice;

(2) Require all warranties to be executed, in writing, for the benefit of the owner, as directed by the owner, and

(3) Enforce all warranties for the benefit of the owner.

This warranty shall not limit the Owner’s rights with respect to latent defects, gross mistakes, or fraud.

90-11  PROJECT CLOSEOUT.  Approval of final payment to the contractor is contingent upon completion and submittal of the items listed below. The final payment will not be approved until the engineer approves the contractor’s submittal.

The contractor shall:

(a)	Provide two (2) copies of all manufacturers warranties specified for materials, equipment, and installations.

(b)	Provide weekly payroll records (not previously received) from the general contractor and all subcontractors.

(c)	Complete final clean up in accordance with Subsection 40-09.

(d)	Complete all punch list items identified during the Final Inspection.

(e)	Provide an executed Certification Regarding Settlement of Claims for release of all claims for labor and material arising out of the Contract. Form is available on the MoDOT Aviation Website.

END OF SECTION 90

# SECTION 100

CONTRACTOR QUALITY CONTROL PROGRAM

100-01  GENERAL.  When the specification requires a Contractor Quality Control Program, the Contractor shall establish, provide, and maintain an effective Quality Control Program that details the methods and procedures that will be taken to assure that all materials and completed construction required by this contract conform to contract plans, technical specifications and other requirements, whether manufactured by the Contractor, or procured from subcontractors or vendors.  Although guidelines are established and certain minimum requirements are specified herein and elsewhere in the contract technical specifications, the Contractor shall assume full responsibility for accomplishing the stated purpose.

The intent of this section is to enable the Contractor to establish a necessary level of control that will:

a.  Adequately provide for the production of acceptable quality materials.

b.  Provide sufficient information to assure both the Contractor and the Engineer that the specification requirements can be met.

c.  Allow the Contractor as much latitude as possible to develop his or her own standard of control.

The Contractor shall be prepared to discuss and present, at the preconstruction conference, his/her understanding of the quality control requirements.  The Contractor shall not begin any construction or production of materials to be incorporated into the completed work until the Quality Control Program has been reviewed by the Engineer.  No partial payment will be made for materials subject to specific quality control requirements until the Quality Control Program has been reviewed.

The quality control requirements contained in this section and elsewhere in the contract technical specifications are in addition to and separate from the acceptance testing requirements.  Acceptance testing requirements are the responsibility of the Engineer.

- 100-02  DESCRIPTION OF PROGRAM.

a.  General Description.  The Contractor shall establish a Quality Control Program to perform inspection and testing of all items of work required by the technical specifications, including those performed by subcontractors.  This Quality Control Program shall ensure conformance to applicable specifications and plans with respect to materials, workmanship, construction, finish, and functional performance.  The Quality Control Program shall be effective for control of all construction work performed under this Contract and shall specifically include surveillance and tests required by the technical specifications, in addition to other requirements of this section and any other activities deemed necessary by the Contractor to establish an effective level of quality control.

b.  Quality Control Program.  The Contractor shall describe the Quality Control Program in a written document that shall be reviewed by the Engineer prior to the start of any production, construction, or off-site fabrication.  The written Quality Control Program shall be submitted to the Engineer for review at least {      } calendar days before the {       }.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

The Engineer should choose an adequate period for review.  A minimum of 5 days before the preconstruction conference or the start of work is recommended.

Submittal of the written Quality Control Program prior to the preconstruction conference will allow the Engineer to review the contents and make suggestions at the preconstruction meeting.

Submittal of the written Quality Control Program prior to the start of work will allow for detailed discussion of the requirements at the preconstruction meeting.  This will give the Contractor a better understanding of the requirements before developing the Quality Control Program.

When selecting the required days for the contractor to submit the Quality Control program, adequate time should be allowed for the Quality Control Program to be a supplement to the Owner's Construction Management Plan.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

The Quality Control Program shall be organized to address, as a minimum, the following items:

a.  Quality control organization;

b.  Project progress schedule;

c.  Submittals schedule;

d.  Inspection requirements;

e.  Quality control testing plan;

f.  Documentation of quality control activities; and

g.  Requirements for corrective action when quality control and/or acceptance criteria are not met.

The Contractor is encouraged to add any additional elements to the Quality Control Program that he/she deems necessary to adequately control all production and/or construction processes required by this contract.

100-03  QUALITY CONTROL ORGANIZATION.  The Contractor Quality Control Program shall be implemented by the establishment of a separate quality control organization.  An organizational chart shall be developed to show all quality control personnel and how these personnel integrate with other management/production and construction functions and personnel.

The organizational chart shall identify all quality control staff by name and function, and shall indicate the total staff required to implement all elements of the Quality Control Program, including inspection and testing for each item of work.  If necessary, different technicians can be utilized for specific inspection and testing functions for different items of work.  If an outside organization or independent testing laboratory is used for implementation of all or part of the Quality Control Program, the personnel assigned shall be subject to the qualification requirements of paragraph 100-03a and 100-03b.  The organizational chart shall indicate which personnel are Contractor employees and which are provided by an outside organization.

The quality control organization shall consist of the following minimum personnel:

a.  Program Administrator.  The Program Administrator shall be a full-time employee of the Contractor, or a consultant engaged by the Contractor.  The Program Administrator shall have a minimum of 5 years of experience in airport and/or highway construction and shall have had prior quality control experience on a project of comparable size and scope as the contract.

Additional qualifications for the Program Administrator shall include at least 1 of the following requirements:

(1)  Professional engineer with 1 year of airport paving experience acceptable to the Engineer.

(2)  Engineer-in-training with 2 years of airport paving experience acceptable to the Engineer.

(3)  An individual with 3 years of highway and/or airport paving experience acceptable to the Engineer, with a Bachelor of Science Degree in Civil Engineering, Civil Engineering Technology or Construction.

(4)  Construction materials technician certified at Level III by the National Institute for Certification in Engineering Technologies (NICET).

(5)  Highway materials technician certified at Level III by NICET.

(6)  Highway construction technician certified at Level III by NICET.

(7)  A NICET certified engineering technician in Civil Engineering Technology with 5 years of highway and/or airport paving experience acceptable to the Engineer.

The Program Administrator shall have full authority to institute any and all actions necessary for the successful implementation of the Quality Control Program to ensure compliance with the contract plans and technical specifications.  The Program Administrator shall report directly to a responsible officer of the construction firm.  The Program Administrator may supervise the Quality Control Program on more than one project provided that person can be at the job site within 2 hours after being notified of a problem.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

If, in the opinion of the Engineer, the project is of sufficient scope and size to warrant a full time, on-site Program Administrator, paragraph 100-03a should be modified accordingly.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

b.  Quality Control Technicians.  A sufficient number of quality control technicians necessary to adequately implement the Quality Control Program shall be provided.  These personnel shall be either engineers, engineering technicians, or experienced craftsman with qualifications in the appropriate field equivalent to NICET Level II or higher construction materials technician or highway construction technician and shall have a minimum of 2 years of experience in their area of expertise.

The quality control technicians shall report directly to the Program Administrator and shall perform the following functions:

(1)  Inspection of all materials, construction, plant, and equipment for conformance to the technical specifications, and as required by Section 100-06.

(2)  Performance of all quality control tests as required by the technical specifications and Section 100-07.

Certification at an equivalent level, by a state or nationally recognized organization will be acceptable in lieu of NICET certification.

c.  Staffing Levels.  The Contractor shall provide sufficient qualified quality control personnel to monitor each work activity at all times.  Where material is being produced in a plant for incorporation into the work, separate plant and field technicians shall be provided at each plant and field placement location.  The scheduling and coordinating of all inspection and testing must match the type and pace of work activity.  The Quality Control Program shall state where different technicians will be required for different work elements.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

On projects > 1 million dollars of paving recommend requiring full time QC on site during all operations related to construction of pavement section, e.g. grading, base and paving.

* * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * * *

100-04  PROJECT PROGRESS SCHEDULE.  The Contractor shall submit a coordinated construction schedule for all work activities.  The schedule shall be prepared as a network diagram in Critical Path Method (CPM), PERT, or other format, or as otherwise specified in the contract.  As a minimum, it shall provide information on the sequence of work activities, milestone dates, and activity duration.

The Contractor shall maintain the work schedule and provide an update and analysis of the progress schedule on a twice-monthly basis, or as otherwise specified in the contract.  Submission of the work schedule shall not relieve the Contractor of overall responsibility for scheduling, sequencing, and coordinating all work to comply with the requirements of the contract.

100-05  SUBMITTALS SCHEDULE.  The Contractor shall submit a detailed listing of all submittals (e.g., mix designs, material certifications) and shop drawings required by the technical specifications.  The listing can be developed in a spreadsheet format and shall include:

a.  Specification item number;

b.  Item description;

c.  Description of submittal;

d.  Specification paragraph requiring submittal; and

e.  Scheduled date of submittal.

100-06  INSPECTION REQUIREMENTS.  Quality control inspection functions shall be organized to provide inspections for all definable features of work, as detailed below.  All inspections shall be documented by the Contractor as specified by Section 100-07.

Inspections shall be performed daily to ensure continuing compliance with contract requirements until completion of the particular feature of work.  These shall include the following minimum requirements:

a.  During plant operation for material production, quality control test results and periodic inspections shall be utilized to ensure the quality of aggregates and other mix components, and to adjust and control mix proportioning to meet the approved mix design and other requirements of the technical specifications.  All equipment utilized in proportioning and mixing shall be inspected to ensure its proper operating condition.  The Quality Control Program shall detail how these and other quality control functions will be accomplished and utilized.

b.  During field operations, quality control test results and periodic inspections shall be utilized to ensure the quality of all materials and workmanship.  All equipment utilized in placing, finishing, and compacting shall be inspected to ensure its proper operating condition and to ensure that all such operations are in conformance to the technical specifications and are within the plan dimensions, lines, grades, and tolerances specified.  The Program shall document how these and other quality control functions will be accomplished and utilized.

100-07  QUALITY CONTROL TESTING PLAN.  As a part of the overall Quality Control Program, the Contractor shall implement a quality control testing plan, as required by the technical specifications.  The testing plan shall include the minimum tests and test frequencies required by each technical specification Item, as well as any additional quality control tests that the Contractor deems necessary to adequately control production and/or construction processes.

The testing plan can be developed in a spreadsheet fashion and shall, as a minimum, include the following:

a.  Specification item number (e.g., P-401);

b.  Item description (e.g., Plant Mix Bituminous Pavements);

c.  Test type (e.g., gradation, grade, asphalt content);

d.  Test standard (e.g., ASTM or AASHTO test number, as applicable);

e.  Test frequency (e.g., as required by technical specifications or minimum frequency when requirements are not stated);

f.  Responsibility (e.g., plant technician); and

g.  Control requirements (e.g., target, permissible deviations).

The testing plan shall contain a statistically-based procedure of random sampling for acquiring test samples in accordance with ASTM D 3665.  The Engineer shall be provided the opportunity to witness quality control sampling and testing.

All quality control test results shall be documented by the Contractor as required by Section 100-08.

100-08  DOCUMENTATION.  The Contractor shall maintain current quality control records of all inspections and tests performed.  These records shall include factual evidence that the required inspections or tests have been performed, including type and number of inspections or tests involved; results of inspections or tests; nature of defects, deviations, causes for rejection, etc.; proposed remedial action; and corrective actions taken.

These records must cover both conforming and defective or deficient features, and must include a statement that all supplies and materials incorporated in the work are in full compliance with the terms of the contract.  Legible copies of these records shall be furnished to the Engineer daily.  The records shall cover all work placed subsequent to the previously furnished records and shall be verified and signed by the Contractor's Program Administrator.

Specific Contractor quality control records required for the contract shall include, but are not necessarily limited to, the following records:

a.  Daily Inspection Reports.  Each Contractor quality control technician shall maintain a daily log of all inspections performed for both Contractor and subcontractor operations on a form acceptable to the Engineer.  These technician's daily reports shall provide factual evidence that continuous quality control inspections have been performed and shall, as a minimum, include the following:

(1)  Technical specification item number and description;

(2)  Compliance with approved submittals;

(3)  Proper storage of materials and equipment;

(4)  Proper operation of all equipment;

(5)  Adherence to plans and technical specifications;

(6)  Review of quality control tests; and

(7)  Safety inspection.

The daily inspection reports shall identify inspections conducted, results of inspections, location and nature of defects found, causes for rejection, and remedial or corrective actions taken or proposed.

The daily inspection reports shall be signed by the responsible quality control technician and the Program Administrator.  The Engineer shall be provided at least one copy of each daily inspection report on the work day following the day of record.

b.  Daily Test Reports.  The Contractor shall be responsible for establishing a system that will record all quality control test results.  Daily test reports shall document the following information:

(1)  Technical specification item number and description;

(2)  Test designation;

(3)  Location;

(4)  Date of test;

(5)  Control requirements;

(6)  Test results;

(7)  Causes for rejection;

(8)  Recommended remedial actions; and

(9)  Retests.

Test results from each day's work period shall be submitted to the Engineer prior to the start of the next day's work period.  When required by the technical specifications, the Contractor shall maintain statistical quality control charts.  The daily test reports shall be signed by the responsible quality control technician and the Program Administrator.

100-09  CORRECTIVE ACTION REQUIREMENTS.  The Quality Control Program shall indicate the appropriate action to be taken when a process is deemed, or believed, to be out of control (out of tolerance) and detail what action will be taken to bring the process into control.  The requirements for corrective action shall include both general requirements for operation of the Quality Control Program as a whole, and for individual items of work contained in the technical specifications.

The Quality Control Program shall detail how the results of quality control inspections and tests will be used for determining the need for corrective action and shall contain clear sets of rules to gauge when a process is out of control and the type of correction to be taken to regain process control.

When applicable or required by the technical specifications, the Contractor shall establish and utilize statistical quality control charts for individual quality control tests.  The requirements for corrective action shall be linked to the control charts.

100-10  SURVEILLANCE BY THE ENGINEER.  All items of material and equipment shall be subject to surveillance by the Engineer at the point of production, manufacture or shipment to determine if the Contractor, producer, manufacturer or shipper maintains an adequate quality control system in conformance with the requirements detailed herein and the applicable technical specifications and plans.  In addition, all items of materials, equipment and work in place shall be subject to surveillance by the Engineer at the site for the same purpose.

Surveillance by the Engineer does not relieve the Contractor of performing quality control inspections of either on-site or off-site Contractor's or subcontractor's work.

- 100-11  NONCOMPLIANCE.

a.  The Engineer will notify the Contractor of any noncompliance with any of the foregoing requirements.  The Contractor shall, after receipt of such notice, immediately take corrective action.  Any notice, when delivered by the Engineer or his/her authorized representative to the Contractor or his/her authorized representative at the site of the work, shall be considered sufficient notice.

b.  In cases where quality control activities do not comply with either the Contractor Quality Control Program or the contract provisions, or where the Contractor fails to properly operate and maintain an effective Quality Control Program, as determined by the Engineer, the Engineer may:

(1)  Order the Contractor to replace ineffective or unqualified quality control personnel or subcontractors.

(2)  Order the Contractor to stop operations until appropriate corrective actions are taken.

END OF SECTION 100

SECTION 110

METHOD OF ESTIMATING PERCENTAGE OF MATERIAL
WITHIN SPECIFICATION LIMITS (PWL)

110-01  GENERAL.  When the specifications provide for acceptance of material based on the method of estimating percentage of material within specification limits (PWL), the PWL will be determined in accordance with this section.  All test results for a lot will be analyzed statistically to determine the total estimated percent of the lot that is within specification limits.  The PWL is computed using the sample average (X) and sample standard deviation (Sn) of the specified number (n) of sublots for the lot and the specification tolerance limits, L for lower and U for upper, for the particular acceptance parameter.  From these values, the respective Quality index(s), QL for Lower Quality Index and/or QU for Upper Quality Index, is computed and the PWL for the lot for the specified n is determined from Table 1.  All specification limits specified in the technical sections shall be absolute values.  Test results used in the calculations shall be to the significant figure given in the test procedure.

There is some degree of uncertainty (risk) in the measurement for acceptance because only a small fraction of production material (the population) is sampled and tested.  This uncertainty exists because all portions of the production material have the same probability to be randomly sampled.  The Contractor's risk is the probability that material produced at the acceptable quality level is rejected or subjected to a pay adjustment.  The Owner’s risk is the probability that material produced at the rejectable quality level is accepted.

IT IS THE INTENT OF THIS SECTION TO INFORM THE CONTRACTOR THAT, IN ORDER TO CONSISTENTLY OFFSET THE CONTRACTOR’S RISK FOR MATERIAL EVALUATED, PRODUCTION QUALITY (USING POPULATION AVERAGE AND POPULATION STANDARD DEVIATION) MUST BE MAINTAINED AT THE ACCEPTABLE QUALITY SPECIFIED OR HIGHER.  IN ALL CASES, IT IS THE RESPONSIBILITY OF THE CONTRACTOR TO PRODUCE AT QUALITY LEVELS THAT WILL MEET THE SPECIFIED ACCEPTANCE CRITERIA WHEN SAMPLED AND TESTED AT THE FREQUENCIES SPECIFIED.

110-02  METHOD FOR COMPUTING PWL.  The computational sequence for computing PWL is as follows:

a.  Divide the lot into n sublots in accordance with the acceptance requirements of the specification.

b. Locate the random sampling position within the sublot in accordance with the requirements of the specification.

c.  Make a measurement at each location, or take a test portion and make the measurement on the test portion in accordance with the testing requirements of the specification.

d.  Find the sample average (X) for all sublot values within the lot by using the following formula:

X  =  (x1 + x2 + x3 + . . .xn) / n

Where:  X =  Sample average of all sublot values within a lot

x1, x2  =  Individual sublot values

n  =  Number of sublots

e.  Find the sample standard deviation (Sn) by use of the following formula:

Sn  =  [(d12 + d22 + d32 + . . .dn2)/(n-1)]1/2

Where:	Sn  =  Sample standard deviation of the number of sublot values in the set

d1, d2,  =  Deviations of the individual sublot values x1, x2, … from the average value X

that is:  d1 = (x1 - X), d2 = (x2 - X)  … dn = (xn - X)

n  =  Number of sublots

f.  For single sided specification limits (i.e., L only), compute the Lower Quality Index QL by use of the following formula:

QL = (X - L) / Sn

Where:	L = specification lower tolerance limit

Estimate the percentage of material within limits (PWL) by entering Table 1 with QL, using the column appropriate to the total number (n) of measurements.  If the value of QL falls between values shown on the table, use the next higher value of PWL.

g.  For double-sided specification limits (i.e. L and U), compute the Quality Indexes QL and QU by use of the following formulas:

QL = (X - L) / Sn and QU = (U - X) / Sn

Where:	L and U = specification lower and upper tolerance limits

Estimate the percentage of material between the lower (L) and upper (U) tolerance limits (PWL) by entering Table 1 separately with QL and QU, using the column appropriate to the total number (n) of measurements, and determining the percent of material above PL and percent of material below PU for each tolerance limit.  If the values of QL fall between values shown on the table, use the next higher value of PL or PU.  Determine the PWL by use of the following formula:

PWL = (PL + PU) - 100

Where:  	PL = percent within lower specification limit

PU = percent within upper specification limit

#### EXAMPLE OF PWL CALCULATION

Project:	  Example Project

Test Item:  Item P-401, Lot A.

- A.  PWL Determination for Mat Density.

1.  Density of four random cores taken from Lot A.

A-1    96.60

A-2    97.55

A-3    99.30

A-4    98.35

n = 4

2.  Calculate average density for the lot.

X = (x1 + x2 + x3 + . . .xn) / n

X = (96.60 + 97.55 + 99.30 + 98.35) / 4

X = 97.95 percent density

3.  Calculate the standard deviation (Sn) for the lot.

Sn  =  [(d12 + d22 + d32 + . . .dn2)/(n-1)]1/2

Sn  = [((96.60 - 97.95)2 + (97.55 - 97.95)2 +(99.30 -97.95)2 + (98.35 -97.95)2)) / (4 - 1)]1/2

Sn = [(1.82 + 0.16 + 1.82 + 0.16) / 3]1/2

Sn = 1.15

4.  Calculate the Lower Quality Index QL for the lot. (L=96.3)

QL = (X -L) / Sn

QL = (97.95 - 96.30) / 1.15

QL = 1.4348

5.  Determine PWL by entering Table 1 with QL= 1.44 and n= 4.

PWL = 98

- B.  PWL Determination for Air Voids.

1.  Air Voids of four random samples taken from Lot A.

A-1    5.00

A-2    3.74

A-3    2.30

A-4    3.25

2.  Calculate the average air voids for the lot.

X = (x1 + x2 + x3 +. . .xn) / n

X = (5.00 + 3.74 + 2.30 + 3.25) / 4

X = 3.57 percent

3.  Calculate the standard deviation (Sn) for the lot.

Sn  =  [(d12 + d22 + d32 + . . .dn2)/(n-1)]1/2

Sn = [((3.57 - 5.00)2 + (3.57 - 3.74)2 + (3.57 - 2.30)2 + (3.57 -3.25)2) / (4 - 1)]1/2

Sn = [(2.04 + 0.03 + 1.62 + 0.10 ) / 3]1/2

Sn = 1.12

4.  Calculate the Lower Quality Index QL for the lot. (L= 2.0)

QL = (X - L) / Sn

QL = (3.57 - 2.00) / 1.12

QL = 1.3992

5.  Determine PL by entering Table 1 with QL = 1.41 and n = 4.

PL = 97

6.  Calculate the Upper Quality Index QU for the lot. (U= 5.0)

QU = (U - X) / Sn

QU = (5.00 - 3.57) / 1.12

QU = 1.2702

7.  Determine PU by entering Table 1 with QU = 1.29 and n = 4.

PU = 93

8.  Calculate Air Voids PWL

PWL = (PL + PU) - 100

PWL = (97 + 93) - 100 = 90

EXAMPLE OF OUTLIER CALCULATION (Reference ASTM E 178)

Project:  Example Project

Test Item:  Item P-401, Lot A.

- A.  Outlier Determination for Mat Density.

1.  Density of four random cores taken from Lot A. arranged in descending order.

A-3    99.30

A-4    98.35

A-2    97.55

A-1    96.60

2.  Use n=4 and upper 5 percent significance level of to find the critical value for test criterion = 1.463.

3.  Use average density, standard deviation, and test criterion value to evaluate density measurements.

a.  For measurements greater than the average:

If:  (measurement - average)/(standard deviation) is less than test criterion,

Then:  the measurement is not considered an outlier

for A-3   Check if ( 99.30 - 97.95 ) / 1.15 greater than 1.463

1.174 is less than 1.463, the value is not an outlier

b.  For measurements less than the average:

If  (average - measurement)/(standard deviation) is less than test criterion,

the measurement is not considered an outlier

for A-1   Check if ( 97.95 - 96.60 ) / 1.15 greater than 1.463

1.0 is less than 1.463, the value is not an outlier

NOTE:  In this example, a measurement would be considered an outlier if the density was:

greater than (97.95+1.463x1.15) = 99.63 percent or,

less than  (97.95-1.463x1.15) = 96.27 percent

| TABLE 1. TABLE FOR ESTIMATING PERCENT OF LOT WITHIN LIMITS (PWL) |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Percent Within Limits (PL and PU) | Positive Values of Q (QL and QU) |  |  |  |  |  |  |  |
|  | n=3 | n=4 | n=5 | n=6 | n=7 | n=8 | n=9 | n=10 |
| 99 | 1.1541 | 1.4700 | 1.6714 | 1.8008 | 1.8888 | 1.9520 | 1.9994 | 2.0362 |
| 98 | 1.1524 | 1.4400 | 1.6016 | 1.6982 | 1.7612 | 1.8053 | 1.8379 | 1.8630 |
| 97 | 1.1496 | 1.4100 | 1.5427 | 1.6181 | 1.6661 | 1.6993 | 1.7235 | 1.7420 |
| 96 | 1.1456 | 1.3800 | 1.4897 | 1.5497 | 1.5871 | 1.6127 | 1.6313 | 1.6454 |
| 95 | 1.1405 | 1.3500 | 1.4407 | 1.4887 | 1.5181 | 1.5381 | 1.5525 | 1.5635 |
| 94 | 1.1342 | 1.3200 | 1.3946 | 1.4329 | 1.4561 | 1.4717 | 1.4829 | 1.4914 |
| 93 | 1.1269 | 1.2900 | 1.3508 | 1.3810 | 1.3991 | 1.4112 | 1.4199 | 1.4265 |
| 92 | 1.1184 | 1.2600 | 1.3088 | 1.3323 | 1.3461 | 1.3554 | 1.3620 | 1.3670 |
| 91 | 1.1089 | 1.2300 | 1.2683 | 1.2860 | 1.2964 | 1.3032 | 1.3081 | 1.3118 |
| 90 | 1.0982 | 1.2000 | 1.2290 | 1.2419 | 1.2492 | 1.2541 | 1.2576 | 1.2602 |
| 89 | 1.0864 | 1.1700 | 1.1909 | 1.1995 | 1.2043 | 1.2075 | 1.2098 | 1.2115 |
| 88 | 1.0736 | 1.1400 | 1.1537 | 1.1587 | 1.1613 | 1.1630 | 1.1643 | 1.1653 |
| 87 | 1.0597 | 1.1100 | 1.1173 | 1.1192 | 1.1199 | 1.1204 | 1.1208 | 1.1212 |
| 86 | 1.0448 | 1.0800 | 1.0817 | 1.0808 | 1.0800 | 1.0794 | 1.0791 | 1.0789 |
| 85 | 1.0288 | 1.0500 | 1.0467 | 1.0435 | 1.0413 | 1.0399 | 1.0389 | 1.0382 |
| 84 | 1.0119 | 1.0200 | 1.0124 | 1.0071 | 1.0037 | 1.0015 | 1.0000 | 0.9990 |
| 83 | 0.9939 | 0.9900 | 0.9785 | 0.9715 | 0.9671 | 0.9643 | 0.9624 | 0.9610 |
| 82 | 0.9749 | 0.9600 | 0.9452 | 0.9367 | 0.9315 | 0.9281 | 0.9258 | 0.9241 |
| 81 | 0.9550 | 0.9300 | 0.9123 | 0.9025 | 0.8966 | 0.8928 | 0.8901 | 0.8882 |
| 80 | 0.9342 | 0.9000 | 0.8799 | 0.8690 | 0.8625 | 0.8583 | 0.8554 | 0.8533 |
| 79 | 0.9124 | 0.8700 | 0.8478 | 0.8360 | 0.8291 | 0.8245 | 0.8214 | 0.8192 |
| 78 | 0.8897 | 0.8400 | 0.8160 | 0.8036 | 0.7962 | 0.7915 | 0.7882 | 0.7858 |
| 77 | 0.8662 | 0.8100 | 0.7846 | 0.7716 | 0.7640 | 0.7590 | 0.7556 | 0.7531 |
| 76 | 0.8417 | 0.7800 | 0.7535 | 0.7401 | 0.7322 | 0.7271 | 0.7236 | 0.7211 |
| 75 | 0.8165 | 0.7500 | 0.7226 | 0.7089 | 0.7009 | 0.6958 | 0.6922 | 0.6896 |
| 74 | 0.7904 | 0.7200 | 0.6921 | 0.6781 | 0.6701 | 0.6649 | 0.6613 | 0.6587 |
| 73 | 0.7636 | 0.6900 | 0.6617 | 0.6477 | 0.6396 | 0.6344 | 0.6308 | 0.6282 |
| 72 | 0.7360 | 0.6600 | 0.6316 | 0.6176 | 0.6095 | 0.6044 | 0.6008 | 0.5982 |
| 71 | 0.7077 | 0.6300 | 0.6016 | 0.5878 | 0.5798 | 0.5747 | 0.5712 | 0.5686 |
| 70 | 0.6787 | 0.6000 | 0.5719 | 0.5582 | 0.5504 | 0.5454 | 0.5419 | 0.5394 |
| 69 | 0.6490 | 0.5700 | 0.5423 | 0.5290 | 0.5213 | 0.5164 | 0.5130 | 0.5105 |
| 68 | 0.6187 | 0.5400 | 0.5129 | 0.4999 | 0.4924 | 0.4877 | 0.4844 | 0.4820 |
| 67 | 0.5878 | 0.5100 | 0.4836 | 0.4710 | 0.4638 | 0.4592 | 0.4560 | 0.4537 |
| 66 | 0.5563 | 0.4800 | 0.4545 | 0.4424 | 0.4355 | 0.4310 | 0.4280 | 0.4257 |
| 65 | 0.5242 | 0.4500 | 0.4255 | 0.4139 | 0.4073 | 0.4030 | 0.4001 | 0.3980 |
| 64 | 0.4916 | 0.4200 | 0.3967 | 0.3856 | 0.3793 | 0.3753 | 0.3725 | 0.3705 |
| 63 | 0.4586 | 0.3900 | 0.3679 | 0.3575 | 0.3515 | 0.3477 | 0.3451 | 0.3432 |
| 62 | 0.4251 | 0.3600 | 0.3392 | 0.3295 | 0.3239 | 0.3203 | 0.3179 | 0.3161 |
| 61 | 0.3911 | 0.3300 | 0.3107 | 0.3016 | 0.2964 | 0.2931 | 0.2908 | 0.2892 |
| 60 | 0.3568 | 0.3000 | 0.2822 | 0.2738 | 0.2691 | 0.2660 | 0.2639 | 0.2624 |
| 59 | 0.3222 | 0.2700 | 0.2537 | 0.2461 | 0.2418 | 0.2391 | 0.2372 | 0.2358 |
| 58 | 0.2872 | 0.2400 | 0.2254 | 0.2186 | 0.2147 | 0.2122 | 0.2105 | 0.2093 |
| 57 | 0.2519 | 0.2100 | 0.1971 | 0.1911 | 0.1877 | 0.1855 | 0.1840 | 0.1829 |
| 56 | 0.2164 | 0.1800 | 0.1688 | 0.1636 | 0.1607 | 0.1588 | 0.1575 | 0.1566 |
| 55 | 0.1806 | 0.1500 | 0.1406 | 0.1363 | 0.1338 | 0.1322 | 0.1312 | 0.1304 |
| 54 | 0.1447 | 0.1200 | 0.1125 | 0.1090 | 0.1070 | 0.1057 | 0.1049 | 0.1042 |
| 53 | 0.1087 | 0.0900 | 0.0843 | 0.0817 | 0.0802 | 0.0793 | 0.0786 | 0.0781 |
| 52 | 0.0725 | 0.0600 | 0.0562 | 0.0544 | 0.0534 | 0.0528 | 0.0524 | 0.0521 |
| 51 | 0.0363 | 0.0300 | 0.0281 | 0.0272 | 0.0267 | 0.0264 | 0.0262 | 0.0260 |
| 50 | 0.0000 | 0.0000 | 0.0000 | 0.0000 | 0.0000 | 0.0000 | 0.0000 | 0.0000 |
| TABLE 1. TABLE FOR ESTIMATING PERCENT OF LOT WITHIN LIMITS (PWL) |  |  |  |  |  |  |  |  |
| Percent Within Limits (PL and PU) | Negative Values of Q (QL and QU) |  |  |  |  |  |  |  |
|  | n=3 | n=4 | n=5 | n=6 | n=7 | n=8 | n=9 | n=10 |
| 49 | -0.0363 | -0.0300 | -0.0281 | -0.0272 | -0.0267 | -0.0264 | -0.0262 | -0.0260 |
| 48 | -0.0725 | -0.0600 | -0.0562 | -0.0544 | -0.0534 | -0.0528 | -0.0524 | -0.0521 |
| 47 | -0.1087 | -0.0900 | -0.0843 | -0.0817 | -0.0802 | -0.0793 | -0.0786 | -0.0781 |
| 46 | -0.1447 | -0.1200 | -0.1125 | -0.1090 | -0.1070 | -0.1057 | -0.1049 | -0.1042 |
| 45 | -0.1806 | -0.1500 | -0.1406 | -0.1363 | -0.1338 | -0.1322 | -0.1312 | -0.1304 |
| 44 | -0.2164 | -0.1800 | -0.1688 | -0.1636 | -0.1607 | -0.1588 | -0.1575 | -0.1566 |
| 43 | -0.2519 | -0.2100 | -0.1971 | -0.1911 | -0.1877 | -0.1855 | -0.1840 | -0.1829 |
| 42 | -0.2872 | -0.2400 | -0.2254 | -0.2186 | -0.2147 | -0.2122 | -0.2105 | -0.2093 |
| 41 | -0.3222 | -0.2700 | -0.2537 | -0.2461 | -0.2418 | -0.2391 | -0.2372 | -0.2358 |
| 40 | -0.3568 | -0.3000 | -0.2822 | -0.2738 | -0.2691 | -0.2660 | -0.2639 | -0.2624 |
| 39 | -0.3911 | -0.3300 | -0.3107 | -0.3016 | -0.2964 | -0.2931 | -0.2908 | -0.2892 |
| 38 | -0.4251 | -0.3600 | -0.3392 | -0.3295 | -0.3239 | -0.3203 | -0.3179 | -0.3161 |
| 37 | -0.4586 | -0.3900 | -0.3679 | -0.3575 | -0.3515 | -0.3477 | -0.3451 | -0.3432 |
| 36 | -0.4916 | -0.4200 | -0.3967 | -0.3856 | -0.3793 | -0.3753 | -0.3725 | -0.3705 |
| 35 | -0.5242 | -0.4500 | -0.4255 | -0.4139 | -0.4073 | -0.4030 | -0.4001 | -0.3980 |
| 34 | -0.5563 | -0.4800 | -0.4545 | -0.4424 | -0.4355 | -0.4310 | -0.4280 | -0.4257 |
| 33 | -0.5878 | -0.5100 | -0.4836 | -0.4710 | -0.4638 | -0.4592 | -0.4560 | -0.4537 |
| 32 | -0.6187 | -0.5400 | -0.5129 | -0.4999 | -0.4924 | -0.4877 | -0.4844 | -0.4820 |
| 31 | -0.6490 | -0.5700 | -0.5423 | -0.5290 | -0.5213 | -0.5164 | -0.5130 | -0.5105 |
| 30 | -0.6787 | -0.6000 | -0.5719 | -0.5582 | -0.5504 | -0.5454 | -0.5419 | -0.5394 |
| 29 | -0.7077 | -0.6300 | -0.6016 | -0.5878 | -0.5798 | -0.5747 | -0.5712 | -0.5686 |
| 28 | -0.7360 | -0.6600 | -0.6316 | -0.6176 | -0.6095 | -0.6044 | -0.6008 | -0.5982 |
| 27 | -0.7636 | -0.6900 | -0.6617 | -0.6477 | -0.6396 | -0.6344 | -0.6308 | -0.6282 |
| 26 | -0.7904 | -0.7200 | -0.6921 | -0.6781 | -0.6701 | -0.6649 | -0.6613 | -0.6587 |
| 25 | -0.8165 | -0.7500 | -0.7226 | -0.7089 | -0.7009 | -0.6958 | -0.6922 | -0.6896 |
| 24 | -0.8417 | -0.7800 | -0.7535 | -0.7401 | -0.7322 | -0.7271 | -0.7236 | -0.7211 |
| 23 | -0.8662 | -0.8100 | -0.7846 | -0.7716 | -0.7640 | -0.7590 | -0.7556 | -0.7531 |
| 22 | -0.8897 | -0.8400 | -0.8160 | -0.8036 | -0.7962 | -0.7915 | -0.7882 | -0.7858 |
| 21 | -0.9124 | -0.8700 | -0.8478 | -0.8360 | -0.8291 | -0.8245 | -0.8214 | -0.8192 |
| 20 | -0.9342 | -0.9000 | -0.8799 | -0.8690 | -0.8625 | -0.8583 | -0.8554 | -0.8533 |
| 19 | -0.9550 | -0.9300 | -0.9123 | -0.9025 | -0.8966 | -0.8928 | -0.8901 | -0.8882 |
| 18 | -0.9749 | -0.9600 | -0.9452 | -0.9367 | -0.9315 | -0.9281 | -0.9258 | -0.9241 |
| 17 | -0.9939 | -0.9900 | -0.9785 | -0.9715 | -0.9671 | -0.9643 | -0.9624 | -0.9610 |
| 16 | -1.0119 | -1.0200 | -1.0124 | -1.0071 | -1.0037 | -1.0015 | -1.0000 | -0.9990 |
| 15 | -1.0288 | -1.0500 | -1.0467 | -1.0435 | -1.0413 | -1.0399 | -1.0389 | -1.0382 |
| 14 | -1.0448 | -1.0800 | -1.0817 | -1.0808 | -1.0800 | -1.0794 | -1.0791 | -1.0789 |
| 13 | -1.0597 | -1.1100 | -1.1173 | -1.1192 | -1.1199 | -1.1204 | -1.1208 | -1.1212 |
| 12 | -1.0736 | -1.1400 | -1.1537 | -1.1587 | -1.1613 | -1.1630 | -1.1643 | -1.1653 |
| 11 | -1.0864 | -1.1700 | -1.1909 | -1.1995 | -1.2043 | -1.2075 | -1.2098 | -1.2115 |
| 10 | -1.0982 | -1.2000 | -1.2290 | -1.2419 | -1.2492 | -1.2541 | -1.2576 | -1.2602 |
| 9 | -1.1089 | -1.2300 | -1.2683 | -1.2860 | -1.2964 | -1.3032 | -1.3081 | -1.3118 |
| 8 | -1.1184 | -1.2600 | -1.3088 | -1.3323 | -1.3461 | -1.3554 | -1.3620 | -1.3670 |
| 7 | -1.1269 | -1.2900 | -1.3508 | -1.3810 | -1.3991 | -1.4112 | -1.4199 | -1.4265 |
| 6 | -1.1342 | -1.3200 | -1.3946 | -1.4329 | -1.4561 | -1.4717 | -1.4829 | -1.4914 |
| 5 | -1.1405 | -1.3500 | -1.4407 | -1.4887 | -1.5181 | -1.5381 | -1.5525 | -1.5635 |
| 4 | -1.1456 | -1.3800 | -1.4897 | -1.5497 | -1.5871 | -1.6127 | -1.6313 | -1.6454 |
| 3 | -1.1496 | -1.4100 | -1.5427 | -1.6181 | -1.6661 | -1.6993 | -1.7235 | -1.7420 |
| 2 | -1.1524 | -1.4400 | -1.6016 | -1.6982 | -1.7612 | -1.8053 | -1.8379 | -1.8630 |
| 1 | -1.1541 | -1.4700 | -1.6714 | -1.8008 | -1.8888 | -1.9520 | -1.9994 | -2.0362 |

# END OF SECTION 110

# SECTION 4

# SUPPLEMENTARY PROVISIONS

# PART A

# STATE REQUIREMENTS

# 1.	MoDOT INSPECTION/REVIEW

# 2.	OCCUPATIONAL SAFETY AND HEALTH ADMINISTRATION CONSTRCUTION SAFETY TRAINING

# 3.	EXECUTIVE ORDER 94-03

# 4.	CERTIFICATION REGARDING ANTI-COLLUSION

# 5.	CERTIFICATION REGARDING MISSOURI DOMESTIC PRODUCTS PROCUREMENT ACT

6.	PROMPT PAYMENT

# 1.	MoDOT INSPECTION/REVIEW

# The contractor shall allow any authorized representative of MoDOT to inspect and review any work or materials used in the performance of this contract.

2.	OCCUPATIONAL SAFETY AND HEALTH ADMINISTRATION CONSTRCUTION SAFETY TRAINING

The Contractor and its subcontractors (if any subcontractors are retained) shall comply with all applicable provisions of section 292.675, Revised Statutes of Missouri, which statute is incorporated herein by reference and is made a part of this contract.  Section 292.675 states that any person signing a contract to work on the construction of public works for any public body shall provide a ten hour Occupational Safety and Health Administration (OSHA) construction safety program for their on-site employees, which includes a course in construction safety and health approved by OSHA or a similar program approved by the Department of Labor and Industrial Relations which is at least as stringent as an approved OSHA program, unless such employees have previously completed the required program and hold documentation of such prior completion.  All employees who have not previously completed the program are required to complete the program within sixty (60) days of beginning work on such construction project.  Any employee found on a worksite subject to section 292.675's requirements without documentation of the successful completion of this course shall have twenty (20) days to produce such documentation before being subject to removal from the project.

# The Contractor shall forfeit as penalty to the public body on whose behalf the contract is made or awarded two thousand five hundred dollars ($2,500) plus one hundred dollars ($100) for each employee employed by the contractor or subcontractor, for each calendar day, or portion thereof, such employee is employed by the contractor or subcontractor without the required training.  These penalties shall not begin to accrue until the sixty (60) day and twenty (20) day time periods described above have elapsed.  The public body awarding the contract shall withhold and retain therefrom all sums and amounts due and owing as a result of any violation of section 292.675 when making payments to the Contractor under the contract.  The Contractor may withhold from any subcontractor sufficient sums to cover any penalties the public body has withheld from the Contractor resulting from the subcontractor's failure to comply with the terms of section 292.675.

# 3.	EXECUTIVE ORDER 94-03

# The Contractor shall comply with all the provisions of Executive Order 94-03, issued by the Honorable Mel Carnahan, Governor of Missouri, on the fourteenth (14th) day of January 1994, which executive order is incorporated herein by reference and is made a part of this contract. This Executive Order which promulgates a Code of Fair Practices in regard to nondiscrimination, is incorporated herein by reference and made a part of this Contract. This Executive Order prohibits discriminatory practices by the state, the contractor or its subcontractors based on race, color, religion, national origin, sex, age, disability, or veterans status.

# 4.	CERTIFICATION REGARDING ANTI-COLLUSION

# In accordance with 23 USC #112 the bidder hereby states, under penalty of perjury, that they have not, either directly or indirectly, entered into any agreement, participated in any collusion, or otherwise taken any action in restraint of free competitive bidding in connection with this contract.

# 5.	CERTIFICATION REGARDING MISSOURI DOMESTIC PRODUCTS PROCUREMENT ACT

# The bidder’s attention is directed to sections 34.350 et seq RSMo Supp 2005 which required all manufactured goods or commodities used or supplied in the performance of this contract or any subcontract to be manufactured, assembled or produced in the United States. Sections 34.350 et seq RSMo Supp 2005 does not apply if the total bid is less than One Thousand Dollars (1,000.00).

# Section 34.355 RSMo Supp 2005 requires the vendor or bidder to certify their compliance with section 34.353 RSMo Supp 2005 and, if applicable, section 34.359 RSMo Supp 2005 at the time of the bidding and prior to payment. Failure to comply with section 34.353 RSMo 2005 during performance of the contract and to provide certification of compliance prior to payment will result in nonpayment for those goods or commodities.

# The bidder certifies that all the specified goods or products for which this bid was solicited are manufactured, assembled or produced in the United States, and more than one line of the specified goods or products are manufactured, assembled or produced in the United States. If there are any exceptions, the bidder shall list them below:

# ______________________________________________________________________

# _________________________________________________________________________

# _________________________________________________________________________

# For any specified goods or products which are manufactured, assembled or produced in the United States and for which only one line are manufactured, assembled or produced in the United States, the bidder shall indicate the specified goods or products.

# Item Number(s)	Item number(s)

# ___________________________	___________________________

# ___________________________	___________________________

# ___________________________	___________________________

# (use additional sheets if necessary)

# For any other exceptions noted, the bidder shall indicate the specified goods or products which are manufactured, assembled or produced in a country other than the “United States” as defined in section 34.350.2(2) RSMo Supp 2005 and: (a) list the country, other than the United States, where each good or product you propose to furnish is manufactured, assembled or produced; (b) check box(es) at left of the applicable paragraph(s).

# Location Where Item Manufactured,

# Item Number(s)	Assembled or Produced

# ___________________________	___________________________

# ___________________________	___________________________

# ___________________________	___________________________

# (use additional sheets if necessary)

# The specified goods or products cannot be manufactured, assembled or produced in the United States in sufficient quantities or in time to meet the contract specifications. Item number(s)  __________________________________

# ____________________________________________________________________________________________

# ____________________________________________________________________________________________

# (use additional sheets if necessary)

# The specified goods or products are treated as manufactured, assembled or produced in the United States under an existing treaty, law, agreement or regulation of the United States regarding export-import restrictions and international trade. Item number(s)  _______________________________________________________________

# ____________________________________________________________________________________________

# ___________________________________________________________________________________________

# (use additional sheets if necessary)

The bidder hereby certifies that the above information is true and correct and further certifies that this bid complies with all the provisions of sections 34.350 et seq RSMo Supp 2005.

6.	PROMPT PAYMENT

MoDOT and the city require all contractors to pay all subcontractors and suppliers for satisfactory performance of services in compliance with the prompt payment statute, Mo. Revised Statutes, Chapter 34, Section 34.057 (included below).  MoDOT and the city also requires the prompt, as defined in Section 34.057, return of all retainage held on all subcontractors after the subcontractor’s work is satisfactorily completed, as MoDOT and city personnel may ultimately determine (if necessary).

# Missouri Revised Statutes

## Chapter 34

## State Purchasing and Printing

## Section 34.057

## August 28, 2009

____________________________________________________________________________________________

Public works contracts--prompt payment by public owner to contractor--prompt payment by contractor to subcontractor-- progress payments--retainage--late payment charges-- withholding of payments.

34.057. 1. Unless contrary to any federal funding requirements or unless funds from a state grant are not timely received by the contracting public municipality but notwithstanding any other law to the contrary, all public works contracts made and awarded by the appropriate officer, board or agency of the state or of a political subdivision of the state or of any district therein, including any municipality, county and any board referred to as the public owner, for construction, reconstruction or alteration of any public works project, shall provide for prompt payment by the public owner to the contractor and prompt payment by the contractor to the subcontractor and material supplier in accordance with the following:

(1) A public owner shall make progress payments to the contractor on at least a monthly basis as the work progresses, or, on a lump sum basis according to the terms of the lump sum contract. Except in the case of lump sum contracts, payments shall be based upon estimates prepared at least monthly of work performed and material delivered, as determined by the project architect or engineer. Retainage withheld on public works projects shall not exceed five percent of the value of the contract or subcontract unless the public owner and the architect or engineer determine that a higher rate of retainage is required to ensure performance of the contract. Retainage, however, shall not exceed ten percent of the value of the contract or subcontract. Except as provided in subsection 4 of this section, the public owner shall pay the contractor the amount due, less a retainage not to exceed ten percent, within thirty days following the latter of the following:

(a) The date of delivery of materials or construction services purchased;

(b) The date, as designated by the public owner, upon which the invoice is duly delivered to the person or place designated by the public owner; or

(c) In those instances in which the contractor approves the public owner's estimate, the date upon which such notice of approval is duly delivered to the person or place designated by the public owner;

(2) Payments shall be considered received within the context of this section when they are duly posted with the United States Postal Service or other agreed upon delivery service or when they are hand-delivered to an authorized person or place as agreed to by the contracting parties;

(3) If, in the discretion of the owner and the project architect or engineer and the contractor, it is determined that a subcontractor's performance has been completed and the subcontractor can be released prior to substantial completion of the public works contract without risk to the public owner, the contractor shall request such adjustment in retainage, if any, from the public owner as necessary to enable the contractor to pay the subcontractor in full. The public owner may reduce or eliminate retainage on any contract payment if, in the public owner's opinion, the work is proceeding satisfactorily. If retainage is released and there are any remaining minor items to be completed, an amount equal to two hundred percent of the value of each item as determined by the public owner's duly authorized representative shall be withheld until such item or items are completed;

(4) The public owner shall pay the retainage, less any offsets or deductions authorized in the contract or otherwise authorized by law, to the contractor after substantial completion of the contract work and acceptance by the public owner's authorized contract representative, or as may otherwise be provided by the contract specifications for state highway, road or bridge projects administered by the state highways and transportation commission. Such payment shall be made within thirty days after acceptance, and the invoice and all other appropriate documentation and certifications in complete and acceptable form are provided, as may be required by the contract documents. If at that time there are any remaining minor items to be completed, an amount equal to two hundred percent of the value of each item as determined by the public owner's representative shall be withheld until such items are completed;

(5) All estimates or invoices for supplies and services purchased, approved and processed, or final payments, shall be paid promptly and shall be subject to late payment charges provided in this section. Except as provided in subsection 4 of this section, if the contractor has not been paid within thirty days as set forth in subdivision (1) of subsection 1 of this section, the contracting agency shall pay the contractor, in addition to the payment due him, interest at the rate of one and one-half percent per month calculated from the expiration of the thirty-day period until fully paid;

(6) When a contractor receives any payment, the contractor shall pay each subcontractor and material supplier in proportion to the work completed by each subcontractor and material supplier his application less any retention not to exceed ten percent. If the contractor receives less than the full payment due under the public construction contract, the contractor shall be obligated to disburse on a pro rata basis those funds received, with the contractor, subcontractors and material suppliers each receiving a prorated portion based on the amount of payment. When, however, the public owner does not release the full payment due under the contract because there are specific areas of work or materials he is rejecting or because he has otherwise determined such areas are not suitable for payment then those specific subcontractors or suppliers involved shall not be paid for that portion of the work rejected or deemed not suitable for payment and all other subcontractors and suppliers shall be paid in full;

(7) If the contractor, without reasonable cause, fails to make any payment to his subcontractors and material suppliers within fifteen days after receipt of payment under the public construction contract, the contractor shall pay to his subcontractors and material suppliers, in addition to the payment due them, interest in the amount of one and one-half percent per month, calculated from the expiration of the fifteen-day period until fully paid. This subdivision shall also apply to any payments made by subcontractors and material suppliers to their subcontractors and material suppliers and to all payments made to lower tier subcontractors and material suppliers throughout the contracting chain;

(8) The public owner shall make final payment of all moneys owed to the contractor, less any offsets or deductions authorized in the contract or otherwise authorized by law, within thirty days of the due date. Final payment shall be considered due upon the earliest of the following events:

(a) Completion of the project and filing with the owner of all required documentation and certifications, in complete and acceptable form, in accordance with the terms and conditions of the contract;

(b) The project is certified by the architect or engineer authorized to make such certification on behalf of the owner as having been completed, including the filing of all documentation and certifications required by the contract, in complete and acceptable form; or

(c) The project is certified by the contracting authority as having been completed, including the filing of all documentation and certifications required by the contract, in complete and acceptable form.

2. Nothing in this section shall prevent the contractor or subcontractor, at the time of application or certification to the public owner or contractor, from withholding such applications or certifications to the owner or contractor for payment to the subcontractor or material supplier. Amounts intended to be withheld shall not be included in such applications or certifications to the public owner or contractor. Reasons for withholding such applications or certifications shall include, but not be limited to, the following: unsatisfactory job progress; defective construction work or material not remedied; disputed work; failure to comply with other material provisions of the contract; third party claims filed or reasonable evidence that a claim will be filed; failure of the subcontractor to make timely payments for labor, equipment and materials; damage to a contractor or another subcontractor or material supplier; reasonable evidence that the contract can not be completed for the unpaid balance of the subcontract sum or a reasonable amount for retention, not to exceed the initial percentage retained by the owner.

3. Should the contractor determine, after application or certification has been made and after payment has been received from the public owner, or after payment has been received by a contractor based upon the public owner's estimate of materials in place and work performed as provided by contract, that all or a portion of the moneys needs to be withheld from a specific subcontractor or material supplier for any of the reasons enumerated in this section, and such moneys are withheld from such subcontractor or material supplier, then such undistributed amounts shall be specifically identified in writing and deducted from the next application or certification made to the public owner or from the next estimate by the public owner of payment due the contractor, until a resolution of the matter has been achieved. Disputes shall be resolved in accordance with the terms of the contract documents. Upon such resolution the amounts withheld by the contractor from the subcontractor or material supplier shall be included in the next application or certification made to the public owner or the next estimate by the public owner and shall be paid promptly in accordance with the provisions of this section. This subsection shall also apply to applications or certifications made by subcontractors or material suppliers to the contractor and throughout the various tiers of the contracting chain.

4. The contracts which provide for payments to the contractor based upon the public owner's estimate of materials in place and work performed rather than applications or certifications submitted by the contractor, the public owner shall pay the contractor within thirty days following the date upon which the estimate is required by contract to be completed by the public owner, the amount due less a retainage not to exceed five percent. All such estimates by the public owner shall be paid promptly and shall be subject to late payment charges as provided in this subsection. After the thirtieth day following the date upon which the estimate is required by contract to be completed by the public owner, the contracting agency shall pay the contractor, in addition to the payment due him, interest at a rate of one and one-half percent per month calculated from the expiration of the thirty-day period until fully paid.

5. Nothing in this section shall prevent the owner from withholding payment or final payment from the contractor, or a subcontractor or material supplier. Reasons for withholding payment or final payment shall include, but not be limited to, the following: liquidated damages; unsatisfactory job progress; defective construction work or material not remedied; disputed work; failure to comply with any material provision of the contract; third party claims filed or reasonable evidence that a claim will be filed; failure to make timely payments for labor, equipment or materials; damage to a contractor, subcontractor or material supplier; reasonable evidence that a subcontractor or material supplier cannot be fully compensated under its contract with the contractor for the unpaid balance of the contract sum; or citation by the enforcing authority for acts of the contractor or subcontractor which do not comply with any material provision of the contract and which result in a violation of any federal, state or local law, regulation or ordinance applicable to that project causing additional costs or damages to the owner.

6. Notwithstanding any other provisions in this section to the contrary, no late payment interest shall be due and owing for payments which are withheld in good faith for reasonable cause pursuant to subsections 2 and 5 of this section. If it is determined by a court of competent jurisdiction that a payment which was withheld pursuant to subsections 2 and 5 of this section was not withheld in good faith for reasonable cause, the court may impose interest at the rate of one and one-half percent per month calculated from the date of the invoice and may, in its discretion, award reasonable attorney fees to the prevailing party. In any civil action or part of a civil action brought pursuant to this section, if a court determines after a hearing for such purpose that the cause was initiated, or a defense was asserted, or a motion was filed, or any proceeding therein was done frivolously and in bad faith, the court shall require the party who initiated such cause, asserted such defense, filed such motion, or caused such proceeding to be had to pay the other party named in such action the amount of the costs attributable thereto and reasonable expenses incurred by such party, including reasonable attorney fees.

(L. 1990 S.B. 808 & 672 § 1)

(2004) Act contemplates a contract between the parties to such a cause of action and provides for such action against a public owner only by the contractor, not a subcontractor or supplier. Mays-Maune & Associates v. Werner Brothers, 139 S.W.3d 201 (Mo.App. E.D.).

# PART B

# LOCAL PROVISIONS

# {Insert appropriate local requirements as needed (liability insurance, etc.)}

# PART C

# STATE WAGE RATES

# {Insert the current state wage rates}

# {The sponsor is responsible for obtaining the appropriate State Wage Rates for the county in which the work is to be performed from the Missouri Division of Labor Standards. Information regarding these state wage rates is available on their website at http://www.dolir.missouri.gov/ls/prevailingwage/index.asp.

The state wage rates need to be current within 10 days of the bid opening date.}

# SECTION 5

# TECHNICAL SPECIFICATIONS

{FAA Advisory Circular 150/5370-10 contains the FAA standards for specifying construction of airports and airport related development. These standards may be supplemented by various engineering briefs issued by Airport Engineering Division of the Office of Airport Safety and Standards.

The FAA Regional Office may also supplement or amend the FAA standards for purposes of accommodating regional and local conditions that may not be adequately covered by the broader national standard. These modifications to AC 150/5370-10 are available under AIP Sponsor Guide No. 940 (FAA Central Region website).

Sponsors and their consultants must utilize AC 150/5370-10 as a guide specification when preparing a project specification. Sponsors may not modify or deviate from the accepted FAA standard unless expressed written approval is obtained from MoDOT. Sponsors desiring to make such modifications must refer to AIP Sponsor Guide No. 950 (FAA Central Region website) for the required procedure to properly request a sponsor-initiated modification to FAA standards.

While AC 150/5370-10 provides the required technical specifications for construction projects, the FAA does allow MoDOT to modify these standards to incorporate the use of State highway specifications. These modified technical specifications are available on the MoDOT Aviation website and must be utilized in the development of the project specifications. All other technical specifications related to items other than those listed on the MoDOT Aviation website shall be obtained from AC 150/5370-10 on the FAA Central Region website.

The FAA standard and MoDOT modified specifications includes several "notes to engineers" that elaborate on permissible options and modifications an engineer may choose when preparing a project specification. The engineer shall use their sound engineering judgment to make appropriate and permissible decisions that account for project specific materials, site conditions, methods and other requirements.}

# APPENDIX

# {Insert appropriate reference Advisory Circulars such as 150/5370-2E Operational Safety on Airports During Construction.}

# PROPOSAL FORM

{SPONSOR NAME)

Project No. {MoDOT PROJECT NUMBER}

# TO:	City/County Manager

The undersigned, in compliance with the request for bids for construction of the following Project:

{BRIEF AND CONCISE DESCRIPTION OF PROJECT}:

hereby proposes to furnish all labor, permits, material, machinery, tools, supplies and equipment to faithfully perform all work required for construction of the Project in accordance with the project manual, project drawings and issued Addenda within the specified time of performance for the following prices:

| BASE BID |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BID ITEM | FAA or MoDOT SPEC. | ITEM DESCRIPTION | APPROX. QUANTITY AND UNITS | UNIT PRICE |  | EXTENSION |  |
|  |  |  |  | DOLLARS | CTS | DOLLARS | CTS |
| 1 | MO-100 | Mobilization | 1 Lump Sum |  |  |  |  |
| 2 | MO-152 | Class A Excavation | 42,500 C.Y. |  |  |  |  |
| 3 | MO-209 | Crushed Aggregate Base Course | 14,250 Tons |  |  |  |  |
| 4 | MO-401F | Mineral Aggregate (BP-1 Mix) | 3,250 Tons |  |  |  |  |
| 5 | MO-401F | Asphalt Cement (BP-1 Mix) | 150 Tons |  |  |  |  |
| 6 | MO-602 | Bituminous Prime Coat | 21,200 Gals. |  |  |  |  |
| 7 | MO-620 | Airport Runway Pavement Marking (White) | 65,000 S.F. |  |  |  |  |
| 8 | L-108 | Underground Cable (1/c, #8 AWG, 5kV) | 5,000 L.F. |  |  |  |  |
| TOTAL BID (Base Bid) |  |  |  |  |  |  |  |

ACKNOWLEDGEMENTS BY BIDDER

a.	By submittal of a proposal, the BIDDER acknowledges and accepts that the quantities established by the OWNER are an approximate estimate of the quantities required to fully complete the Project and that the estimated quantities are principally intended to serve as a basis for evaluation of bids.  The BIDDER further acknowledges and accepts that payment under this contract will be made only for actual quantities and that quantities will vary in accordance with the General Provisions subsection entitled “Alteration of Work and Quantities”.

b.	The BIDDER acknowledges and accepts that the Bid Documents are comprised of the documents identified within the General Provisions. The BIDDER further acknowledges that each the individual documents that comprise the Bid Documents are complementary to one another and together establishes the complete terms, conditions and obligations of the successful BIDDER.

c.	As evidence of good faith in submitting this proposal, the undersigned encloses a bid guaranty in the form of a certified check, cashier’s check or bid bond in the amount of 5% of the bid price.  The BIDDER acknowledges and accepts that refusal or failure to accept award and execute a contract within the terms and conditions established herein will result in forfeiture of the bid guaranty to the owner as a liquidated damage.

d.	The BIDDER acknowledges and accepts the OWNER’S right to reject any or all bids.

e.	The BIDDER acknowledges and accepts the OWNER’S right to hold all Proposals for purposes of review and evaluation and not issue a notice-of-award for a period not to exceed {NUMBER OF DAYS} calendar days from the stated date for receipt of bids.

f.	The undersigned agrees that upon written notice of award of contract, he or she will execute the contract within thirty (30) days of the notice-of-award, and furthermore, and provide executed payment and performance bonds within fifteen (15) days from the date of contract execution. The undersigned accepts that failure to execute the contract and provide the required bonds within the stated timeframe shall result in forfeiture of the bid guaranty to the owner as a liquidated damage.

g.	Time of Performance:  By submittal of this proposal, the undersigned acknowledges and agrees to commence work within ten (10) calendar days of the date specified in the written “Notice-to-Proceed” as issued by the OWNER. The undersigned further agrees to complete the Project within {NUMBER OF DAYS} Calendar days from the commencement date specified in the Notice-to-Proceed.

h.	The undersigned acknowledges and accepts that for each and every Calendar day the project remains incomplete beyond the contract time of performance, the Contractor shall pay the non-penal amount of  ${DOLLAR AMOUNT} per Calendar day as a liquidated damage to the OWNER.

i.	The BIDDER, by submission of a proposal, acknowledges that award of this contract is subject to the provisions of the Missouri Prevailing Wage Law. The BIDDER accepts the requirement to pay prevailing wages for each classification and type of worker as established in the attached wage rate determinations as issued by the Missouri Division of Labor Standards.  The BIDDER further acknowledges and accepts their requirement to incorporate the provision to pay the established prevailing wages in every subcontract agreement entered into by the Bidder under this project.

j.	The undersigned acknowledges receipt of the following addenda:

Addendum No. 		, dated 				Date Received

Addendum No. 		, dated 				Date Received

Addendum No. 		, dated 				Date Received

Addendum No. 		, dated 				Date Received

Addendum No. 		, dated 				Date Received

REPRESENTATIONS BY BIDDER

By submittal of a proposal (bid), the BIDDER represents the following:

a.	The BIDDER has read and thoroughly examined the bid documents including all authorized addenda.

b.	The BIDDER has a complete understanding of the terms and conditions required for the satisfactory performance of project work.

c.	The BIDDER has fully informed themselves of the project site, the project site conditions and the surrounding area.

d.	The BIDDER has familiarized themselves of the requirements of working on an operating airport and understands the conditions that may in any manner affect cost, progress or performance of the work

e.	The BIDDER has correlated their observations with that of the project documents.

f.	The BIDDER has found no errors, conflicts, ambiguities or omissions in the project documents, except as previously submitted in writing to the owner that would affect cost, progress or performance of the work.

g.	The BIDDER is familiar with all applicable Federal, State and local laws, rules and regulations pertaining to execution of the contract and the project work.

h.	The BIDDER has complied with all requirements of these instructions and the associated project documents.

CERTIFICATION BY BIDDER

a.	The undersigned hereby declares and certifies that the only parties interested in this proposal are named herein and that this proposal is made without collusion with any other person, firm or corporation.

b.	Compliance with the Work Authorization Law (as required by Section 285.530, Revised Statues of Missouri)

For all contracts which include state or local funds in excess of $5,000, the Bidder, by submission of an offer and by signing the Worker Eligibility Verification Affidavit for All Contract Agreements in Excess of $5,000, certifies that it:

- does not knowingly employ any person who is an unauthorized alien in connection with the contracted services;

- has enrolled and actively participates in a federal work authorization program;

A general contractor or subcontractor of any tier shall not be liable under sections 285.525 to 285.550 when such general contractor or subcontractor contracts with its direct subcontractor who violates subsection 1 of this section, if the contract binding the contractor and subcontractor affirmatively states that the direct subcontractor is not knowingly in violation of subsection 1 of this section and shall not henceforth be in such violation and the contractor or subcontractor receives a sworn affidavit under the penalty of perjury attesting to the fact that the direct subcontractor’s employees are lawfully present in the United States.

WORKER ELIGIBILITY VERIFICATION AFFIDAVIT FOR ALL

CONTRACT AGREEMENTS IN EXCESS OF $5,000

(for joint ventures, a separate affidavit is required for each business entity)

STATE OF ________________	)

) ss

COUNTY OF ________________	)

On this _______ day of _____________________, 20_____, before me appeared _________________________________, personally known to me or proved to me on the basis of satisfactory evidence to be a person whose name is subscribed to this affidavit, who being by me duly sworn, deposed as follows:

My name is __________________________________, and I am of sound mind, capable of making this affidavit, and personally certify the facts herein stated, as required by Section 285.530, RSMo, to enter into any contract agreement with the state or any of its political subdivisions to perform any job, task, employment, labor, personal services, or any other activity for which compensation is provided, expected, or due, including but not limited to all activities conducted by business entities:

I am the __________________ of  ______________________________, and I am duly authorized, directed, and/or empowered to act officially and properly on behalf of this business entity.

(title)

(business name)

I hereby affirm and warrant that the aforementioned business entity is enrolled in a federal work authorization program operated by the United States Department of Homeland Security, and the aforementioned business entity shall participate in said program to verify information (employment eligibility) of newly hired employees working in connection to work under the within contract agreement.  I have attached documentation to this affidavit to evidence enrollment/participation by the aforementioned business entity in a federal work authorization program, as required by Section 285.530, RSMo.

In addition, I hereby affirm and warrant that the aforementioned business entity does not and shall not knowingly employ, in connection to work under the within contract agreement, any alien who does not have the legal right or authorization under federal law to work in the United States, as defined in 8 U.S.C. § 1324a(h)(3).

I am aware and recognize that, unless certain contract and affidavit conditions are satisfied pursuant to Section 285.530, RSMo, the aforementioned business entity may be held liable under Sections 285.525 though 285.550, RSMo, for subcontractors that knowingly employ or continue to employ any unauthorized alien to work within the state of Missouri.

I acknowledge that I am signing this affidavit as a free act and deed of the aforementioned business entity and not under duress.

__________________________________

(Affiant Signature)

Subscribed and sworn to before me this ______ day of ________________, 20_____.

___________________________

(Notary Public)

My commission expires:

[Documentation of enrollment/participation in a federal work authorization program is attached.  Acceptable enrollment and participation documentation consists of the following two pages of the E-Verify Memorandum of Understanding: (1) A valid, completed copy of the first page identifying the business entity; and (2) A valid copy of the signature page completed and signed by the business entity, the Social Security Administration, and the Department of Homeland Security – Verification Division.]

- THIS EXECUTED PROPOSAL FORM MUST BE SUBMITTED - IN THE ORIGINAL BOUND PROJECT MANUAL.

SIGNATURE OF BIDDER

The undersigned states that the correct LEGAL NAME AND ADDRESS of (1) the individual bidder, (2) each partner or joint venturer (whether individuals or corporations, and whether doing business under a fictitious name), or (3) the corporation (with the state in which it is incorporated) are shown below; that (if not signing with the intention to bind themselves to become responsible and sole bidder) they are the agent of, and they are signing and executing this (as indicated in the proper spaces below) as the bid of a

(  ) sole individual		(  ) partnership		        (  ) joint venture

(  ) corporation, incorporated under the laws of state of _______________________________.

Executed by bidder this ____________ day of ________________________ 20______.

Name of individual,

all partners

or joint venturers:					Address of each:

doing business under the name of:			Address of principal place of business in

Missouri:

(If using a fictitious name, show this name

above in addition to legal names)

(If a corporation, show its name above)

ATTEST:   (SEAL)

(Signature)		        Secretary		(Signature)			(Title)

Please print name					Please print name

NOTE:  If bidder is doing business under a fictitious name, the bid shall be executed in the legal name of the individual partners, joint ventures, or corporation, with the legal address shown, and registration of fictitious name filed with the secretary of state, as required by sections 417.200 to 417.230 RSMo. If the bidder is a corporation not organized under the laws of Missouri, it shall procure a certificate of authority to do business in Missouri, as required by section 351.572 et seq RSMo.

| PERFORMANCE BOND | BOND NUMBER |
| --- | --- |
| PRINCIPAL (Legal Name and Business Address) |  |
| SURETY (Legal Name and Business Address) | STATE OF INCORPORATION |
| PENAL SUM OF BOND (Expressed in words and numerals) | CONTRACT DATE |

OBLIGATION

KNOW ALL PERSONS BY THESE PRESENTS, that the above named PRINCIPAL, hereinafter referred to and called CONTRACTOR, and the above named SURETY hereby bind themselves unto {LEGAL NAME AND ADRRESS OF SPONSOR}, as OBLIGEE, hereinafter referred to and called OWNER, in the penal sum stated above, in lawful money of the United States of America to be paid to OWNER. For payment of the penal sum, we bind ourselves, our heirs, executors, administrators, successors and assigns, jointly and severally, firmly by these presents.

WHEREAS,

CONTRACTOR has entered into the written contract agreement identified hereinabove with the OWNER for the following project:

{PROJECT NAME}

{PROJECT LOCATION}

which said contract and associated contract documents, including any present or future amendment thereto, is incorporated herein by reference and is hereinafter referred to as the Contract.

CONDITION

NOW, THEREFORE, THE CONDITION OF THIS OBLIGATION is such that, if CONTRACTOR shall promptly and faithfully perform all undertakings, covenants, terms, conditions and agreements of the Contract during the original term of the Contract and any extensions thereof that are granted by the OWNER, with or without notice to the SURETY, and during the period of any guarantee or warranties required under the Contract, and if CONTRACTOR shall perform and fulfill all undertakings, covenants, terms, conditions and agreements of any and all duly authorized modifications of the Contract that hereafter are made, then this obligation shall be void; otherwise it shall remain in full force and effect subject to the following additional conditions:

1.	SURETY, for value received, hereby stipulates and agrees that no change, extension of time, modification, omission, addition or change in or to the Contract, or the work performed thereunder or the specifications accompanying the same, shall in any way affect the SURETY’S obligation on this bond; and SURETY hereby agrees to waive notice of any and all such extensions, modifications, omissions, alterations, and additions to the terms of the Contract, work or specifications.

2.	Whenever CONTRACTOR shall be and declared by the OWNER to be in default under the Contract, the Surety shall promptly and at the SURETY’S expense remedy the default by implementing one or more of the following actions:

a.	Arrange for the CONTRACTOR, with consent of the OWNER, to perform and complete the Contract; or

b.	Undertake to perform and complete the Contract itself, through its agents or through independent contractors; or

c.	Obtain bids or negotiated proposals from qualified contractors acceptable to the OWNER for a contract for performance and completion of the Contract; arrange for a contract to be prepared for execution by the OWNER and the contractor selected with the OWNER’S concurrence, to be secured with performance and payment bonds executed by a qualified surety equivalent to the Bonds issued on the Contract; and make available as work progresses (even though there should be a default or a succession of defaults under the contract or contracts of completion arranged under this paragraph) sufficient funds to pay the cost of completion less the balance of the contract price; but not exceeding, including other costs and damages for which the Surety may be liable hereunder, the penal sum of the bond.  The term "balance of the contract price", as used in this paragraph, shall mean the total amount payable by OWNER to CONTRACTOR under the Contract and any amendments thereto, disbursed at the rate provided in the original contract, less the amount properly paid by OWNER to CONTRACTOR.

d.	With written consent of the OWNER, SURETY may waive its right to perform and complete, arrange for completion or obtain a new contractor and with reasonable promptness, investigate and determine the amount the SURETY is liable to the OWNER and tender payment therefor to the OWNER.

3.	CONTRACTOR and SURETY agree that if in connection with the enforcement of this Bond, the OWNER is required to engage the services of an attorney, that reasonable attorney fees incurred by the OWNER, with or without suit, are in addition to the balance of the contract price.

4.	No right of action shall accrue on this bond to or for the use of any person or corporation other than the OWNER named herein or the successors or assigns of the OWNER.

WITNESS

In witness whereof, this instrument is executed this the 	 day of 				, 20	.

INDIVIDUAL PRINCIPAL:

Company Name:

Signature:

Name and Title:

CORPORATE PRINCIPAL:

ATTEST:	Corporate Name:

Signature: 			Signature:

Name and Title: 			Name and Title:

(Affix Corporate Seal)

SURETY:

ATTEST:	Surety Name:

Signature: 			Signature:

Name and Title: 			Name and Title:

(Affix Seal)	(Attach Power of Attorney)

OWNER ACCEPTANCE:

The OWNER approves the form of this Performance Bond.

ATTEST:	Date:

Signature: 			Signature:

Name and Title: 			Name and Title:

(Affix Seal)

| PAYMENT BOND | BOND NUMBER |
| --- | --- |
| PRINCIPAL (Legal Name and Business Address) |  |
| SURETY (Legal Name and Business Address) | STATE OF INCORPORATION |
| PENAL SUM OF BOND (Expressed in words and numerals) | CONTRACT DATE |

OBLIGATION

KNOW ALL PERSONS BY THESE PRESENTS, that the above named PRINCIPAL, hereinafter referred to and called CONTRACTOR, and the above named SURETY hereby bind themselves unto {LEGAL NAME AND ADDRESS OF SPONSOR}, as OBLIGEE, hereinafter referred to and called OWNER, in the penal sum stated above, in lawful money of the United States of America to be paid to OWNER. For payment of the penal sum, we bind ourselves, our heirs, executors, administrators, successors and assigns, jointly and severally, firmly by these presents.

WHEREAS,

CONTRACTOR has entered into the written contract agreement identified hereinabove with the OWNER for the following project:

{PROJECT NAME}

{PROJECT LOCATION}

which said contract and associated contract documents, including any present or future amendment thereto, is incorporated herein by reference and is hereinafter referred to as the Contract.

CONDITION

NOW, THEREFORE, THE CONDITION OF THIS OBLIGATION is such that, if CONTRACTOR shall promptly make payment to all employees, persons, firms or corporations for all incurred indebtedness and just claims for labor, supplies, materials and services furnished for or used in connection with the performance of the Contract, then this obligation shall be void; otherwise it shall remain in full force and effect subject to the following additional conditions:

1.	CONTRACTOR and SURETY indemnify and hold harmless the OWNER for all claims, demands, liens or suits that arise from performance of the Contract

2.	SURETY, for value received, hereby stipulates and agrees that no change, extension of time, modification, omission, addition or change in or to the Contract, or the work performed thereunder or the specifications accompanying the same, shall in any way affect the SURETY’S obligation on this bond; and SURETY hereby agrees to waive notice of any and all such extensions, modifications, omissions, alterations, and additions to the terms of the Contract, work or specifications.

3.	No final settlement between the OWNER and the CONTRACTOR shall abridge the right of any beneficiary hereunder, whose claim may be unsatisfied.

4.	The amount of this bond shall be reduced by and to the extent of any payments made in good faith hereunder.

5.	Amounts owed by the OWNER to the CONTRACTOR under the Contract shall be used for the performance of the Contract and to satisfy claims, if any, under any Performance Bond. By the CONTRACTOR furnishing and the OWNER accepting this Bond, they agree that all funds earned by the CONTRACTOR in the performance of the Contract are dedicated to satisfy obligations of the CONTRACTOR and the SURETY under this Bond, subject to the OWNER’S priority to use the funds for the completion of the project.

WITNESS

In witness whereof, this instrument is executed this the 	 day of 				, 20	.

INDIVIDUAL PRINCIPAL:

Company Name:

Signature:

Name and Title:

CORPORATE PRINCIPAL:

ATTEST:	Corporate Name:

Signature: 			Signature:

Name and Title: 			Name and Title:

(Affix Corporate Seal)

SURETY:

ATTEST:	Surety Name:

Signature: 			Signature:

Name and Title: 			Name and Title:

(Affix Seal)	(Attach Power of Attorney)

OWNER ACCEPTANCE:

The OWNER approves the form of this Payment Bond.

ATTEST:	Date:

Signature: 			Signature:

Name and Title: 			Name and Title:

(Affix Seal)

FORM OF

CONTRACT AGREEMENT

{SPONSOR NAME)

Project No. {MoDOT PROJECT NUMBER}

THIS AGREEMENT, made as of this ____________ day of ________________________, 20______, is

BY AND BETWEEN

the OWNER:			Name: 		     {OWNER’S NAME}

Address: 	     {ADDRESS}

City/State/Zip Code: {CITY/STATE/ZIP CODE}

And the CONTRACTOR:		Name:

Address:

City/State/Zip Code:

WITNESSETH:

WHEREAS it is the intent of the Owner to make improvements at {NAME OF AIRPORT} generally described as follows;

{BRIEF AND CONCISE DESCRIPTION OF PROJECT}.

hereinafter referred to as the Project.

NOW THEREFORE in consideration of the mutual covenants hereinafter set forth, OWNER and CONTRACTOR agree as follows:

Article 1 – Work

It is hereby mutually agreed that for and in consideration of the payments as provided for herein to the CONTRACTOR by the OWNER, CONTRACTOR shall faithfully furnish all necessary labor, equipment, and material and shall fully perform all necessary work to complete the Project in strict accordance with this Contract Agreement and the Contract Documents.

Article 2 – Contract Documents

CONTRACTOR agrees that the Contract Documents consist of the following: this Agreement, General Provisions, Supplementary Provisions, Specifications, Drawings, all issued addenda, Notice-to-Bidders, Instructions-to-Bidders, Proposal and associated attachments, Performance Bond, Payment Bond, Wage Rate Determination, Insurance certificates, documents incorporated by reference, documents incorporated by attachment, and all OWNER authorized change orders issued subsequent to the date of this agreement. All documents comprising the Contract Documents are complementary to one another and together establish the complete terms, conditions and obligations of the CONTRACTOR. All said Contract Documents are incorporated by reference into the Contract Agreement as if fully rewritten herein or attached thereto.

Article 3 – Contract Price

In consideration of the faithful performance and completion of the Work by the CONTRACTOR in accordance with the Contract Documents, OWNER shall pay the CONTRACTOR an amount equal to:

$		($	)

(Amount in Written Words)	(Amount in Numerals)

subject to the following;

a.	Said amount is based on the schedule of prices and estimated quantities stated in CONTRACTOR’S Bid Proposal, which is attached to and made a part of this Agreement;

b.	Said amount is the aggregate sum of the result of the CONTRACTOR’S stated unit prices multiplied by the associated estimated quantities;

c.	CONTRACTOR and OWNER agree that said estimated quantities are not guaranteed and that the determination of actual quantities is to be made by the OWNER’S ENGINEER;

d.	Said amount is subject to modification for additions and deductions as provided for within the Contract General Provisions.

Article 4 – Payment

Upon the completion of the work and its acceptance by the OWNER, all sums due the CONTRACTOR by reason of faithful performance of the work, taking into consideration additions to or deductions from the Contract price by reason of alterations or modifications of the original Contract or by reason of “Extra Work” authorized under this Contract, will be paid to the CONTRACTOR by the OWNER after said completion and acceptance.

The acceptance of final payment by the CONTRACTOR shall be considered as a release in full of all claims against the OWNER, arising out of, or by reason of, the work completed and materials furnished under this Contract.

OWNER shall make progress payments to the CONTRACTOR in accordance with the terms set forth in the General Provisions.  Progress payments shall be based on estimates prepared by the ENGINEER for the value of work performed and materials completed in place in accordance with the Contract Drawings and Specifications.

Progress payments are subject to retainage requirements as set forth in the General Provisions.

Article 5 – Contract Time

The CONTRACTOR agrees to commence work within ten (10) calendar days of the date specified in the OWNER’S Notice-to-Proceed. CONTRACTOR further agrees to complete said work within {NUMBER OF DAYS) of the commencement date stated within the Notice-to-Proceed.

It is expressly understood and agreed that the stated Contract Time is reasonable for the completion of the Work, taking all factors into consideration. Furthermore, extensions of the Contract Time may only be permitted by execution of a formal modification to this Contract Agreement in accordance with the General Provisions and as approved by the OWNER.

Article 6 – Liquidated Damages

The CONTRACTOR and OWNER understand and agree that time is of essence for completion of the Work and that the OWNER will suffer additional expense and financial loss if said Work is not completed within the authorized Contract Time. Furthermore, the CONTRACTOR and OWNER recognize and understand the difficulty, delay, and expense in establishing the exact amount of actual financial loss and additional expense. Accordingly, in place of requiring such proof, the CONTRACTOR expressly agrees to pay the OWNER as liquidated damages the non-penal sum of ${DOLLAR AMOUNT} per day for each calendar day required in excess of the authorized Contract Time.

Furthermore, the CONTRACTOR understands and agrees that;

a.	the OWNER has the right to deduct from any moneys due the CONTRACTOR, the amount of said liquidated damages;

b.	the OWNER has the right to recover the amount of said liquidated damages from the CONTRACTOR, SURETY or both.

Article 7 – CONTRACTOR’S Representations

The CONTRACTOR understands and agrees that all representations made by the CONTRACTOR within the Proposal Form shall apply under this Agreement as if fully rewritten herein.

Article 8 – Miscellaneous

a.	CONTRACTOR understands that it shall be solely responsible for the means, methods, techniques, sequences and procedures of construction in connection with completion of the Work;

b.	CONTRACTOR understands and agrees that it shall not accomplish any work or furnish any materials that are not covered or authorized by the Contract Documents unless authorized in writing by the OWNER or ENGINEER;

c.	The rights of each party under this Agreement shall not be assigned or transferred to any other person, entity, firm or corporation without prior written consent of both parties;

d.	OWNER and CONTRACTOR each bind itself, their partners, successors, assigns and legal representatives to the other party in respect to all covenants, agreements, and obligations contained in the Contract Documents.

Article 9 – OWNER’S Representative

The OWNER’S Representative, herein referred to as ENGINEER, is defined as follows:

{NAME OF FIRM}

{ADDRESS}

{CITY/STATE/ZIP CODE}

Said ENGINEER will act as the OWNER’S representative and shall assume all rights and authority assigned to the ENGINEER as stated within the Contract Documents in connection with the completion of the Project Work.

IN WITNESS WHEREOF, OWNER and CONTRACTOR have executed five (5) copies of this Agreement on the day and year first noted herein.

OWNER	CONTRACTOR

Name: 			Name:

Address: 		Address:

By:			By:

Signature			Signature

Title of Representative			Title of Representative

ATTEST:		ATTEST

By: 			By:

Signature			Signature

Title			Title