## Slide 1
2022
2023
Week 1
6
11
16
21
26
31
36
41
Schedule meeting with Exec leadership
9/1/2022
Finalize project selection list
12/1/2022
Start posting 1st round of RFPs
1/16/2023
52 days
9/1/2022 - 11/1/2022
Collect ideas internal and external and host Research Needs Day
31 days
10/17/2022 - 11/16/2022
Review existing project timelines and budgets
16 days
11/2/2022 - 11/16/2022
Prioritize list with SMT Leadership
16 days
11/16/2022 - 11/30/2022
Meet with Executive Leadership
15 days
12/1/2022 - 12/17/2022
Prioritize top projects for 1st round of RFPs
32 days
12/20/2022 - 2/15/2023
Develop 1st round of RFPs
46 days
4/3/2023 - 5/2/2023
Select winning proposal
33 days
4/17/2023 - 6/1/2023
Put project under contract
92 days
7/1/2023
Start receiving Invoices
Estimated Timeline for FY2024 Research Project Prioritization
Post 1st round of RFPs
1/16/2023 - 4/17/2023