## page
District | MPO | County | Route | Job Number | Length | Lane Miles | No. of Bridges | Description | SFY | Previous Engineering | Current Year Engineering | 2027-2030 Engineering | Engineering 5-Yr Total | Previous Right of Way | Current Year Right of Way | 2027-2030 Right of Way | Right of Way 5-Yr Total | Previous Construction | Current Year Construction | 2027-2030 Construction | Total Estimate
Northwest | N | ANDREW | US 169 S | NW0072 | 0.293 | 0.45 | 0 | Intersection improvements at Woodbine Road and County Line Road 0.5 mile north of I-29 near St. Joseph. | 2027 | 90 | 30 | 100 | 130 | 0 | 135 | 0 | 135 | 0 | 0 | 1279 | 1634
Northwest | N | ANDREW | RT B E | NW0047 | 0.296 | 0.592 | 1 | Bridge rehabilitation over One Hundred and Two River 0.8 mile west of Bolckow. Project involves bridge A1251. | 2027 | 40 | 60 | 111 | 171 | 0 | 5 | 0 | 5 | 0 | 0 | 1561 | 1777
Northwest | N | ATCHISON | MO 111 N | NW0103 | 0.676 | 1.352 | 29 | Bridge rehabilitations on various routes in Atchison, Holt and Nodaway Counties. Project involves various bridges. | 2026 | 180 | 312 | 0 | 312 | 0 | 0 | 0 | 0 | 0 | 2716 | 0 | 3208
Northwest | N | ATCHISON | US 136 E | NW0021 | 29.764 | 59.602 | 0 | Pavement resurfacing from I-29 to Rte. 71. | 2026 | 160 | 740 | 0 | 740 | 0 | 0 | 0 | 0 | 0 | 9330 | 0 | 10230
Northwest | N | ATCHISON | US 136 E | NW0125 | 0.228 | 0.456 | 1 | Bridge washing over the Missouri River at Brownsville, Nebraska. Project involves bridge L0098. | 2028 | 1 | 1 | 18 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 161 | 181
Northwest | N | ATCHISON | US 275 N | NW0055 | 0.22 | 0.44 | 2 | Bridge replacement over the West Fork of High Creek and over High Creek near Rte. T. Project involves bridges J0221 and J0222. | 2028 | 20 | 30 | 282 | 312 | 0 | 0 | 0 | 0 | 0 | 0 | 3355 | 3687
Northwest | N | ATCHISON | IS 29 N | NW0060 | 16.257 | 66.671 | 0 | Pavement resurfacing from the Iowa State line to Rte. 111 near Rock Port. | 2028 | 95 | 100 | 1135 | 1235 | 0 | 0 | 0 | 0 | 0 | 0 | 14068 | 15398
Northwest | N | ATCHISON | IS 29 S | NW0109 | 107.892 | 0 | 0 | Job Order Contracting for pavement repair from the Iowa State line to Platte County line. Includes I-229 in Andrew and Buchanan Counties. | 2026 | 15 | 45 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 560
Northwest | N | ATCHISON | IS 29 S | NW0150 | 107.892 | 0 | 0 | Job Order Contracting for pavement repair from the Iowa State line to Platte County line. Includes I-229 in Andrew and Buchanan Counties. | 2028 | 0 | 1 | 37 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 568
Northwest | N | ATCHISON | MO 46 E | NW0041 | 15.276 | 30.552 | 0 | Pavement resurfacing from Rte. 59 near Fairfax to the Nodaway River west of Rte. 113 near Burlington Junction. | 2026 | 25 | 167 | 0 | 167 | 0 | 0 | 0 | 0 | 0 | 2387 | 0 | 2579
Northwest | N | BUCHANAN | US 169 S | NW0045 | 0.5 | 1 | 0 | Modify intersection configuration at Riverside Terrace 0.6 mile south of Rte. AC. $1,296,000 Open Container funds. | 2026 | 190 | 204 | 0 | 204 | 25 | 0 | 0 | 0 | 0 | 3392 | 0 | 3811
Northwest | N | BUCHANAN | US 169 S | NW0073 | 0.1 | 0.2 | 0 | Add turn lanes at Rte. FF 0.6 mile south of I-29 in St. Joseph. $552,000 Open Container funds. | 2026 | 50 | 85 | 0 | 85 | 30 | 0 | 0 | 0 | 0 | 948 | 0 | 1113
Northwest | N | BUCHANAN | IS 229 S | NW0134 | 3.746 | 14.168 | 10 | Bridge removal and construct roadway Highland Ave to Rte 36, bridge rehabilitation I-229 flyover to Rte 36 and Rte 36 over 6th St and replacement Rte 36 over 9th St. Potential Design-Build. Bridges A2225, A2227, A2226, A2229, A2228, A2230, A2231, A2232, L0319, L0320. | 2028 | 1 | 1600 | 9783 | 11383 | 0 | 0 | 103 | 103 | 0 | 0 | 115830 | 127317
Northwest | N | BUCHANAN | IS 29 S | NW0051 | 8.923 | 35.601 | 0 | Pavement resurfacing from Pigeon Creek to the Platte County line near Faucett. | 2026 | 85 | 464 | 0 | 464 | 0 | 0 | 0 | 0 | 0 | 6324 | 0 | 6873
Northwest | N | BUCHANAN | US 36 E | NW0063 | 10.989 | 22.19 | 0 | Pavement resurfacing on eastbound lane from east of Rte. AC to east of Rte. 31 north near St. Joseph. | 2028 | 45 | 30 | 276 | 306 | 0 | 0 | 0 | 0 | 0 | 0 | 3962 | 4313
Northwest | N | BUCHANAN | RT AC S | 1S3030 | 0.054 | 0.134 | 1 | Bridge replacement over Rte. 36 in St. Joseph. Project involves bridge A2822. | 2027 | 492 | 350 | 713 | 1063 | 0 | 5 | 0 | 5 | 0 | 0 | 9201 | 10761
Northwest | N | BUCHANAN | RT DD E | NW0048 | 0.053 | 0.106 | 1 | Bridge rehabilitation over Bee Creek near Faucett. Project involves bridge A2581. | 2027 | 14 | 30 | 67 | 97 | 0 | 5 | 0 | 5 | 0 | 0 | 976 | 1092
Northwest | N | BUCHANAN | CST GENE FIELD RD E | 1I3332 | 0.042 | 0.084 | 1 | Urgent bridge replacement over I-29 in St. Joseph. Project involves bridge A0701. | 2026 | 97 | 861 | 0 | 861 | 0 | 70 | 0 | 70 | 0 | 4536 | 0 | 5564
Northwest | N | CALDWELL | US 36 W | NW0116 | 12.17 | 47.152 | 0 | Pavement resurfacing on eastbound lanes 0.4 mile east of Rte. K in Caldwell County to 0.4 mile west of Rte. C in Livingston County and shoulder reconstruction on westbound lanes 0.3 mile west of Rte. 13 to 1.1 mile east of I-35. | 2029 | 10 | 5 | 579 | 584 | 0 | 0 | 0 | 0 | 0 | 0 | 8720 | 9314
Northwest | N | CALDWELL | RT U W | NW0144 | 0.019 | 0.038 | 1 | Bridge replacement over Tom Creek 1 mile east of Rte. 13. Project involves bridge N0318. | 2026 | 150 | 102 | 0 | 102 | 0 | 10 | 0 | 10 | 0 | 1783 | 0 | 2045
Northwest | N | CARROLL | US 24 E | NW0084 | 58.168 | 116.686 | 0 | Pavement preservation treatment from Carrolton to Keytesville and Rte. 11 from Brunswick to Rte. 36. | 2026 | 40 | 189 | 0 | 189 | 0 | 0 | 0 | 0 | 0 | 2465 | 0 | 2694
Northwest | N | CARROLL | US 24 E | NW0126 | 0.412 | 0.824 | 1 | Bridge deck sealing over the Grand River. Project involves bridge A4613. | 2029 | 2 | 2 | 107 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 1058 | 1169
Northwest | N | CARROLL | RT B E | NW0010 | 0.593 | 1.186 | 4 | Bridge rehabilitation in Carroll, Chariton and Livingston Counties. Project involves bridges N0826, N0727, A1889 and L0548. | 2026 | 180 | 267 | 0 | 267 | 5 | 0 | 0 | 0 | 0 | 3587 | 0 | 4039
Northwest | N | CLINTON | IS 35 N | NW0153 | 8.266 | 33.823 | 0 | Pavement resurfacing from 1 mile north of Rte. 116 to the Clay County line. | 2029 | 0 | 2 | 484 | 486 | 0 | 0 | 0 | 0 | 0 | 0 | 7068 | 7554
Northwest | N | CLINTON | US 69 S | NW0042 | 7.007 | 14.017 | 0 | Pavement resurfacing from Rte. 116 near Lathrop to the Clay County line. | 2026 | 35 | 92 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 1197 | 0 | 1324
Northwest | N | CLINTON | RT H E | NW0029 | 27.908 | 55.816 | 0 | Pavement resurfacing on Rte. CC (Buchanan County), Rte. J (Clay County), Rte. H, Rte. J and Rte. O (Clinton County). | 2026 | 70 | 210 | 0 | 210 | 0 | 0 | 0 | 0 | 0 | 2891 | 0 | 3171
Northwest | N | DAVIESS | MO 13 S | NW0089 | 16.867 | 33.756 | 0 | Pavement resurfacing from Rte. 6 in Gallatin to Hamilton south city limits and on Bus. 36 from Rte. 36 to Rte. 13. | 2026 | 19 | 370 | 0 | 370 | 0 | 0 | 0 | 0 | 0 | 5320 | 0 | 5709
Northwest | N | DAVIESS | MO 13 S | NW0105 | 0.384 | 0.768 | 19 | Bridge rehabilitation on various routes in Daviess, Grundy, Harrison, Linn, Mercer, Putnam and Sullivan Counties. Project involves various bridges. | 2027 | 10 | 80 | 123 | 203 | 0 | 0 | 0 | 0 | 0 | 0 | 1470 | 1683
Northwest | N | DAVIESS | MO 190 W | NW0053 | 12.444 | 24.888 | 0 | Pavement resurfacing from Rte. 146 to Rte. F in Jamesport. | 2027 | 25 | 30 | 152 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 2129 | 2336
Northwest | N | DAVIESS | IS 35 N | NW0032 | 9.413 | 38.206 | 0 | Pavement repair from Rte. C near Pattonsburg to Rte. 69. | 2028 | 30 | 20 | 385 | 405 | 0 | 0 | 0 | 0 | 0 | 0 | 4244 | 4679
Northwest | N | DAVIESS | IS 35 N | NW0155 | 0.376 | 1.252 | 2 | Bridge preventative maintenance over the Grand River and over Granite Avenue. Project involves bridges A1756 and A1758. | 2030 | 0 | 1 | 74 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 1086 | 1161
Northwest | N | DAVIESS | MO 6 E | NW0062 | 22.112 | 45.445 | 0 | Pavement resurfacing west of Rte. V to 4th Street in Trenton. | 2027 | 37 | 20 | 218 | 238 | 0 | 0 | 0 | 0 | 0 | 0 | 5436 | 5711
Northwest | N | DAVIESS | RT BB E | NW0070 | 0.162 | 0.324 | 1 | Bridge replacement over I-35 3.6 miles north of Cameron. Project involves bridge R0237. | 2030 | 25 | 10 | 638 | 648 | 0 | 0 | 0 | 0 | 0 | 0 | 2913 | 3586
Northwest | N | DEKALB | US 36 E | NW0122 | 0.286 | 1.144 | 0 | Add intersection turn lanes and upgrade traffic signal at Bob F. Griffin Road. $1,564,011.50 Cameron and $1,223,111 Cost Share funds. | 2026 | 24 | 343 | 0 | 343 | 0 | 0 | 0 | 0 | 0 | 2787 | 0 | 3154
Northwest | N | DEKALB | US 36 E | NW0122B | 0.144 | 0.576 | 0 | Payment to Cameron for engineering, right of way and utilities for project NW0122 to add intersection turn lanes and upgrade traffic signal at Bob F. Griffin Road. $295,861 Cost Share funds. | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296 | 0 | 296
Northwest | N | DEKALB | US 36 W | NW0003 | 5.52 | 34.612 | 0 | Pavement preservation treatment on westbound lanes from 0.8 mile east of Rte. 31 to 0.6 mile east of Rte. 33 and eastbound lanes from 2 miles west of Rte. C to the Caldwell County line near Cameron. | 2026 | 14 | 70 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 996 | 0 | 1080
Northwest | N | DEKALB | US 36 W | NW0156 | 1.011 | 2.022 | 0 | Road realignment on the westbound lanes 1.5 miles east of Rte. 31 north junction. | 2028 | 0 | 150 | 529 | 679 | 0 | 0 | 0 | 0 | 0 | 0 | 3541 | 4220
Northwest | N | GENTRY | MO 48 E | NW0113 | 0.032 | 0.064 | 2 | Bridge replacement over 3rd fork Platte River 1.6 miles east of King City and Elm Grove Branch 3 miles east of King City. Project involves bridges J0083 and J0084. | 2030 | 15 | 10 | 436 | 446 | 0 | 0 | 0 | 0 | 0 | 0 | 2723 | 3184
Northwest | N | GRUNDY | MO 6 W | NW0037 | 36.967 | 106.158 | 0 | Pavement preservation treatment in Daviess, Grundy and Linn Counties. Includes Rte. 36, Rte. 69 and Rte. 6. | 2026 | 19 | 178 | 0 | 178 | 0 | 0 | 0 | 0 | 0 | 2899 | 0 | 3096
Northwest | N | GRUNDY | US 65 N | NW0086 | 36.804 | 73.608 | 0 | Pavement resurfacing from the Iowa State line to Rte. 6. | 2030 | 11 | 2 | 1402 | 1404 | 0 | 0 | 0 | 0 | 0 | 0 | 20822 | 22237
Northwest | N | GRUNDY | US 65 S | NW0088 | 19.882 | 43.853 | 0 | Pavement resurfacing from Rte. 6 to north of Rte. 190 near Chillicothe. | 2030 | 15 | 5 | 837 | 842 | 0 | 0 | 0 | 0 | 0 | 0 | 12420 | 13277
Northwest | N | GRUNDY | RT E E | NW0013 | 0.676 | 1.352 | 3 | Bridge rehabilitation in Grundy and Linn Counties. Project involves bridges X0153, P0891 and A1802. | 2026 | 90 | 142 | 0 | 142 | 5 | 0 | 0 | 0 | 0 | 1995 | 0 | 2232
Northwest | N | HARRISON | US 136 E | NW0075 | 0.044 | 0.088 | 1 | Bridge replacement over I-35 in Bethany. Project involves bridge A0698. | 2030 | 23 | 2 | 1032 | 1034 | 0 | 0 | 0 | 0 | 0 | 0 | 5406 | 6463
Northwest | N | HARRISON | IS 35 S | NW0052 | 8.192 | 34.148 | 0 | Pavement resurfacing from the Iowa State line to Rte. N near Eagleville. | 2027 | 210 | 50 | 480 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 6898 | 7638
Northwest | N | HARRISON | IS 35 S | NW0108 | 81.382 | 0 | 0 | Job Order Contracting for pavement repair from the Iowa State line to the Clay County line. | 2026 | 15 | 59 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 774
Northwest | N | HARRISON | IS 35 S | NW0151 | 81.382 | 0 | 0 | Job Order Contracting for pavement repair from the Iowa State line to the Clay County line. | 2028 | 0 | 1 | 51 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 743 | 795
Northwest | N | HARRISON | US 69 N | NW0057 | 0.165 | 0.33 | 1 | Bridge replacement over Zadie Branch 1 mile west of I-35. Project involves bridge L0267. | 2027 | 100 | 200 | 214 | 414 | 0 | 10 | 0 | 10 | 0 | 0 | 962 | 1486
Northwest | N | HARRISON | RT N E | NW0058 | 0.469 | 0.938 | 1 | Bridge rehabilitation over East Fork Big Creek 1.6 miles east of I-35. Project involves bridge A2402. | 2028 | 20 | 20 | 154 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 1610 | 1804
Northwest | N | HARRISON | RT W N | NW0164 | 61.83 | 123.66 | 0 | Pavement resurfacing including Rte. C in Daviess County, Rte. UU in Gentry County, Rtes. W, D, and P in Harrison County, and Rte. J in Nodaway County. $5,200,000 District Operation funds. | 2026 | 0 | 369 | 0 | 369 | 0 | 0 | 0 | 0 | 0 | 5200 | 0 | 5569
Northwest | N | HOLT | MO 111 N | NW0056 | 0.359 | 0.718 | 1 | Bridge replacement over the Tarkio River near Craig. Project involves bridge T0104. | 2027 | 70 | 100 | 142 | 242 | 0 | 10 | 0 | 10 | 0 | 0 | 1904 | 2226
Northwest | N | HOLT | MO 118 E | NW0059 | 0.033 | 0.066 | 1 | Bridge rehabilitation over I-29. Project involves bridge A1766. | 2028 | 40 | 50 | 240 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 2164 | 2494
Northwest | N | HOLT | US 159 N | 1P3383 | 0.462 | 0.924 | 1 | Payment to Nebraska DOT for bridge rehabilitation over the Missouri River near Rulo Nebraska. Project involves bridge A7698. | 2029 | 3 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 863 | 869
Northwest | N | HOLT | IS 29 N | NW0050 | 15.09 | 61.417 | 0 | Pavement resurfacing from Rte. 118 to Rte. W near Mound City. | 2027 | 45 | 100 | 774 | 874 | 0 | 0 | 0 | 0 | 0 | 0 | 11563 | 12482
Northwest | N | HOLT | IS 29 N | NW0061 | 16.633 | 67.778 | 0 | Pavement resurfacing from Rte. 59 to Rte. 118. | 2028 | 80 | 150 | 1210 | 1360 | 0 | 0 | 0 | 0 | 0 | 0 | 14068 | 15508
Northwest | N | HOLT | IS 29 N | NW0067 | 0.156 | 0.624 | 2 | Bridge rehabilitation over Little Tarkio Creek 1.6 miles south of Rte. 59 near Craig. Project involves bridge A1909. | 2030 | 25 | 1 | 716 | 717 | 0 | 0 | 0 | 0 | 0 | 0 | 5920 | 6662
Northwest | N | HOLT | US 59 S | NW0019 | 0.1 | 0 | 0 | Repair slide 1.1 miles south of Rte. 111 near Oregon. | 2028 | 335 | 10 | 266 | 276 | 20 | 0 | 0 | 0 | 0 | 0 | 3960 | 4591
Northwest | N | HOLT | RT B S | NW0139 | 0.146 | 0.292 | 3 | Bridge painting in Atchison and Holt Counties. Project includes bridges A1834, A1907 and A2708. | 2029 | 1 | 1 | 346 | 347 | 0 | 0 | 0 | 0 | 0 | 0 | 3121 | 3469
Northwest | N | LINN | US 36 E | NW0138 | 25.54 | 101.472 | 0 | Pavement resurfacing from Parson's Creek to the Macon County Line and on the eastbound lanes from 1.1 miles east of Rte. B near Wheeling to 0.5 mile west of Rte. EE. | 2029 | 5 | 5 | 1550 | 1555 | 0 | 0 | 0 | 0 | 0 | 0 | 22686 | 24246
Northwest | N | LINN | US 36 W | NW0117 | 0 | 0.082 | 2 | Bridge improvements over Big Turkey Creek and Big Turkey Creek Overflow 1 mile east of Laclede. Project involves bridges A0793 and A0845. | 2029 | 10 | 10 | 190 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 1235 | 1445
Northwest | N | LINN | US 36 W | NW0127 | 0.392 | 1.568 | 0 | Intersection improvements at Rte. 129 near Bucklin. $1,177,000 Open Container funds. | 2028 | 35 | 150 | 360 | 510 | 0 | 0 | 0 | 0 | 0 | 0 | 3183 | 3728
Northwest | N | LINN | US 36 W | NW0128 | 0.94 | 3.76 | 0 | Intersection improvements at Rte. F 2.6 miles east of Brookfield. | 2027 | 35 | 200 | 306 | 506 | 0 | 25 | 0 | 25 | 0 | 0 | 3064 | 3630
Northwest | N | LINN | MO 5 N | NW0054 | 32.476 | 65.154 | 0 | Pavement resurfacing from Rte. 36 to Rte. 6 north near Milan. | 2028 | 30 | 15 | 635 | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 8116 | 8796
Northwest | N | LIVINGSTON | US 36 E | NW0074 | 0.3 | 1.202 | 0 | Intersection realignment at Rte. B near Wheeling. | 2027 | 70 | 80 | 254 | 334 | 10 | 0 | 0 | 0 | 0 | 0 | 2609 | 3023
Northwest | N | LIVINGSTON | US 36 E | NW0120 | 0.968 | 3.872 | 0 | Intersection improvements at Mitchell Road in Chillicothe. $1,182,000 Open Container funds. | 2027 | 40 | 20 | 232 | 252 | 0 | 185 | 0 | 185 | 0 | 0 | 3404 | 3881
Northwest | N | LIVINGSTON | US 65 S | NW0143 | 0.556 | 2.405 | 0 | Upgrade pedestrian facilities to comply with ADA Transition Plan at various intersections in Chillicothe. | 2026 | 5 | 26 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 351 | 0 | 382
Northwest | N | LIVINGSTON | RT DD E | NW0132 | 0.05 | 0.1 | 1 | Bridge replacement over Shoal Creek Drain 0.8 mile west of Rte. C in Livingston County. Project involves bridge P0932. | 2029 | 5 | 5 | 354 | 359 | 0 | 0 | 0 | 0 | 0 | 0 | 2452 | 2816
Northwest | N | MERCER | US 136 E | 1S3396 | 0.11 | 0.22 | 1 | Section 14 streambank protection at bridge over Weldon Fork. Corps of Engineers to design and administer project. Cost shown represents MoDOT's share. Payment to Corps for design work. Project involves bridge A2634. | 2026 | 40 | 16 | 0 | 16 | 0 | 20 | 0 | 20 | 0 | 200 | 0 | 276
Northwest | N | MERCER | US 136 E | 1S3442 | 24.175 | 48.91 | 0 | Pavement resurfacing from Rte. C to Rte. 5 west of Unionville. | 2026 | 125 | 736 | 0 | 736 | 0 | 0 | 0 | 0 | 0 | 7087 | 0 | 7948
Northwest | N | MERCER | US 136 W | NW0049 | 0.089 | 0.178 | 1 | Bridge rehabilitation over Grand River Overflow in Princeton. Project involves bridge A2635. | 2026 | 65 | 402 | 0 | 402 | 0 | 0 | 0 | 0 | 0 | 2943 | 0 | 3410
Northwest | N | MERCER | US 65 S | 1S3438 | 1.06 | 2.12 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan in Princeton and South Lineville. | 2026 | 494 | 188 | 0 | 188 | 20 | 0 | 0 | 0 | 0 | 1188 | 0 | 1890
Northwest | N | MERCER | RT E E | NW0014 | 0.901 | 1.802 | 4 | Bridge rehabilitation in Mercer, Putnam and Sullivan Counties. Project involves bridges A2636, N0254, P0833 and N0973. | 2026 | 150 | 192 | 0 | 192 | 0 | 5 | 0 | 5 | 0 | 2495 | 0 | 2842
Northwest | N | NODAWAY | US 71 S | NW0044 | 20.346 | 40.692 | 0 | Pavement resurfacing from the Iowa State line to Rte. CC north of Maryville. | 2026 | 185 | 525 | 0 | 525 | 0 | 0 | 0 | 0 | 0 | 6190 | 0 | 6900
Northwest | N | NODAWAY | US 71 S | NW0165 | 1.4 | 5.598 | 0 | Add J-turns at 340th Street. $2,780,000 private entity funds. | 2026 | 0 | 280 | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 2500 | 0 | 2780
Northwest | N | NODAWAY | RT C E | NW0147 | 0.128 | 0.256 | 1 | Bridge replacement over Moss Branch. Project involves bridge S0360. | 2030 | 3 | 2 | 279 | 281 | 0 | 0 | 0 | 0 | 0 | 0 | 1244 | 1528
Northwest | N | NODAWAY | RT E N | NW0163 | 27.269 | 54.538 | 0 | Pavement resurfacing on Rtes. EE and E in Nodaway County. $2,900,000 District Operation funds. | 2026 | 0 | 208 | 0 | 208 | 0 | 0 | 0 | 0 | 0 | 2900 | 0 | 3108
Northwest | N | NODAWAY | RT F S | NW0106 | 0.329 | 0.658 | 13 | Bridge rehabilitation on various routes in Gentry, Harrison, Nodaway and Worth Counties. Project involves various bridges. | 2027 | 10 | 84 | 91 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 1064 | 1249
Northwest | N | NODAWAY | RT VV E | NW0046 | 0.207 | 0.414 | 1 | Bridge replacement over Platte River 0.4 mile west of Rte. AH near Conception Junction. Project involves bridge R0014. | 2026 | 365 | 167 | 0 | 167 | 0 | 10 | 0 | 10 | 0 | 2800 | 0 | 3342
Northwest | N | PUTNAM | US 136 E | NW0043 | 17.486 | 34.972 | 0 | Pavement resurfacing from Rte. 5 west of Unionville to Rte. N at Livonia. | 2026 | 95 | 625 | 0 | 625 | 0 | 0 | 0 | 0 | 0 | 5462 | 0 | 6182
Northwest | N | PUTNAM | MO 5 S | NW0040 | 20.667 | 41.334 | 0 | Pavement resurfacing from Rte. 136 east of Unionville to Rte. 6 north of Milan. | 2026 | 200 | 419 | 0 | 419 | 0 | 0 | 0 | 0 | 0 | 5372 | 0 | 5991
Northwest | N | SULLIVAN | MO 129 S | 1P3168 | 1.19 | 2.38 | 0 | Upgrade pedestrian facilities to comply with ADA Transition Plan in Green City. | 2026 | 215 | 67 | 0 | 67 | 0 | 43 | 0 | 43 | 0 | 612 | 0 | 937
Northwest | N | VARIOUS | Various | 5B0800O | 0 | 0 | 152 | Payback beginning in SFY 2008 for Safe and Sound bridges in the Northwest District. | 2033 | 0 | 0 | 0 | 0 | 169 | 0 | 0 | 0 | 125442 | 8973 | 35892 | 170476
Northwest | N | VARIOUS | Various | NW0110 |  | 0 | 0 | On-call work zone enforcement at various locations in the Northwest District. | 2026 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 43
Northwest | N | VARIOUS | Various | NW0130 |  | 0 | 0 | On-call work zone enforcement at various locations in the Northwest District. | 2027 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 43
Northwest | N | VARIOUS | Various | NW0131 |  | 0 | 0 | Job Order Contracting for guardrail and guard cable repair on various major routes in the Northwest District. | 2027 | 1 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2266 | 2270
Northwest | N | VARIOUS | Various | NW0141 | 0 | 0 | 0 | On-call work zone enforcement at various locations in the Northwest District. | 2028 | 0 | 1 | 5 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 46
Northeast | N | ADAIR | MO 149 S | NE0198 | 3.17 | 8.775 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan between Tenth Street and Second Street and on Rte. O west of Oakland Avenue to Corrigan Street in Novinger and on Bus. 63 in Kirksville. | 2026 | 200 | 40 | 0 | 40 | 0 | 5 | 0 | 5 | 0 | 776 | 0 | 1021
Northeast | N | ADAIR | MO 6 E | NE0142 | 0.201 | 0.402 | 1 | Bridge improvement over abandoned railroad 0.3 mile east of Rte. B in Kirksville. Project involves bridge A2901. | 2027 | 90 | 5 | 48 | 53 | 0 | 2 | 0 | 2 | 0 | 0 | 640 | 785
Northeast | N | ADAIR | MO 6 E | NE0254 | 0.86 | 1.72 | 0 | Pavement resurfacing from east of Baltimore Street to 0.2 mile west of Rte. 63 in Kirksville. | 2027 | 0 | 8 | 16 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 207 | 231
Northeast | N | ADAIR | BU 63 S | NE0100 | 3.179 | 10.234 | 0 | Pavement improvement from 0.4 mile south of Rte. 63 to Rte. 11 in Kirksville. | 2029 | 9 | 5 | 266 | 271 | 0 | 0 | 2 | 2 | 0 | 0 | 3358 | 3640
Northeast | N | ADAIR | US 63 S | NE0213 | 16.916 | 34.418 | 0 | Pavement improvement from 0.5 mile north of Rte. D to north of Rte. DD in Macon County. | 2029 | 9 | 9 | 486 | 495 | 0 | 0 | 0 | 0 | 0 | 0 | 5348 | 5852
Northeast | N | ADAIR | RT H S | NE0212 | 2.305 | 4.61 | 0 | Pavement resurfacing from LaHarpe Street to Rte. 11 in Kirksville. | 2026 | 5 | 25 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 296 | 0 | 326
Northeast | N | ADAIR | RT P E | NE0025 | 1.562 | 3.124 | 0 | Pavement resurfacing from Bus. 63 to Rte. 63 in Kirksville. | 2026 | 7 | 19 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 230 | 0 | 256
Northeast | N | ADAIR | RT P E | NE0209 | 3.514 | 7.028 | 0 | Pavement resurfacing from 0.3 mile east of Rte. 63 to Bass Way near Kirksville. | 2026 | 5 | 37 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 463 | 0 | 505
Northeast | N | AUDRAIN | MO 15 S | 2P3396 | 6.926 | 18.736 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in Mexico and Farber and pavement resurfacing on Rte. 15, Rte. 22 and Bus. 54 in Mexico. | 2026 | 271 | 315 | 0 | 315 | 0 | 75 | 0 | 75 | 0 | 4229 | 0 | 4890
Northeast | N | AUDRAIN | MO 22 E | NE0151 | 1.322 | 2.644 | 1 | Bridge improvement over CPKC railroad 0.2 mile west of Rte. 151 west junction near Sturgeon. Project involves bridge K0672. | 2027 | 425 | 25 | 699 | 724 | 0 | 50 | 0 | 50 | 0 | 0 | 10617 | 11816
Northeast | N | AUDRAIN | MO 22 E | NE0211 | 6.493 | 12.986 | 0 | Pavement resurfacing from 0.1 mile west of Rte. E to Morris Street in Mexico. | 2026 | 25 | 269 | 0 | 269 | 0 | 0 | 0 | 0 | 0 | 2461 | 0 | 2755
Northeast | N | AUDRAIN | MO 22 W | 2P3095 | 17.662 | 35.429 | 0 | Pavement improvement and add rumble stripes from 0.1 mile west of Rte. E near Mexico to Rte. F in Boone County. $749,000 Open Container funds. | 2027 | 67 | 50 | 257 | 307 | 0 | 1 | 0 | 1 | 0 | 0 | 3713 | 4088
Northeast | N | AUDRAIN | US 54 E | NE0251 | 13.863 | 27.726 | 0 | Roadway improvement from Farber to Curryville in Audrain, Ralls, and Pike Counties. $24,892,433 BUILD Grant. | 2030 | 0 | 2250 | 1908 | 4158 | 0 | 0 | 513 | 513 | 0 | 0 | 24480 | 29151
Northeast | N | AUDRAIN | US 54 E | NE0253 | 3.29 | 6.579 | 0 | Roadway improvement from east of Rte. 19 to 0.3 mile west of Rte. AA near Farber. | 2030 | 0 | 300 | 1024 | 1324 | 0 | 0 | 233 | 233 | 0 | 0 | 7015 | 8572
Northeast | N | AUDRAIN | US 54 W | NE0216 | 0 | 0.046 | 1 | Bridge improvement over Beaverdam Creek 0.6 mile north of Rte. HH near Mexico. Project involves bridge H0594. | 2029 | 10 | 200 | 297 | 497 | 0 | 0 | 1 | 1 | 0 | 0 | 2341 | 2849
Northeast | N | AUDRAIN | RT J E | NE0112 | 17.913 | 35.887 | 0 | Pavement preservation treatment from Bus. 54 in Mexico to 0.1 mile west of Rte. 54 at Basinger Corner. | 2027 | 3 | 5 | 52 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 707 | 767
Northeast | N | AUDRAIN | RT NN S | NE0062 | 2.082 | 4.164 | 0 | Pavement resurfacing from County Road 377 to Rte. 22 near Mexico. | 2026 | 5 | 23 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 261 | 0 | 289
Northeast | N | CLARK | US 136 E | NE0155 | 0.016 | 0.032 | 1 | Bridge improvement over drainage ditch 3 miles west of Rte. 61 near Alexandria. Project involves bridge F0955. | 2028 | 235 | 50 | 113 | 163 | 0 | 2 | 0 | 2 | 0 | 0 | 1441 | 1841
Northeast | N | CLARK | US 61 S | 2P3353 | 13.161 | 91.426 | 0 | Pavement improvements from the Iowa State line to 0.5 mile north of Rte. B in Lewis County near LaGrange (nine disconnected sections). Project includes southbound and northbound lanes on Rte. 27 from the Iowa State line to the Rte. 61 interchange. | 2029 | 134 | 30 | 468 | 498 | 0 | 0 | 0 | 0 | 0 | 0 | 6968 | 7600
Northeast | N | CLARK | US 61 S | NE0048 | 14.706 | 29.412 | 0 | Pavement improvement on southbound lanes from Fox River to 1.2 miles north of Rte. B in Lewis County near Canton (seven disconnected sections) and from Iowa State line to Rte. 27. | 2027 | 170 | 100 | 466 | 566 | 0 | 0 | 0 | 0 | 0 | 0 | 5863 | 6599
Northeast | N | KNOX | MO 11 S | NE0024 | 42.609 | 85.218 | 0 | Pavement resurfacing from Rte. 15 near Baring to Rte. 129 in Linn County (three disconnected sections). | 2027 | 102 | 50 | 360 | 410 | 0 | 0 | 0 | 0 | 0 | 0 | 5253 | 5765
Northeast | N | KNOX | MO 15 S | NE0101 | 32.044 | 64.088 | 0 | Pavement improvement from Rte. 6 north junction at Edina to Rte. 168 in Shelbyville in Shelby County. | 2027 | 4 | 2 | 89 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 1328 | 1423
Northeast | N | KNOX | RT BB S | NE0148 | 0.025 | 0.05 | 1 | Bridge improvement over North River 1.1 miles south of Rte. 15. Project involves bridge P0989. | 2028 | 222 | 20 | 128 | 148 | 0 | 2 | 0 | 2 | 0 | 0 | 1362 | 1734
Northeast | N | KNOX | RT F E | NE0149 | 0.016 | 0.032 | 1 | Bridge improvement over Little Fabius Creek 3.3 miles west of Rte. 15 near Hurdland. Project involves bridge P0400. | 2028 | 152 | 10 | 83 | 93 | 0 | 2 | 0 | 2 | 0 | 0 | 978 | 1225
Northeast | N | KNOX | RT K E | NE0156 | 0.034 | 0.068 | 1 | Bridge improvement over Middle Fabius River 0.5 mile east of Rte. V near Colony. Project involves bridge X0617. | 2027 | 200 | 150 | 252 | 402 | 0 | 2 | 0 | 2 | 0 | 0 | 2286 | 2890
Northeast | N | LEWIS | RT C E | NE0027 | 14.38 | 28.76 | 0 | Pavement resurfacing from Rte. 6 in Ewing to Rte. B in LaGrange. | 2026 | 42 | 153 | 0 | 153 | 1 | 0 | 0 | 0 | 0 | 2084 | 0 | 2280
Northeast | N | LEWIS | RT H S | NE0150 | 0.06 | 0.12 | 1 | Bridge improvement over Middle Fabius River 2.3 miles south of Rte. Y near Lewistown. Project involves bridge R0153. | 2029 | 377 | 25 | 242 | 267 | 0 | 0 | 2 | 2 | 0 | 0 | 2742 | 3388
Northeast | N | LEWIS | RT V E | NE0146 | 0.484 | 0.964 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan from Olive Avenue to 292nd Avenue in Maywood. | 2026 | 99 | 38 | 0 | 38 | 2 | 0 | 0 | 0 | 0 | 537 | 0 | 676
Northeast | N | LINCOLN | MO 147 S | NE0124 | 0.015 | 0.03 | 1 | Bridge improvement over Little Sugar Creek 0.9 mile north of Rte. 47 near Troy. Project involves bridge L0844. | 2030 | 225 | 10 | 85 | 95 | 1 | 0 | 0 | 0 | 0 | 0 | 733 | 1054
Northeast | N | LINCOLN | MO 47 S | NE0003 | 6.88 | 13.76 | 0 | Pavement resurfacing, add center turn lane from Rte. H to Bennington Drive, add shoulders from 0.1 mile west of Rtes. H and J in Troy to Rtes. A and D in Hawk Point. $1,841,000 Open Container funds. | 2026 | 1580 | 1275 | 0 | 1275 | 2685 | 0 | 0 | 0 | 0 | 19050 | 0 | 24590
Northeast | N | LINCOLN | MO 47 S | NE0023 | 0.213 | 0.426 | 1 | Bridge improvement over Cuivre River 1.3 miles east of Rte. 61 near Troy. Project involves bridge A5595. | 2028 | 22 | 1 | 54 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 798 | 875
Northeast | N | LINCOLN | MO 47 S | NE0248 | 2.099 | 7.097 | 0 | Pavement resurfacing from Turnbull Trail to 0.1 mile west of Rtes. H and J in Troy. | 2026 | 0 | 144 | 0 | 144 | 0 | 0 | 0 | 0 | 0 | 1367 | 0 | 1511
Northeast | N | LINCOLN | E OR 61 S | NE0096 | 5.155 | 10.31 | 0 | Pavement resurfacing from 1 mile south of Rte. V to Rte. C on various segments of the east and west outer roads (eight disconnected sections). $487,440 District Operation funds. | 2026 | 0 | 44 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 565 | 0 | 609
Northeast | N | LINCOLN | US 61 N | NE0236 | 0 | 30.638 | 0 | Pavement improvement on northbound lanes from Big Creek to Rte. V near Troy. $3,000,000 District Operations funds. | 2028 | 0 | 100 | 611 | 711 | 0 | 0 | 0 | 0 | 0 | 0 | 8278 | 8989
Northeast | N | LINCOLN | US 61 S | NE0004 | 2.948 | 8.684 | 0 | Add interchange with roundabouts and outer roads from 0.2 mile north of Rtes. V and K to 0.1 mile south of Creech Lane. $556,000 Open Container funds. | 2027 | 2000 | 700 | 1924 | 2624 | 0 | 1102 | 0 | 1102 | 0 | 0 | 23068 | 28794
Northeast | N | LINCOLN | US 61 S | NE0144 | 2.404 | 7.462 | 0 | Safety and intersection improvements at Rte. B and Rte. E near Troy. | 2028 | 1200 | 750 | 1611 | 2361 | 0 | 50 | 0 | 50 | 0 | 0 | 21638 | 25249
Northeast | N | LINCOLN | US 61 S | NE0235 | 17.776 | 36.567 | 0 | Pavement improvements on southbound lanes from Rte. E to Big Creek near Moscow Mills. | 2028 | 0 | 75 | 715 | 790 | 0 | 0 | 0 | 0 | 0 | 0 | 9898 | 10688
Northeast | N | LINCOLN | MO 79 S | NE0086 | 17.063 | 34.126 | 0 | Pavement improvement from Pike County line to Rte. 47 in Winfield. | 2029 | 56 | 5 | 247 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 3688 | 3996
Northeast | N | LINCOLN | RT B E | NE0094 | 10.593 | 21.186 | 0 | Pavement preservation treatment from Rte. 61 to Rte. 79 at Elsberry. | 2026 | 10 | 39 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 427 | 0 | 476
Northeast | N | LINCOLN | RT C E | NE0089 | 10.881 | 22.246 | 0 | Pavement improvement from Elm Tree Road to Main Street in Old Monroe. $1,429,000 Open Container funds. | 2028 | 15 | 10 | 510 | 520 | 0 | 0 | 3 | 3 | 0 | 0 | 4018 | 4556
Northeast | N | LINCOLN | RT C W | NE0219 | 0.164 | 0.328 | 2 | Bridge improvement over Cuivre River 0.1 mile east of Front Street in Moscow Mills and over Rte. 61 on Old Cap Au Gris Road in Troy. Project involves bridges A1658 and A2606. | 2027 | 10 | 50 | 170 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 1808 | 2038
Northeast | N | LINCOLN | CST EAST CHERRY ST E | NE0196 | 0.051 | 0.102 | 1 | Bridge improvement over Rte. 61 in Troy. Project involves bridge A2605. | 2027 | 200 | 10 | 110 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 1503 | 1823
Northeast | N | LINCOLN | RT EE S | NE0093 | 5.256 | 10.512 | 0 | Pavement resurfacing from Rte. Y to Rte. 47 near Winfield. | 2026 | 0 | 54 | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 642 | 0 | 696
Northeast | N | LINCOLN | RT J S | NE0051 | 0.084 | 0.168 | 1 | Bridge replacement over Big Creek 0.2 mile south of Rte. U. Project involves bridge P0746. | 2026 | 390 | 175 | 0 | 175 | 0 | 2 | 0 | 2 | 0 | 2254 | 0 | 2821
Northeast | N | LINCOLN | RT J S | NE0237 | 11.623 | 23.312 | 0 | Pavement improvement from Rte. H in Troy to I-70 north Outer Road in Wright City. | 2028 | 0 | 100 | 471 | 571 | 0 | 0 | 10 | 10 | 0 | 0 | 4955 | 5536
Northeast | N | LINCOLN | RT U E | NE0087 | 13.106 | 26.212 | 0 | Pavement preservation treatment from Rte. 47 to 0.7 mile west of Rte. 61 near Moscow Mills (two disconnected sections). | 2026 | 10 | 38 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 488 | 0 | 536
Northeast | N | LINCOLN | RT W S | 2S3377 | 4.047 | 8.094 | 0 | Pavement resurfacing from Rte. KK to Rte. 47 near Troy. | 2026 | 13 | 44 | 0 | 44 | 0 | 0 | 0 | 0 | 0 | 562 | 0 | 619
Northeast | N | LINCOLN | RT W S | NE0092 | 7.825 | 15.65 | 0 | Pavement preservation treatment from Rte. B to Rte. KK near Brussells. | 2026 | 5 | 23 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 265 | 0 | 293
Northeast | N | MACON | MO 149 S | NE0158 | 0.01 | 0.02 | 1 | Culvert improvement over Little Walnut Creek 0.1 mile south of Rte. 156 near Gifford. Project involves culvert X0936. | 2029 | 350 | 10 | 119 | 129 | 0 | 2 | 0 | 2 | 0 | 0 | 1415 | 1896
Northeast | N | MACON | MO 156 E | NE0147 | 1.457 | 2.914 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in La Plata, Elmer, Ethel, South Gifford and College Mound. | 2026 | 69 | 65 | 0 | 65 | 2 | 0 | 0 | 0 | 0 | 927 | 0 | 1063
Northeast | N | MACON | US 36 E | NE0120 | 6.83 | 30.44 | 4 | Pavement resurfacing and bridge joint and deck repair from 0.5 mile west of Rte. C to 0.1 mile east of Kellogg Avenue near Macon and on westbound from Kellogg Avenue to 1.7 miles west of Rte. O. Project involves bridges A3820 and A2041. | 2026 | 200 | 479 | 0 | 479 | 0 | 0 | 0 | 0 | 0 | 6834 | 0 | 7513
Northeast | N | MACON | US 63 S | NE0137 | 0.555 | 2.13 | 1 | Bridge rehabilitation, widen interchange ramps and signalize intersections at Rte. 36 and add raised islands at Rte. 36 and Kellogg Avenue in Macon. Project involves bridge A2043. | 2026 | 295 | 249 | 0 | 249 | 2 | 0 | 0 | 0 | 0 | 3198 | 0 | 3744
Northeast | N | MACON | RT D S | NE0061 | 1.003 | 2.006 | 0 | Pavement resurfacing from Rte. 63 to Rte. 156 in La Plata. | 2026 | 3 | 18 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 224 | 0 | 245
Northeast | N | MACON | RT UU S | 2S3315 | 0.277 | 0.554 | 1 | Bridge improvement over BNSF Railway 0.5 mile north of Rte. 36 near Callao. Project involves bridge W0401. | 2028 | 18 | 300 | 446 | 746 | 0 | 0 | 52 | 52 | 0 | 0 | 3030 | 3846
Northeast | N | MACON | RT VV S | NE0139 | 0.356 | 0.712 | 1 | Bridge replacement over BNSF Railway 0.2 mile south of Arctic Road near Hart. Project involves bridge W0404. | 2026 | 350 | 256 | 0 | 256 | 0 | 40 | 0 | 40 | 0 | 3001 | 0 | 3647
Northeast | N | MACON | RT YY E | NE0058 | 6.286 | 12.572 | 0 | Pavement resurfacing from Rte. 63 near Macon to end of state maintenance. | 2026 | 17 | 60 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 804 | 0 | 881
Northeast | N | MARION | MO 168 E | NE0054 | 5.315 | 10.63 | 0 | Pavement resurfacing from 0.1 mile east of Rte. BB in Palmyra to 0.2 mile east of Rte. JJ and on Rte. JJ. | 2026 | 45 | 107 | 0 | 107 | 0 | 0 | 0 | 0 | 0 | 1128 | 0 | 1280
Northeast | N | MARION | MO 168 E | NE0065 | 6.68 | 13.36 | 0 | Pavement improvement and add rumble stripes from 0.2 mile east of Rte. JJ to Rte. 61 at Hannibal. | 2027 | 81 | 50 | 117 | 167 | 0 | 2 | 0 | 2 | 0 | 0 | 1609 | 1859
Northeast | N | MARION | US 24 E | NE0108 | 0.43 | 0.86 | 1 | Payment to IDOT for bridge replacement study on the Quincy Memorial Bridge over the Mississippi River. Project involves bridge L0099. | 2027 | 3 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 4005
Northeast | N | MARION | US 24 E | NE0231 | 0.433 | 0.866 | 1 | Payment to IDOT for bridge replacement on the Quincy Memorial Bridge over the Mississippi River at Quincy. Project involves bridge L0099. | 2030 | 0 | 1 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 105005
Northeast | N | MARION | US 24 E | NE0245 | 0.145 | 0.29 | 1 | Bridge improvement over South Fabius River 1.2 miles south of Rte. 6 near Taylor. Project involves bridge A2021. | 2028 | 0 | 30 | 81 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 556 | 667
Northeast | N | MARION | US 24 W | NE0109 | 0 | 0.914 | 1 | Payment to IDOT for rehabilitation on Quincy Bayview Bridge over the Mississippi River. Project involves bridge A4274. | 2028 | 2 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 5005
Northeast | N | MARION | US 24 W | NE0233 | 0 | 0.682 | 0 | Intersection safety improvement at southbound Rte. 61, westbound Rte. 24 and Rte. F. | 2027 | 0 | 150 | 187 | 337 | 0 | 0 | 0 | 0 | 0 | 0 | 2061 | 2398
Northeast | N | MARION | US 61 S | NE0008 | 0 | 0 | 0 | Signal and striping improvements at various locations in Hannibal, Troy, Warrenton, Kirksville, Macon and Moberly. | 2027 | 10 | 10 | 35 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 381 | 436
Northeast | N | MARION | IS 72 E | 2I3367 | 0.394 | 1.6 | 1 | Bridge washing on the Mark Twain Memorial Bridge over the Mississippi River at Hannibal. Project involves bridge A5054. $46,000 IDOT funds. | 2026 | 4 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 103
Northeast | N | MARION | IS 72 E | NE0200 | 0.394 | 1.6 | 1 | Bridge washing on the Mark Twain Memorial Bridge over the Mississippi River at Hannibal. Project involves bridge A5054. $55,000 IDOT funds. | 2029 | 1 | 1 | 11 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 133
Northeast | N | MARION | IS 72 E | NE0232 | 0.394 | 1.6 | 1 | Bridge improvement on the Mark Twain Memorial Bridge over the Mississippi River at Hannibal. Project involves bridge A5054. $3,760,000 IDOT funds. | 2030 | 0 | 1 | 1511 | 1512 | 0 | 0 | 0 | 0 | 0 | 0 | 8464 | 9976
Northeast | N | MARION | RT A S | NE0066 | 8.52 | 17.04 | 1 | Pavement preservation treatment from Rte. 6 to Rte. 168 near Palmyra. Project involves bridge X0343. | 2026 | 15 | 35 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 291 | 0 | 341
Northeast | N | MARION | RT H S | NE0070 | 13.675 | 27.35 | 0 | Pavement preservation treatment from Rte. 36 to Rte. 19 at Center in Ralls County. | 2026 | 10 | 37 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 463 | 0 | 510
Northeast | N | MONROE | MO 15 S | NE0214 | 0.068 | 0.136 | 1 | Bridge improvement over North Fork of Fabius River 0.3 mile south of Rte. 24 in Paris. Project involves bridge A4396. | 2027 | 50 | 75 | 99 | 174 | 0 | 1 | 0 | 1 | 0 | 0 | 735 | 960
Northeast | N | MONROE | US 24 E | NE0047 | 8.931 | 17.862 | 2 | Culvert extension from 0.8 mile west of Rte. 107 to Rte. W at Monroe City. Project involves culverts J0767 and J0795. | 2026 | 120 | 171 | 0 | 171 | 0 | 5 | 0 | 5 | 0 | 2343 | 0 | 2639
Northeast | N | MONROE | RT AA E | NE0153 | 0.086 | 0.172 | 1 | Bridge improvement over Elk Fork Salt River 3.3 miles south of Rte. 24 near Madison. Project involves bridge R0548. | 2028 | 150 | 30 | 98 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 1205 | 1483
Northeast | N | MONTGOMERY | IS 70 E | 2I3226Z | 4.098 | 0 | 0 | Payback for MTFC loan to add eastbound and westbound climbing lanes, replace westbound bridge over Loutre River Overflow from 1.1 miles east of Rte. N to 0.3 mile west of Rte. 161 near Mineola. Total cost of $3,878,000 with payments from 2024 to 2030. | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1108 | 554 | 2216 | 3878
Northeast | N | MONTGOMERY | IS 70 E | NE0129 | 38.598 | 0 | 0 | Job Order Contracting for pavement repair from the Callaway County line to the St. Charles County line. | 2027 | 1 | 1 | 38 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 541 | 581
Northeast | N | MONTGOMERY | IS 70 E | NE0201 | 42.194 | 0 | 0 | Job Order Contracting for guard cable repair on I-70 in Montgomery and Warren Counties, Rte. 61 in Lincoln County, Rte. T in Ralls County and Rte. 36 in Macon County. | 2027 | 1 | 1 | 50 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 721 | 773
Northeast | N | PIKE | RT B E | NE0052 | 0.037 | 0.074 | 1 | Bridge replacement over Peno Creek 0.4 mile west of Rte. 61 near Frankford. Project involves bridge L0242. | 2026 | 340 | 119 | 0 | 119 | 2 | 0 | 0 | 0 | 0 | 1581 | 0 | 2042
Northeast | N | PIKE | RT D S | NE0075 | 15.092 | 30.184 | 0 | Pavement resurfacing from Rte. 79 to Rte. 61 in Eolia. | 2026 | 32 | 136 | 0 | 136 | 0 | 0 | 0 | 0 | 0 | 1683 | 0 | 1851
Northeast | N | PIKE | RT W S | NE0152 | 0.02 | 0.04 | 1 | Bridge replacement over Little Ramsey Creek 0.5 mile north of Rte. H in Paynesville. Project involves bridge P0366. | 2026 | 185 | 72 | 0 | 72 | 2 | 0 | 0 | 0 | 0 | 905 | 0 | 1164
Northeast | N | RALLS | MO 154 E | NE0107 | 12.351 | 24.702 | 0 | Pavement improvement from Rte. 19 south junction to Rte. 54 near Vandalia in Pike County. | 2027 | 6 | 4 | 105 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 1563 | 1678
Northeast | N | RALLS | US 61 S | NE0244 | 7.89 | 32.401 | 0 | Pavement improvement from Warren Barrett Drive in Hannibal to 0.5 mile south of Rte. 19 near New London. | 2027 | 0 | 200 | 767 | 967 | 0 | 0 | 0 | 0 | 0 | 0 | 8510 | 9477
Northeast | N | RALLS | RT J S | NE0072 | 19.163 | 38.326 | 0 | Pavement improvement from Rte. 36 to Rte. 154 in Perry (two disconnected sections). | 2028 | 41 | 5 | 391 | 396 | 0 | 0 | 0 | 0 | 0 | 0 | 4109 | 4546
Northeast | N | RANDOLPH | US 24 E | NE0170 | 0.025 | 0.05 | 1 | Bridge improvement over East Fork Salt River 0.5 mile east of Rte. YY near Milton. Project involves bridge L0118. | 2028 | 300 | 250 | 815 | 1065 | 0 | 0 | 10 | 10 | 0 | 0 | 4870 | 6245
Northeast | N | RANDOLPH | BU 63 S | NE0002 | 0.301 | 0.602 | 0 | Payment to Moberly for ADA Transition Plan improvements and add center turn lane from Burkhart Street to Carpenter Street. $1,056,161 Cost Share funds. | 2026 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 1056 | 0 | 1066
Northeast | N | RANDOLPH | BU 63 S | NE0038 | 1.805 | 3.61 | 0 | Pavement resurfacing from Carpenter Street to Rte. A in Moberly. | 2026 | 85 | 58 | 0 | 58 | 0 | 0 | 0 | 0 | 0 | 695 | 0 | 838
Northeast | N | RANDOLPH | RT B W | NE0077 | 18.294 | 36.588 | 0 | Pavement improvement from Rte. 63 near Clark to Rte. 3 near Roanoke in Howard County. | 2028 | 17 | 10 | 230 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 2296 | 2553
Northeast | N | SCHUYLER | RT N S | NE0097 | 7.981 | 15.962 | 0 | Pavement improvement from Iowa State line to Rte. 136 in Downing. | 2028 | 3 | 3 | 22 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 310 | 338
Northeast | N | SCOTLAND | MO 15 S | NE0056 | 10.821 | 21.642 | 0 | Pavement preservation treatment from the Iowa State line to Rte. 136 east junction in Memphis. | 2026 | 17 | 40 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 436 | 0 | 493
Northeast | N | SCOTLAND | MO 15 S | NE0057 | 22.466 | 44.932 | 0 | Pavement preservation treatment from Rte. 136 west junction at Memphis to Rte. 6 north junction at Edina in Knox County. | 2026 | 41 | 83 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 913 | 0 | 1037
Northeast | N | SCOTLAND | RT MM S | NE0098 | 5.238 | 10.476 | 0 | Pavement improvement from Rte. 136 in Memphis to Rte. M. | 2027 | 3 | 1 | 49 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 718 | 771
Northeast | N | SHELBY | MO 15 S | NE0028 | 0.4 | 0.48 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan in Shelbina and Leonard on Rte. H. | 2026 | 275 | 95 | 0 | 95 | 0 | 15 | 0 | 15 | 0 | 506 | 0 | 891
Northeast | N | SHELBY | MO 168 E | NE0063 | 31.27 | 62.54 | 0 | Pavement improvement from Rte. 15 to Bus. 61 in Palmyra in Marion County and add rumble stripes from Philadelphia to Palmyra. | 2027 | 350 | 50 | 336 | 386 | 0 | 20 | 0 | 20 | 0 | 0 | 4669 | 5425
Northeast | N | SHELBY | US 36 E | NE0221 | 0.019 | 0.038 | 1 | Bridge improvement over Branch of Crooked Creek 1 mile east of Rte. TT near Clarence. Project involves bridge H0590. | 2027 | 10 | 15 | 22 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 182 | 229
Northeast | N | SHELBY | US 36 E | NE0252 | 7.225 | 14.45 | 0 | Pavement repair from 0.5 mile east of North Fork Salt River near Hunnewell to 0.4 mile east of County Road 381 in Marion County near Monroe City. $1,465,445 District Operation funds. | 2026 | 0 | 182 | 0 | 182 | 0 | 0 | 0 | 0 | 0 | 1925 | 0 | 2107
Northeast | N | SHELBY | RT C E | NE0067 | 19.006 | 38.012 | 0 | Pavement improvement from Rte. Z to Rte. 168 near Palmyra in Marion County. | 2029 | 28 | 20 | 164 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 2376 | 2588
Northeast | N | VARIOUS | Various | 5B0800Q | 0 | 0 | 81 | Payback beginning in SFY 2008 for Safe and Sound bridges in the Northeast District. | 2033 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 73154 | 5280 | 21120 | 99650
Northeast | N | VARIOUS | Various | NE0134 | 0 | 0 | 0 | Job Order Contracting for guardrail repair at various locations in the Northeast District. | 2027 | 3 | 1 | 155 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 2266 | 2425
Northeast | N | VARIOUS | Various | NE0175 | 0 | 0 | 0 | On-call work zone enforcement at various locations in the Northeast District. | 2026 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 13
Northeast | N | VARIOUS | Various | NE0202 | 0 | 0 | 0 | On-call work zone enforcement at various locations in the Northeast District. | 2027 | 1 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 14
Northeast | N | VARIOUS | Various | NE0203 | 0 | 0 | 0 | On-call work zone enforcement at various locations in the Northeast District. | 2028 | 1 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 14
Northeast | N | WARREN | MO 47 S | NE0117 | 21.709 | 43.531 | 0 | Pavement improvement from 0.1 mile south of Rtes. M and MM in Warrenton to Missouri River Bridge near Washington. | 2028 | 7 | 30 | 197 | 227 | 0 | 0 | 0 | 0 | 0 | 0 | 2652 | 2886
Northeast | N | WARREN | MO 47 S | NE0247 | 0.513 | 1.026 | 0 | Payment to Warren County R-III School District to add turn lanes and signals at Nina Drive and add turn lanes at Ash Road in Warrenton. $1,416,805 Cost Share funds. | 2027 | 0 | 5 | 15 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 1417 | 1437
Kansas City | Y | CASS | MO 2 E | KU0049 | 14.657 | 29.352 | 0 | Pavement resurfacing from Independence Street to Rte. ZZ in Johnson County. | 2026 | 7 | 245 | 0 | 245 | 0 | 0 | 0 | 0 | 0 | 3466 | 0 | 3718
Kansas City | Y | CASS | MO 2 E | KU0293 | 0.045 | 0 | 8 | Erosion repairs at bridges and culverts at various locations in the urban Kansas City District. Project involves bridges A2087, A3301, A3329, A3980, N0327, N0360, N0836 and P0812. | 2026 | 40 | 252 | 0 | 252 | 0 | 1 | 0 | 1 | 0 | 806 | 0 | 1099
Kansas City | Y | CASS | MO 2 E | KU0299 | 0.046 | 0.092 | 0 | Culvert replacement over Muddy Creek. $204,090 Cost Share, $215,000 Harrisonville, and $861,000 STBG-Urban funds. | 2026 | 20 | 135 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 1280 | 0 | 1435
Kansas City | Y | CASS | MO 2 E | KU0299B | 0.046 | 0.092 | 0 | Payment to Harrisonville for design and right of way acquisition for culvert replacment over Muddy Creek. $29,742 Cost Share funds. | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 30
Kansas City | Y | CASS | MO 291 S | KU0267 | 8.684 | 18.119 | 0 | Pavement resurfacing from Rte. 58 to Waters Road. | 2027 | 15 | 463 | 556 | 1019 | 0 | 0 | 0 | 0 | 0 | 0 | 8040 | 9074
Kansas City | Y | CASS | IS 49 N | KU0028 | 3.388 | 16.12 | 2 | Rebuild pavement, add lane, widen shoulders and replace barriers from 155th Street to Rte. 58 in Belton and bridge rehabilitation at 163rd Street. Project involves bridges A7352 and A7353. | 2028 | 1800 | 1500 | 5885 | 7385 | 0 | 0 | 1403 | 1403 | 0 | 0 | 69755 | 80343
Kansas City | Y | CASS | IS 49 S | KU0283 | 10.18 | 41.981 | 0 | Pavement resurfacing from Rte. 7 to Bates County line. | 2029 | 15 | 150 | 1124 | 1274 | 0 | 0 | 0 | 0 | 0 | 0 | 11055 | 12344
Kansas City | Y | CASS | W OR 49 S | KU0229 | 1.17 | 2.34 | 0 | Pavement improvements from 275th Street to 283rd Street in Harrisonville. | 2029 | 46 | 50 | 326 | 376 | 0 | 0 | 0 | 0 | 0 | 0 | 2993 | 3415
Kansas City | Y | CASS | MO 58 E | KU0400 | 14.188 | 28.408 | 0 | Pavement resurfacing from Rte. 291 to Johnson County line. | 2026 | 10 | 447 | 0 | 447 | 0 | 0 | 0 | 0 | 0 | 5828 | 0 | 6285
Kansas City | Y | CASS | MO 7 S | KU0098 | 0.09 | 0.18 | 1 | Bridge replacement over Big Creek 0.3 mile north of Raffurty Road and 0.9 mile south of First Street near Pleasant Hill. Project involves bridge L0023. | 2026 | 590 | 1042 | 0 | 1042 | 0 | 10 | 0 | 10 | 0 | 6174 | 0 | 7816
Kansas City | Y | CASS | RT A E | KU0149 | 0.046 | 0.092 | 1 | Bridge replacement at I-49. Project involves bridge A3222. | 2030 | 15 | 150 | 677 | 827 | 0 | 0 | 0 | 0 | 0 | 0 | 4344 | 5186
Kansas City | Y | CASS | RT B E | KU0148 | 0.123 | 0 | 0 | Repair slides at South Grand River 0.4 mile from I-49. | 2026 | 15 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 175 | 0 | 205
Kansas City | Y | CASS | RT CC S | KU0390 | 54.898 | 109.979 | 0 | Pavement preservation treatment including Rtes. N and D in Cass County, Rtes. D, W and JJ in Clay County, Rte. F in Jackson County, Rte. N in Platte County and Rte. A in Ray County. | 2026 | 5 | 164 | 0 | 164 | 0 | 0 | 0 | 0 | 0 | 2162 | 0 | 2331
Kansas City | Y | CASS | RT D S | KU0109 | 0.142 | 0.294 | 1 | Bridge rehabilitation over Massey Creek 0.9 mile south of 231st Street and 1.1 miles north of Rte. Y. Project involves bridge A2251. | 2027 | 65 | 49 | 82 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 1148 | 1344
Kansas City | Y | CASS | RT D S | KU0144 | 0.62 | 0 | 0 | Repair slides from 223rd Street to 227th Terrace. | 2026 | 15 | 125 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 1596 | 0 | 1736
Kansas City | Y | CASS | RT J N | KU0237 | 6.108 | 12.415 | 0 | Add roundabouts at Hubach Hill Road and 203rd Street, add turn lanes at 195th Street and 211th Street and pavement resurfacing from Rte. 58 to Rte. 49. $2,541,000 Open Container funds. | 2027 | 460 | 700 | 629 | 1329 | 0 | 147 | 0 | 147 | 0 | 0 | 8074 | 10010
Kansas City | Y | CASS | RT K S | KU0277 | 6.541 | 13.08 | 0 | Pavement resurfacing from Rte. P to Rte. 2 and Spur K from Ohio Street to Rte. 2. | 2029 | 15 | 5 | 128 | 133 | 0 | 0 | 0 | 0 | 0 | 0 | 1662 | 1810
Kansas City | Y | CLAY | MO 1 S | KU0096 | 0.266 | 0.603 | 0 | Upgrade pedestrian facilities under I-35 from Northeast 43rd Street to Northeast 44th Street. | 2026 | 115 | 391 | 0 | 391 | 0 | 27 | 0 | 27 | 0 | 1584 | 0 | 2117
Kansas City | Y | CLAY | MO 152 E | KU0142 | 0.344 | 1.656 | 0 | Payback to Kansas City to add bicycle and pedestrian overpass at Rte. 169. $1,059,392 Cost Share funds. | 2026 | 11 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 1059 | 0 | 1076
Kansas City | Y | CLAY | US 169 N | 4P3093 | 0.631 | 1.905 | 10 | Bridge rehabilitation at various locations in the urban Kansas City District. Project involves bridges A3527, A3528, A3530, A5249, A5260, A5313, A6333, A6334, A6335 and L0642. | 2026 | 500 | 499 | 0 | 499 | 0 | 0 | 0 | 0 | 0 | 4080 | 0 | 5079
Kansas City | Y | CLAY | US 169 S | KU0064 | 4.514 | 19.623 | 0 | Pavement resurfacing from I-29 to the Buck O'Neil Bridge. | 2026 | 55 | 398 | 0 | 398 | 0 | 0 | 0 | 0 | 0 | 4465 | 0 | 4918
Kansas City | Y | CLAY | MO 210 E | KU0111 | 0.329 | 1.352 | 2 | Bridge rehabilitation over Rte. 269 0.8 mile east of Walker Road and 0.8 mile west of North Brighton Avenue. Project involves bridges A2175 and A2176. | 2029 | 1086 | 262 | 1602 | 1864 | 0 | 0 | 5 | 5 | 0 | 0 | 8047 | 11002
Kansas City | Y | CLAY | MO 269 S | KU0425 | 0.51 | 2.036 | 1 | Bridge rehabilitation over Missouri River. Project involves bridge A5817. | 2029 | 20 | 50 | 1214 | 1264 | 0 | 0 | 0 | 0 | 0 | 0 | 7816 | 9100
Kansas City | Y | CLAY | IS 29 S | 4I3458 | 0.591 | 3.942 | 2 | Bridge replacement over Guinotte Avenue 0.4 mile south of Missouri River and 0.7 mile north of Rte. 24 and over Bedford Avenue 1 mile south of Rte. 210 and 0.5 mile north of Missouri River. Project involves bridges L0788 and L0789. | 2028 | 1769 | 10500 | 28360 | 38860 | 0 | 0 | 1 | 1 | 0 | 0 | 217448 | 258078
Kansas City | Y | CLAY | IS 29 S | KU0061 | 0.324 | 1.731 | 2 | Bridge rehabilitation over Parvin Road 0.7 mile north of Rte. 1 and 1.5 miles south of Rte. 210. Project involves bridges L0659 and L0660. | 2027 | 550 | 800 | 1480 | 2280 | 0 | 0 | 0 | 0 | 0 | 0 | 10456 | 13286
Kansas City | Y | CLAY | IS 29 S | KU0292 | 0.089 | 0.402 | 2 | Bridge rehabilitation over southbound Rte. 169 and bridge replacement over northbound Rte. 169. Project involves bridges A1613 and L0719. | 2026 | 200 | 230 | 0 | 230 | 0 | 0 | 0 | 0 | 0 | 2601 | 0 | 3031
Kansas City | Y | CLAY | MO 291 N | KU0125 | 0.07 | 1.031 | 1 | Bridge rehabilitation over Union Pacific Railroad 1.2 miles north of Ruth Ewing Road and 0.2 mile south of Leonard Street. Project involves bridge A2503. | 2026 | 197 | 154 | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 1640 | 0 | 1991
Kansas City | Y | CLAY | MO 291 N | KU0205 | 1.379 | 7.021 | 0 | Pavement resurfacing from Leonard Street to Orchard Avenue. | 2029 | 7 | 25 | 258 | 283 | 0 | 0 | 0 | 0 | 0 | 0 | 2118 | 2408
Kansas City | Y | CLAY | MO 291 N | KU0402 | 0.64 | 3.35 | 0 | Payment to Liberty for sidewalk and signal upgrades from Stewart Road to Kansas Street. $1,092,500 Cost Share funds. | 2026 | 11 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1092 | 0 | 1108
Kansas City | Y | CLAY | MO 291 S | KU0117 | 0.915 | 1.419 | 0 | Upgrade signals at Flintlock Road and corridor improvements from 0.1 mile north of Northeast 104th Street to 0.1 mile west of North Overton Avenue. $4,000,000 Community Funded Projects funding. | 2028 | 15 | 400 | 2207 | 2607 | 0 | 0 | 530 | 530 | 0 | 0 | 9519 | 12671
Kansas City | Y | CLAY | MO 33 N | KU0035 | 13.122 | 27.727 | 0 | Pavement resurfacing from Rte. PP to Rte. 69. | 2026 | 247 | 263 | 0 | 263 | 0 | 0 | 0 | 0 | 0 | 3545 | 0 | 4055
Kansas City | Y | CLAY | MO 33 S | 4S3507 | 0.061 | 0.152 | 0 | Payment to Kearney to add turn lanes, pedestrian signals, traffic signals, sidewalks, and bike lanes at 19th Street. $1,224,582 Cost Share funds. | 2026 | 25 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 1225 | 0 | 1260
Kansas City | Y | CLAY | IS 435 S | KU0030 | 3.307 | 19.731 | 0 | Pavement resurfacing from Rte. 69 to the Missouri River. | 2026 | 99 | 370 | 0 | 370 | 0 | 0 | 0 | 0 | 0 | 4147 | 0 | 4616
Kansas City | Y | CLAY | IS 435 S | KU0146 | 0.005 | 0 | 0 | Repair erosion in the median 0.4 mile north of I-35. | 2030 | 15 | 3 | 46 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 226 | 290
Kansas City | Y | CLAY | US 69 N | 4S3482 | 0.895 | 4.082 | 0 | Payment to Kansas City to add shared use path, upgrade pedestrian facilities and upgrade drainage from Highland Avenue to Chouteau Trafficway. $2,745,217 Cost Share funds. | 2026 | 7 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 2745 | 0 | 2758
Kansas City | Y | CLAY | US 69 N | KU0097 | 0.507 | 2.639 | 0 | Upgrade sidewalks from Agnes Avenue to North Cleveland Avenue. | 2026 | 122 | 119 | 0 | 119 | 24 | 0 | 0 | 0 | 0 | 865 | 0 | 1130
Kansas City | Y | CLAY | US 69 S | KU0055 | 0.31 | 0.62 | 0 | Add roundabout at Rte. D in Lawson. | 2027 | 30 | 25 | 269 | 294 | 0 | 8 | 0 | 8 | 0 | 0 | 3669 | 4001
Kansas City | Y | CLAY | MO 9 N | 4S3401 | 0 | 5.08 | 0 | Payment to North Kansas City for pavement resurfacing and ADA upgrades from 10th Avenue to 32nd Avenue. | 2026 | 5 | 21 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 288 | 0 | 314
Kansas City | Y | CLAY | MO 9 S | KU0031 | 1.948 | 5.843 | 0 | Pavement resurfacing on the south bound lane from North Oak Trafficway to BNSF Railway Company Brookfield Sub. | 2026 | 82 | 73 | 0 | 73 | 0 | 4 | 0 | 4 | 0 | 897 | 0 | 1056
Kansas City | Y | CLAY | MO 9 S | KU0465 | 1.515 | 8.015 | 0 | Repair pavement and replace guardrail from 10th Avenue to Admiral Boulevard. | 2026 | 0 | 66 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 748 | 0 | 814
Kansas City | Y | CLAY | MO 92 E | KU0274 | 7.117 | 15.131 | 0 | Pavement resurfacing from Rte. 33 to Rte. 69. | 2030 | 7 | 10 | 279 | 289 | 0 | 0 | 0 | 0 | 0 | 0 | 3736 | 4032
Kansas City | Y | CLAY | CST BROADWAY BLVD N | KU0099 | 0.375 | 0.296 | 1 | Bridge replacement over BNSF Railway Company 2.7 miles north of Harlem Road and 0.6 mile south of Rte. 9. Project involves bridge A4642. | 2026 | 1500 | 2264 | 0 | 2264 | 0 | 20 | 0 | 20 | 0 | 19619 | 0 | 23403
Kansas City | Y | CLAY | CST BRYANT ST N | KU0123 | 0.031 | 0.062 | 1 | Bridge replacement over I-35 0.3 mile east of Poe Avenue and 0.5 mile west of I-435. Project involves bridge L0756. | 2027 | 12 | 351 | 200 | 551 | 0 | 0 | 0 | 0 | 0 | 0 | 2107 | 2670
Kansas City | Y | CLAY | RT C S | KU0276 | 7.162 | 14.324 | 0 | Pavement resurfacing from Clinton County line to Rte. 92. | 2026 | 74 | 164 | 0 | 164 | 0 | 0 | 0 | 0 | 0 | 1659 | 0 | 1897
Kansas City | Y | CLAY | RT H E | KU0269 | 8.958 | 8.958 | 0 | Pavement resurfacing from Liberty city limits to McKee Road. | 2030 | 15 | 5 | 144 | 149 | 0 | 0 | 3 | 3 | 0 | 0 | 2001 | 2168
Kansas City | Y | CLAY | RP IS29S TO IS35N N | KU0025 | 0 | 0.155 | 1 | Bridge rehabilitation over I-35 0.2 mile south of Davidson Road and 0.5 mile west of Rte. 1. Project involves bridge A1763. | 2027 | 301 | 680 | 718 | 1398 | 0 | 0 | 0 | 0 | 0 | 0 | 10177 | 11876
Kansas City | Y | CLAY | CRD RHODUS RD N | KU0236 | 0.21 | 0.42 | 0 | Intersection realignment from Rte. 69 to end of state maintenance in Mosby. | 2026 | 17 | 36 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 227 | 0 | 280
Kansas City | Y | JACKSON | MO 12 E | 4P3268G | 4.658 | 21.22 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan from Arlington Avenue to Spring Street and from Rte. 291 to Salem Drive. | 2026 | 494 | 166 | 0 | 166 | 39 | 0 | 0 | 0 | 0 | 1706 | 0 | 2405
Kansas City | Y | JACKSON | MO 150 E | KU0140 | 0.52 | 2.486 | 2 | Bridge rehabilitation over Union Pacific Railroad and Blue River from Wyandotte Street to 0.8 mile east of Holmes Road. Project involves bridges A5495 and A5496. | 2027 | 406 | 300 | 616 | 916 | 0 | 0 | 0 | 0 | 0 | 0 | 7259 | 8581
Kansas City | Y | JACKSON | MO 150 E | KU0362 | 5.905 | 26.268 | 0 | Roadway improvements from State Line Road to CPKC Railroad and on Rte. 78 from Swope Drive to 0.1 mile west of Powhatan Court. | 2029 | 10 | 5 | 85 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 1115 | 1215
Kansas City | Y | JACKSON | US 24 E | KU0204 | 6.49 | 27.745 | 0 | Pavement resurfacing from I-435 to Rte. 291. | 2029 | 7 | 10 | 253 | 263 | 0 | 0 | 0 | 0 | 0 | 0 | 3545 | 3815
Kansas City | Y | JACKSON | US 24 E | KU0226 | 0.67 | 2.874 | 0 | Upgrade bicycle, pedestrian facilities, drainage, signals and add intersection lighting from Sterling Avenue to Wilson Road and relocate Huttig Avenue to realign with Ash Avenue. $3,443,438 Cost Share, $1,913,000 Independence, $1,395,095 CMAQ funds. | 2026 | 180 | 446 | 0 | 446 | 250 | 0 | 0 | 0 | 0 | 6501 | 0 | 7377
Kansas City | Y | JACKSON | US 24 E | KU0273 | 5.412 | 24.363 | 0 | Pavement resurfacing from Rte. 291 to Rte. 7. | 2030 | 7 | 15 | 388 | 403 | 0 | 0 | 0 | 0 | 0 | 0 | 5631 | 6041
Kansas City | Y | JACKSON | US 24 W | KU0038 | 0.096 | 0.312 | 2 | Bridge rehabilitation over Union Pacific Railroad 0.2 mile west of Lake City Buckner Road and bridge rehabilitation over Fire Prairie Creek 0.2 mile east of North Holly Road. Project involves bridges A2725 and A2726. | 2026 | 125 | 335 | 0 | 335 | 0 | 0 | 0 | 0 | 0 | 3246 | 0 | 3706
Kansas City | Y | JACKSON | IS 29 N | KU0426 | 0.302 | 2.172 | 1 | Bridge rehabilitation over the Missouri River. Project involves bridge A7650. | 2029 | 1 | 1 | 18 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 183
Kansas City | Y | JACKSON | MO 291 N | 4P3471 | 0.346 | 1.488 | 2 | Bridge replacement, bridge rehabilitation and add pedestrian facilities over the Missouri River. Design-Build project. Project involves bridges L0568 and A4757. $1,000 Transportation Alternatives and $1,000 Carbon Reduction Program funds. | 2027 | 4355 | 4047 | 6288 | 10335 | 0 | 200 | 0 | 200 | 0 | 0 | 94776 | 109666
Kansas City | Y | JACKSON | MO 291 N | KU0272 | 5.176 | 17.439 | 0 | Pavement resurfacing from I-470 to Rte. 50. | 2030 | 7 | 20 | 367 | 387 | 0 | 0 | 0 | 0 | 0 | 0 | 4879 | 5273
Kansas City | Y | JACKSON | MO 291 S | KU0130 | 1.059 | 5.414 | 0 | Upgrade signal, lighting and turn lane extension from Rte. 78 to Hidden Valley Road. | 2027 | 9 | 25 | 55 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 698 | 787
Kansas City | Y | JACKSON | IS 35 N | KU0263 | 0.179 | 1.068 | 1 | Bridge rehabilitation over Southwest Boulevard. Project involves bridge A1701. | 2028 | 20 | 10 | 121 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 1252 | 1403
Kansas City | Y | JACKSON | MO 350 E | KU0404 | 0.288 | 1.246 | 1 | Bridge replacement, pavement resurfacing and adding turn lanes at Rte. 350 and Noland Road (Rte. V). Project involves bridge K0444. $5,100,000 MARC STBG-Urban funds. | 2026 | 142 | 402 | 0 | 402 | 272 | 0 | 0 | 0 | 0 | 6028 | 0 | 6844
Kansas City | Y | JACKSON | US 40 E | 4P3268I | 2.663 | 12.325 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in Jackson County. | 2026 | 510 | 200 | 0 | 200 | 23 | 0 | 0 | 0 | 0 | 2198 | 0 | 2931
Kansas City | Y | JACKSON | US 40 E | KU0066 | 0.667 | 3.789 | 0 | Corridor improvements and signal upgrades from Cliff Avenue to Little Blue Parkway. | 2027 | 604 | 509 | 800 | 1309 | 0 | 20 | 0 | 20 | 0 | 0 | 4378 | 6311
Kansas City | Y | JACKSON | US 40 E | KU0201 | 1.191 | 2.525 | 0 | Add signal at Kirby Road and turn lane at Barr Road and median barrier at Northwest Sni-A-Bar Boulevard. | 2026 | 90 | 56 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 717 | 0 | 863
Kansas City | Y | JACKSON | US 40 E | KU0479 | 2.681 | 12.28 | 0 | Mulitmodal safety and operational improvements from I-435 to Blue Ridge Boulevard. $2,633,000 Open Container funds. | 2028 | 0 | 500 | 2150 | 2650 | 0 | 0 | 0 | 0 | 0 | 0 | 8927 | 11577
Kansas City | Y | JACKSON | IS 435 S | KU0062 | 1.74 | 11.801 | 0 | Pavement resurfacing from Rte. 24 to Rte. 78. | 2026 | 208 | 378 | 0 | 378 | 0 | 0 | 0 | 0 | 0 | 4110 | 0 | 4696
Kansas City | Y | JACKSON | IS 435 S | KU0282 | 8.204 | 58.056 | 0 | Pavement resurfacing from 0.3 mile north of Raytown Road to 0.6 mile south of Rte. W. | 2027 | 60 | 20 | 1082 | 1102 | 0 | 0 | 0 | 0 | 0 | 0 | 12922 | 14084
Kansas City | Y | JACKSON | IS 435 S | KU0288 | 1.315 | 9.447 | 0 | Pavement resurfacing from Rte. 78 to Rte. 40. | 2027 | 7 | 25 | 183 | 208 | 0 | 0 | 0 | 0 | 0 | 0 | 2355 | 2570
Kansas City | Y | JACKSON | IS 49 N | KU0198 | 3.32 | 21.31 | 0 | Pavement resurfacing from Blue Ridge Avenue to 0.2 mile north of Rte. 150. | 2026 | 300 | 508 | 0 | 508 | 0 | 0 | 0 | 0 | 0 | 5865 | 0 | 6673
Kansas City | Y | JACKSON | IS 49 S | 4I3494 | 0.619 | 0.121 | 2 | Bridge replacement over Little Blue River 0.6 mile north of 155th Street and 0.6 mile south of Rte. 150. Project involves bridges A0478 and L0530. | 2028 | 1525 | 450 | 1774 | 2224 | 0 | 0 | 0 | 0 | 0 | 0 | 18334 | 22083
Kansas City | Y | JACKSON | IS 49 S | 4P3268H | 28.67 | 220.863 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in Kansas City and Grandview. | 2026 | 559 | 279 | 0 | 279 | 0 | 0 | 0 | 0 | 0 | 2195 | 0 | 3033
Kansas City | Y | JACKSON | US 50 E | KU0451 | 0.174 | 1.003 | 0 | Urgent sound abatement wall repair 0.3 mile west of Grandview Road. | 2026 | 75 | 33 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 408 | 0 | 516
Kansas City | Y | JACKSON | US 50 E | KU0453 | 0.155 | 0.62 | 0 | Urgent concrete barrier repair at Wornall Road in Kansas City. | 2026 | 65 | 23 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 255 | 0 | 343
Kansas City | Y | JACKSON | MO 7 N | 4S3298B | 0.486 | 2.499 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan from Roanoke Drive to Pink Hill Road. | 2026 | 28 | 45 | 0 | 45 | 0 | 10 | 0 | 10 | 0 | 287 | 0 | 370
Kansas City | Y | JACKSON | MO 7 S | KU0010 | 1.555 | 8.073 | 0 | Add sidewalks, bicycle/pedestrian trail, turn lanes and upgrade traffic signals from Shaw Parkway to Rte. 40. $850,000 Blue Springs and $3,400,000 STBG-Urban funds. | 2026 | 850 | 308 | 0 | 308 | 10 | 0 | 0 | 0 | 0 | 4250 | 0 | 5418
Kansas City | Y | JACKSON | MO 7 S | KU0415 | 1.567 | 8.145 | 0 | Upgrade turn lanes and signal from Shaw Parkway to Rte. 40. | 2026 | 322 | 117 | 0 | 117 | 0 | 0 | 0 | 0 | 0 | 1638 | 0 | 2077
Kansas City | Y | JACKSON | IS 70 E | 4I3211 | 0.1 | 0.6 | 1 | Bridge improvements at Union Pacific Railroad over I-70. Project involves bridge L0975. | 2030 | 255 | 750 | 3194 | 3944 | 0 | 0 | 0 | 0 | 0 | 0 | 17423 | 21622
Kansas City | Y | JACKSON | IS 70 E | 4I3459 | 0.851 | 4.852 | 2 | Bridge rehabilitation over Liberty Street and Mulberry Street from Kansas State line to 0.2 mile west of Broadway Street. Project involves bridges A0507 and A5658. | 2030 | 30 | 5 | 1853 | 1858 | 0 | 0 | 0 | 0 | 0 | 0 | 21951 | 23839
Kansas City | Y | JACKSON | IS 70 E | 4P3323B | 3.921 | 27.141 | 0 | Replace median barrier from Manchester Trafficway to Chrysler Street. | 2027 | 135 | 134 | 357 | 491 | 0 | 0 | 0 | 0 | 0 | 0 | 3692 | 4318
Kansas City | Y | JACKSON | IS 70 E | KU0016 | 0.088 | 0.578 | 2 | Bridge replacement at 11th Street 0.1 mile south of 10th Street and 0.1 mile north of 12th Street. Project involves bridge A0243. | 2027 | 991 | 590 | 894 | 1484 | 0 | 0 | 0 | 0 | 0 | 0 | 7077 | 9552
Kansas City | Y | JACKSON | IS 70 E | KU0114 | 0.614 | 3.696 | 4 | Bridge replacement over Rte. 40 0.1 mile west of Blue Ridge Boulevard and bridge replacement over Sterling Avenue 0.7 mile east of Pittman Road. Potential Design-Build. Project involves twin bridges L0972 and L0973. | 2029 | 1120 | 5 | 8492 | 8497 | 0 | 0 | 0 | 0 | 0 | 0 | 36394 | 46011
Kansas City | Y | JACKSON | IS 70 E | KU0156 | 0.031 | 0.155 | 2 | Bridge replacement over 12th Street. Project involves bridges A0244 and A0245. | 2027 | 780 | 700 | 889 | 1589 | 0 | 0 | 0 | 0 | 0 | 0 | 10345 | 12714
Kansas City | Y | JACKSON | IS 70 E | KU0291 | 7.225 | 44.77 | 0 | Pavement resurfacing from Kansas State line to 0.2 mile east of Rte. 40. | 2027 | 15 | 125 | 936 | 1061 | 0 | 0 | 0 | 0 | 0 | 0 | 12174 | 13250
Kansas City | Y | JACKSON | IS 70 W | KU0284 | 7.87 | 51.432 | 0 | Pavement resurfacing from Manchester Trafficway to I-470. | 2030 | 15 | 50 | 1136 | 1186 | 0 | 0 | 0 | 0 | 0 | 0 | 15324 | 16525
Kansas City | Y | JACKSON | US 71 N | 4S3415 | 0 | 0.254 | 1 | Bridge replacement over 12th Street 0.1 mile south of 10th Street and 0.1 mile north of 13th Street. Project involves bridge A0246. | 2027 | 135 | 350 | 523 | 873 | 0 | 0 | 0 | 0 | 0 | 0 | 4154 | 5162
Kansas City | Y | JACKSON | US 71 N | 4S3490 | 0.712 | 3.625 | 5 | Bridge rehabilitation over Rte. W (Bannister Road) 0.6 mile north of I-435 and 0.7 mile south of Blue River Road. Project involves twin bridges L0842 and culverts A2395 and H0033. | 2026 | 2788 | 2221 | 0 | 2221 | 0 | 0 | 0 | 0 | 0 | 21523 | 0 | 26532
Kansas City | Y | JACKSON | US 71 N | KU0460 | 0.198 | 1.188 | 2 | Bridge rehabilitation over Brush Creek. Project involves bridges A4997 and A4998. | 2030 | 0 | 5 | 115 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 1558 | 1678
Kansas City | Y | JACKSON | US 71 N | KU0461 | 0.205 | 0.675 | 2 | Bridge rehabilitation over Rte. 71. Project involves bridges A5162 and A5163. | 2030 | 0 | 5 | 71 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 844 | 920
Kansas City | Y | JACKSON | US 71 S | KU0321 | 0.56 | 3.652 | 29 | Bridge deck sealing in Jackson and Clay Counties. Involves bridges A0053, A1346, A2149, A2443, A2444, A2733, A2745, A4736, A4737, A4739, A4740, A4993, A4994, A5161, A5162, A5164, A5165, A5167, A5169, A7503, A7504, A7647, A7652, A7653, A7654, L0781, L0792, L0981, L0983. | 2027 | 5 | 5 | 47 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 630 | 687
Kansas City | Y | JACKSON | MO 78 E | 4P3268F | 4.596 | 22.99 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan from Maywood Street to Redwood Avenue. | 2026 | 471 | 225 | 0 | 225 | 30 | 0 | 0 | 0 | 0 | 3093 | 0 | 3819
Kansas City | Y | JACKSON | MO 78 E | KU0042 | 6.026 | 29.332 | 0 | Pavement resurfacing from I-435 to Rte. 291. | 2026 | 123 | 692 | 0 | 692 | 0 | 0 | 0 | 0 | 0 | 10779 | 0 | 11594
Kansas City | Y | JACKSON | MO 9 N | KU0270 | 0.718 | 3.426 | 1 | Bridge rehabilitation over Missouri River. Project involves bridge A4060. | 2029 | 106 | 900 | 4813 | 5713 | 0 | 0 | 0 | 0 | 0 | 0 | 35384 | 41203
Kansas City | Y | JACKSON | CST EASTWOOD TRFY E | KU0145 | 0.038 | 0 | 0 | Repair slides on northbound I-435 ramp. | 2030 | 3 | 5 | 42 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 424 | 474
Kansas City | Y | JACKSON | RT F S | KU0110 | 0.06 | 0.12 | 1 | Culvert replacement over Phillips Creek 0.5 mile north of Zumait Road and 0.5 mile south of Cline Road. Project involves culvert Y0024. | 2026 | 220 | 132 | 0 | 132 | 5 | 0 | 0 | 0 | 0 | 1018 | 0 | 1375
Kansas City | Y | JACKSON | CST HOLMES ST N | KU0024 | 0.61 | 0.122 | 1 | Bridge replacement over I-670, 0.1 mile north of Truman Road and 0.1 mile south of 13th Street. Project involves bridge A0825. | 2026 | 833 | 781 | 0 | 781 | 10 | 0 | 0 | 0 | 0 | 7049 | 0 | 8673
Kansas City | Y | JACKSON | RP RTD TO MO150E E | KU0147 | 0.251 | 0 | 0 | Repair slides at Holmes Road entrance ramp. | 2026 | 3 | 89 | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 529 | 0 | 621
Kansas City | Y | JACKSON | CST STADIUM DR E | KU0012 | 0.128 | 0.41 | 1 | Bridge painting over I-70. Project involves bridges A2842. | 2026 | 22 | 113 | 0 | 113 | 0 | 0 | 0 | 0 | 0 | 1338 | 0 | 1473
Kansas City | Y | JACKSON | RP STADIUM DR TO IS435S S | 4I3501 | 0.192 | 0.454 | 4 | Bridge rehabilitation over Raytown Road and Rock Island Trail 0.5 mile south of I-70. Project involves bridges A2843, A2844, A2852 and A2853. | 2028 | 51 | 715 | 666 | 1381 | 0 | 0 | 0 | 0 | 0 | 0 | 5385 | 6817
Kansas City | Y | JACKSON | CST VIEW HIGH DR N | 4I3470 | 0.184 | 0.678 | 0 | Payment to I-470 Western Gateway Transportation Development District to modify interchange configuration at I-470. $5,195,000 Cost Share funds. | 2026 | 12 | 275 | 0 | 275 | 0 | 0 | 0 | 0 | 0 | 5195 | 0 | 5482
Kansas City | Y | JACKSON | RT W E | KU0264 | 4.286 | 21.245 | 0 | Pavement rebuild from State Line Road to Holmes Road and pavement resurfacing from Holmes Road to I-435. | 2027 | 50 | 40 | 754 | 794 | 0 | 0 | 0 | 0 | 0 | 0 | 10966 | 11810
Kansas City | Y | JACKSON | CST W 14TH ST E | KU0129 | 0.082 | 0.164 | 1 | Bridge replacement over I-35 0.1 mile west of Pennsylvania Avenue to Summit Street. Project involves bridge A1122. | 2029 | 350 | 100 | 988 | 1088 | 0 | 0 | 0 | 0 | 0 | 0 | 6031 | 7469
Kansas City | N | JOHNSON | BU 13 S | 3S3229 | 0.528 | 2.103 | 2 | Bridge rehabilitation over Rte. 50 and pavement resurfacing 0.3 mile south of Cooper Avenue and 0.1 mile north of Russell Avenue. Project involves bridges A0143 and A0321. | 2029 | 40 | 25 | 131 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 1574 | 1770
Kansas City | N | JOHNSON | MO 13 S | 3P3109 | 0.261 | 0.52 | 0 | Add turn lanes, grading and drainage at the intersection of Rte. E. | 2026 | 118 | 174 | 0 | 174 | 5 | 55 | 0 | 55 | 0 | 2062 | 0 | 2414
Kansas City | N | JOHNSON | MO 2 W | KR0126 | 0.345 | 0.741 | 0 | Intersection improvements at Rte. 13. $711,000 Open Container funds. | 2029 | 15 | 109 | 392 | 501 | 0 | 0 | 50 | 50 | 0 | 0 | 2439 | 3005
Kansas City | N | JOHNSON | MO 23 S | KR0139 | 0.425 | 0.85 | 7 | Bridge painting in the rural Kansas City District. Project includes bridges A0207, A0808, A1983, A2124, A2850, R0545 and X0223. | 2026 | 60 | 124 | 0 | 124 | 0 | 0 | 0 | 0 | 0 | 1739 | 0 | 1923
Kansas City | N | JOHNSON | BU 50 E | 3P3202 | 1.198 | 1.707 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan and pavement resurfacing in Knob Noster from Washington Avenue to Sunshine Lane and Rte. J from Southeast 25 Road to State maintenance ends. | 2027 | 558 | 225 | 416 | 641 | 0 | 50 | 0 | 50 | 0 | 0 | 3148 | 4397
Kansas City | N | JOHNSON | US 50 E | KR0101 | 0.739 | 2.956 | 2 | Bridge rehabilitation over Blackwater Creek and bridge replacement over Butchers Branch 0.4 mile east of County Road 671 and 1.4 miles west of County Road Northwest 601. Project involves bridges A1175 and A1176. | 2026 | 835 | 486 | 0 | 486 | 0 | 0 | 0 | 0 | 0 | 4988 | 0 | 6309
Kansas City | N | JOHNSON | US 50 E | KR0104 | 0.071 | 0.142 | 1 | Bridge rehabilitation over South Fork Blackwater River 1 mile west of County Road Northwest 1601 and 0.1 mile east of Rte. Z. Project involves bridge A1223. | 2027 | 555 | 150 | 263 | 413 | 0 | 0 | 0 | 0 | 0 | 0 | 2492 | 3460
Kansas City | N | JOHNSON | US 50 E | KR0107 | 0.738 | 2.952 | 2 | Bridge rehabilitation over Devils Branch and Post Oak Creek 0.6 mile west of County Road 105 and 0.7 mile east of County Road Northwest 191. Project involves bridges A1042 and A1043. | 2027 | 435 | 20 | 559 | 579 | 0 | 0 | 0 | 0 | 0 | 0 | 3550 | 4564
Kansas City | N | JOHNSON | US 50 W | KR0102 | 0.201 | 0.804 | 1 | Bridge rehabilitation over Clear Fork Creek, 1.3 miles west of Rte. 23 and 0.9 mile east of 175th Street. Project involves bridge L0901. | 2026 | 75 | 133 | 0 | 133 | 0 | 0 | 0 | 0 | 0 | 1568 | 0 | 1776
Kansas City | N | JOHNSON | US 50 W | KR0403 | 1.462 | 7.159 | 0 | Intersection improvements from west of Northwest 1511 Road to west of NW 1391 Road. $865,000 Open Container funds. | 2028 | 10 | 5 | 465 | 470 | 0 | 0 | 0 | 0 | 0 | 0 | 3350 | 3830
Kansas City | N | JOHNSON | MO 58 W | KR0220 | 21.925 | 43.89 | 0 | Pavement resurfacing from Johnson County line to Rte. 50. | 2030 | 15 | 50 | 930 | 980 | 0 | 0 | 3 | 3 | 0 | 0 | 12552 | 13550
Kansas City | N | JOHNSON | CST N MAGUIRE ST N | KR0450 | 0.102 | 0.3 | 2 | Payment to Warrensburg for design of North Maguire Street and Holden Street bridge improvements over Rte. 50. Project involves bridges A0321 and A0143. $1,067,000 Cost Share funds. | 2026 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 1067 | 0 | 1077
Kansas City | N | JOHNSON | RT TT W | KR0296 | 0.037 | 0.074 | 6 | Bridge and culvert improvements at various locations in the rural Kansas City District. Project involves bridges A2384, A5622, N0299, P0609, P0813, and S0067. | 2029 | 15 | 75 | 286 | 361 | 0 | 0 | 0 | 0 | 0 | 0 | 1828 | 2204
Kansas City | N | LAFAYETTE | MO 13 S | 4P2333 | 12.034 | 24.075 | 0 | Pavement resurfacing and add turn lanes from Northwest 435th Road to 0.5 mile south of I-70. | 2026 | 3520 | 1487 | 0 | 1487 | 630 | 0 | 0 | 0 | 0 | 23341 | 0 | 28978
Kansas City | N | LAFAYETTE | MO 13 S | KR0076 | 6.877 | 14.076 | 0 | Pavement and safety improvements from Rte. 20 to I-70 in Higginsville. | 2029 | 29 | 15 | 229 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 3012 | 3285
Kansas City | Y | LAFAYETTE | MO 13 S | KR0351 | 2.222 | 9.448 | 0 | Pavement repair from Missouri River to Rte. 24. | 2029 | 4 | 5 | 93 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 1292 | 1394
Kansas City | N | LAFAYETTE | MO 20 E | KR0079 | 12.07 | 24.14 | 0 | Pavement repair from Rte. W in Lafayette County to Rte. EE in Saline County. | 2026 | 36 | 301 | 0 | 301 | 0 | 0 | 0 | 0 | 0 | 3843 | 0 | 4180
Kansas City | N | LAFAYETTE | US 24 E | KR0243 | 0.45 | 0.9 | 1 | Bridge rehabilitation on the Waverly River Bridge over the Missouri River. Project involves bridge A5910. | 2028 | 210 | 97 | 800 | 897 | 0 | 0 | 0 | 0 | 0 | 0 | 9272 | 10379
Kansas City | N | LAFAYETTE | US 24 W | KR0105 | 0.045 | 0.09 | 1 | Bridge rehabilitation over Tabo Creek 0.6 mile west of Garr Road. Project involves bridge A2850. | 2029 | 61 | 10 | 199 | 209 | 0 | 0 | 0 | 0 | 0 | 0 | 2352 | 2622
Kansas City | N | PETTIS | US 50 E | 3P3205 | 0.66 | 2.904 | 2 | Bridge rehabilitation, pavement resurfacing and upgrade guardrail over Muddy Creek 0.5 mile east of Rte. MM and 1.7 miles west of Main Street. Project involves bridge A2663. | 2027 | 278 | 50 | 358 | 408 | 0 | 0 | 0 | 0 | 0 | 0 | 5216 | 5902
Kansas City | N | PETTIS | US 50 E | KR0240 | 0.253 | 1.012 | 0 | Rebuild pavement from Massachusetts Avenue to Thompson Avenue. | 2029 | 7 | 5 | 111 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 1285 | 1408
Kansas City | N | PETTIS | US 65 S | 3P3206 | 0.425 | 1.696 | 2 | Bridge rehabilitation over Turkey Creek 0.1 mile south of John Road and 1.2 miles north of Smelser Road. Project involves bridges A0808 and A3039. | 2026 | 45 | 290 | 0 | 290 | 0 | 0 | 0 | 0 | 0 | 2312 | 0 | 2647
Kansas City | N | PETTIS | US 65 S | KR0168 | 1.016 | 4.188 | 0 | Corridor improvements from just north of Rte. HH to North Ohio Avenue in Sedalia. $704,000 Open Container funds. | 2027 | 275 | 58 | 439 | 497 | 0 | 23 | 0 | 23 | 0 | 0 | 2633 | 3428
Kansas City | N | PETTIS | RT H S | 3S3228 | 0.03 | 0.06 | 1 | Bridge replacement over Sewer Branch at Georgetown Road. Project involves bridge W0535. | 2029 | 40 | 133 | 281 | 414 | 0 | 25 | 0 | 25 | 0 | 0 | 1366 | 1845
Kansas City | Y | PLATTE | MO 273 S | KU0041 | 4.59 | 9.337 | 0 | Pavement resurfacing and replace guardrail from Rte. 45 to Rte. 371. | 2026 | 158 | 197 | 0 | 197 | 0 | 0 | 0 | 0 | 0 | 2766 | 0 | 3121
Kansas City | Y | PLATTE | IS 29 N | KU0455 | 0.416 | 1.755 | 0 | Repair slides and guardrail 0.3 mile south of North American Avenue, 0.6 mile south of North American Avenue, and 0.2 mile south of Rte. 92. | 2026 | 20 | 345 | 0 | 345 | 0 | 0 | 0 | 0 | 0 | 2772 | 0 | 3137
Kansas City | Y | PLATTE | IS 29 S | KU0017 | 13.992 | 40.913 | 0 | Pavement resurfacing on southbound lanes from 0.8 mile south of Mexico Avenue to Rte. 69 and on North Prairie View Road from Cookingham Drive to 112th Street and on outer road beginning of state maintenance to 72nd Street. | 2026 | 488 | 1420 | 0 | 1420 | 0 | 0 | 0 | 0 | 0 | 17203 | 0 | 19111
Kansas City | Y | PLATTE | IS 635 S | KU0095 | 0.303 | 0.909 | 1 | Bridge rehabilitation over the Missouri River. Project involves bridge A1800. $979,000 KDOT funds. | 2026 | 150 | 154 | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 1958 | 0 | 2262
Kansas City | Y | PLATTE | US 69 N | KU0427 | 0.403 | 1.505 | 1 | Bridge rehabilitation over Missouri River. Project involves bridge A8340. | 2028 | 10 | 10 | 369 | 379 | 0 | 0 | 0 | 0 | 0 | 0 | 2302 | 2691
Kansas City | Y | PLATTE | MO 92 E | KU0056 | 14.503 | 35.493 | 0 | Pavement resurfacing from Rte. 273 to Rte. DD. | 2027 | 45 | 5 | 610 | 615 | 0 | 0 | 0 | 0 | 0 | 0 | 7481 | 8141
Kansas City | Y | PLATTE | MO 92 E | KU0303 | 1.238 | 3.593 | 0 | Payment to Platte City for roadway realignment and add bicycle and pedestrian facilities. $6,667,950 Governor's Cost Share Program funds. | 2026 | 1 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 6668 | 0 | 6671
Kansas City | Y | PLATTE | MO 92 E | KU0373 | 0.247 | 0.494 | 1 | Payment to KDOT for bridge replacement of Centennial Bridge over the Missouri River at Leavenworth. Project involves bridge K0941. | 2028 | 2 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 62688 | 62693
Kansas City | Y | PLATTE | MO 92 E | KU0374 | 0.687 | 1.371 | 1 | Payment to KDOT for roadway widening at Centennial Bridge over the Missouri River. Project involves bridge K0941. | 2028 | 2 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 11976 | 11981
Kansas City | Y | PLATTE | MO 92 E | KU0448 | 0.21 | 0.42 | 1 | Right of way acquisition for roadway widening at Centennial Bridge over the Missouri River. | 2026 | 5 | 1 | 0 | 1 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 21
Kansas City | Y | PLATTE | RT B S | 4S3492 | 0.11 | 0.312 | 1 | Bridge replacement over Grove Creek 0.1 mile north of Perrin Street and 0.1 mile south of Main Street. Project involves bridge R0247. | 2026 | 275 | 98 | 0 | 98 | 38 | 0 | 0 | 0 | 0 | 1280 | 0 | 1691
Kansas City | Y | PLATTE | RT FF E | KU0068 | 1.96 | 3.92 | 0 | Pavement resurfacing from River Road to Crooked Road. | 2026 | 11 | 64 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 846 | 0 | 921
Kansas City | Y | PLATTE | RT FF E | KU0394 | 1.913 | 0 | 0 | Drainage and erosion improvements from River Road to 0.1 mile west of Crooked Road. | 2026 | 410 | 359 | 0 | 359 | 0 | 0 | 0 | 0 | 0 | 1779 | 0 | 2548
Kansas City | Y | PLATTE | RT H S | KU0135 | 0.153 | 0.249 | 0 | Replace culverts north of Taulbee Road 0.3 mile south of Taulbee Road and Rte. E 0.3 mile east of Skinner Lake Road. | 2026 | 176 | 526 | 0 | 526 | 0 | 50 | 0 | 50 | 0 | 2152 | 0 | 2904
Kansas City | Y | PLATTE | RT HH E | KU0128 | 0.125 | 0.253 | 1 | Modify interchange configuration at I-29. Project involves bridge A7784. | 2027 | 500 | 450 | 808 | 1258 | 0 | 5 | 0 | 5 | 0 | 0 | 5398 | 7161
Kansas City | Y | PLATTE | RT KK E | KU0271 | 3.144 | 6.296 | 0 | Pavement resurfacing from Rte. B to Platte County line. | 2029 | 15 | 5 | 72 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 938 | 1030
Kansas City | Y | PLATTE | CST NW 76TH ST W | KU0238 | 0.018 | 0.036 | 1 | Bridge replacement and add pedestrian trail over Brush Creek 0.4 mile west of Schott Drive. Project involves bridge 2220012. $693,000 BRO, $200,000 Local Transportation Alternative and $100,000 Platte County Local funds. | 2026 | 105 | 469 | 0 | 469 | 0 | 1 | 0 | 1 | 0 | 1474 | 0 | 2049
Kansas City | Y | PLATTE | CST NW COOKINGHAM DR E | 4S3489 | 0.198 | 0.938 | 1 | Bridge rehabilitation over I-435 1 mile west of Rte. 169 and 1 mile east of NW Robinhood Lane. Project involves bridge A3287. | 2026 | 1078 | 1084 | 0 | 1084 | 0 | 0 | 0 | 0 | 0 | 9187 | 0 | 11349
Kansas City | Y | PLATTE | CRD OLD PIKE RD E | KU0053 | 0.209 | 0.418 | 1 | Bridge replacement over I-29 on Old Pike Road. Project involves bridge A0105. | 2027 | 377 | 251 | 230 | 481 | 0 | 9 | 0 | 9 | 0 | 0 | 2713 | 3580
Kansas City | Y | PLATTE | CST RIVERWAY BLVD N | KU0487 | 0.61 | 0.967 | 0 | Payment to Riverside to add roundabouts, modify interchange ramps and extend sidewalks and streets at Riverway Boulevard. $1,500,000 in Cost Share funds. | 2026 | 0 | 16 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1516
Kansas City | Y | PLATTE | RT Z E | KU0047 | 12.9 | 25.937 | 0 | Pavement resurfacing from I-29 to Rte. 169 in Clinton County. | 2026 | 50 | 173 | 0 | 173 | 0 | 0 | 0 | 0 | 0 | 2182 | 0 | 2405
Kansas City | Y | RAY | BU 10 E | KR0222 | 5.41 | 5.41 | 0 | Pavement resurfacing from north of Rte. EE to east of Rte. 13. | 2030 | 7 | 5 | 166 | 171 | 0 | 0 | 0 | 0 | 0 | 0 | 2150 | 2328
Kansas City | Y | RAY | MO 10 E | KR0077 | 8.425 | 18.369 | 0 | Pavement resurfacing and replace guardrail from Rte. C to Merrifield Lane. | 2026 | 43 | 821 | 0 | 821 | 0 | 0 | 0 | 0 | 0 | 6418 | 0 | 7282
Kansas City | Y | RAY | MO 10 E | KR0078 | 11.015 | 22.03 | 0 | Pavement resurfacing and upgrade guardrail from Merrifield Lane to Rte. FF in Carroll County. | 2026 | 55 | 305 | 0 | 305 | 0 | 0 | 0 | 0 | 0 | 4221 | 0 | 4581
Kansas City | Y | RAY | MO 13 N | KU0464 | 0.128 | 0.624 | 0 | Upgrade signals at Main Street, South Street and Walmart Avenue. | 2027 | 0 | 40 | 49 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 591 | 680
Kansas City | Y | RAY | MO 210 W | KR0246 | 9.855 | 19.884 | 0 | Pavement resurfacing from 0.8 mile east of South Union Road to Rte. 10. | 2030 | 7 | 20 | 516 | 536 | 0 | 0 | 0 | 0 | 0 | 0 | 7142 | 7685
Kansas City | Y | RAY | RT A S | KU0480 | 19.109 | 38.218 | 0 | Pavement resurfacing and repair from Rte. 10 to the Caldwell County line. | 2030 | 0 | 10 | 243 | 253 | 0 | 0 | 0 | 0 | 0 | 0 | 3329 | 3582
Kansas City | Y | RAY | RT J N | KU0419 | 8.83 | 17.66 | 0 | Pavement resurfacing from Rte. 10 to 0.7 mile north of Rte. CC. | 2026 | 10 | 203 | 0 | 203 | 0 | 0 | 0 | 0 | 0 | 2815 | 0 | 3028
Kansas City | N | RAY | RT KK S | KR0218 | 2.191 | 4.382 | 0 | Pavement resurfacing from Hunter Lane to Rte. D. | 2030 | 15 | 1 | 28 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 391 | 435
Kansas City | Y | RAY | RT Z S | KR0103 | 0.101 | 0.202 | 1 | Bridge replacement over Kinny Creek 0.6 mile south of Agnes Street and 0.3 mile north of Centennial Road. Project involves bridge A1773. | 2026 | 103 | 72 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 1041 | 0 | 1216
Kansas City | N | SALINE | MO 127 S | KR0411 | 0.183 | 0.468 | 0 | Add turn lanes and lower vertical curve at I-70. $624,999 Cost Share funds. $639,999 Sweet Springs funds. | 2026 | 120 | 99 | 0 | 99 | 0 | 67 | 0 | 67 | 0 | 994 | 0 | 1280
Kansas City | N | SALINE | MO 20 E | KR0252 | 6.792 | 13.706 | 0 | Pavement resurfacing from Rte. EE to Rte. 65. | 2027 | 35 | 50 | 182 | 232 | 0 | 0 | 0 | 0 | 0 | 0 | 2163 | 2430
Kansas City | N | SALINE | MO 41 S | 3P3175 | 11.367 | 22.734 | 0 | Pavement resurfacing from Rte. 240 to Cooper County line. | 2030 | 25 | 5 | 147 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 1844 | 2021
Kansas City | N | SALINE | MO 41 S | 3P3177 | 13.853 | 27.706 | 0 | Pavement resurfacing from Carroll County line to just north of Rte. 240. | 2030 | 27 | 5 | 122 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 1992 | 2146
Kansas City | N | SALINE | US 65 S | KR0122 | 1.783 | 4.103 | 0 | Upgrade signals from Rte. 20 (Arrow Street) to Fairground Road in Marshall. | 2027 | 34 | 8 | 35 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 402 | 479
Kansas City | N | SALINE | RT E N | KR0106 | 0.072 | 0.144 | 1 | Bridge rehabilitation over Salt Fork Creek 1.2 miles north of 170th Trail and 0.3 mile south of Mallard Trail. Project involves bridge R0545. | 2027 | 20 | 15 | 162 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 1262 | 1459
Kansas City | N | SALINE | RT O S | KR0188 | 11.298 | 22.596 | 0 | Pavement resurfacing from Rte. 41 to Rt. C in Slater. | 2027 | 15 | 10 | 116 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 1589 | 1730
Kansas City | Y | VARIOUS | VARIOUS | KU0457 |  | 0 | 0 | Emergency response operations and staffing in the urban Kansas City District. | 2028 | 0 | 1 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2090 | 2094
Kansas City | N | VARIOUS | Various | 5B0800R | 0 | 0 | 130 | Payback beginning in SFY 2008 for Safe and Sound bridges in rural Kansas City District. | 2033 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 83837 | 4626 | 18504 | 107117
Kansas City | Y | VARIOUS | Various | 5B0800S | 0 | 0 | 19 | Payback beginning in SFY 2008 for Safe and Sound bridges in urban Kansas City District. | 2033 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 57329 | 5006 | 20024 | 82420
Kansas City | N | VARIOUS | Various | KR0309 | 0 | 0 | 0 | Job Order Contracting for asphalt pavement repair in the rural Kansas City District. | 2026 | 4 | 37 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 510 | 0 | 551
Kansas City | N | VARIOUS | Various | KR0311 | 0 | 0 | 0 | On-call work zone enforcement at various locations in the rural Kansas City District. | 2026 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 32
Kansas City | N | VARIOUS | Various | KR0317 | 0 | 0 | 0 | Job Order Contracting for concrete pavement repair at various major routes and interstate locations in the rural Kansas City District. | 2026 | 5 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1080
Kansas City | N | VARIOUS | Various | KR0320 | 0 | 0 | 0 | Job Order Contracting for asphalt pavement repair in the rural Kansas City District. | 2026 | 5 | 41 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 510 | 0 | 556
Kansas City | N | VARIOUS | Various | KR0346 | 0 | 0 | 0 | Job Order Contracting for concrete pavement repair at various major route and interstate locations in the rural Kansas City District. | 2027 | 1 | 1 | 71 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 1030 | 1103
Kansas City | N | VARIOUS | Various | KR0348 | 0 | 0 | 0 | Job Order Contracting for concrete pavement repair at various major route and interstate locations in the rural Kansas City District. | 2028 | 2 | 5 | 80 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 1061 | 1148
Kansas City | N | VARIOUS | Various | KR0349 | 0 | 0 | 0 | Job Order Contracting for guard cable and guardrail repair at various locations in the rural Kansas City District. | 2027 | 1 | 1 | 150 | 151 | 0 | 0 | 0 | 0 | 0 | 0 | 2060 | 2212
Kansas City | N | VARIOUS | Various | KR0414 | 0 | 0 | 0 | On-call work zone enforcement at various locations in the rural Kansas City District. | 2027 | 1 | 1 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 35
Kansas City | N | VARIOUS | Various | KR0471 | 0 | 0 | 0 | On-call work zone enforcement at various locations in the rural Kansas City District. | 2028 | 0 | 1 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 40
Kansas City | Y | VARIOUS | Various | KU0034 | 0 | 0 | 0 | Upgrade signage at various locations in the urban Kansas City District. | 2026 | 125 | 69 | 0 | 69 | 0 | 0 | 0 | 0 | 0 | 765 | 0 | 959
Kansas City | Y | VARIOUS | Various | KU0037 | 0 | 0 | 0 | Upgrade signage at various locations in the urban Kansas City District. | 2027 | 102 | 55 | 140 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 1545 | 1842
Kansas City | Y | VARIOUS | Various | KU0108 | 0 | 0 | 0 | Scout Intelligent Transportation System (ITS) asset management and device replacements at various locations in Clay and Platte Counties in the urban Kansas City District. | 2026 | 22 | 108 | 0 | 108 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 680
Kansas City | Y | VARIOUS | Various | KU0300 |  | 0 | 0 | ITS operations, staffing and equipment for the Kansas City Scout ITS at the Transportation Management Center building in the urban Kansas City District. $2,833,591 KDOT funds. | 2026 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 6021 | 0 | 6023
Kansas City | Y | VARIOUS | Various | KU0301 |  | 0 | 0 | Emergency response operations and staffing in the urban Kansas City District. | 2026 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2018 | 0 | 2020
Kansas City | Y | VARIOUS | Various | KU0306 | 0 | 0 | 0 | Job Order Contracting for fence repair at various locations in the urban Kansas City District. | 2026 | 1 | 29 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 430
Kansas City | Y | VARIOUS | Various | KU0308 | 0 | 0 | 0 | Job Order Contracting for lighting repair at various locations in the urban Kansas City District. | 2026 | 2 | 169 | 0 | 169 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 2571
Kansas City | Y | VARIOUS | Various | KU0312 | 0 | 0 | 0 | On-call work zone enforcement at various locations in the urban Kansas City District. | 2026 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 252
Kansas City | Y | VARIOUS | Various | KU0313 | 0 | 0 | 0 | Job Order Contracting for fence repair at various locations in the urban Kansas City District. | 2026 | 2 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 432
Kansas City | Y | VARIOUS | Various | KU0316 | 0 | 0 | 0 | Job Order Contracting for concrete pavement repair at various locations in the urban Kansas City District. | 2026 | 5 | 145 | 0 | 145 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2150
Kansas City | Y | VARIOUS | Various | KU0319 | 0 | 0 | 0 | Job Order Contracting for asphalt pavement repair at various locations in the urban Kansas City District. | 2026 | 5 | 145 | 0 | 145 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2150
Kansas City | Y | VARIOUS | Various | KU0335 |  | 0 | 0 | Job Order Contracting for concrete pavement repair at various locations in the urban Kansas City District. | 2027 | 10 | 25 | 165 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 2060 | 2260
Kansas City | Y | VARIOUS | Various | KU0338 |  | 0 | 0 | Job Order Contracting for fence repair at various primary route locations in the urban Kansas City District. | 2027 | 5 | 5 | 33 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 412 | 455
Kansas City | Y | VARIOUS | Various | KU0339 |  | 0 | 0 | Job Order Contracting for asphalt pavement repair at various locations in the urban Kansas City District. | 2027 | 5 | 5 | 145 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 2060 | 2215
Kansas City | Y | VARIOUS | Various | KU0341 |  | 0 | 0 | On-call work zone enforcement at various locations in the urban Kansas City District. | 2027 | 5 | 5 | 23 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 283
Kansas City | Y | VARIOUS | Various | KU0342 |  | 0 | 0 | Job Order Contracting for guard cable and guardrail repair at various locations in the urban Kansas City District. | 2027 | 5 | 5 | 446 | 451 | 0 | 0 | 0 | 0 | 0 | 0 | 6483 | 6939
Kansas City | Y | VARIOUS | Various | KU0343 |  | 0 | 0 | Job Order Contracting for lighting repair at various locations in the urban Kansas City District. | 2028 | 10 | 5 | 178 | 183 | 0 | 0 | 0 | 0 | 0 | 0 | 2546 | 2739
Kansas City | Y | VARIOUS | Various | KU0408 |  | 0 | 0 | ITS operations, staffing and equipment for the Kansas City Scout ITS at the Transportation Management Center building in the urban Kansas City District. $2,845,805 KDOT funds. | 2027 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 6040 | 6041
Kansas City | Y | VARIOUS | Various | KU0409 |  | 0 | 0 | Emergency response operations and staffing in the urban Kansas City District. | 2027 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1995 | 1996
Kansas City | Y | VARIOUS | Various | KU0422 |  | 0 | 0 | Job Order Contracting for signage replacement at various locations in the urban Kansas City District. | 2026 | 5 | 74 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1079
Kansas City | Y | VARIOUS | Various | KU0423 |  | 0 | 0 | Job Order Contracting for signage replacement at various locations in the urban Kansas City District. | 2027 | 5 | 5 | 75 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 1030 | 1115
Kansas City | Y | VARIOUS | Various | KU0424 |  | 0 | 0 | Repair signals at various locations in the urban Kansas City District. | 2026 | 5 | 26 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 331
Kansas City | Y | VARIOUS | Various | KU0456 |  | 0 | 0 | ITS operations, staffing and equipment for the Kansas City Scout Traffic Management Center building in the urban Kansas City District. $2,878,627 KDOT funds. | 2028 | 0 | 1 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 6104 | 6108
Kansas City | Y | VARIOUS | Various | KU0462 |  | 0 | 0 | Scout intelligent transportation system device replacements and other ITS needs in the urban Kansas City District. | 2028 | 0 | 5 | 330 | 335 | 0 | 0 | 0 | 0 | 0 | 0 | 1862 | 2197
Kansas City | Y | VARIOUS | Various | KU0466 | 0 | 0 | 1 | Job Order Contracting for bridge repairs at various locations in the urban Kansas City District. | 2027 | 0 | 5 | 285 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 4120 | 4410
Kansas City | Y | VARIOUS | Various | KU0467 |  | 0 | 0 | Job Order Contracting for signage replacement at various locations in the urban Kansas City District. | 2028 | 0 | 5 | 80 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 1061 | 1146
Kansas City | Y | VARIOUS | Various | KU0468 |  | 0 | 0 | Job Order Contracting for asphalt pavement repair at various locations in the urban Kansas City District. | 2028 | 0 | 5 | 150 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 2122 | 2277
Kansas City | Y | VARIOUS | Various | KU0469 |  | 0 | 0 | Job Order Contracting for concrete pavement repair at various locations in the urban Kansas City District. | 2028 | 0 | 10 | 175 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 2122 | 2307
Kansas City | Y | VARIOUS | Various | KU0470 |  | 0 | 0 | Job Order Contracting for fence repair at various primary route locations in the urban Kansas City District. | 2028 | 0 | 5 | 38 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 424 | 467
Kansas City | Y | VARIOUS | Various | KU0472 |  | 0 | 0 | On-call work zone enforcement at various locations in the urban Kansas City District. | 2028 | 0 | 5 | 28 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 283
Kansas City | N | VARIOUS | Various | KR0344 |  | 0 | 0 | Job Order Contracting for asphalt pavement repair in the rural Kansas City District. | 2027 | 1 | 1 | 46 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 525 | 573
Kansas City | N | VARIOUS | Various | KR0347 |  | 0 | 0 | Job Order Contracting for asphalt pavement repair in the rural Kansas City District. | 2028 | 2 | 5 | 46 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 541 | 594
Central | N | BOONE | MO 163 S | CD0190 | 6.173 | 12.346 | 0 | Pavement resurfacing from Rte. K to Rte. 63 outer road. | 2027 | 1 | 1 | 52 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 908 | 962
Central | N | BOONE | MO 163 S | CD0193 | 3.589 | 7.228 | 0 | Pavement resurfacing from 0.5 mile north of Deer Park Road to Rte. H and Outer Road 63 from Meyer Industrial Drive to Rte. 163. | 2026 | 2 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 1324 | 0 | 1406
Central | N | BOONE | MO 163 S | CD0333 | 0.5 | 2.266 | 1 | Bridge improvement over Hinkson Creek. Project involves bridge A1899. | 2027 | 0 | 52 | 403 | 455 | 0 | 5 | 0 | 5 | 0 | 0 | 2259 | 2719
Central | N | BOONE | E OR 63 S | CD0166 | 0.02 | 0.04 | 1 | Bridge improvement over Bass Creek. Project involves bridge G0742. | 2028 | 2 | 1 | 264 | 265 | 0 | 0 | 10 | 10 | 0 | 0 | 778 | 1055
Central | N | BOONE | US 63 S | CD0021 | 0.102 | 0.29 | 3 | Bridge painting over Rte. B and Wagon Trail Road over Rte. 63. Project involves bridges A4033, A4086 and A4087. | 2026 | 22 | 236 | 0 | 236 | 0 | 0 | 0 | 0 | 0 | 1362 | 0 | 1620
Central | N | BOONE | US 63 S | CD0204 | 0.621 | 2.486 | 0 | Modify intersection configuration at Rte. CC. | 2026 | 50 | 519 | 0 | 519 | 0 | 10 | 0 | 10 | 0 | 2535 | 0 | 3114
Central | N | BOONE | US 63 S | CD0286 | 0.059 | 0.118 | 1 | Bridge improvement over Rocky Fork Creek. Project involves bridge A0661. | 2029 | 0 | 1 | 84 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 509 | 594
Central | N | BOONE | US 63 S | CD0301 | 2.249 | 8.99 | 0 | Safety improvements at Route 124. $278,000 Open Container funds. | 2028 | 0 | 19 | 672 | 691 | 0 | 0 | 1 | 1 | 0 | 0 | 3255 | 3947
Central | N | BOONE | LP 70 E | CD0124 | 2.458 | 10.569 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan from I-70 Drive to Range Line Street in Columbia. | 2027 | 7 | 65 | 61 | 126 | 0 | 95 | 0 | 95 | 0 | 0 | 520 | 748
Central | N | BOONE | S OR 70 E | CD0194 | 2.28 | 4.55 | 0 | Pavement improvement from Rte. 63 connector to St. Charles Road. | 2029 | 2 | 1 | 41 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 776 | 820
Central | N | BOONE | S OR 70 E | CD0202 | 0.015 | 0.03 | 1 | Bridge improvement over Hominy Creek and Trail. Project involves bridge H0196. | 2029 | 1 | 1 | 634 | 635 | 0 | 0 | 16 | 16 | 0 | 0 | 1890 | 2542
Central | N | BOONE | MO 740 E | CD0227 | 25.306 | 0 | 0 | Upgrade pavement markings on Rte. 740, Rte. 163, Rte. 763, Loop 70, Rte. B, Rte. AC and Rte. TT in Columbia. | 2026 | 2 | 95 | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 761 | 0 | 858
Central | N | BOONE | MO 763 S | CD0125 | 6.289 | 29.053 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan including Rte. 163 and Rte. PP in Columbia. | 2026 | 116 | 323 | 0 | 323 | 0 | 13 | 0 | 13 | 0 | 1618 | 0 | 2070
Central | N | BOONE | RT A E | CD0197 | 4.358 | 8.716 | 0 | Pavement preservation treatment from Rte. 63 to end of state maintenance. | 2026 | 2 | 11 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 164 | 0 | 177
Central | N | BOONE | RT AC E | CD0123 | 2.239 | 9.749 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan in Columbia. | 2026 | 153 | 319 | 0 | 319 | 0 | 1 | 0 | 1 | 0 | 1713 | 0 | 2186
Central | N | BOONE | RT B S | CD0226 | 0.105 | 0.466 | 0 | Intersection improvements at East Brown Station Road. Includes Rte. 763 at University Avenue and Rollins Street. | 2027 | 10 | 10 | 672 | 682 | 0 | 15 | 0 | 15 | 0 | 0 | 1082 | 1789
Central | N | BOONE | RT DD N | CD0198 | 7.332 | 14.664 | 0 | Pavement improvement from end of state maintenance to Rte. M. Includes Rte. DD from Minor Hill Road to Rte. M. | 2027 | 1 | 1 | 48 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 845 | 895
Central | N | BOONE | RT F S | CD0325 | 13.148 | 26.296 | 0 | Pavement improvement from west of Rte. 63 to Rte. 124. | 2028 | 0 | 1 | 33 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 416 | 450
Central | N | BOONE | RT H E | CD0328 | 8.154 | 16.298 | 0 | Pavement improvement from Rte. 63 to end of state maintenance and Rte. AB from Rte. 63 to end of state maintenance. | 2028 | 0 | 1 | 29 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 370 | 400
Central | N | BOONE | RT J S | CD0196 | 24.37 | 48.74 | 0 | Pavement preservation treatment from Rte. 124 to Rte. O. Includes Rte. O from I-70 to end of state maintenance; Rte. UU from I-70 to Rte. O and Outer Road 70 from east of Rte. UU to west of Rte. UU. | 2026 | 2 | 69 | 0 | 69 | 0 | 0 | 0 | 0 | 0 | 899 | 0 | 970
Central | N | BOONE | RT M E | CD0191 | 8.151 | 16.29 | 0 | Pavement improvement from end of state maintenance to Rte. 63. | 2027 | 1 | 1 | 49 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 858 | 909
Central | N | BOONE | CST MEXICO GRAVEL RD E | CD0287 | 0.038 | 0.077 | 1 | Bridge improvement over Rte. 63. Project involves bridge A4088. | 2029 | 0 | 1 | 82 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 492 | 575
Central | N | BOONE | CRD PRATHERSVILLE RD E | CD0288 | 0.124 | 0.248 | 2 | Bridge improvement over Rte. 63. Project involves bridges A4032 and A4031. | 2029 | 0 | 1 | 222 | 223 | 0 | 0 | 0 | 0 | 0 | 0 | 1327 | 1550
Central | N | CALLAWAY | S OR 54 E | CD0156 | 0.716 | 1.432 | 0 | Pavement resurfacing from South Summit Drive to end of state maintenance. | 2026 | 1 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 102
Central | N | CALLAWAY | US 54 E | CD0276 | 0.045 | 0.19 | 2 | Bridge improvement over Rte. J. Project involves bridges A3449 and A3450. | 2030 | 0 | 1 | 132 | 133 | 0 | 0 | 0 | 0 | 0 | 0 | 818 | 951
Central | N | CALLAWAY | US 54 W | CD0170 | 0.273 | 4.929 | 0 | Add westbound lanes north of the Missouri River bridge in Jefferson City and modify interchange configuration at Rte. W and Rte. 54 westbound and signage upgrades. | 2026 | 175 | 577 | 0 | 577 | 0 | 250 | 0 | 250 | 0 | 3509 | 0 | 4511
Central | N | CALLAWAY | W OR 63 S | CD0155 | 1.297 | 2.594 | 0 | Pavement resurfacing from end of state maintenance to Cedar City Drive. | 2026 | 1 | 9 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 139 | 0 | 149
Central | N | CALLAWAY | N OR 70 E | CD0145 | 7.741 | 15.482 | 0 | Pavement preservation treatment from Rte. 54 to Rte. JJ interchange. Includes Outer Road 70 from Rte. A/Z interchange to Rte. D. | 2026 | 2 | 16 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 247 | 0 | 265
Central | N | CALLAWAY | MO 94 E | CD0294 | 31.781 | 63.562 | 0 | Pavement improvement from Rte. 63/54 interchange to Montgomery County line. | 2027 | 0 | 25 | 192 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 3617 | 3834
Central | N | CALLAWAY | RT AA E | CD0250 | 21.137 | 42.606 | 0 | Pavement improvement from Rte. OO to Rte. 94, Rte. AE from Rte. J to Rte. 54, Rte. TT from Rte. 54 to end of state maintenance, Rte. OO from end of state maintenance to Rte. 54 and Platinum Road from end of state maintenance to Rte. AA. | 2028 | 0 | 1 | 41 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 733 | 775
Central | N | CALLAWAY | RT B E | CD0277 | 0.12 | 0.24 | 1 | Bridge improvement over Rte. 54. Project involves bridge A4777. | 2030 | 0 | 1 | 116 | 117 | 0 | 0 | 0 | 0 | 0 | 0 | 716 | 833
Central | N | CALLAWAY | RT C S | CD0313 | 23.52 | 47.04 | 0 | Pavement improvement from East First Street to Rte. 94. Includes Rte. CC from Rte. O to Rte. 94 and Rte. AD from Rte. C to end of state maintenance. | 2028 | 0 | 1 | 41 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 716 | 758
Central | N | CALLAWAY | RT D S | CD0182 | 18.481 | 36.962 | 0 | Pavement preservation treatment from I-70 to Rte. 94. | 2028 | 1 | 2 | 35 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 648 | 686
Central | N | CALLAWAY | RT F E | CD0246 | 0.093 | 0.186 | 1 | Bridge improvements over Rte. 54. Project involves bridge A2296. | 2027 | 2 | 5 | 741 | 746 | 0 | 1 | 0 | 1 | 0 | 0 | 2597 | 3346
Central | N | CALLAWAY | RT H E | CD0073 | 0.025 | 0.05 | 1 | Bridge rehabilitation over Middle River. Project involves bridge R0417. | 2026 | 20 | 98 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 565 | 0 | 683
Central | N | CALLAWAY | RT JJ S | CD0146 | 6.567 | 13.134 | 0 | Pavement preservation treatment from Rte. Z to Rte. UU. | 2026 | 2 | 13 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 211 | 0 | 226
Central | N | CALLAWAY | RT N S | CD0298 | 0.04 | 0.08 | 1 | Bridge improvement over Loutre River. Project involves bridge X0759. | 2028 | 0 | 2 | 131 | 133 | 0 | 0 | 5 | 5 | 0 | 0 | 678 | 816
Central | N | CALLAWAY | RT O E | CD0144 | 15.322 | 30.644 | 0 | Pavement preservation treatment from State Street to Rte. D. | 2026 | 2 | 36 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 542 | 0 | 580
Central | N | CALLAWAY | CRD S SUMMIT DR S | CD0072 | 0.051 | 0.102 | 1 | Bridge improvement over Rte. 54. Project involves bridge A3521. | 2027 | 4 | 27 | 86 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 651 | 768
Central | N | CALLAWAY | RT UU E | CD0143 | 6.313 | 12.626 | 0 | Pavement preservation treatment from Rte. O to Rte. JJ. | 2026 | 1 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 219 | 0 | 234
Central | N | CAMDEN | MO 242 E | CD0200 | 2.417 | 9.131 | 0 | Pavement resurfacing from Rte. MM to Bagnell Dam Boulevard and Rte. MM from Lake of the Ozarks to Rte. 242. | 2026 | 5 | 73 | 0 | 73 | 0 | 0 | 0 | 0 | 0 | 1264 | 0 | 1342
Central | N | CAMDEN | MO 5 S | CD0213 | 19.473 | 52.517 | 0 | Pavement improvement from Niangua River bridge to south of Laclede County line, including ramps. Includes Rte. 7 from Rte. 5 to Old Rte. 5. | 2028 | 1 | 30 | 474 | 504 | 0 | 0 | 0 | 0 | 0 | 0 | 8687 | 9192
Central | N | CAMDEN | MO 5 S | CD0256 | 1.225 | 2.45 | 2 | Bridge improvement over Osage Arm and Niangua Arm of the Lake of the Ozarks. Project involves bridges A7875 and A5998. | 2029 | 0 | 1 | 421 | 422 | 0 | 0 | 0 | 0 | 0 | 0 | 2961 | 3383
Central | N | CAMDEN | US 54 E | 5P3554 | 18.65 | 73.068 | 0 | Pavement resurfacing from west of the Niangua River to Camdenton, Rte. 54 from Bus. 5 to Grand Glaize bridge, from east of Osage Beach Parkway to Osage River. Rte. KK from SME to West Osage Beach Parkway and Osage Beach Parkway from Rte. 54 to east of Passover Rd. | 2026 | 284 | 473 | 0 | 473 | 0 | 0 | 0 | 0 | 0 | 9214 | 0 | 9971
Central | N | CAMDEN | US 54 E | 5P3573 | 1.375 | 4.321 | 0 | Add lanes from South Bus. Rte. 5 to city limits of Camdenton. | 2026 | 685 | 631 | 0 | 631 | 108 | 0 | 0 | 0 | 0 | 7413 | 0 | 8837
Central | N | CAMDEN | US 54 E | CD0181 | 16.244 | 43.849 | 0 | Pavement improvement from east of Little Niangua River near the Hickory County line to west of Niangua River near Camdenton. | 2027 | 20 | 35 | 259 | 294 | 0 | 0 | 0 | 0 | 0 | 0 | 5247 | 5561
Central | N | CAMDEN | US 54 E | CD0211 | 0.234 | 0.651 | 1 | Bridge improvement over Macks Creek. Project involves bridge A1320. | 2028 | 1 | 1 | 302 | 303 | 0 | 0 | 0 | 0 | 0 | 0 | 1432 | 1736
Central | N | CAMDEN | US 54 E | CD0295 | 7.006 | 25.012 | 0 | Pavement improvement from Grand Glaize bridge to east of Osage Beach Parkway and Rte. 42 from west of Rte. 54 to east of School of the Osage. Includes several ramps. | 2029 | 0 | 1 | 327 | 328 | 0 | 0 | 0 | 0 | 0 | 0 | 5805 | 6133
Central | N | CAMDEN | MO 7 S | 5P3538 | 0.248 | 0.496 | 2 | Bridge rehabilitation over Sellars Creek and Murphy's Creek south of Rte. T. Project involves bridges A1236 and A1237. | 2026 | 131 | 211 | 0 | 211 | 0 | 0 | 0 | 0 | 0 | 1381 | 0 | 1723
Central | N | CAMDEN | MO 7 S | CD0260 | 0.088 | 0.176 | 6 | Bridge painting over Sellars Creek and Murphy's Creek. Includes Rte. W in Morgan County over Indian Creek. Project involves bridges A1236, A1237 and R0605. | 2027 | 0 | 1 | 52 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 290 | 343
Central | N | CAMDEN | MO 7 S | CD0278 | 0.848 | 1.696 | 4 | Bridge improvement over Dry Auglaize Creek and on Rte. N in Camden County over Macks Creek and Rte. ZZ in Laclede County over Panther Creek. Project involves bridges A4479, N0878, R0007 and N0950. | 2030 | 0 | 1 | 96 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 593 | 690
Central | N | CAMDEN | RT MM E | CD0178 | 20.881 | 41.767 | 0 | Pavement improvements from Rte. TT to Lake of Ozarks, Rte. TT from Rte. F to end of state maintenance, Rte. F from Rte. 5 to end of state maintenance and Rte. O from Rte. 5 to end of state maintenance. | 2027 | 5 | 62 | 232 | 294 | 0 | 0 | 0 | 0 | 0 | 0 | 4984 | 5283
Central | N | CAMDEN | RT MM E | CD0257 | 1.054 | 2.108 | 2 | Bridge improvement over Lake of the Ozarks and over Beauty Cove Hollow. Project involves A5677 and A6340. | 2029 | 0 | 1 | 549 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 3869 | 4419
Central | N | COLE | MO 17 S | CD0206 | 26 | 52 | 0 | Pavement improvement from Rte. 54 in Cole County to Rte. 42 in Miller County. | 2029 | 1 | 1 | 218 | 219 | 0 | 0 | 0 | 0 | 0 | 0 | 3912 | 4132
Central | N | COLE | MO 179 S | CD0074 | 0.182 | 0.364 | 1 | Bridge rehabilitation over Rock Creek. Project involves bridge X0035. | 2026 | 20 | 122 | 0 | 122 | 0 | 5 | 0 | 5 | 0 | 682 | 0 | 829
Central | N | COLE | MO 179 S | CD0215 | 34.182 | 74.068 | 0 | Upgrade pedestrian facilities at various locations in Jefferson City, Lake Ozark, Clarksburg, Pilot Grove and Dixon. | 2027 | 22 | 150 | 218 | 368 | 0 | 10 | 0 | 10 | 0 | 0 | 1490 | 1890
Central | N | COLE | S OR 50 E | 5S3418 | 0.357 | 1.521 | 0 | Add signals and turn lane at South Ten Mile Drive in Jefferson City. | 2026 | 167 | 252 | 0 | 252 | 184 | 0 | 0 | 0 | 0 | 1623 | 0 | 2226
Central | N | COLE | US 50 E | CD0106 | 4.99 | 23.64 | 0 | Pavement improvement from west of Shamrock Road to east of Stoney Gap Road. Includes westbound Rte. 50 from west of Maries River to east of Mari Osa Delta Lane and from west of Osage River to Moreau River. Includes High Fricton Surface Treatment. $99,000 Open Container f | 2027 | 4 | 20 | 202 | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 3784 | 4010
Central | N | COLE | US 50 E | CD0140 | 0.228 | 0.908 | 2 | Bridge improvement over Osage River. Project involves bridges A5552 and A0506. | 2028 | 2 | 1 | 146 | 147 | 0 | 0 | 0 | 0 | 0 | 0 | 704 | 853
Central | N | COLE | US 50 E | CD0212 | 3.88 | 7.892 | 0 | Pavement improvement at Rte. 50/63 interchange. Includes Rte. 63 and ramps. | 2027 | 1 | 1 | 22 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 305 | 329
Central | N | COLE | US 50 E | CD0299 | 0.14 | 0.28 | 1 | Bridge improvement over Moreau River. Project involves bridge A0723. | 2028 | 0 | 3 | 59 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 337
Central | N | COLE | US 54 E | CD0139 | 0.583 | 2.332 | 1 | Bridge improvement over the Missouri River. Project involves bridges A4497. | 2029 | 3 | 1 | 1089 | 1090 | 0 | 0 | 0 | 0 | 0 | 0 | 5347 | 6440
Central | N | COLE | US 54 E | CD0219 | 3.647 | 16.207 | 0 | Intersection improvement from west of United Road to east of Gray Road. $4,155,000 Open Container funds. | 2027 | 124 | 955 | 1946 | 2901 | 0 | 22 | 0 | 22 | 0 | 0 | 12354 | 15401
Central | N | COLE | US 54 E | CD0219B | 4.19 | 18.532 | 0 | Tree removal for intersection improvement from west of United Road to east of Gray Road. | 2027 | 0 | 1 | 126 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 513 | 640
Central | N | COLE | US 54 E | CD0259 | 0.583 | 4.09 | 2 | Bridge washing over Missouri River. Project involves bridges A4497 and L0550. | 2029 | 0 | 1 | 41 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 372
Central | N | COLE | US 54 E | CD0293 | 18.27 | 82.228 | 0 | Pavement improvement from Miller County line to south of Stadium Boulevard. | 2030 | 0 | 1 | 691 | 692 | 0 | 0 | 0 | 0 | 0 | 0 | 12642 | 13334
Central | N | COLE | RT A W | CD0207 | 0.22 | 0.44 | 1 | Bridge improvement over Brush Creek. Project involves bridge R0248. | 2028 | 1 | 1 | 102 | 103 | 0 | 0 | 16 | 16 | 0 | 0 | 1192 | 1312
Central | N | COLE | RT AA S | 5S3551 | 0.12 | 0.24 | 1 | Bridge rehabilitation over South Moreau Creek. Project involves bridge R0445. | 2026 | 20 | 301 | 0 | 301 | 0 | 5 | 0 | 5 | 0 | 940 | 0 | 1266
Central | N | COLE | RT AA S | CD0230 | 0.552 | 1.104 | 5 | Bridge painting over S. Moreau Cr. and Rte. CC in Moniteau Co. Includes Rte. T over Loose Creek in Osage Co., Rte. 179 over Rock Creek in Cole Co. and Rte. H over Middle River in Callaway Co. Project involves bridges R0445, A1835, A1839, X0035 and R0417. | 2027 | 2 | 11 | 76 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 486 | 575
Central | N | COLE | RT B S | CD0258 | 0.212 | 0.424 | 1 | Bridge rehabilitation over Osage River. Project involves bridge K0656. | 2027 | 0 | 75 | 253 | 328 | 0 | 0 | 0 | 0 | 0 | 0 | 1799 | 2127
Central | N | COLE | RT J S | CD0184 | 5.076 | 10.152 | 0 | Pavement improvement from Rte. 50 to end of state maintenance. Includes Liberty Road from Rte. M to end of state maintenance and Christy Drive from west of Veterans Lane to south of Stadium Boulevard. | 2027 | 1 | 6 | 36 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 717 | 760
Central | N | COLE | RT M E | CD0183 | 8.121 | 16.242 | 0 | Pavement improvement from Rte. 50 to Rte. B. | 2027 | 1 | 2 | 17 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 328 | 348
Central | N | COOPER | MO 135 S | CD0192 | 20.44 | 40.88 | 0 | Pavement preservation treatment from I-70 to Pettis County line. | 2026 | 1 | 66 | 0 | 66 | 0 | 0 | 0 | 0 | 0 | 851 | 0 | 918
Central | N | COOPER | IS 70 E | 5I3358Z | 4.8 | 0 | 1 | Payback for MTFC loan to construct new Missouri River bridge at Rocheport. Total cost of $60,739,000 with payments from SFY 2024 to SFY 2030. Project involves bridge L0962. | 2030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17354 | 8677 | 34708 | 60739
Central | N | COOPER | IS 70 E | CD0011 | 78.025 | 0 | 0 | Job Order Contracting for concrete pavement repair in Cooper, Boone and Callaway Counties. | 2026 | 3 | 35 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 538
Central | N | COOPER | IS 70 E | CD0253 | 0.572 | 2.288 | 2 | Bridge improvement over Missouri River. Project involves bridge A8900 and A9100. | 2029 | 0 | 1 | 68 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 599
Central | N | COOPER | IS 70 E | CD0269 | 77.277 | 0 | 0 | Job Order Contracting for concrete pavement repair in Cooper, Boone and Callaway Counties. | 2027 | 0 | 1 | 36 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 552
Central | N | COOPER | MO 87 S | CD0023 | 0.056 | 0.112 | 1 | Bridge rehabilitation over Petite Saline Creek. Project involves bridge A4607. | 2026 | 12 | 63 | 0 | 63 | 0 | 5 | 0 | 5 | 0 | 406 | 0 | 486
Central | N | COOPER | MO 87 S | CD0024 | 0.037 | 0.074 | 1 | Bridge rehabilitation over Clarks Fork Creek. Project involves bridge A4608. | 2026 | 12 | 54 | 0 | 54 | 0 | 5 | 0 | 5 | 0 | 361 | 0 | 432
Central | N | COOPER | MO 87 S | CD0329 | 29.718 | 59.436 | 0 | Pavement improvement from south of I-70 to Rte. O. | 2027 | 0 | 5 | 269 | 274 | 0 | 0 | 0 | 0 | 0 | 0 | 4579 | 4853
Central | N | COOPER | RT M S | CD0189 | 9.017 | 18.034 | 0 | Pavement improvement from Rte. K to Rte. 135. | 2027 | 1 | 1 | 64 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 1099 | 1165
Central | N | CRAWFORD | N OR 44 E | CD0248 | 26.816 | 53.632 | 0 | Pavement resurfacing from Hobby Hut Rd to Rte. C. Includes OR 44 from E Grand Rd to Hollingshead Rd, Hollingshead Rd to SME, from Bourbon to Rte. D in Franklin County, from Rte. N to Rte. W., Rte. CC from Rte. 21 to SME and Rte. H from N OR 44 to S OR 44. | 2026 | 30 | 142 | 0 | 142 | 0 | 0 | 0 | 0 | 0 | 2797 | 0 | 2969
Central | N | CRAWFORD | MO 8 E | CD0102 | 28.213 | 57.095 | 0 | Pavement improvement from west of the Washington County line to the Big River in St. Francois County. | 2027 | 12 | 77 | 472 | 549 | 0 | 0 | 0 | 0 | 0 | 0 | 7762 | 8323
Central | N | CRAWFORD | MO 8 E | CD0342 | 0.201 | 0.402 | 1 | Scour repair at the Meramec River. Project involves bridge A4966. | 2026 | 0 | 72 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 392 | 0 | 464
Central | N | CRAWFORD | RT C E | CD0255 | 51.643 | 103.286 | 0 | Pavement improvements from Rte. 72 to Rte. 32, Rte. F from Rte. 19 to SOR I-44, Rte. C from Rte. 72 to Rte. 32 in Dent County and Rte. C from Rte. 133 to Rte. 28 in Pulaski County. | 2027 | 0 | 58 | 266 | 324 | 0 | 0 | 0 | 0 | 0 | 0 | 5298 | 5622
Central | N | CRAWFORD | RT N W | CD0037 | 0.068 | 0.136 | 1 | Bridge improvement over the Meramec River. Project involves bridge A3354. | 2027 | 3 | 48 | 202 | 250 | 0 | 1 | 0 | 1 | 0 | 0 | 1143 | 1397
Central | N | DENT | MO 119 S | CD0338 | 0.06 | 0.12 | 1 | Scour repair at Pigeon Creek. Project involves bridge A5335. $164,000 Emergency Relief funds, November 2024 flood event. | 2026 | 0 | 74 | 0 | 74 | 0 | 1 | 0 | 1 | 0 | 204 | 0 | 279
Central | N | DENT | MO 19 S | CD0035 | 0.012 | 0.024 | 1 | Bridge improvement over Spring Creek. Project involves bridge A4433. | 2027 | 3 | 7 | 23 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 196
Central | N | DENT | MO 19 S | CD0336 | 0.117 | 0.234 | 0 | Repair slide 0.3 mile south of County Road 4050. $572,000 Emergency Relief funds, November 2024 flood event. | 2027 | 0 | 75 | 184 | 259 | 0 | 1 | 0 | 1 | 0 | 0 | 735 | 995
Central | N | DENT | MO 32 E | CD0129 | 3.108 | 11.69 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan including Rte. 19 in Salem. | 2026 | 188 | 200 | 0 | 200 | 95 | 0 | 0 | 0 | 0 | 1416 | 0 | 1899
Central | N | DENT | MO 32 E | CD0235 | 0.092 | 0.184 | 1 | Bridge improvement over Huzzah Creek. Project involves bridge J0573. | 2027 | 1 | 314 | 560 | 874 | 0 | 20 | 0 | 20 | 0 | 0 | 2080 | 2975
Central | N | DENT | MO 32 E | CD0337 | 0.03 | 0.06 | 1 | Repair bank erosion at Spring Creek. Project involves bridge B0468. $102,000 Emergency Relief funds, November 2024 flood event. | 2026 | 0 | 46 | 0 | 46 | 0 | 1 | 0 | 1 | 0 | 128 | 0 | 175
Central | N | DENT | MO 32 W | CD0285 | 0.033 | 0.066 | 1 | Bridge improvement over Dry Valley Creek. Project involves bridge A8446. | 2029 | 0 | 1 | 22 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 67 | 90
Central | N | DENT | MO 72 E | CD0339 | 0.06 | 0.12 | 1 | Scour repair at Dry Fork Creek. Project involves bridge A6744. $246,000 Emergency Relief funds, November 2024 flood event. | 2026 | 0 | 111 | 0 | 111 | 0 | 1 | 0 | 1 | 0 | 306 | 0 | 418
Central | N | DENT | RT B E | 5S3559 | 0.02 | 0.04 | 1 | Bridge replacement over Dry Creek. Project involves bridge T0582. | 2026 | 80 | 489 | 0 | 489 | 0 | 1 | 0 | 1 | 0 | 1258 | 0 | 1828
Central | N | DENT | RT B E | CD0340 | 0.045 | 0.09 | 1 | Scour repair at Dry Branch. Project involves bridge A5558. $328,000 Emergency Relief funds, November 2024 flood event. | 2027 | 0 | 40 | 98 | 138 | 0 | 1 | 0 | 1 | 0 | 0 | 420 | 559
Central | N | DENT | RT FF E | CD0282 | 0.08 | 0.16 | 1 | Bridge improvement over Dry Fork Creek. Project involves bridge A2060. | 2029 | 0 | 1 | 75 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 244 | 320
Central | N | DENT | RT FF E | CD0341 | 0.072 | 0.144 | 1 | Scour repair at Dry Fork Creek. Project involves bridge A2060. $450,000 Emergency Relief funds, November 2024 flood event. | 2026 | 0 | 204 | 0 | 204 | 0 | 1 | 0 | 1 | 0 | 561 | 0 | 766
Central | N | DENT | RT H E | CD0240 | 0.19 | 0.38 | 4 | Bridge improvements over Dry Fork Creek and Barnett Prong Dry Creek and on Rte. 32 over Dry Fork Creek and Pigeon Creek. Project involves bridges A2588, A2587, A4408 and A4261. | 2028 | 1 | 1 | 488 | 489 | 0 | 0 | 1 | 1 | 0 | 0 | 2077 | 2568
Central | N | DENT | RT P S | CD0303 | 7.13 | 14.26 | 0 | Pavement improvement from Rte. 72 to end of state maintenance. Includes Rte. JJ from Rte. N to end of state maintenance. | 2027 | 0 | 18 | 87 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 1726 | 1831
Central | N | GASCONADE | RT A S | CD0185 | 21.894 | 43.788 | 0 | Pavement improvement from Rte. 50 to Rte. 28. Includes Rte. Y from Rte. A to Rte. 28. | 2027 | 2 | 24 | 104 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 2170 | 2300
Central | N | GASCONADE | RT B S | CD0153 | 22.369 | 44.762 | 0 | Pavement preservation treatment from Rte. 28 to Rte. 68. | 2026 | 2 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 733 | 0 | 785
Central | N | GASCONADE | RT T S | CD0315 | 17.436 | 34.872 | 0 | Pavement improvement from Rte. 50 to end of state maintenance and Rte. V from Rte. 19 to Rte. T. | 2028 | 0 | 1 | 30 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 523 | 554
Central | N | HOWARD | MO 124 E | CD0195 | 30.839 | 61.678 | 0 | Pavement resurfacing, add shoulder and rumble stripes from Rte. 240 to Rte. B. Includes pavement resurfacing on Rte. BB from Central Street to I-70 and Rte. CC from Rte. 63 to Rte. V. | 2026 | 2 | 449 | 0 | 449 | 0 | 5 | 0 | 5 | 0 | 6187 | 0 | 6643
Central | N | HOWARD | BU 240 E | CD0163 | 0.304 | 0.608 | 1 | Bridge improvements over CPKC railroad. Project involves bridge K0382. | 2027 | 2 | 370 | 756 | 1126 | 0 | 10 | 0 | 10 | 0 | 0 | 3156 | 4294
Central | N | HOWARD | MO 240 E | CD0137 | 0.105 | 0.21 | 1 | Bridge replacement over Salt Creek south of Fayette. Project involves bridge K0045. | 2027 | 291 | 1 | 176 | 177 | 0 | 10 | 0 | 10 | 0 | 0 | 1149 | 1627
Central | N | HOWARD | MO 240 E | CD0203 | 0.006 | 0.012 | 1 | Bridge improvement over Pipes Branch. Project involves bridge H0287. | 2029 | 1 | 1 | 787 | 788 | 0 | 0 | 16 | 16 | 0 | 0 | 2346 | 3151
Central | N | HOWARD | MO 3 S | CD0164 | 0.037 | 0.074 | 1 | Bridge improvements over CPKC railroad. Project involves bridge K0962. | 2027 | 2 | 402 | 946 | 1348 | 0 | 20 | 0 | 20 | 0 | 0 | 3774 | 5144
Central | N | HOWARD | US 40 E | CD0289 | 0.07 | 0.14 | 1 | Bridge improvement over Moniteau Creek. Project involves bridge G0544. | 2029 | 0 | 1 | 319 | 320 | 0 | 0 | 5 | 5 | 0 | 0 | 1686 | 2011
Central | N | HOWARD | MO 5 S | 5P3532 | 0.027 | 0.054 | 1 | Bridge rehabilitation over Sulphur Creek. Project involves bridge H0266. | 2026 | 13 | 54 | 0 | 54 | 0 | 5 | 0 | 5 | 0 | 367 | 0 | 439
Central | N | HOWARD | MO 5 S | CD0110 | 0.972 | 1.944 | 0 | Modify intersection configuration at Rte. 5 and Rte. 40 south of New Franklin. | 2026 | 193 | 156 | 0 | 156 | 0 | 5 | 0 | 5 | 0 | 1321 | 0 | 1675
Central | N | HOWARD | MO 5 S | CD0199 | 1.566 | 3.132 | 0 | Pavement improvement from Chariton County line to Rte. 240. | 2027 | 1 | 1 | 18 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 338 | 358
Central | N | HOWARD | RT J E | CD0326 | 16.707 | 33.414 | 0 | Pavement improvements from Rte. Z to Rte. 5 and Rte. DD from Rte. 5 to Rte. P. | 2028 | 0 | 1 | 62 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 781 | 844
Central | N | HOWARD | RT W E | CD0165 | 0.017 | 0.034 | 1 | Scour repair over Branch of Bonne Femme Creek. Project involves bridge N0966. | 2027 | 3 | 1 | 5 | 6 | 0 | 5 | 0 | 5 | 0 | 0 | 81 | 95
Central | N | HOWARD | RT W E | CD0188 | 7.313 | 14.626 | 0 | Pavement improvement from Rte. 240 to Rte. A. | 2027 | 1 | 1 | 48 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 833 | 883
Central | N | LACLEDE | IS 44 E | CD0009 | 112.213 | 0 | 0 | Job Order Contracting for asphalt pavement repair in Laclede, Pulaski, Phelps and Crawford Counties. | 2026 | 3 | 50 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 753
Central | N | LACLEDE | IS 44 E | CD0010 | 112.213 | 0 | 0 | Job Order Contracting for concrete pavement repair in Laclede, Pulaski, Phelps and Crawford Counties. | 2026 | 3 | 71 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1074
Central | N | LACLEDE | IS 44 E | CD0263 | 112.213 | 0 | 0 | Job Order Contracting for asphalt pavement repair in Laclede, Pulaski, Phelps and Crawford Counties. | 2028 | 0 | 1 | 51 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 743 | 795
Central | N | LACLEDE | IS 44 E | CD0264 | 112.213 | 0 | 0 | Job Order Contracting for concrete pavement repair in Laclede, Pulaski, Phelps and Crawford Counties. | 2028 | 0 | 1 | 72 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 1061 | 1134
Central | N | LACLEDE | IS 44 E | CD0265 | 112.214 | 0 | 0 | Striping upgrades in Laclede, Pulaski, Phelps and Crawford Counties. | 2026 | 0 | 122 | 0 | 122 | 0 | 0 | 0 | 0 | 0 | 940 | 0 | 1062
Central | N | LACLEDE | IS 44 E | CD0270 | 5.856 | 21.953 | 0 | Pavement resurfacing and rebuild from 0.6 miles west of Rte. F to 2.1 miles east of Rt. F and east of Swallow Dr. to 0.6 miles west of Rte. 133. Includes I-44 westbound. | 2027 | 0 | 460 | 2357 | 2817 | 0 | 0 | 0 | 0 | 0 | 0 | 24663 | 27480
Central | N | LACLEDE | RT AD S | CD0221 | 0.233 | 0.466 | 1 | Bridge improvement over Gasconade River. Project involves bridge R0601. | 2029 | 1 | 1 | 395 | 396 | 0 | 0 | 0 | 0 | 0 | 0 | 2085 | 2482
Central | N | LACLEDE | CRD DOVE RD E | 5S3562 | 0.096 | 0.192 | 1 | Bridge improvement over I-44. Project involves bridge A2892. | 2027 | 7 | 15 | 60 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 458 | 540
Central | N | LACLEDE | RT J E | CD0056 | 0.093 | 0.186 | 1 | Bridge improvement over I-44. Project includes bridge A1196. | 2027 | 6 | 21 | 162 | 183 | 0 | 0 | 0 | 0 | 0 | 0 | 935 | 1124
Central | N | LACLEDE | RT O E | CD0217 | 0.148 | 0.296 | 1 | Bridge improvement over Sterns Creek. Project involves bridge A2676. | 2028 | 1 | 20 | 216 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 1208 | 1445
Central | N | MARIES | MO 68 E | CD0309 | 11.833 | 23.722 | 0 | Pavement improvement from Rte. 63 to north of Matlock Drive. | 2027 | 0 | 10 | 181 | 191 | 0 | 0 | 0 | 0 | 0 | 0 | 3189 | 3380
Central | N | MILLER | MO 17 S | CD0234 | 0.266 | 0.532 | 1 | Bridge improvement over Osage River. Project involves bridge A7536. | 2029 | 1 | 1 | 42 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 503 | 547
Central | N | MILLER | MO 42 E | 5P3569 | 58.481 | 116.962 | 0 | Pavement preservation treatment from east of Osage Beach Parkway in Osage Beach to Rte. 28. | 2027 | 4 | 36 | 135 | 171 | 0 | 0 | 0 | 0 | 0 | 0 | 2108 | 2283
Central | N | MILLER | MO 42 E | CD0222 | 0.238 | 0.476 | 2 | Bridge improvements over Spring Branch and Barren Fork. Project involves bridge A1350 and A1351. | 2029 | 1 | 1 | 332 | 333 | 0 | 0 | 0 | 0 | 0 | 0 | 1751 | 2085
Central | N | MILLER | MO 42 E | CD0279 | 0.721 | 2.007 | 3 | Bridge improvement over Tavern Creek and Wiemer Creek and on Rte. 54 in Camden County over Rte. 5. Project involves bridges A4490, A4492 and A6392. | 2030 | 0 | 1 | 176 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 1465 | 1642
Central | N | MILLER | MO 52 E | CD0233 | 0.288 | 0.576 | 1 | Bridge improvement over South Fork Moreau Creek. Project involves bridge A3964. | 2027 | 1 | 3 | 50 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 302 | 356
Central | N | MILLER | RT A E | CD0280 | 0.239 | 0.478 | 1 | Bridge improvement over Tavern Creek. Project involves bridge N0455. | 2030 | 0 | 1 | 34 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 209 | 244
Central | N | MILLER | RT U S | CD0147 | 15.364 | 30.728 | 0 | Pavement preservation treatment from Rte. 42 to Rte. 17. | 2026 | 5 | 42 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 558 | 0 | 605
Central | N | MONITEAU | MO 179 S | CD0176 | 22.331 | 44.846 | 0 | Pavement improvement from Rte. 87 to 0.14 mile north of West Main Street and to Rte. AA from Rte. 87 to Rte. 179. | 2030 | 1 | 1 | 131 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 2416 | 2549
Central | N | MONITEAU | MO 179 S | CD0335 | 0.11 | 1.085 | 3 | Bridge painting over Moniteau Creek, Rte. U over Howard Creek and Rte. 54 over Neighorn Branch. Project involves bridges A1984, A2358 and G0302. | 2026 | 0 | 107 | 0 | 107 | 0 | 0 | 0 | 0 | 0 | 565 | 0 | 672
Central | N | MONITEAU | BU 50 E | CD0142 | 5.716 | 11.763 | 0 | Pavement resurfacing from Rte. 50 west to Rte. 50 east and Lookout Trail from Bus. 50 to end of state maintenance. | 2026 | 4 | 67 | 0 | 67 | 0 | 0 | 0 | 0 | 0 | 1146 | 0 | 1217
Central | N | MONITEAU | US 50 E | CD0272 | 0.025 | 0.05 | 2 | Bridge improvement over Moreau Creek Branch. Project involves bridges H0154 and H0108. | 2030 | 0 | 1 | 33 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 206 | 240
Central | N | MONITEAU | MO 87 S | CD0302 | 0.062 | 0.124 | 1 | Bridge improvement over Moreau Creek. Project involves bridge A1204. | 2027 | 0 | 19 | 54 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 412 | 485
Central | N | MONITEAU | RT CC S | 5S3555 | 0.161 | 0.322 | 1 | Bridge rehabilitation over South Moreau Creek. Project involves bridge A1835. | 2026 | 26 | 256 | 0 | 256 | 0 | 5 | 0 | 5 | 0 | 827 | 0 | 1114
Central | N | MONITEAU | RT CC S | CD0205 | 36.474 | 72.947 | 0 | Pavement improvement from Rte. E to Rte. C and from Rte. C to north of Rte. 52 in Eldon, Rte. M from Rte. 54 interchange to end of state maintenance in Miller County and Rte. W from Versailles city limit to Rte. Y in Morgan County. | 2027 | 1 | 19 | 75 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 1141 | 1236
Central | N | MONITEAU | RT E S | CD0319 | 31.799 | 63.598 | 0 | Pavement improvement from Rte. 50 to Rte. C, Rte. K from Rte. E to end of state maintenance, Rte. TT from Rte. 5 to Rte. 5 and Rte. FF from Rte. 52 to end of state maintenance. | 2028 | 0 | 1 | 75 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 940 | 1016
Central | N | MONITEAU | RT F E | CD0154 | 7.823 | 15.646 | 0 | Pavement resurfacing from Rte. E to Rte. 87. | 2026 | 2 | 43 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 734 | 0 | 779
Central | N | MONITEAU | RT T S | CD0229 | 0.08 | 0.16 | 1 | Bridge improvement over Burris Fork. Project involves bridge N0747. | 2027 | 1 | 5 | 19 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 139 | 164
Central | N | MORGAN | MO 135 S | CD0223 | 0.341 | 0.682 | 1 | Bridge improvement over Flat Creek. Project involves bridge A1838. | 2029 | 1 | 1 | 309 | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 1636 | 1947
Central | N | MORGAN | MO 5 S | CD0070 | 0.646 | 1.292 | 1 | Bridge improvement over Gravois Creek. Includes intersection improvement at Rte. J and Rte. 5. Project involves bridge A0146. | 2028 | 3 | 250 | 1520 | 1770 | 0 | 0 | 26 | 26 | 0 | 0 | 5116 | 6915
Central | N | MORGAN | MO 5 S | CD0216 | 0.513 | 1.026 | 1 | Bridge improvement over Straight Fork Moreau. Project involves bridge A5253. | 2028 | 1 | 1 | 26 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 191
Central | N | MORGAN | US 50 E | CD0266 | 254.986 | 0 | 0 | Signage upgrades from west Morgan County line to east Gasconade County line and Rte. 5 from northwest Howard County line to south Laclede County line. | 2027 | 0 | 30 | 143 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 788 | 961
Central | N | MORGAN | US 50 E | CD0281 | 0.36 | 0.72 | 1 | Bridge improvement over Lamine River. Project involves bridge A1193. | 2030 | 0 | 1 | 295 | 296 | 0 | 0 | 0 | 0 | 0 | 0 | 1813 | 2109
Central | N | MORGAN | US 50 E | CD0323 | 23.276 | 63.572 | 0 | Pavement improvement from Morgan County line to Cole County line. | 2029 | 0 | 1 | 196 | 197 | 0 | 0 | 0 | 0 | 0 | 0 | 3500 | 3697
Central | N | MORGAN | RT J S | CD0179 | 8.06 | 16.12 | 0 | Pavement preservation treatment from Rte. 5 to Rte. 135 and from Rte. 135 to end of state maintenance. | 2026 | 2 | 18 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 239 | 0 | 259
Central | N | MORGAN | RT W S | 5S3536 | 0.129 | 0.258 | 1 | Bridge rehabilitation over Indian Creek south of Rte. AA. Project involves bridge R0605. | 2026 | 68 | 133 | 0 | 133 | 0 | 0 | 0 | 0 | 0 | 777 | 0 | 978
Central | N | OSAGE | MO 133 S | CD0275 | 0.024 | 0.048 | 1 | Bridge improvement over Sugar Creek. Project involves bridge B0368. | 2030 | 0 | 1 | 19 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 123 | 143
Central | N | OSAGE | US 50 E | CD0180 | 0.298 | 0.596 | 0 | Payment to State Technical College of Missouri to construct new intersection 0.7 mile east of Rte. CC. $443,400 Cost Share funds. | 2026 | 2 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 43 | 400 | 0 | 453
Central | N | OSAGE | US 50 E | CD0273 | 0.085 | 0.17 | 1 | Bridge improvement over Rte. 50/63. Project involves Bridge A5553. | 2030 | 0 | 1 | 125 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 769 | 895
Central | N | OSAGE | US 63 N | CD0274 | 0 | 0.06 | 1 | Bridge improvement over Rte. 50/63. Project involves bridge A5554. | 2030 | 0 | 1 | 58 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 359 | 418
Central | N | OSAGE | US 63 S | CD0108 | 5.951 | 13.175 | 2 | Corridor improvements from Rte. 50 to Maries River bridge south of Westphalia and bridge improvement over the Maries River. Project involves bridge A4322 and A4328. | 2028 | 2247 | 1500 | 10024 | 11524 | 0 | 8701 | 0 | 8701 | 0 | 0 | 64976 | 87448
Central | N | OSAGE | MO 89 S | CD0105 | 0.08 | 0.16 | 1 | Bridge improvement over Indian Creek. Project involves bridge K0214. | 2027 | 3 | 70 | 249 | 319 | 0 | 20 | 0 | 20 | 0 | 0 | 899 | 1241
Central | N | OSAGE | MO 89 S | CD0150 | 17.266 | 34.532 | 0 | Pavement resurfacing from Rte. 50 to Rte. 28. | 2026 | 4 | 116 | 0 | 116 | 0 | 0 | 0 | 0 | 0 | 1935 | 0 | 2055
Central | N | OSAGE | MO 89 S | CD0151 | 18.139 | 36.278 | 0 | Pavement resurfacing from Rte. 100 to Rte. 50. | 2026 | 10 | 102 | 0 | 102 | 0 | 0 | 0 | 0 | 0 | 1809 | 0 | 1921
Central | N | OSAGE | SP 89 S | CD0327 | 1.553 | 3.106 | 0 | Pavement resurfacing from Rte. 89 to Rte. 50. | 2026 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 137 | 0 | 145
Central | N | OSAGE | RT C E | CD0297 | 0.08 | 0.16 | 1 | Bridge improvement over Loose Creek. Project involves bridge A1847. | 2028 | 0 | 2 | 173 | 175 | 0 | 0 | 5 | 5 | 0 | 0 | 890 | 1070
Central | N | OSAGE | RT CC S | CD0152 | 4.66 | 9.32 | 0 | Pavement improvement from Rte. 50 to end of state maintenance. | 2030 | 1 | 1 | 26 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 536 | 564
Central | N | OSAGE | RT T S | CD0071 | 0.03 | 0.06 | 1 | Bridge rehabilitation over Loose Creek. Project involves bridge A1839. | 2027 | 22 | 5 | 82 | 87 | 0 | 5 | 0 | 5 | 0 | 0 | 537 | 651
Central | N | OSAGE | RT U S | CD0332 | 14.701 | 29.402 | 0 | Pavement improvement from Rte. 50 to Rte. E and Rte. E from Rte. 63 to Rte. 89. | 2028 | 0 | 1 | 29 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 525 | 555
Central | N | PHELPS | US 63 S | CD0088 | 30.227 | 85.311 | 0 | Pavement improvement from north of Rolla to Rte. CC. | 2027 | 132 | 60 | 747 | 807 | 0 | 0 | 0 | 0 | 0 | 0 | 11451 | 12390
Central | N | PHELPS | US 63 S | CD0214 | 33.907 | 79.712 | 0 | Upgrade pedestrian facilities at various locations in Rolla, Osage Beach, California, Richland, Crocker and Bourbon. | 2026 | 10 | 752 | 0 | 752 | 0 | 10 | 0 | 10 | 0 | 2782 | 0 | 3554
Central | N | PHELPS | MO 8 E | CD0033 | 0.081 | 0.242 | 2 | Bridge painting over I-44. Project involves bridges A0602 and A1869. | 2026 | 19 | 132 | 0 | 132 | 0 | 0 | 0 | 0 | 0 | 782 | 0 | 933
Central | N | PHELPS | MO 8 E | CD0236 | 0.063 | 0.252 | 1 | Bridge improvement over I-44. Project involves bridge A0602. | 2028 | 1 | 1 | 257 | 258 | 0 | 0 | 0 | 0 | 0 | 0 | 1320 | 1579
Central | N | PHELPS | MO 8 E | CD0290 | 0.044 | 0.088 | 1 | Bridge improvement over Asher Creek. Project involves bridge A4962. | 2029 | 0 | 1 | 126 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 474 | 601
Central | N | PHELPS | RT BB E | CD0089 | 0.077 | 0.308 | 1 | Bridge rehabilitation over Oak Street, Olive Street and BNSF Railway. Project involves bridge A3080. | 2026 | 140 | 289 | 0 | 289 | 0 | 1 | 0 | 1 | 0 | 2816 | 0 | 3246
Central | N | PHELPS | RT D E | CD0284 | 0.113 | 0.226 | 1 | Bridge improvement over Gasconade River. Projects involves bridge A5215. | 2029 | 0 | 1 | 237 | 238 | 0 | 0 | 0 | 0 | 0 | 0 | 1264 | 1502
Central | N | PHELPS | RT F E | CD0283 | 0.04 | 0.08 | 1 | Bridge improvement over Dry Fork Creek. Project involves bridge A2946. | 2029 | 0 | 1 | 188 | 189 | 0 | 0 | 0 | 0 | 0 | 0 | 1020 | 1209
Central | N | PHELPS | RT F E | CD0291 | 0.04 | 0.08 | 1 | Bridge improvement over Norman Creek. Project involves bridge R0522. | 2029 | 0 | 1 | 168 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 787 | 956
Central | N | PHELPS | RT HH S | CD0036 | 0.03 | 0.06 | 1 | Bridge improvement over Spring Creek. Project involves bridge N0668. | 2027 | 52 | 151 | 336 | 487 | 0 | 20 | 0 | 20 | 0 | 0 | 1471 | 2030
Central | N | PHELPS | RT J S | CD0238 | 0.05 | 0.1 | 1 | Bridge improvement over Spring Creek. Project involves bridge T0878. | 2028 | 1 | 1 | 149 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 701 | 852
Central | N | PHELPS | RT K E | CD0160 | 0.14 | 0.28 | 1 | Bridge improvements over Sherrill Creek. Project involves bridge A0523. | 2029 | 2 | 1 | 606 | 607 | 0 | 0 | 21 | 21 | 0 | 0 | 1766 | 2396
Central | N | PHELPS | RT K E | CD0239 | 0.16 | 0.32 | 1 | Bridge improvement over Spring Creek. Project involves bridge A0524. | 2029 | 1 | 1 | 53 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 288 | 343
Central | N | PULASKI | MO 28 E | CD0247 | 56.402 | 112.804 | 0 | Pavement resurfacing from Rte. Z to Rte. 63, Rte. 133 from Rte. 17 to I-44, I-44 OR from Rte. 17 to Rte. H, I-44 OR from Rte. H to Salina RD, Rte. AA form Rte. AB to Rte. H, Rte. P from I-44 to Rte. 17, Spur 28 from Rte. 28 to Rte. 63 and Rte. 7 from Rte. 133 to RR. | 2026 | 70 | 279 | 0 | 279 | 0 | 0 | 0 | 0 | 0 | 6780 | 0 | 7129
Central | N | PULASKI | IS 44 E | CD0111 | 1.462 | 2.943 | 0 | Add auxiliary lane from Superior Road to 0.7 mile west of Rte. 66 Trail. $1,915,000 Open Container funds. | 2026 | 761 | 2291 | 0 | 2291 | 0 | 0 | 0 | 0 | 0 | 7916 | 0 | 10968
Central | N | PULASKI | IS 44 W | CD0111B | 0.76 | 1.522 | 0 | Add auxiliary lanes from 1 mile east of Rte. H to 0.1 mile west of Superior Road. | 2026 | 307 | 1955 | 0 | 1955 | 0 | 0 | 0 | 0 | 0 | 7395 | 0 | 9657
Central | N | PULASKI | IS 44 W | CD0112 | 0.407 | 0.407 | 0 | Modify ramps at westbound on-ramp at Loop 44 in St. Robert. | 2026 | 120 | 114 | 0 | 114 | 0 | 10 | 0 | 10 | 0 | 2169 | 0 | 2413
Central | N | PULASKI | LP 44 E | CD0128 | 3.788 | 11.023 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan from Ridgeview Drive to 0.2 mile east of Plattner Avenue in St. Robert and Rte. 17 from Summit Avenue to Lynn Street in Waynesville. | 2026 | 246 | 429 | 0 | 429 | 46 | 0 | 0 | 0 | 0 | 2102 | 0 | 2823
Central | N | PULASKI | SP 44 E | CD0127 | 2.221 | 9.686 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan from east of St. Robert Boulevard to the east intersection of Gateway Circle in St. Robert. | 2026 | 146 | 206 | 0 | 206 | 0 | 1 | 0 | 1 | 0 | 1287 | 0 | 1640
Central | N | PULASKI | SP 44 E | CD0162 | 5.21 | 19.147 | 0 | Pavement improvement from I-44 to end of state maintenance and on Bus. 44 from Rte. 17 to I-44 Spur. | 2027 | 2 | 43 | 304 | 347 | 0 | 0 | 0 | 0 | 0 | 0 | 4563 | 4912
Central | N | PULASKI | MO 7 S | 5P3544 | 0.137 | 0.274 | 1 | Bridge improvement over the Gasconade River. Project involves bridge A0843. | 2028 | 4 | 1 | 121 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 642 | 768
Central | N | PULASKI | MO 7 S | CD0031 | 0.056 | 0.112 | 1 | Bridge rehabilitation over I-44. Project involves bridge A3051. | 2026 | 82 | 215 | 0 | 215 | 0 | 0 | 0 | 0 | 0 | 1850 | 0 | 2147
Central | N | TEXAS | MO 32 E | CD0249 | 46.596 | 98.859 | 0 | Pavement resurfacing from Rte. 63 in Texas County to Rte. KK in Iron County. | 2026 | 76 | 398 | 0 | 398 | 0 | 0 | 0 | 0 | 0 | 6892 | 0 | 7366
Central | N | VARIOUS | Various | 5B0800T | 0 | 0 | 92 | Payback beginning in SFY 2008 for Safe and Sound bridges in the Central District. | 2033 | 0 | 0 | 0 | 0 | 107 | 0 | 0 | 0 | 66787 | 4399 | 17596 | 88889
Central | N | VARIOUS | Various | CD0004 | 0 | 0 | 0 | Job Order Contracting for guard cable and guardrail repair on various routes in the northern portion of the Central District. | 2027 | 3 | 1 | 155 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 2266 | 2425
Central | N | VARIOUS | Various | CD0005 | 0 | 0 | 0 | Job Order Contracting for guard cable and guardrail repair on various routes in the southern portion of the Central District. | 2027 | 3 | 1 | 204 | 205 | 0 | 0 | 0 | 0 | 0 | 0 | 2987 | 3195
Central | N | VARIOUS | Various | CD0141 | 0 | 0 | 0 | On-call work zone enforcement at various locations in the Central District. | 2026 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 64
Central | N | VARIOUS | Various | CD0175 | 0 | 0 | 0 | On-call work zone enforcement at various locations in the Central District. | 2027 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 64
Central | N | VARIOUS | Various | CD0254 | 0 | 0 | 0 | On-call work zone enforcement at various locations in the Central District. | 2028 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 64
Central | N | VARIOUS | Various | CD0267 | 0 | 0 | 0 | Job Order Contracting for guard cable and guardrail repair on various routes in the northern portion of the Central District. | 2029 | 0 | 1 | 143 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 2185 | 2329
Central | N | VARIOUS | Various | CD0268 | 0 | 0 | 0 | Job Order Contracting for guard cable and guardrail repair on various routes in the southern portion of the Central District. | 2029 | 0 | 1 | 213 | 214 | 0 | 0 | 0 | 0 | 0 | 0 | 3278 | 3492
Central | N | WASHINGTON | MO 185 S | 5S3557 | 0.03 | 0.06 | 1 | Bridge rehabilitation over Miller Swan Brook. Project involves bridge A0761. | 2026 | 20 | 141 | 0 | 141 | 0 | 1 | 0 | 1 | 0 | 704 | 0 | 866
Central | N | WASHINGTON | MO 185 S | CD0034 | 0.04 | 0.08 | 1 | Bridge improvement over Bates Creek. Project involves bridge A0760. | 2027 | 3 | 43 | 167 | 210 | 0 | 1 | 0 | 1 | 0 | 0 | 961 | 1175
Central | N | WASHINGTON | MO 185 S | CD0261 | 0.395 | 0.929 | 7 | Bridge paint over Bates CR. Rte. J-Laclede over I-44, Rte. N-Crawford over Meramec Rvr, Rte. 163 & Rte. 740 over Hinkson CR in Boone, Rte. T over Burris Fork-Moniteau & S. Summit Dr over Rte. 54-Callaway. Involves bridges A0760, A1196, A1256, A1899, A3354, A3521, N0747. | 2028 | 0 | 1 | 509 | 510 | 0 | 0 | 0 | 0 | 0 | 0 | 2860 | 3370
Central | N | WASHINGTON | MO 21 S | CD0092 | 32.3 | 65.373 | 0 | Pavement improvement from Jefferson County line to Rte. 32 in Iron County. | 2029 | 3 | 1 | 686 | 687 | 0 | 0 | 0 | 0 | 0 | 0 | 9138 | 9828
Central | N | WASHINGTON | MO 47 S | CD0135 | 0.589 | 1.178 | 0 | Modify railroad crossing interchange at Union Pacific Railroad 1.2 miles south of Rte. E. $6,134,000 STBG-Rail and $323,000 Union Pacific Railroad funds. | 2026 | 889 | 1281 | 0 | 1281 | 0 | 137 | 0 | 137 | 0 | 6320 | 0 | 8627
Central | N | WASHINGTON | MO 8 E | 5P3558 | 0.074 | 0.148 | 3 | Bridge rehabilitation over Allen Creek, over Mid Fork Fourche a Renault and over North Fork Fourche a Renault. Project involves bridges A1437, A1438 and A1439. | 2026 | 83 | 492 | 0 | 492 | 0 | 1 | 0 | 1 | 0 | 2519 | 0 | 3095
Central | N | WASHINGTON | RT A E | CD0228 | 0.34 | 0.68 | 1 | Bridge replacement over Indian Creek. Project involves bridge A0331. | 2026 | 255 | 771 | 0 | 771 | 0 | 20 | 0 | 20 | 0 | 2465 | 0 | 3511
Central | N | WASHINGTON | RT T S | 5S3556 | 0.05 | 0.1 | 1 | Bridge rehabilitation over Big Indian Creek. Project involves bridge W0217. | 2026 | 20 | 37 | 0 | 37 | 0 | 1 | 0 | 1 | 0 | 275 | 0 | 333
Central | N | WASHINGTON | RT U S | CD0208 | 43.325 | 86.701 | 0 | Pavement preservation treatment from Springtown to Rte. BB in St. Francois County and Rte. E from Rte. CC to Rte. 21. Rte. ZZ from Rte. F to McLeod St. and Rte. DD from southeast of Brush Creek to west of Rte. 19, Rte. F from Rte. 32 to Rte. E. | 2026 | 22 | 103 | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 1598 | 0 | 1723
Central | N | WASHINGTON | RT W S | CD0032 | 0.023 | 0.046 | 1 | Bridge rehabilitation over Ashley Branch. Project involves bridge R0442. | 2026 | 17 | 132 | 0 | 132 | 0 | 0 | 0 | 0 | 0 | 657 | 0 | 806
St. Louis | Y | FRANKLIN | MO 100 E | 6S3583B | 0.126 | 0.572 | 0 | Replace signals at Rte. AT and on South Woods Mill Road at South Outer Forty Drive in St. Louis County. | 2028 | 45 | 5 | 120 | 125 | 0 | 0 | 1 | 1 | 0 | 0 | 1082 | 1253
St. Louis | Y | FRANKLIN | MO 100 E | SL0180 | 0.28 | 0.564 | 0 | Payment to Washington to add turn lanes east of Vossbrink Drive. $1,610,000 Cost Share funds. | 2026 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 1610 | 0 | 1625
St. Louis | Y | FRANKLIN | MO 30 E | 6S3435 | 30.596 | 94.131 | 7 | Pavement resurfacing, upgrade guardrail and bridge deck sealing from I-44 North Outer Road to 1.3 miles east of Bethel Church Road and 0.1 mile west of Oak Grove Church Road to Rte. PP. Project involves bridges A3045, A3046, A3104, A3105, A4629, A4975 and A7124. | 2026 | 2430 | 1712 | 0 | 1712 | 25 | 0 | 0 | 0 | 0 | 24936 | 0 | 29103
St. Louis | Y | FRANKLIN | MO 30 E | 6S3435B | 0.852 | 1.704 | 2 | Bridge replacement and rebuild pavement from 1.3 miles east of Bethel Church Road to 0.1 mile west of Oak Grove Church Road and upgrade pedestrian facilities to comply with the ADA Transition Plan at Bardot Street. Project involves bridges H0994 and H0995. | 2027 | 250 | 440 | 466 | 906 | 0 | 75 | 0 | 75 | 0 | 0 | 6837 | 8068
St. Louis | Y | FRANKLIN | IS 44 E | SL0038 | 15.966 | 66.512 | 1 | Pavement resurfacing, replace signage, upgrade guardrail from 0.3 mile west of Rte. 185 to 0.5 mile east of Rte. 30, rest area, weigh scale site improvements, and ramp extensions in St. Clair. Project involves bridge A2049. $13,472,000 General Services Operation funds. | 2027 | 500 | 1202 | 1600 | 2802 | 0 | 20 | 0 | 20 | 0 | 0 | 22531 | 25853
St. Louis | Y | FRANKLIN | IS 44 E | SL0048 | 4.754 | 29.469 | 0 | Pavement resurfacing and upgrade guardrail from Rte. 100 to Viaduct Street. | 2027 | 347 | 300 | 407 | 707 | 0 | 0 | 0 | 0 | 0 | 0 | 3816 | 4870
St. Louis | Y | FRANKLIN | IS 44 E | SL0297 | 1.4 | 4.078 | 5 | Interchange improvements at Rte. 50, intersection improvements at Rte. AT and Rte. 50, bridge painting at Rte. 50, Rte. AH and Outer Road I-44, bridge rehabilitation over Birch Creek, and culvert rehabilitation 0.3 mile east of Old Hwy. 50. Design-Build project. | 2027 | 0 | 3436 | 10240 | 13676 | 0 | 3000 | 0 | 3000 | 0 | 0 | 45564 | 62240
St. Louis | Y | FRANKLIN | MO 47 S | SL0033 | 1.741 | 8.429 | 0 | Pavement resurfacing and upgrade guardrail from 0.1 mile north of Missouri Avenue to 0.4 mile south of Rte. 100. | 2027 | 200 | 50 | 71 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 917 | 1238
St. Louis | Y | FRANKLIN | MO 47 S | SL0082 | 12.697 | 29.536 | 0 | Safety and capacity improvements from Rte. 100 to I-44 (Phase I). Potential Design-Build project. | 2028 | 2210 | 2000 | 5030 | 7030 | 0 | 0 | 2060 | 2060 | 0 | 0 | 76120 | 87420
St. Louis | Y | FRANKLIN | US 50 E | SL0067 | 0.272 | 1.397 | 2 | Bridge rehabilitation over the Bourbeuse River. Project involves bridges A3961 and A4047. | 2027 | 467 | 6 | 194 | 200 | 0 | 10 | 0 | 10 | 0 | 0 | 2850 | 3527
St. Louis | Y | FRANKLIN | RT A S | SL0049 | 7.546 | 15.961 | 0 | Pavement resurfacing, pavement repair and upgrade signage from Rte. 100 to 0.1 mile north of Independence Drive. | 2027 | 349 | 5 | 159 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 2321 | 2834
St. Louis | Y | FRANKLIN | RT AB S | SL0050 | 2.037 | 4.074 | 0 | Pavement resurfacing, pavement repair and signage upgrade from Roller Road to North Outer Road I-44. | 2027 | 123 | 1 | 37 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 545 | 706
St. Louis | Y | FRANKLIN | RT H S | SL0217 | 33.505 | 67.6 | 0 | Pavement preservation treatment from 0.2 mile north of Antioch Road to Rte. 50, Rte. AT from Rte. 50 to Rte. 100, Rte. BB from Rte. A to Rte. 50, Rte. TT from North Commercial Avenue to Mill Hill Road, and Rte. T from South Main Street to Rte. 94. | 2026 | 2 | 75 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 836 | 0 | 913
St. Louis | Y | FRANKLIN | RT K S | SL0059 | 0.232 | 0.464 | 3 | Bridge rehabilitation over the Meramec River and bridge replacement over Brush Creek north of Heynes Memorial Annex and 0.8 mile south of Heynes Memorial Annex. Project involves bridges A3871, A8533 and A8534. | 2028 | 460 | 50 | 597 | 647 | 0 | 0 | 52 | 52 | 0 | 0 | 8460 | 9619
St. Louis | Y | FRANKLIN | CRD OLD HIGHWAY 100 E | 6S3627 | 0.035 | 0.07 | 1 | Bridge replacement over Dubois Creek 0.2 mile east of Fifth Street. Project involves bridge 4330001. | 2027 | 339 | 52 | 146 | 198 | 0 | 10 | 0 | 10 | 0 | 0 | 1891 | 2438
St. Louis | Y | FRANKLIN | RT PP S | SL0032 | 6.719 | 13.496 | 2 | Pavement resurfacing, pipe replacement, upgrade guardrail and replace signage from Rte. 30 to Pickles Ford Road, culvert replacement over Dry Branch and culvert extension over Hoosier Creek. Project involves culvert R0261 and R0262. | 2026 | 240 | 266 | 0 | 266 | 0 | 75 | 0 | 75 | 0 | 3152 | 0 | 3733
St. Louis | Y | FRANKLIN | RT T E | 6S3611 | 14.976 | 29.952 | 1 | Pavement resurfacing, pavement repair, and upgrade guardrail from west junction Rte. 100 to east junction Rte. 100 and bridge deck sealing over Labadie Creek. Project involves bridge A7212. $4,400,000 STBG-Urban funds. | 2026 | 470 | 386 | 0 | 386 | 25 | 0 | 0 | 0 | 0 | 5549 | 0 | 6430
St. Louis | Y | FRANKLIN | RT VV S | SL0068 | 0.204 | 0.572 | 4 | Culvert rehabilitation over Rohlfing Creek, on Rte. UU over Buesher Creek, on I-44 over branch of the Bourbeuse River and on Rte. OO over Little Fox Creek. Project involves culverts A4693, L0355, N0351 and N0820. | 2027 | 60 | 15 | 39 | 54 | 0 | 10 | 0 | 10 | 0 | 0 | 364 | 488
St. Louis | Y | JEFFERSON | MO 110 E | SL0069 | 0.501 | 1.602 | 3 | Bridge rehabilitation over Union Pacific Railroad and Joachim Creek, Rte. 61 over Rock Creek and Rte. T over Plattin Creek. Project involves bridges A3616, A4588 and A4789. | 2028 | 225 | 10 | 164 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 2304 | 2703
St. Louis | Y | JEFFERSON | MO 30 E | SL0046 | 7.897 | 32.852 | 0 | Pavement resurfacing, pavement repairs, upgrade guardrail and replace signage from 0.2 mile west of Rte. PP to 0.2 mile west of Gravois Bluffs Boulevard and Rte. PP from Byrnes Mill Road to Rte. 30. | 2027 | 437 | 100 | 350 | 450 | 0 | 10 | 0 | 10 | 0 | 0 | 4508 | 5405
St. Louis | Y | JEFFERSON | IS 55 N | 6I3290 | 0.284 | 3.011 | 2 | Bridge rehabilitation over the Meramec River. Project involves twin bridges A0609. | 2026 | 1846 | 1223 | 0 | 1223 | 0 | 10 | 0 | 10 | 0 | 17811 | 0 | 20890
St. Louis | Y | JEFFERSON | IS 55 S | SL0154 | 0.24 | 1.293 | 6 | Bridge rehabilitation at Church Road, Vogel Road, Richardson Road, Rock Creek and Imperial Main Street. Project involves bridges A5459, A5728, A5729, A5929, A6112 and A6113. | 2029 | 424 | 1 | 122 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 1752 | 2299
St. Louis | Y | JEFFERSON | W OR 55 S | SL0268 | 0.07 | 0.162 | 0 | Add signals at Miller Road and Seckman Road. $917,440 Congestion Mitigation and Air Quality Improvement Program funds. | 2028 | 0 | 113 | 94 | 207 | 0 | 0 | 0 | 0 | 0 | 0 | 997 | 1204
St. Louis | Y | JEFFERSON | US 61 N | 6S3289 | 0.919 | 3.676 | 1 | Bridge replacement over Joachim Creek between Scenic Drive and Herky-Horine Road and slide repair north of Herky-Horine Road to Joachim Avenue. Project involves bridge K0294. | 2026 | 1331 | 1235 | 0 | 1235 | 925 | 0 | 0 | 0 | 0 | 17267 | 0 | 20758
St. Louis | Y | JEFFERSON | US 61 N | 6S3391 | 1.078 | 4.42 | 0 | Pavement resurfacing and add center turn lane from Brandon Wallace Way to 6th Street. | 2026 | 426 | 323 | 0 | 323 | 85 | 0 | 0 | 0 | 0 | 3982 | 0 | 4816
St. Louis | Y | JEFFERSON | US 61 N | 6S3399 | 10.972 | 45.076 | 3 | Pavement resurfacing, upgrade guardrail and upgrade pedestrian facilities to comply with the ADA Transition Plan from Rte. M to Rte. 67 and replace culverts 0.1 mile south of Schmidt Rd. and south of Hillside Estates Dr. Project involves culverts G0511, G0512 and G0641. | 2026 | 960 | 1056 | 0 | 1056 | 0 | 684 | 0 | 684 | 0 | 14654 | 0 | 17354
St. Louis | Y | JEFFERSON | US 61 S | SL0215 | 33.993 | 157.95 | 0 | Pavement preservation treatment on Rte. 61, Rte. A, Rte. 94, Rte. 30, Rte. 100 and Rte. 340. | 2027 | 1 | 5 | 77 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 863 | 946
St. Louis | Y | JEFFERSON | RT CC S | SL0041 | 5.601 | 11.202 | 0 | Pavement resurfacing, upgrade guardrail and signage from Rte. 67 to Rte. 110. | 2026 | 299 | 120 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 1728 | 0 | 2147
St. Louis | Y | JEFFERSON | RT FF S | SL0274 | 4.545 | 9.09 | 1 | Pavement resurfacing, upgrade guardrail, signage, repair signals from Rte. 109 to Rte. F and bridge rehabilitation over Labarque Creek. Project involves bridge N0199. | 2029 | 0 | 10 | 214 | 224 | 0 | 0 | 11 | 11 | 0 | 0 | 3006 | 3241
St. Louis | Y | JEFFERSON | RT M E | 6S3652 | 7.309 | 31.186 | 8 | Pavement resurfacing, upgrade guardrail, replace signage and bridge deck sealing from Rte. 21 to west of Metropolitan Boulevard and on Rte. MM from Buckeye Valley Road to Rte. 21. Project involves bridges A5415, A5416, A5417, A5418, A5581, A5582, A5633 and A5634. | 2027 | 160 | 25 | 162 | 187 | 0 | 20 | 0 | 20 | 0 | 0 | 2054 | 2421
St. Louis | Y | JEFFERSON | RT T W | SL0254 | 25.758 | 51.706 | 0 | Pavement preservation treatment from Rte. JJ to Rte. TT, Rte. TT from Rte. 61 north junction to Rte. 61 south junction and Rte. BB from Rte. 30 to Rte. 21. | 2028 | 0 | 1 | 76 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 887 | 964
St. Louis | Y | ST. CHARLES | MO 370 E | 6P3551 | 0.248 | 1.522 | 8 | Bridge rehabilitation over Lakeside Park Drive, Cole Creek, New Town Boulevard and Elm Point Industrial Drive. Project involves bridges A5116, A5123, A5308, A5309, A5322, A5323, A5326 and A5327. | 2029 | 310 | 10 | 873 | 883 | 0 | 0 | 0 | 0 | 0 | 0 | 5786 | 6979
St. Louis | Y | ST. CHARLES | MO 370 E | 6P3554 | 0.64 | 5.202 | 2 | Bridge rehabilitation over the Missouri River. Project involves bridge A4557. | 2026 | 3036 | 4237 | 0 | 4237 | 0 | 0 | 0 | 0 | 0 | 58097 | 0 | 65370
St. Louis | Y | ST. CHARLES | MO 370 E | 6P3612 | 0.122 | 0.345 | 3 | Bridge rehabilitation over Premier Parkway and Salt River Road over Rte. 370. Project involves bridges A5321, A5493 and A5494. | 2029 | 82 | 5 | 214 | 219 | 0 | 0 | 0 | 0 | 0 | 0 | 2216 | 2517
St. Louis | Y | ST. CHARLES | MO 370 E | SL0248 | 0.047 | 0.708 | 2 | Bridge rehabilitation over Rte. 94. Project involves bridges A4999 and A5109. | 2026 | 100 | 114 | 0 | 114 | 0 | 0 | 0 | 0 | 0 | 1302 | 0 | 1516
St. Louis | Y | ST. CHARLES | E OR 61 S | SL0014 | 0.548 | 1.096 | 0 | Pavement resurfacing from Pitman Avenue to end of state maintenance. | 2026 | 8 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 152 | 0 | 172
St. Louis | Y | ST. CHARLES | US 61 S | SL0083 | 6.044 | 25.121 | 0 | Safety and operational improvements from Dietrich Road to 1.0 mile north of I-64 (Phase I). $5,578,000 Open Container funds. | 2027 | 1400 | 2940 | 2910 | 5850 | 0 | 5343 | 0 | 5343 | 0 | 0 | 36175 | 48768
St. Louis | Y | ST. CHARLES | IS 64 E | 6I3650 | 51.947 | 0 | 0 | Replace structural signs from I-70 to the Mississippi River and on I-170 from I-270 to Eager Road. | 2026 | 810 | 697 | 0 | 697 | 0 | 0 | 0 | 0 | 0 | 7976 | 0 | 9483
St. Louis | Y | ST. CHARLES | N OR 64 E | SL0016 | 0.04 | 0.088 | 1 | Bridge replacement over Peruque Creek. Project involves bridge J0991. | 2028 | 105 | 70 | 365 | 435 | 0 | 0 | 0 | 0 | 0 | 0 | 5098 | 5638
St. Louis | Y | ST. CHARLES | N OR 64 W | SL0013 | 10.377 | 23.809 | 0 | Pavement resurfacing and upgrade guardrail from Warsen Avenue to Wolfrum Road, Rte. N from Spring Borough Drive to Technology Drive and on South Outer Road 64 from Prospect Road to Hickory Glen Court and from Rte. N to south of Kent Drive. | 2028 | 15 | 5 | 759 | 764 | 0 | 0 | 0 | 0 | 0 | 0 | 5546 | 6325
St. Louis | Y | ST. CHARLES | S OR 64 W | 6S3507 | 1.005 | 2.01 | 0 | Payment to St. Charles County for construction of Interstate Drive from east of Quail Ridge Park to Prospect Road. $1,524,500 Cost Share funds. | 2026 | 11 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 1525 | 0 | 1542
St. Louis | Y | ST. CHARLES | US 67 S | 6P3414 | 0.188 | 0.738 | 1 | Payment to IDOT for inspection of stay cables on the Clark Bridge. Project involves bridge A4278. | 2026 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 751
St. Louis | Y | ST. CHARLES | US 67 S | 6P3636 | 3.001 | 12.475 | 0 | Add J-turns and pavement resurfacing between Riverlands Way and the Missouri River. $6,945,000 Open Container funds. | 2026 | 625 | 2854 | 0 | 2854 | 0 | 25 | 0 | 25 | 0 | 19859 | 0 | 23363
St. Louis | Y | ST. CHARLES | US 67 S | SL0107 | 0.635 | 2.54 | 1 | Bridge preventative maintenance and upgrade drainage on the Lewis Bridge. Project involves bridge A3047. | 2027 | 15 | 5 | 73 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 1025 | 1118
St. Louis | Y | ST. CHARLES | US 67 S | SL0212 | 73.176 | 0 | 0 | Replace signage from the Mississippi River to Swan Drive in St. Louis County and 0.2 mile north of Big Bend Road in St. Louis County to 0.2 mile south of Rte. V in Jefferson County. | 2028 | 50 | 150 | 343 | 493 | 0 | 0 | 0 | 0 | 0 | 0 | 2976 | 3519
St. Louis | Y | ST. CHARLES | IS 70 E | SL0134 | 0.08 | 0.516 | 4 | Bridge rehabilitation over Peruque Creek and Rte. A. Project involves bridges A4236, A4237, L0206 and L0709. | 2029 | 20 | 10 | 275 | 285 | 0 | 0 | 0 | 0 | 0 | 0 | 1664 | 1969
St. Louis | Y | ST. CHARLES | IS 70 E | SL0174 | 132.039 | 0 | 0 | Upgrade striping from Rte. A to the Mississippi River, I-55 from I-44 to 0.2 mile south of Meramec Bottom Road, I-170 from I-270 to I-64, I-270 from east of Lilac Avenue to I-55, I-255 from I-55 to the Mississippi River and I-64 from west of Rte. K to I-44. | 2026 | 50 | 187 | 0 | 187 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2237
St. Louis | Y | ST. CHARLES | IS 70 E | SL0188 | 4.005 | 30.384 | 11 | Bridge washing over the Missouri River on I-70, I-64, Rte. 47, Rte. 364, Rte. 370, Rte. 67 and on Rte. 364 over Creve Coeur Lake. Project involves bridges A3047, A3292, A4017, A4557, A5584, A5585, A7577, A8141 and L0561. | 2028 | 25 | 20 | 188 | 208 | 0 | 0 | 0 | 0 | 0 | 0 | 2212 | 2445
St. Louis | Y | ST. CHARLES | IS 70 E | SL0294 | 26.858 | 0 | 0 | Emergency response operations for Improve I-70 from 0.4 mile west of Rte. W to the Missouri River. $2,279,110 Congestion Mitigation and Air Quality Improvement Program funds. | 2026 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2849 | 0 | 2850
St. Louis | Y | ST. CHARLES | IS 70 E | SL0305 | 0.04 | 0.385 | 2 | Bridge rehabilitation over 5th Street. Project involves bridges A3582 and A3583. | 2027 | 0 | 100 | 294 | 394 | 0 | 0 | 0 | 0 | 0 | 0 | 4263 | 4657
St. Louis | Y | ST. CHARLES | MO 79 N | SL0015 | 0.049 | 0.489 | 9 | Bridge rehabilitation at various locations on Rte. T, Rte. N, Rte. 61, I-70 and I-64. Project involves bridges A2348, A4728, A6157, A6755, A6986, A7043, A7103, A8539 and H0141. | 2029 | 60 | 50 | 100 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 936 | 1146
St. Louis | Y | ST. CHARLES | MO 94 E | SL0120 | 1.206 | 2.751 | 0 | Add intersection turn lanes and replace signal at Rte. D. $1,917,900 Congestion Mitigation and Air Quality Improvement Program funds. | 2027 | 405 | 40 | 276 | 316 | 0 | 656 | 0 | 656 | 0 | 0 | 2195 | 3572
St. Louis | Y | ST. CHARLES | MO 94 E | SL0120B | 1.216 | 2.928 | 0 | Add lanes from Rte. D to I-64. | 2027 | 150 | 50 | 139 | 189 | 0 | 1000 | 0 | 1000 | 0 | 0 | 1780 | 3119
St. Louis | Y | ST. CHARLES | MO 94 E | SL0208 | 2.124 | 10.169 | 77 | Bridge deck sealing at various locations in St. Charles, St. Louis, and Franklin Counties. Project involves bridges on Rte. 94, Rte. 364, Rte. 79, Rte. K, I-70, Rte. 61, Rte. D, Rte. N, Rte. T, Rte. Z, I-64, I-270, I-170, Rte. 67, Rte. 141, Rte. N, Rte. AF, and Rte. 47. | 2026 | 5 | 160 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 1695
St. Louis | Y | ST. CHARLES | MO 94 E | SL0222B | 0.167 | 0.334 | 0 | Add pedestrian signal at Katy Trail crossings. $306,000 Open Container funds. | 2026 | 48 | 23 | 0 | 23 | 0 | 0 | 0 | 0 | 0 | 306 | 0 | 377
St. Louis | Y | ST. CHARLES | MO 94 E | SL0235 | 0.171 | 0.342 | 0 | Add intersection turn lanes and signal at Rte. B. $712,890 Congestion Mitigation and Air Quality Improvement Program funds. | 2027 | 59 | 7 | 84 | 91 | 0 | 150 | 0 | 150 | 0 | 0 | 1155 | 1455
St. Louis | Y | ST. CHARLES | CST LAKE ST LOUIS BLVD E | SL0118 | 0.445 | 1.555 | 0 | Payment to Lake Saint Louis for pavement resurfacing, add lanes, sidewalks and upgrade drainage from north of Hawk Ridge Crossing to south of Hawk Ridge Circle. $600,000 Cost Share funds. | 2026 | 25 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 635
St. Louis | Y | ST. CHARLES | N OR 70 E | SL0119 | 0 | 0 | 0 | Construct new north outer road and relocate ramps from Rte. 94 to Zumbehl Road. $5,069,000 Cost Share, $3,000,000 Congestion Mitigation and Air Quality Program and $2,431,000 St. Charles County funds. | 2026 | 10 | 1051 | 0 | 1051 | 0 | 0 | 0 | 0 | 0 | 10500 | 0 | 11561
St. Louis | Y | ST. CHARLES | N OR 70 E | SL0161 |  | 0 | 0 | Payback to St. Charles County to construct new north outer road and relocate ramps from Rte. 94 to Zumbehl Road. $475,966 Cost Share funds. | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 476 | 0 | 476
St. Louis | Y | ST. CHARLES | RT P E | 6S3666 | 0.5 | 1 | 0 | Add signals at Koch Road. | 2027 | 205 | 45 | 80 | 125 | 0 | 64 | 0 | 64 | 0 | 0 | 1119 | 1513
St. Louis | Y | ST. CHARLES | RT P E | SL0218 | 19.455 | 39.068 | 0 | Pavement preservation treatment from Rte. 61 to Rte. M and on Rte. B from Rte. C to Rte. 94. | 2027 | 1 | 5 | 71 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 861 | 938
St. Louis | Y | ST. CHARLES | US 67 S | SL0246 | 0 | 0 | 0 | Clearing and wildlife barrier from Riverlands Way to the Missouri River. | 2026 | 2 | 31 | 0 | 31 | 0 | 0 | 0 | 0 | 0 | 422 | 0 | 455
St. Louis | Y | ST. LOUIS | MO 100 E | 6P3510D | 3.53 | 17.38 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan from Rte. 340 (Clarkson Road) to Baxter Road. | 2026 | 0 | 900 | 0 | 900 | 0 | 10 | 0 | 10 | 0 | 4376 | 0 | 5286
St. Louis | Y | ST. LOUIS | MO 100 E | SL0251 | 0.45 | 2.996 | 0 | Payment to Manchester to add sidewalk from Rte. 141 to west of Knollhaven Drive. $1,340,362 Cost Share funds. | 2027 | 0 | 3 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 255 | 1085 | 1348
St. Louis | Y | ST. LOUIS | MO 109 S | SL0295 | 8.124 | 23.462 | 0 | Signal optimization from Shepard Road to The Legends Parkway, modify turn lanes at Eureka High School, 5th Street and I-44. $2,260,000 Congestion Mitigation and Air Quality Improvement Program funds. | 2027 | 0 | 65 | 500 | 565 | 0 | 0 | 0 | 0 | 0 | 0 | 2328 | 2893
St. Louis | Y | ST. LOUIS | MO 115 S | SL0172 | 1.324 | 5.493 | 0 | Pavement resurfacing, replace signage, upgrade lighting and guardrail from I-70 to Engler Avenue. | 2027 | 50 | 78 | 218 | 296 | 0 | 0 | 0 | 0 | 0 | 0 | 2521 | 2867
St. Louis | Y | ST. LOUIS | MO 141 S | SL0025 | 0.22 | 0.842 | 3 | Bridge rehabilitation over Rte. 370 at Taussig Avenue, West St. Louis Mills Boulevard and Rte. 141. Project involves bridges A4919, A4920 and A7015. | 2028 | 45 | 100 | 1206 | 1306 | 0 | 0 | 0 | 0 | 0 | 0 | 7309 | 8660
St. Louis | Y | ST. LOUIS | MO 141 S | SL0026 | 2.821 | 12.638 | 0 | Pavement resurfacing and replace signage from Rte. 370 to I-70. | 2027 | 15 | 15 | 152 | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 2136 | 2318
St. Louis | Y | ST. LOUIS | MO 141 S | SL0234 | 0.147 | 0.897 | 0 | Add intersection turn lanes and upgrade signals at Parkway South Middle School and at Springdale Lane. $224,484 Congestion Mitigation and Air Quality Improvement Program funds. | 2027 | 21 | 3 | 28 | 31 | 0 | 25 | 0 | 25 | 0 | 0 | 210 | 287
St. Louis | Y | ST. LOUIS | IS 170 E | 6I3567 | 0.265 | 2.159 | 11 | Bridge rehabilitation over I-64 ramps, Ladue Road, Galleria Parkway, Clayton Road and Brentwood Boulevard and bridge replacement at Forest Park Parkway. Project involves bridges A2779, A2780, A2782, A2788, A2790, A8011, A8012 and A8015. | 2027 | 550 | 375 | 1061 | 1436 | 0 | 182 | 0 | 182 | 0 | 0 | 13279 | 15447
St. Louis | Y | ST. LOUIS | IS 170 E | 6I3572 | 7.51 | 53.032 | 4 | Bridge and culvert rehabilitation and upgrade guardrail from Nyflot Avenue to 0.2 mile north of Rte. 340 and sound abatement repairs near East Sherwood Drive. Project involves bridges A2807, A2809, A3176 and culvert A2808. $50,000 District Operation funds. | 2027 | 1210 | 100 | 882 | 982 | 0 | 135 | 0 | 135 | 0 | 0 | 13289 | 15616
St. Louis | Y | ST. LOUIS | IS 170 E | SL0261 | 0.213 | 0.852 | 1 | Bridge rehabilitation over Norfolk Southern Railway 0.4 mile north of Airport Road. Project involves bridge A2926. | 2030 | 0 | 5 | 2176 | 2181 | 0 | 0 | 0 | 0 | 0 | 0 | 11993 | 14174
St. Louis | Y | ST. LOUIS | MO 180 E | 6S3311 | 0.097 | 0.597 | 2 | Bridge replacement, ramp extensions, upgrade ITS equipment and add sidewalk on St. Charles Rock Road at I-70. Project involves bridge L0887. | 2029 | 991 | 440 | 1053 | 1493 | 25 | 0 | 53 | 53 | 0 | 0 | 16570 | 19132
St. Louis | Y | ST. LOUIS | MO 180 E | SL0211 | 50.816 | 227.749 | 0 | Pavement preservation treatment on Rte. 180, Rte. 50, I-70, I-55, Rte. A, and Rte. 61. | 2026 | 1 | 82 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 838 | 0 | 921
St. Louis | Y | ST. LOUIS | MO 21 S | SL0194 | 1.483 | 4.208 | 9 | Bridge washing over the Meramec River on Rte. 21, Rte. 30, Rte. 61, Rte. 109, Rte. 141, Rte. 185, Rte. F, Rte. K and Rte. O. Project involves bridges A2137, A2187, A2955, A3871, A3967, A3998, A4975, A6474 and K0637. | 2027 | 1 | 5 | 49 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 451 | 506
St. Louis | Y | ST. LOUIS | MO 231 N | 6S3631 | 3.072 | 12.16 | 0 | Pavement resurfacing and upgrade pedestrian facilities to comply with the ADA Transition Plan from River City Casino Boulevard to Sappington Barracks Road. | 2026 | 1050 | 1751 | 0 | 1751 | 1861 | 0 | 0 | 0 | 0 | 16774 | 0 | 21436
St. Louis | Y | ST. LOUIS | MO 231 S | 6S3632 | 7.078 | 34.944 | 0 | Pavement resurfacing and upgrade pedestrian facilities to comply with the ADA Transition Plan from Franru Lane to the Meramec River. | 2026 | 1085 | 1563 | 0 | 1563 | 695 | 0 | 0 | 0 | 0 | 22705 | 0 | 26048
St. Louis | Y | ST. LOUIS | IS 270 E | 6I3020D | 1.425 | 5.765 | 1 | Add lanes and bridge replacement from Lilac Avenue to 0.1 mile west of Rte. H (Riverview Drive). Project involves bridge A0221. | 2027 | 1384 | 5 | 984 | 989 | 0 | 50 | 0 | 50 | 0 | 0 | 14698 | 17121
St. Louis | Y | ST. LOUIS | IS 270 E | 6I3580B | 3.592 | 20.056 | 0 | Pavement resurfacing and median barrier replacement from west of Rte. 367 to the Mississippi River. | 2029 | 0 | 200 | 532 | 732 | 0 | 0 | 0 | 0 | 0 | 0 | 5785 | 6517
St. Louis | Y | ST. LOUIS | IS 270 E | 6I3618 | 0.022 | 0.135 | 1 | Culvert rehabilitation west of Rte. AC (New Halls Ferry Road). Project involves culvert J0888. $150,000 Metropolitain St. Louis Sewer District funds. | 2026 | 34 | 181 | 0 | 181 | 0 | 20 | 0 | 20 | 0 | 1116 | 0 | 1351
St. Louis | Y | ST. LOUIS | IS 270 E | SL0021 | 2.834 | 17.935 | 3 | Bridge replacement over Rte. 367 and Bellefontaine Rd., rebuild pavement, replace median barrier 0.6 mile west of Rte. 367 to 0.4 mile west of Lilac Ave., replace signals and upgrade pedestrian facilities at Bellefontaine Road. Project involves bridges A0241 and J0847. | 2027 | 2524 | 25 | 2197 | 2222 | 0 | 20 | 0 | 20 | 0 | 0 | 28527 | 33293
St. Louis | Y | ST. LOUIS | IS 270 E | SL0021B | 0.089 | 0.493 | 3 | Bridge rehabilitation on I-270 and Dunn Road over BNSF Railway. Project involves bridges J0493 and L0749. | 2029 | 54 | 200 | 393 | 593 | 0 | 0 | 21 | 21 | 0 | 0 | 3573 | 4241
St. Louis | Y | ST. LOUIS | IS 270 E | SL0022 | 0.515 | 4.068 | 4 | Bridge rehabilitation over Norfolk Southern Railway, on Rte. 370 over Norfolk Southern Railway, on ramp from Missouri Bottom Road to I-270 and on Missouri Bottom Road over I-270. Project involves bridges A0170, A4277, A4898 and A4899. | 2028 | 385 | 205 | 926 | 1131 | 0 | 0 | 0 | 0 | 0 | 0 | 8130 | 9646
St. Louis | Y | ST. LOUIS | IS 270 E | SL0024 | 6.237 | 53.078 | 0 | Pavement resurfacing and median barrier replacement from I-70 to I-170. | 2027 | 200 | 300 | 1827 | 2127 | 0 | 0 | 0 | 0 | 0 | 0 | 15725 | 18052
St. Louis | Y | ST. LOUIS | IS 270 E | SL0053 | 0.397 | 2.319 | 11 | Bridge rehabilitation over Marshall Road, Rott Road, Von Talge Road, River Sub Railroad, I-55 and ramp from I-55 to I-255. Project involves bridges A0967, A1026, A1033, A1233, A1234, A1235, A4876, A4877 and A5082. | 2027 | 570 | 90 | 1113 | 1203 | 0 | 0 | 0 | 0 | 0 | 0 | 16256 | 18029
St. Louis | Y | ST. LOUIS | N OR 270 E | 6I3580 | 4.862 | 10.719 | 0 | Pavement resurfacing from Rte. 367 to west of Rte. H (Riverview Drive), South Outer Road 270 from 0.1 mile west of Rafterty Lane to Rafterty Lane, 0.3 mile west to 0.5 mile east of Lilac Avenue and on Rte. H (Riverview Drive) from 0.5 mile north of I-270 to I-270. | 2029 | 222 | 20 | 379 | 399 | 0 | 0 | 0 | 0 | 0 | 0 | 2338 | 2959
St. Louis | Y | ST. LOUIS | N OR 270 E | SL0169 | 7.655 | 16.456 | 0 | Pavement resurfacing and pavement repairs on various outer roads from Rte. 340 (Olive Boulevard) to I-55. | 2029 | 150 | 50 | 300 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 3985 | 4485
St. Louis | Y | ST. LOUIS | MO 30 E | SL0081 | 9.062 | 45.228 | 1 | Pavement resurfacing, replace signals, guardrail, lighting from 0.2 mile west of Rte. 141 to east of Hannover Avenue and bridge deck sealing over I-270. Project involves bridge A1027. | 2026 | 270 | 578 | 0 | 578 | 0 | 0 | 0 | 0 | 0 | 7256 | 0 | 8104
St. Louis | Y | ST. LOUIS | MO 340 E | SL0076B | 7.765 | 40.57 | 0 | Pavement resurfacing and repair sidewalk from I-270 to Ferguson Avenue. | 2026 | 120 | 262 | 0 | 262 | 0 | 130 | 0 | 130 | 0 | 3525 | 0 | 4037
St. Louis | Y | ST. LOUIS | MO 340 E | SL0151 | 3.826 | 19.726 | 0 | Pavement resurfacing, upgrade signals, guardrail and ITS equipment from Lea Oak Drive to Rte. 100 (Manchester Road). | 2027 | 40 | 300 | 886 | 1186 | 0 | 0 | 0 | 0 | 0 | 0 | 8799 | 10025
St. Louis | Y | ST. LOUIS | MO 340 E | SL0181 | 0.341 | 1.96 | 0 | Payment to Olivette for intersection improvements at Dielman Industrial Drive and Price Road. $631,500 Cost Share funds. | 2027 | 6 | 2 | 7 | 9 | 0 | 0 | 0 | 0 | 0 | 442 | 190 | 647
St. Louis | Y | ST. LOUIS | MO 364 E | SL0030 | 0.88 | 6.88 | 2 | Bridge rehabilitation at Page Avenue over I-270. Project involves twin bridges A1243. | 2030 | 515 | 5 | 642 | 647 | 0 | 0 | 0 | 0 | 0 | 0 | 10264 | 11426
St. Louis | Y | ST. LOUIS | MO 367 S | SL0117 | 3.264 | 15.307 | 0 | Safety and operational improvements from I-270 to Longridge Drive. | 2027 | 629 | 250 | 840 | 1090 | 0 | 1 | 0 | 1 | 0 | 0 | 9604 | 11324
St. Louis | Y | ST. LOUIS | MO 370 E | 6P3615 | 0.146 | 0.9 | 5 | Bridge rehabilitation over Cowmire Creek, Ferguson Lane and Missouri Bottom Road. Project involves bridges A4886, A4895, A4896 and A5006. | 2029 | 271 | 25 | 696 | 721 | 0 | 0 | 0 | 0 | 0 | 0 | 5641 | 6633
St. Louis | Y | ST. LOUIS | IS 44 E | 6S3443 | 1.184 | 3.663 | 19 | Bridge replacement at various locations from Rte. 67 to Nebraska Avenue and bridge rehabilitation at Edwards Street. Potential Design-Build. Project involves bridges A1715, A1720, A1721, A1723, A1725, A1726, A1728, A1729, A1730, A1732, A1736, A2092, A2257, A2322, A3263. | 2030 | 3211 | 200 | 5399 | 5599 | 0 | 0 | 273 | 273 | 0 | 0 | 68657 | 77740
St. Louis | Y | ST. LOUIS | IS 44 E | SL0054 | 0.238 | 0.588 | 6 | Bridge rehabilitation at Central Avenue, Lewis Road, Antire Road, Maritz Street, Bowles Avenue and Mraz Lane. Potential Design-Build project. Project involves bridges A1797, A3638, A3856, A3996, A4288 and L0761. | 2030 | 1050 | 400 | 2283 | 2683 | 0 | 0 | 0 | 0 | 0 | 0 | 9961 | 13694
St. Louis | Y | ST. LOUIS | IS 44 E | SL0277 | 0.181 | 1.112 | 8 | Bridge rehabilitation over Fox Creek, Rte. 109, Williams Creek, Rte. 141, culvert rehabilitation 0.5 mile east of Lone Elk Park and 0.6 mile west of Rte. 141. Project involves bridge A0775, A4285, J0255, L0704, L0932 and culverts L0705 and J0254. | 2027 | 0 | 1000 | 1239 | 2239 | 0 | 0 | 0 | 0 | 0 | 0 | 14845 | 17084
St. Louis | Y | ST. LOUIS | IS 55 N | 6I3565 | 0.437 | 3.832 | 9 | Bridge painting over 2nd Street, Union Pacific Railroad, River Des Peres, Green Park Road and Gravois Creek. Project involves bridges A0591, A0607, A1057, A1076, A1085 and A1276. | 2028 | 5 | 151 | 577 | 728 | 0 | 0 | 0 | 0 | 0 | 0 | 6582 | 7315
St. Louis | Y | ST. LOUIS | IS 55 S | SL0194B | 1.246 | 7.916 | 9 | Bridge washing over the Meramec River on I-55, I-44, Rte. 30 and Rte. 231. Project involves bridges A0609, A1796, A2014, A4932, A8231, A8683 and L0611 | 2027 | 1 | 9 | 93 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 713 | 816
St. Louis | Y | ST. LOUIS | IS 55 S | SL0196 | 0.279 | 2.859 | 2 | Bridge rehabilitation over the Meramec River. Project involves bridge A0609. | 2028 | 5 | 5 | 657 | 662 | 0 | 0 | 0 | 0 | 0 | 0 | 8761 | 9428
St. Louis | Y | ST. LOUIS | IS 55 S | SL0207 | 26.466 | 187.698 | 0 | Pavement repair on I-55, Rte. 340, North Outer Road 44, Rte. 100, Rte. 67, and Leffingwell Avenue in St. Louis County, on I-70, South Outer Road 70, Bryan Road, and Rte. A in St. Charles County. | 2026 | 1 | 149 | 0 | 149 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 1680
St. Louis | Y | ST. LOUIS | US 61 S | 6S3578 | 4.448 | 21.07 | 2 | Pavement resurfacing and upgrade pedestrian facilities to comply with the ADA Transition Plan from 0.1 mile north of Lindbergh Boulevard to the Meramec River. Project involves bridges A5352 and A6474. | 2026 | 1090 | 719 | 0 | 719 | 346 | 0 | 0 | 0 | 0 | 9597 | 0 | 11752
St. Louis | Y | ST. LOUIS | IS 64 E | SL0138 | 7.612 | 63.553 | 0 | Pavement resurfacing and median barrier replacement from Rte. 340 to 0.3 mile east of Spoede Road. | 2027 | 200 | 200 | 743 | 943 | 0 | 0 | 0 | 0 | 0 | 0 | 10405 | 11548
St. Louis | Y | ST. LOUIS | N OR 64 E | SL0168 | 6.422 | 14.014 | 0 | Pavement resurfacing, replace guardrail and signage from Mason Road to Conway Road, west of Marsally Drive to Spoede Road and on SOR 64 from Mason Road to Jennifer Lane, 0.3 mile west of Carole Lane to Spoede Road and from Clayton Road to Rolling Rock Lane. | 2027 | 60 | 40 | 182 | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 2585 | 2867
St. Louis | Y | ST. LOUIS | US 67 S | 6S3557 | 3.438 | 16.431 | 0 | Pavement resurfacing, upgrade pedestrian facilities to comply with the ADA Transition Plan, and replace signage, signals, and guardrail from I-70 to Rte. D (Page Avenue). $4,000,000 STBG-Urban funds. | 2026 | 1550 | 1500 | 0 | 1500 | 268 | 0 | 0 | 0 | 0 | 11661 | 0 | 14979
St. Louis | Y | ST. LOUIS | US 67 S | 6S3625 | 1.794 | 9.598 | 0 | Pavement resurfacing, replace signals, guardrail, and upgrade pedestrian facilities to comply with the ADA Transition Plan from 0.1 mile east of Patterson Road to Candle Light Lane. | 2026 | 999 | 611 | 0 | 611 | 0 | 268 | 0 | 268 | 0 | 4311 | 0 | 6189
St. Louis | Y | ST. LOUIS | US 67 S | 6S3625C | 2.001 | 10.123 | 0 | Pavement resurfacing, replace signals, guardrail, and upgrade pedestrian facilities to comply with the ADA Transition Plan from Rte. AC (New Halls Ferry Road) to 0.1 mile east of Patterson Road. | 2026 | 0 | 652 | 0 | 652 | 0 | 0 | 0 | 0 | 0 | 4893 | 0 | 5545
St. Louis | Y | ST. LOUIS | US 67 S | SL0029 | 1.731 | 11.87 | 0 | Pavement resurfacing, replace signals, and repair sidewalk from I-270 to Missouri Bottom Road. | 2026 | 360 | 819 | 0 | 819 | 100 | 0 | 0 | 0 | 0 | 5875 | 0 | 7154
St. Louis | Y | ST. LOUIS | US 67 S | SL0233 | 9.152 | 50.489 | 0 | Signal optimization from Old James Town Road to Missouri Bottom Road and Blake Drive to Old St. Charles Road. $2,801,437 Congestion Mitigation and Air Quality Improvement Program funds. | 2027 | 206 | 32 | 200 | 232 | 0 | 0 | 0 | 0 | 0 | 0 | 3156 | 3594
St. Louis | Y | ST. LOUIS | IS 70 E | 6I3617 | 1.911 | 13.466 | 0 | Replace lighting at the I-270 interchange. | 2029 | 320 | 41 | 286 | 327 | 0 | 0 | 0 | 0 | 0 | 0 | 4314 | 4961
St. Louis | Y | ST. LOUIS | IS 70 E | 6I3654 | 0.2 | 1.203 | 1 | Bridge replacement over I-270. Project involves bridge A0093. | 2029 | 1125 | 10 | 831 | 841 | 0 | 0 | 0 | 0 | 0 | 0 | 13113 | 15079
St. Louis | Y | ST. LOUIS | IS 70 E | SL0058 | 6.971 | 57.359 | 25 | Corridor improvements from the Missouri River to Rte. 67. Potential Design-Build project. Project involves various bridges. | 2029 | 5500 | 50 | 3200 | 3250 | 0 | 0 | 21 | 21 | 0 | 0 | 50156 | 58927
St. Louis | Y | ST. LOUIS | IS 70 E | SL0075 | 2.215 | 15.439 | 0 | Pavement resurfacing and upgrade guardrail from 0.2 mile west of Goodfellow Boulevard to Kingshighway Boulevard. | 2029 | 130 | 25 | 448 | 473 | 0 | 0 | 0 | 0 | 0 | 0 | 4738 | 5341
St. Louis | Y | ST. LOUIS | S OR 70 E | SL0249 | 1.31 | 3.076 | 0 | Pavement resurfacing, replace signage, upgrade lighting and guardrail from 0.2 mile west of Airflight Drive to Rte. 115 (Natural Bridge Road). | 2027 | 0 | 100 | 162 | 262 | 0 | 0 | 0 | 0 | 0 | 0 | 1684 | 1946
St. Louis | Y | ST. LOUIS | RT AC S | 6S3569 | 2.417 | 12.085 | 0 | Pavement resurfacing and upgrade pedestrian facilities to comply with the ADA Transition Plan from Pershall Road to north of St. Cyr Road. | 2026 | 1005 | 1623 | 0 | 1623 | 0 | 120 | 0 | 120 | 0 | 9149 | 0 | 11897
St. Louis | Y | ST. LOUIS | RT AC S | 6S3648 | 3.295 | 16.9 | 0 | Pavement resurfacing and repair pedestrian facilities from Lindbergh Boulevard to 0.1 mile south of I-270. | 2027 | 730 | 400 | 1065 | 1465 | 0 | 50 | 0 | 50 | 0 | 0 | 6514 | 8759
St. Louis | Y | ST. LOUIS | RT AC S | SL0247 | 0.114 | 0.589 | 0 | Upgrade signals at Hambletonian Drive, West Florissant Avenue and Netherton Drive. $745,000 Open Container funds. | 2027 | 0 | 150 | 250 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 1051 | 1451
St. Louis | Y | ST. LOUIS | RT D E | 6S3215B | 1.42 | 6.828 | 1 | Pavement resurfacing, reduce lanes and upgrade pedestrian facilities to comply with the ADA Transition Plan from west of Pennsylvania Avenue to west of Skinker Parkway and bridge rehabilitation over Metrolink. Project involves bridge A5328. | 2026 | 1600 | 941 | 0 | 941 | 105 | 0 | 0 | 0 | 0 | 9122 | 0 | 11768
St. Louis | Y | ST. LOUIS | RT D E | SL0027 | 3.191 | 16.66 | 0 | Pavement resurfacing and replace signage from Rte. 67 (Lindbergh Boulevard) to 0.1 mile east of I-170. | 2027 | 130 | 40 | 406 | 446 | 0 | 0 | 0 | 0 | 0 | 0 | 4278 | 4854
St. Louis | Y | ST. LOUIS | RT D E | SL0186 | 3.086 | 16.185 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan from Rte. 67 (Lindbergh Boulevard) to I-170. | 2026 | 540 | 534 | 0 | 534 | 0 | 120 | 0 | 120 | 0 | 2919 | 0 | 4113
St. Louis | Y | ST. LOUIS | RT D E | SL0232 | 7.643 | 38.808 | 0 | Signal optimization from Schuetz Road to Ogden Avenue. $2,169,690 Congestion Mitigation and Air Quality Improvement Program funds. | 2027 | 160 | 20 | 159 | 179 | 0 | 0 | 0 | 0 | 0 | 0 | 2444 | 2783
St. Louis | Y | ST. LOUIS | CST FROST AVE E | SL0243 | 0.112 | 0.516 | 0 | Pavement resurfacing, replace signals, upgrade pedestrian facilities on Frost Avenue and Airport Road under I-170. | 2028 | 0 | 38 | 123 | 161 | 0 | 0 | 0 | 0 | 0 | 0 | 1443 | 1604
St. Louis | Y | ST. LOUIS | RP IS270E TO IS70W W | SL0086 | 0.055 | 0.372 | 2 | Bridge replacement at the I-270 and I-70 interchange. Project involves bridges A3764 and A3766. | 2029 | 1430 | 900 | 3157 | 4057 | 0 | 0 | 0 | 0 | 0 | 0 | 46608 | 52095
St. Louis | Y | ST. LOUIS | RP IS270W TO IS170E E | SL0264 | 2.729 | 8.401 | 18 | Bridge washing on I-270, I-70, I-170, I-55, I-44, I-64, Rte. 100, Rte. 141 and Rte. 370. Project involves bridge A2926, A3764, A3766, A4650, A4651, A4652, A4653, A4881, A4882, A5093, A5411, A5412, A5682, A6370, A6371, A8013, A8014 and A8375. | 2030 | 0 | 5 | 167 | 172 | 0 | 0 | 0 | 0 | 0 | 0 | 1180 | 1352
St. Louis | Y | ST. LOUIS | RP IS64E TO IS170W W | 6I3634 | 0.237 | 0.508 | 2 | Bridge rehabilitation on ramps between I-170 and I-64. Project involves bridges A8013 and A8014. | 2027 | 262 | 75 | 50 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 670 | 1057
St. Louis | Y | ST. LOUIS | RP IS64W TO LONG RD S | SL0070 | 0.066 | 0.066 | 1 | Bridge replacement over I-64. Project involves bridge A2170. | 2029 | 90 | 90 | 320 | 410 | 0 | 0 | 0 | 0 | 0 | 0 | 3822 | 4322
St. Louis | Y | ST. LOUIS | RP MO141S TO IS44E E | SL0209 | 0.309 | 0.369 | 2 | Bridge deck sealing on southbound Rte. 141 entrance ramp to eastbound I-44 and Outer Road 44 entrance ramp to westbound I-44 over Rte. 141. Project involves bridge A8375 and A8501. | 2027 | 5 | 20 | 164 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 1716 | 1905
St. Louis | Y | ST. LOUIS | CST NORTH HANLEY RD S | SL0023 | 0.079 | 0.359 | 1 | Bridge rehabilitation over I-70. Project involves bridge A6175. | 2027 | 20 | 65 | 195 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 1145 | 1425
St. Louis | Y | ST. LOUIS | CST NORTH HANLEY RD S | SL0278 | 0.079 | 0.359 | 0 | Upgrade pedestrian facilities and replace signals at I-70. | 2027 | 0 | 70 | 134 | 204 | 0 | 5 | 0 | 5 | 0 | 0 | 449 | 658
St. Louis | Y | ST. LOUIS | RT U S | 6S3655 | 2.29 | 10.642 | 0 | Pavement resurfacing and upgrade pedestrian facilities from West Florissant Avenue to Woodrow Avenue. | 2027 | 430 | 300 | 730 | 1030 | 0 | 50 | 0 | 50 | 0 | 0 | 4369 | 5879
St. Louis | Y | ST. LOUIS CITY | MO 100 E | SL0252 | 6.264 | 32.187 | 0 | Upgrade signals from Prather Avenue to 4th Street. | 2028 | 0 | 175 | 121 | 296 | 0 | 0 | 10 | 10 | 0 | 0 | 1326 | 1632
St. Louis | Y | ST. LOUIS CITY | CST 11TH ST S | SL0286 | 0.625 | 1.256 | 2 | Pavement resurfacing, upgrade signals, signage, lighting, sidewalk from 0.1 mile north of Rte. 115 to Destrehan Street, upgrade striping on Rte. 115 and replace fencing over I-70. Project involves bridges A6238 and A6239. | 2029 | 0 | 200 | 279 | 479 | 0 | 0 | 0 | 0 | 0 | 0 | 3244 | 3723
St. Louis | Y | ST. LOUIS CITY | IS 44 E | SL0195 | 1.67 | 17.322 | 8 | Bridge washing from north of Biddle St. to Washington Ave, Gratiot St. to Park Ave, on I-64 Clayton Ave. to west of Compton Ave, 21st St. to 1st St. and on Rte. H I-70 to west of Hall St. Project involves bridges A1501, A1516, A3162, A3594, A7165, L0361 and L0815. | 2029 | 5 | 5 | 106 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 1453 | 1569
St. Louis | Y | ST. LOUIS CITY | IS 44 E | SL0205 | 0.583 | 5.143 | 2 | Bridge preventative maintenance north of Gratiot Street to Park Avenue. Project involves bridges A3162 and L0361. | 2028 | 10 | 25 | 139 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 1449 | 1623
St. Louis | Y | ST. LOUIS CITY | IS 44 E | SL0263 | 0.488 | 2.847 | 1 | Bridge rehabilitation from north of Biddle Street to Washington Avenue. Project involves bridge L0815. | 2030 | 0 | 100 | 6277 | 6377 | 0 | 0 | 0 | 0 | 0 | 0 | 35708 | 42085
St. Louis | Y | ST. LOUIS CITY | IS 44 W | SL0262 | 0.583 | 5.143 | 2 | Bridge painting from Garrot Street to Park Avenue. Project involves bridge A3162 and L0361. | 2030 | 0 | 50 | 5887 | 5937 | 0 | 0 | 0 | 0 | 0 | 0 | 43243 | 49180
St. Louis | Y | ST. LOUIS CITY | IS 44 W | SL0285 | 0 | 5.626 | 0 | Pavement resurfacing from 0.2 mile west of Grand Boulevard to west of Kingshighway Boulevard. | 2026 | 0 | 56 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 446 | 0 | 502
St. Louis | Y | ST. LOUIS CITY | IS 55 S | SL0205B | 0.209 | 1.672 | 1 | Bridge preventative maintenance over the Mississippi River. Project involves bridge A1500. $355,500 IDOT funds. | 2028 | 0 | 40 | 99 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 754 | 893
St. Louis | Y | ST. LOUIS CITY | IS 64 E | 6I3502 | 0.426 | 1.079 | 1 | Bridge replacement over Vandeventer Avenue and Clayton Avenue. Project involves bridge L0667. | 2027 | 3583 | 3178 | 3842 | 7020 | 0 | 1020 | 0 | 1020 | 0 | 0 | 56155 | 67778
St. Louis | Y | ST. LOUIS CITY | IS 64 E | SL0087 | 2.546 | 18.421 | 1 | Bridge rehabilitation and reconfigure ramps from Kingshighway Boulevard to Jefferson Avenue (Partial). Project involves bridge A3651. | 2027 | 1300 | 2500 | 2253 | 4753 | 0 | 1000 | 0 | 1000 | 0 | 0 | 27810 | 34863
St. Louis | Y | ST. LOUIS CITY | IS 64 W | 6I3574 | 1.049 | 3.263 | 1 | Bridge rehabilitation from west of Compton Avenue to west of Clayton Avenue. Project involves bridge A3594. | 2027 | 2326 | 1400 | 2129 | 3529 | 0 | 0 | 0 | 0 | 0 | 0 | 31381 | 37236
St. Louis | Y | ST. LOUIS CITY | IS 70 E | 6I3662 | 1.013 | 4.594 | 4 | Bridge washing over the Mississippi River on I-70, I-55 and I-255. Project involves bridges A1500, A1850, A4936 and A6500. $576,000 IDOT funds. | 2026 | 17 | 93 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 1152 | 0 | 1262
St. Louis | Y | ST. LOUIS CITY | IS 70 E | SL0084 | 0.527 | 2.261 | 1 | Bridge rehabilitation on the Stan Musial Veterans Memorial Bridge over the Mississippi River. Project involves bridge A6500. $6,333,016 IDOT funds. | 2028 | 3 | 150 | 941 | 1091 | 0 | 0 | 0 | 0 | 0 | 0 | 13437 | 14531
St. Louis | Y | ST. LOUIS CITY | RT D W | 6S3438 | 5.777 | 32.203 | 0 | Pavement resurfacing, reduce lanes, upgrade signage and signals from west of Skinker Parkway to Tucker Boulevard. | 2026 | 417 | 1057 | 0 | 1057 | 0 | 10 | 0 | 10 | 0 | 9571 | 0 | 11055
St. Louis | Y | ST. LOUIS CITY | CST DR MARTIN LUTHER KING BRG W | SL0189 | 0.509 | 1.718 | 2 | Payment to IDOT to add navigation lighting on the Martin Luther King Bridge and Clark Bridge over the Mississippi River. Project involves bridges A4278 and A4856. | 2027 | 0 | 0 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 321
St. Louis | Y | ST. LOUIS CITY | RT H S | SL0065 | 3.545 | 9.359 | 0 | Pavement resurfacing and modify lighting from I-270 to Hall Street. | 2027 | 52 | 52 | 244 | 296 | 0 | 0 | 0 | 0 | 0 | 0 | 2886 | 3234
St. Louis | Y | ST. LOUIS CITY | CST WEBER RD E | 6S3442 | 0.132 | 0.557 | 3 | Bridge replacement on Weber Road, Loughborough Avenue over I-55, ramp realignment on northbound I-55 ramp to Idaho Avenue and on ramp at Loughborough Avenue. Project involves bridges A0918 and A1077. | 2027 | 715 | 330 | 891 | 1221 | 0 | 250 | 0 | 250 | 0 | 0 | 13222 | 15408
St. Louis | Y | ST. LOUIS CITY | CST WEST FLORISSANT AVE S | 6S3552 | 0.561 | 1.49 | 4 | Bridge rehabilitation over Terra West Belt Railroad and I-70, Rte. 366 and Rte. 30 over the River Des Peres Drainage Channel and Rte. 115 over Terra West Belt Railroad. Project involves bridges A0482, A3208, A7167 and A7168. | 2028 | 45 | 20 | 377 | 397 | 0 | 0 | 0 | 0 | 0 | 0 | 3195 | 3637
St. Louis | Y | VARIOUS | Various | 5B0800U | 0 | 0 | 21 | Payback beginning in SFY 2008 for Safe and Sound bridges in the St. Louis District. | 2033 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 19448 | 1310 | 5240 | 26028
St. Louis | Y | VARIOUS | Various | 6P3221 | 0 | 0 | 0 | Payment to St. Charles County for engineering services contract for regional ITS Data Sharing Initiative and Phase 1 of data exchange between MoDOT and St. Charles County. | 2026 | 0 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 156
St. Louis | Y | VARIOUS | Various | 6P3510 | 0 | 0 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan throughout the St. Louis District. | 2026 | 2100 | 1320 | 0 | 1320 | 0 | 1345 | 0 | 1345 | 0 | 17447 | 0 | 22212
St. Louis | Y | VARIOUS | Various | 6P3510C | 0 | 0 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan throughout the St. Louis District. | 2026 | 1166 | 1369 | 0 | 1369 | 1719 | 0 | 0 | 0 | 0 | 9748 | 0 | 14002
St. Louis | Y | VARIOUS | Various | 6Q2025D | 0 | 0 | 0 | ITS operations, contract staffing and professional services at the Traffic Management Center building in the St. Louis District. | 2026 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4050 | 0 | 4054
St. Louis | Y | VARIOUS | Various | 6Q2026B | 0 | 0 | 0 | Emergency response operations and staffing in the St. Louis District. | 2026 | 4 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2520 | 0 | 2525
St. Louis | Y | VARIOUS | Various | 6Q2026C | 0 | 0 | 0 | ITS operations, MoDOT staff, equipment maintenance and Transportation Management Center (TMC) operations at the TMC building in the St. Louis District. | 2026 | 4 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 900 | 0 | 905
St. Louis | Y | VARIOUS | Various | 6Q2026D | 0 | 0 | 0 | ITS operations, contract staffing and professional services at the TMC building in the St. Louis District. | 2026 | 4 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 4253 | 0 | 4258
St. Louis | Y | VARIOUS | Various | 6Q2026E | 0 | 0 | 0 | ITS asset management maintenance and operations at various locations in the St. Louis District. | 2026 | 4 | 134 | 0 | 134 | 0 | 0 | 0 | 0 | 0 | 2345 | 0 | 2483
St. Louis | Y | VARIOUS | Various | 6Q2026F | 0 | 0 | 0 | ITS system preservation, repairs and upgrades throughout the St. Louis District. | 2026 | 4 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1750 | 0 | 1755
St. Louis | Y | VARIOUS | Various | 6Q2026G | 0 | 0 | 0 | Advanced Traffic Management System (ATMS) maintenance contract throughout the St. Louis District. | 2026 | 4 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 700 | 0 | 705
St. Louis | Y | VARIOUS | Various | 6Q2026H | 0 | 0 | 0 | ITS network support throughout the St. Louis District. | 2026 | 3 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 554
St. Louis | Y | VARIOUS | Various | SL0096B | 0 | 0 | 0 | Emergency response operations and staffing in the St. Louis District. | 2027 | 3 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2596 | 2601
St. Louis | Y | VARIOUS | Various | SL0096C | 0 | 0 | 0 | ITS operations, MoDOT staff, equipment maintenance and operations at the Traffic Management Center building in the St. Louis District. | 2027 | 3 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 927 | 932
St. Louis | Y | VARIOUS | Various | SL0096D | 0 | 0 | 0 | ITS operations, contract staffing and professional services at the Traffic Management Center building in the St. Louis District. | 2027 | 3 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4381 | 4386
St. Louis | Y | VARIOUS | Various | SL0096E | 0 | 0 | 0 | ITS asset management and operations at various locations in the St. Louis District. | 2027 | 3 | 1 | 134 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 2415 | 2553
St. Louis | Y | VARIOUS | Various | SL0096F | 0 | 0 | 0 | ITS system preservation, repairs and upgrades throughout the St. Louis District. | 2027 | 3 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1838 | 1843
St. Louis | Y | VARIOUS | Various | SL0096G | 0 | 0 | 0 | Advanced Traffic Management System maintenance contract throughout the St. Louis District. | 2027 | 3 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 605
St. Louis | Y | VARIOUS | Various | SL0096H | 0 | 0 | 0 | ITS network support throughout the St. Louis District. | 2027 | 3 | 1 | 40 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 594
St. Louis | Y | VARIOUS | Various | SL0097 | 0 | 0 | 0 | Job Order Contracting for asphalt pavement repair at various major route locations in the St. Louis District. | 2026 | 3 | 211 | 0 | 211 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 3214
St. Louis | Y | VARIOUS | Various | SL0098 | 0 | 0 | 1 | Job Order Contracting for bridge repairs at various major route locations in the St. Louis District. | 2027 | 3 | 1 | 155 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 2266 | 2425
St. Louis | Y | VARIOUS | Various | SL0099 | 0 | 0 | 0 | Job Order Contracting for concrete pavement repair at various locations in the St. Louis District. | 2026 | 3 | 386 | 0 | 386 | 0 | 0 | 0 | 0 | 0 | 5500 | 0 | 5889
St. Louis | Y | VARIOUS | Various | SL0100 | 0 | 0 | 0 | Job Order Contracting for fence repair at various locations in the St. Louis District. | 2026 | 3 | 47 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 700
St. Louis | Y | VARIOUS | Various | SL0101 | 0 | 0 | 0 | Job Order Contracting for guard cable repair at various locations in the St. Louis District. | 2026 | 3 | 71 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1074
St. Louis | Y | VARIOUS | Various | SL0102 | 0 | 0 | 0 | Job Order Contracting for guardrail repair at various locations in St. Louis City and St. Louis County. | 2027 | 3 | 1 | 309 | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 4532 | 4845
St. Louis | Y | VARIOUS | Various | SL0103 | 0 | 0 | 0 | Job Order Contracting for guardrail repair at various locations in Franklin and Jefferson Counties. | 2027 | 3 | 1 | 71 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 1030 | 1105
St. Louis | Y | VARIOUS | Various | SL0104 | 0 | 0 | 0 | Job Order Contracting for guardrail repair at various locations in St. Charles County. | 2027 | 3 | 1 | 71 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 1030 | 1105
St. Louis | Y | VARIOUS | Various | SL0105 | 0 | 0 | 0 | On-call work zone enforcement at various locations in the St. Louis District. | 2026 | 3 | 141 | 0 | 141 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2144
St. Louis | Y | VARIOUS | Various | SL0184 |  | 0 | 0 | Upgrade ITS CCTV and communications equipment on various routes in the St. Louis District. $3,591,585 Carbon Reduction Program funds. | 2026 | 355 | 281 | 0 | 281 | 0 | 0 | 0 | 0 | 0 | 4516 | 0 | 5152
St. Louis | Y | VARIOUS | Various | SL0191 | 0 | 0 | 0 | On-call work zone enforcement at various locations in the St. Louis District. | 2027 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2003
St. Louis | Y | VARIOUS | Various | SL0203 |  | 0 | 0 | Replace ITS dynamic message signs and communications equipment at various locations in the St. Louis District. | 2026 | 5 | 279 | 0 | 279 | 0 | 0 | 0 | 0 | 0 | 2024 | 0 | 2308
St. Louis | Y | VARIOUS | Various | SL0204 |  | 0 | 0 | Replace ITS dynamic message signs and communications equipment at various locations in the St. Louis District. | 2027 | 5 | 5 | 274 | 279 | 0 | 0 | 0 | 0 | 0 | 0 | 2085 | 2369
St. Louis | Y | VARIOUS | Various | SL0216 |  | 0 | 0 | Pavement repair at various locations in the St. Louis District. | 2027 | 1 | 1 | 148 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 1576 | 1726
St. Louis | Y | VARIOUS | Various | SL0219B |  | 0 | 0 | Emergency response operations and staffing in the St. Louis District. | 2028 | 1 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2674 | 2678
St. Louis | Y | VARIOUS | Various | SL0219C |  | 0 | 0 | ITS operations, MoDOT staff, equipment maintenance and operations at the Traffic Management Center building in the St. Louis District. | 2028 | 1 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 990 | 994
St. Louis | Y | VARIOUS | Various | SL0219D |  | 0 | 0 | ITS operations, contract staffing and professional services at the Traffic Management Center building in the St. Louis District. | 2028 | 1 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 4600 | 4604
St. Louis | Y | VARIOUS | Various | SL0219E |  | 0 | 0 | ITS asset management and operations at various locations in the St. Louis District. | 2028 | 1 | 1 | 135 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 2488 | 2625
St. Louis | Y | VARIOUS | Various | SL0219F |  | 0 | 0 | ITS system preservation, repairs and upgrades throughout the St. Louis District. | 2028 | 1 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1930 | 1934
St. Louis | Y | VARIOUS | Various | SL0219G |  | 0 | 0 | Advanced Traffic Management System maintenance contract throughout the St. Louis District. | 2028 | 1 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 664
St. Louis | Y | VARIOUS | Various | SL0219H |  | 0 | 0 | ITS network support throughout the St. Louis District. | 2028 | 1 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 584
St. Louis | Y | VARIOUS | Various | SL0220B |  | 0 | 0 | Emergency response operations and staffing in the St. Louis District. | 2029 | 1 | 1 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2754 | 2759
St. Louis | Y | VARIOUS | Various | SL0220C |  | 0 | 0 | ITS operations, MoDOT staff, equipment maintenance and operations at the Traffic Management Center building in the St. Louis District. | 2029 | 1 | 1 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1040 | 1045
St. Louis | Y | VARIOUS | Various | SL0220D |  | 0 | 0 | ITS operations, contract staffing and professional services at the Traffic Management Center building in the St. Louis District. | 2029 | 1 | 1 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 4680 | 4685
St. Louis | Y | VARIOUS | Various | SL0220E |  | 0 | 0 | ITS asset management and operations at various locations in the St. Louis District. | 2029 | 1 | 1 | 136 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 2562 | 2700
St. Louis | Y | VARIOUS | Various | SL0220F |  | 0 | 0 | ITS system preservation, repairs and upgrades throughout the St. Louis District. | 2029 | 1 | 1 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 2027 | 2032
St. Louis | Y | VARIOUS | Various | SL0220G |  | 0 | 0 | Advanced Traffic Management System maintenance contract throughout the St. Louis District. | 2029 | 1 | 1 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 665
St. Louis | Y | VARIOUS | Various | SL0220H |  | 0 | 0 | ITS network support throughout the St. Louis District. | 2029 | 1 | 1 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 585
St. Louis | Y | VARIOUS | Various | SL0221 |  | 0 | 0 | Upgrade striping at various locations in the St. Louis District. $2,267,000 Open Container funds. | 2027 | 10 | 50 | 280 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 4120 | 4460
St. Louis | Y | VARIOUS | Various | SL0222 |  | 0 | 0 | Safety improvements at various locations in St. Louis and St. Charles Counties and St. Louis City. $233,000 Open Container funds. | 2027 | 50 | 100 | 289 | 389 | 0 | 0 | 0 | 0 | 0 | 0 | 2775 | 3214
St. Louis | Y | VARIOUS | Various | SL0223 |  | 0 | 0 | Payment for bicycle and pedestrian safety action plan at various locations in the St. Louis District. | 2026 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 202
St. Louis | Y | VARIOUS | Various | SL0255 |  | 0 | 0 | Pavement repair at various locations in the St. Louis District. | 2028 | 0 | 1 | 149 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 1623 | 1773
St. Louis | Y | VARIOUS | Various | SL0256 |  | 0 | 0 | Pavement preservation treatment at various locations in the St. Louis District. | 2028 | 0 | 1 | 82 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 889 | 972
St. Louis | Y | VARIOUS | Various | SL0257B |  | 0 | 0 | Emergency response operations and staffing in the St. Louis District. | 2030 | 0 | 1 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2837 | 2842
St. Louis | Y | VARIOUS | Various | SL0257C |  | 0 | 0 | ITS operations, MoDOT staff, equipment maintenance and operations at the Traffic Management Center building in the St. Louis District. | 2030 | 0 | 1 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1071 | 1076
St. Louis | Y | VARIOUS | Various | SL0257D |  | 0 | 0 | ITS operations, contract staffing and professional services at the Transportation Management Center in the St. Louis District. | 2030 | 0 | 1 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 4680 | 4685
St. Louis | Y | VARIOUS | Various | SL0257E |  | 0 | 0 | ITS asset management maintenance and operations at various locations in the St. Louis District. | 2030 | 0 | 1 | 137 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 2639 | 2777
St. Louis | Y | VARIOUS | Various | SL0257F |  | 0 | 0 | ITS system preservation, repairs and upgrades throughout the St. Louis District. | 2030 | 0 | 1 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2128 | 2133
St. Louis | Y | VARIOUS | Various | SL0257G |  | 0 | 0 | Advanced Traffic Management System maintenance contract throughout the St. Louis District. | 2030 | 0 | 1 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 665
St. Louis | Y | VARIOUS | Various | SL0257H |  | 0 | 0 | ITS network support throughout the St. Louis District. | 2030 | 0 | 1 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 585
St. Louis | Y | VARIOUS | Various | SL0258 |  | 0 | 0 | On-call work zone enforcement at various locations in the St. Louis District. | 2028 | 0 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 2003
St. Louis | Y | VARIOUS | Various | SL0265 |  | 0 | 0 | Safety improvements at various locations in the St. Louis District. | 2028 | 0 | 5 | 730 | 735 | 0 | 0 | 0 | 0 | 0 | 0 | 4626 | 5361
St. Louis | Y | VARIOUS | Various | SL0266 |  | 0 | 0 | Upgrade striping at various locations in the St. Louis District. | 2028 | 0 | 10 | 315 | 325 | 0 | 0 | 0 | 0 | 0 | 0 | 4244 | 4569
St. Louis | Y | VARIOUS | Various | SL0270 |  | 0 | 0 | Job Order Contracting for asphalt pavement repair at various major route locations in the St. Louis District. | 2028 | 0 | 10 | 230 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 3183 | 3423
St. Louis | Y | VARIOUS | Various | SL0271 |  | 0 | 0 | Job Order Contracting for concrete pavement repair at various major route locations in the St. Louis District. | 2028 | 0 | 10 | 300 | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 4244 | 4554
St. Louis | Y | VARIOUS | Various | SL0272 |  | 0 | 0 | Job Order Contracting for fence repair at various locations in the St. Louis District. | 2028 | 0 | 5 | 56 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 690 | 751
St. Louis | Y | VARIOUS | Various | SL0273 |  | 0 | 0 | Job Order Contracting for guard cable repair at various locations in the St. Louis District. | 2028 | 0 | 5 | 80 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 1061 | 1146
St. Louis | Y | VARIOUS | Various | SL0279 |  | 0 | 0 | Upgrade striping at various intersections in the St. Louis District. $960,000 Open Container funds. | 2028 | 0 | 10 | 344 | 354 | 0 | 0 | 0 | 0 | 0 | 0 | 4395 | 4749
St. Louis | Y | VARIOUS | Various | SL0283 |  | 0 | 0 | Repair signals, flashers, signage and lighting at various location in the St. Louis District. | 2027 | 0 | 45 | 40 | 85 | 0 | 1 | 0 | 1 | 0 | 0 | 603 | 689
Southwest | N | BARRY | MO 248 E | SR0119 | 0.398 | 0.796 | 1 | Bridge replacement over Flat Creek. Project involves bridge J0382. | 2026 | 761 | 445 | 0 | 445 | 0 | 72 | 0 | 72 | 0 | 3970 | 0 | 5248
Southwest | N | BARRY | MO 37 S | 7S2182 | 0.678 | 1.447 | 0 | Rebuild pavement and sidewalk and intersection reconfiguration on Central Ave from Cleveland St to Bond St and add roundabout at Broadway St in Monett. Design, right of way acquisition by Monett. $2,163,000 Cost Share, $2,786,196 Monett and $399,826 Trans. Alt. funds. | 2026 | 51 | 52 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 5349 | 0 | 5452
Southwest | N | BARRY | MO 39 S | SR0336 | 0.276 | 0.552 | 1 | Bridge rehabilitation over Table Rock Lake in Shell Knob. Project involves bridge A0260. | 2030 | 0 | 2 | 677 | 679 | 0 | 0 | 0 | 0 | 0 | 0 | 10843 | 11522
Southwest | N | BARRY | US 60 E | SR0021 | 18.051 | 47.898 | 0 | Pavement resurfacing, add roundabout at County Road 1100 and add turn lanes at County Roads 1160, 1180, 1200, 1235, 2000 and 2210 from Rte. 37 in Monett to Rte. 14 in Marionville. | 2027 | 1656 | 15 | 2333 | 2348 | 0 | 365 | 0 | 365 | 0 | 0 | 11079 | 15448
Southwest | N | BARRY | MO 86 E | SR0120 | 0.128 | 0.256 | 1 | Bridge rehabilitation over Table Rock Lake. Project involves bridge A0581. | 2028 | 310 | 250 | 941 | 1191 | 0 | 0 | 0 | 0 | 0 | 0 | 4380 | 5881
Southwest | N | BARRY | MO 97 S | SR0133 | 0.099 | 0.198 | 1 | Bridge replacement over Capps Creek 0.2 mile south of County Road 2040. Project involves bridge L0573. | 2026 | 115 | 988 | 0 | 988 | 0 | 7 | 0 | 7 | 0 | 1527 | 0 | 2637
Southwest | N | BARRY | RT BB E | 7S3493 | 5.766 | 11.532 | 0 | Pavement resurfacing from Rte. 37 to County Road 2060. | 2027 | 27 | 1 | 65 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 568 | 661
Southwest | N | BARTON | US 160 E | SR0002 | 0.059 | 0.118 | 1 | Bridge replacement over North Fork Spring River north of Golden City. Project involves bridge H0901. | 2027 | 120 | 316 | 348 | 664 | 0 | 2 | 0 | 2 | 0 | 0 | 2005 | 2791
Southwest | N | BARTON | MO 43 S | SR0284 | 0.082 | 0.164 | 3 | Bridge rehabilitation and guardrail over BNSF Railway, East Fork of Dry Wood Creek, South Fork of Little North Fork. Project involves bridges A2533, A2870 and A2936. | 2027 | 20 | 100 | 283 | 383 | 0 | 0 | 0 | 0 | 0 | 0 | 1695 | 2098
Southwest | N | BARTON | IS 49 S | 7I3426 | 0.046 | 0.092 | 1 | Bridge improvement on the southbound lanes over the North Fork Spring River. Project involves bridge G0578. | 2028 | 70 | 200 | 1122 | 1322 | 0 | 0 | 0 | 0 | 0 | 0 | 3678 | 5070
Southwest | N | BARTON | RT V E | SR0096 | 0.702 | 1.404 | 1 | Bridge replacement and road realignment over Little Drywood Creek 4.4 miles west of I-49. Project involves bridge P0343. | 2028 | 30 | 200 | 778 | 978 | 0 | 0 | 15 | 15 | 0 | 0 | 3101 | 4124
Southwest | N | BATES | MO 18 E | 7P3511 | 2.092 | 2.092 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan on Rte. 18 and on Old Route 71 from Rte. 18 to Ada Street in Adrian, Rte. Y in Merwin and Loop 49, Rte. 52 and Rte. H in Butler. | 2026 | 53 | 34 | 0 | 34 | 2 | 0 | 0 | 0 | 0 | 156 | 0 | 245
Southwest | N | BATES | MO 18 E | SR0308 | 14.137 | 28.274 | 0 | Pavement resurfacing from Rte. Y near Merwin to I-49 in Adrian. | 2028 | 2 | 10 | 196 | 206 | 0 | 0 | 0 | 0 | 0 | 0 | 1403 | 1611
Southwest | N | BATES | IS 49 S | SR0179 | 44.817 | 0 | 0 | Job Order Contracting for pavement repair from the Cass County line to Rte. 54 in Vernon County. | 2026 | 5 | 21 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 106
Southwest | N | BATES | LP 49 S | SR0309 | 4.53 | 9.06 | 0 | Pavement resurfacing and new shoulders with rumble stripes from Rte. F in Passaic to Rte. 52 in Butler. | 2028 | 5 | 10 | 167 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 1309 | 1491
Southwest | N | BATES | MO 52 E | SR0081 | 0.095 | 0.19 | 0 | Replace railroad underpass and add sidewalk on Fort Scott Street in Butler. | 2029 | 706 | 100 | 1490 | 1590 | 0 | 0 | 2387 | 2387 | 0 | 0 | 10763 | 15446
Southwest | N | BATES | MO 52 E | SR0159 | 1.849 | 3.967 | 0 | Pavement resurfacing and safety improvements from I-49 north interchange to I-49 south interchange in Butler. | 2028 | 7 | 5 | 108 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 813 | 933
Southwest | N | BATES | MO 52 E | SR0310 | 27.305 | 27.346 | 1 | Pavement resurfacing from Kansas State line to Rte. BB in Bates County and bridge rehabilitation over I-49. Project involves bridge A2158. | 2026 | 130 | 646 | 0 | 646 | 0 | 0 | 0 | 0 | 0 | 4946 | 0 | 5722
Southwest | N | BATES | RT D E | SR0134 | 0.089 | 0.178 | 1 | Bridge replacement and replace guardrail over I-49 near Passaic. Project involves bridge A2156. | 2026 | 272 | 951 | 0 | 951 | 0 | 0 | 0 | 0 | 0 | 3045 | 0 | 4268
Southwest | N | BENTON | MO 52 E | 7S3398 | 5.804 | 11.608 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan including on Rtes. F and U in Cole Camp, Rte. C in Lincoln, Rtes. J and V in Calhoun and Rte. N in Blairstown. | 2026 | 383 | 138 | 0 | 138 | 20 | 0 | 0 | 0 | 0 | 657 | 0 | 1198
Southwest | N | BENTON | US 65 N | SR0109 | 0.146 | 0.422 | 0 | Add roundabout at Rte. 7 south junction. | 2029 | 158 | 130 | 746 | 876 | 0 | 0 | 155 | 155 | 0 | 0 | 4000 | 5189
Southwest | N | BENTON | MO 7 S | SR0110 | 20.903 | 41.945 | 0 | Add roundabout at Cold Spring Avenue, add pedestrian signal at Main Street in Warsaw and add safety signage at various locations from 0.3 mile west of Rte. C to Rte. 65 in Warsaw. | 2026 | 283 | 685 | 0 | 685 | 268 | 0 | 0 | 0 | 0 | 2155 | 0 | 3391
Southwest | N | BENTON | MO 7 S | SR0318 | 1.971 | 3.942 | 3 | Bridge rehabilitation over Truman Lake near Warsaw, Long Shoal and south of Whitakerville. Project involves bridges A3464, A3465 and A3689. | 2029 | 10 | 10 | 1065 | 1075 | 0 | 0 | 0 | 0 | 0 | 0 | 5036 | 6121
Southwest | N | BENTON | MO 7 S | SR0345 | 15.632 | 0 | 0 | Add safety signage at various locations from Rte. 65 to 0.3 mile east of Rte. AA. | 2026 | 0 | 16 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 50
Southwest | N | BENTON | RT KK S | SR0108 | 20.648 | 41.296 | 0 | Pavement resurfacing and add rumble stripes from Rte. 7 to end of route and on Rte. Z from Rte. 13 to Rte. 7. | 2028 | 95 | 20 | 533 | 553 | 0 | 0 | 0 | 0 | 0 | 0 | 4279 | 4927
Southwest | N | BENTON | RT P E | SR0111 | 15.578 | 31.156 | 0 | Pavement resurfacing from Rte. ZZ to Rte. 65 and Main Street from 1st Street to 3rd Street in Ionia, Rte. F from Rte. 52 to end of state maintenance and Rte. U from Whiteman Road to Rte. 52 in Cole Camp. | 2028 | 25 | 10 | 201 | 211 | 0 | 0 | 0 | 0 | 0 | 0 | 1595 | 1831
Southwest | N | BENTON | RT T N | SR0108B | 9.181 | 18.362 | 1 | Pavement resurfacing and add rumble stripes from Rte. C to Rte. 65. Project involves bridge A3692. | 2028 | 28 | 10 | 268 | 278 | 0 | 0 | 0 | 0 | 0 | 0 | 2209 | 2515
Southwest | N | CEDAR | MO 32 E | 7P3397 | 1.579 | 2.923 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan on East Street/West Street and Rte. 39 (South Street) in Stockton. | 2026 | 175 | 174 | 0 | 174 | 0 | 9 | 0 | 9 | 0 | 612 | 0 | 970
Southwest | N | CEDAR | MO 32 E | SR0059 | 1.555 | 3.11 | 1 | Road realignment at Rte. CC, County Road 1350 and 2.3 miles west of Bolivar, bridge replacement over Barren Creek and add turn lanes at Rte. 245 and Rte. 123. Project involves bridge H0021. | 2027 | 848 | 252 | 1328 | 1580 | 0 | 359 | 0 | 359 | 0 | 0 | 7909 | 10696
Southwest | N | CEDAR | MO 39 S | 7P3485B | 0.036 | 0.072 | 1 | Bridge replacement over Cedar Creek. Project involves bridge X0190. | 2027 | 168 | 200 | 430 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 2038 | 2836
Southwest | N | CEDAR | US 54 E | SR0033 | 25.067 | 50.218 | 0 | Pavement resurfacing from 0.1 mile east of Rte. 32 in El Dorado Springs to Rte. MM. | 2027 | 82 | 120 | 660 | 780 | 0 | 0 | 0 | 0 | 0 | 0 | 5654 | 6516
Southwest | N | CEDAR | RT HH S | SR0324B | 61.855 | 61.855 | 0 | Pavement preservation treatment in Bates, Benton, Cedar, Henry and Vernon Counties. | 2026 | 0 | 117 | 0 | 117 | 0 | 0 | 0 | 0 | 0 | 1815 | 0 | 1932
Southwest | N | CEDAR | RT N E | SR0212 | 0.129 | 0.258 | 1 | Bridge rehabilitation over Big Sac River. Project involves bridge L0537. | 2027 | 62 | 24 | 190 | 214 | 0 | 0 | 0 | 0 | 0 | 0 | 1162 | 1438
Southwest | Y | CHRISTIAN | MO 14 E | 8P0583B | 0.56 | 0.746 | 0 | Add lanes and add sidewalk on South Street from 6th Avenue to 14th Avenue in Ozark. | 2027 | 200 | 1013 | 1223 | 2236 | 0 | 548 | 0 | 548 | 0 | 0 | 4639 | 7623
Southwest | N | CHRISTIAN | US 65 S | SR0105 | 16.181 | 65.403 | 0 | Add climbing lanes, guard cable and safety signage at various locations and add northbound right turn lane at Saddlebrooke Drive from 0.4 mile north of Rte. EE in Christian County to 0.8 mile north of Rte. 76 in Taney County. $3,259,000 Open Container funds. | 2029 | 600 | 50 | 2104 | 2154 | 0 | 0 | 69 | 69 | 0 | 0 | 9031 | 11854
Southwest | Y | CHRISTIAN | RT CC E | 8S0736D | 0.805 | 1.692 | 0 | Add lanes, sidewalk and shared use path from Fremont Road to 22nd Street in Ozark. Design, right of way acquisition and utility relocation by Ozark. $2,021,449 Cost Share, $2,128,397 STBG-Urban and $532,099 Ozark funds. | 2026 | 140 | 479 | 0 | 479 | 0 | 0 | 0 | 0 | 0 | 4682 | 0 | 5301
Southwest | Y | CHRISTIAN | RT CC E | 8S0736E | 0.18 | 0.376 | 1 | Add intersection turn lane, extend culvert and upgrade sidewalk and guardrail at 22nd Street in Ozark. Project involves culvert A3861. | 2026 | 657 | 635 | 0 | 635 | 0 | 368 | 0 | 368 | 0 | 2616 | 0 | 4276
Southwest | N | CHRISTIAN | RT EE E | SR0061 | 3.713 | 7.551 | 0 | Safety improvements at various locations from Rte. 160 in Highlandville to Rte. 65 and add roundabout at Rte. 160. | 2027 | 846 | 567 | 1419 | 1986 | 0 | 1100 | 0 | 1100 | 0 | 0 | 8670 | 12602
Southwest | N | CHRISTIAN | RT EE E | SR0311 | 3.64 | 7.28 | 0 | Pavement resurfacing from Rte. 160 in Highlandville to Rte. 65 near Ozark. | 2027 | 32 | 2 | 54 | 56 | 0 | 2 | 0 | 2 | 0 | 0 | 456 | 546
Southwest | N | CHRISTIAN | RT T E | SR0324 | 100.803 | 100.803 | 0 | Pavement preservation treatment in Barry, Christian, Jasper, McDonald, Newton, Taney and Webster Counties. | 2026 | 0 | 201 | 0 | 201 | 0 | 0 | 0 | 0 | 0 | 3084 | 0 | 3285
Southwest | N | CHRISTIAN | RT W S | SR0041 | 7.051 | 14.102 | 0 | Pavement resurfacing from 0.1 mile south of Timbercrest Road to end of state maintenance. | 2029 | 14 | 5 | 116 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 939 | 1074
Southwest | Y | CHRISTIAN | RT W S | SU0012 | 0.995 | 2.006 | 0 | Pavement resurfacing from Rte. 14 to south of Timbercrest Road near Ozark. | 2029 | 5 | 1 | 25 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 191 | 222
Southwest | N | DADE | US 160 E | SR0104 | 0.573 | 1.146 | 0 | Road realignment from County Road 203 to Rte. 245. | 2027 | 207 | 38 | 262 | 300 | 0 | 92 | 0 | 92 | 0 | 0 | 1590 | 2189
Southwest | N | DADE | RT H S | SR0302 | 0.294 | 0.588 | 1 | Bridge rehabilitation over Stockton Lake. Project involves bridge A2929. | 2028 | 10 | 5 | 84 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 438 | 537
Southwest | N | DALLAS | MO 64 E | 7P3542 | 0.427 | 0.854 | 1 | Bridge replacement over the Niangua River and road realignment near Bennett Spring State Park. Project involves bridge J0782. | 2027 | 1128 | 1042 | 1850 | 2892 | 0 | 184 | 0 | 184 | 0 | 0 | 10025 | 14229
Southwest | N | DALLAS | US 65 S | SR0089 | 6.41 | 13.005 | 0 | Add roundabouts at Rte. 73 and at Truman Road in Buffalo and add passing lane from Rte. 64 to Rte. D in Urbana. | 2029 | 650 | 100 | 1962 | 2062 | 0 | 0 | 1137 | 1137 | 0 | 0 | 11681 | 15530
Southwest | N | GREENE | MO 123 S | SR0165 | 0.125 | 0.25 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan in Walnut Grove. | 2026 | 68 | 38 | 0 | 38 | 2 | 0 | 0 | 0 | 0 | 47 | 0 | 155
Southwest | Y | GREENE | MO 125 S | SU0174 | 0.041 | 0.164 | 1 | Bridge rehabilitation over I-44 in Strafford. Project involves bridge A5400. | 2028 | 250 | 5 | 250 | 255 | 0 | 0 | 0 | 0 | 0 | 0 | 1299 | 1804
Southwest | Y | GREENE | MO 13 S | SU0093 | 1.009 | 4.285 | 1 | Capital improvement on Kansas Expressway from Grand Street to Rte. 413 (Sunshine Street) in Springfield. Project involves bridge A3259. | 2028 | 430 | 350 | 1763 | 2113 | 0 | 0 | 26 | 26 | 0 | 0 | 8188 | 10757
Southwest | N | GREENE | US 160 E | SR0136 | 0.069 | 0.138 | 1 | Culvert replacement over Hamilton Creek between Thurmond Avenue and Perryman Avenue in Ash Grove. Project involves bridge H0468. | 2027 | 70 | 60 | 96 | 156 | 0 | 26 | 0 | 26 | 0 | 0 | 556 | 808
Southwest | Y | GREENE | US 160 E | SU0051 | 0.248 | 1.052 | 3 | Bridge painting over Rte. 60 (James River Freeway), on Republic Street over Rte. 60 and on Rte. 266 (Chestnut Expressway) over I-44 in Springfield. Project involves bridges A4146, A4184 and A0598. | 2028 | 44 | 40 | 334 | 374 | 0 | 0 | 0 | 0 | 0 | 0 | 1807 | 2225
Southwest | Y | GREENE | US 160 E | SU0156 | 6.356 | 31.795 | 1 | Pavement improvement from Rte. 60 in Springfield to Rte. 14 in Nixa. Project involves bridge J0930. | 2028 | 92 | 12 | 327 | 339 | 0 | 0 | 0 | 0 | 0 | 0 | 2913 | 3344
Southwest | Y | GREENE | MO 266 E | SU0080 | 0.096 | 0.192 | 0 | Add roundabouts at Rte. AB and at Rte. B west of Springfield. $919,000 Open Container funds. | 2027 | 577 | 2 | 594 | 596 | 101 | 0 | 0 | 0 | 0 | 0 | 2881 | 4155
Southwest | Y | GREENE | MO 360 E | SU0014 | 3.679 | 14.489 | 0 | Pavement resurfacing and replacement of rumble stripes from I-44 to Rte. 60 in Springfield. | 2029 | 18 | 2 | 183 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 615 | 818
Southwest | Y | GREENE | MO 413 N | SU0200B | 0.304 | 1.922 | 0 | Signal fiber interconnect from Zimmer Road to east of Rte. 160 (West Bypass). | 2026 | 0 | 10 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 75 | 0 | 85
Southwest | N | GREENE | IS 44 E | SR0275 | 0.212 | 0.838 | 7 | Bridge rehabilitation over Pond Creek and on northbound Rte. 65 over Lake Taneycomo, Rte. 13 over Bus. 13, Rte. 14 over Green Valley Creek, Rte. B over BNSF and Rte. AA over Wheeler Creek near Elsey. Project involves bridges A0176, A2597, A2823, A3069, A7914 and A8329. | 2027 | 70 | 60 | 283 | 343 | 0 | 0 | 0 | 0 | 0 | 0 | 1745 | 2158
Southwest | Y | GREENE | IS 44 E | SU0197 | 37.252 | 0 | 0 | Job Order Contracting for pavement repair on I-44, Rte. 65 and Rte. 60 in the urban Southwest District. | 2026 | 5 | 65 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 370
Southwest | Y | GREENE | LP 44 E | 8P3144 | 9.213 | 45.363 | 0 | Signal upgrades at I-44, Main Avenue, Campbell Avenue, Benton Avenue, Grant Avenue, Boonville Avenue, Broadway Avenue and Eastgate Avenue and signal upgrades and adding intersection turn lane at Rte. 65 in Springfield. | 2026 | 1285 | 253 | 0 | 253 | 150 | 0 | 0 | 0 | 0 | 1421 | 0 | 3109
Southwest | N | GREENE | BU 60 E | SR0034 | 3.324 | 6.615 | 0 | Pavement resurfacing and add rumble stripes from Rte. B to 0.3 mile east of White Oak Road in Rogersville and from 0.1 mile south of Rte. 60 to Rte. B. | 2028 | 33 | 1 | 58 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 603 | 695
Southwest | Y | GREENE | US 60 E | 8P0683G | 1.952 | 0 | 0 | Capital improvements from 0.5 mile east of Rte. 65 to Rtes. NN and J. | 2029 | 1251 | 400 | 4109 | 4509 | 0 | 0 | 2758 | 2758 | 0 | 0 | 25266 | 33784
Southwest | Y | GREENE | US 60 E | SU0078 | 1.059 | 4.76 | 0 | Capital improvement from west of County Road 103 to Rte. 360 (James River Freeway) in Republic. | 2028 | 800 | 350 | 2332 | 2682 | 0 | 0 | 5411 | 5411 | 0 | 0 | 10456 | 19349
Southwest | Y | GREENE | BU 65 S | SU0003 | 8.097 | 44.031 | 0 | Operational and pedestrian improvements on Glenstone Avenue from Valley Water Mill Road to Rte. 60 (James River Freeway) in Springfield. | 2029 | 984 | 2 | 444 | 446 | 0 | 0 | 229 | 229 | 0 | 0 | 2273 | 3932
Southwest | Y | GREENE | BU 65 S | SU0327 | 0.002 | 0.014 | 0 | Payment to Springfield to add bicycle/pedestrian trail and upgrade pedestrian signal on Glenstone Avenue at Sunset Street. | 2026 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 45
Southwest | Y | GREENE | E OR 65 S | 8S3158 | 0.227 | 0.454 | 1 | Bridge replacement on Eastgate Avenue over BNSF Railway and add sidewalk from south of Monroe Street to Lombard Street in Springfield. Project involves bridge W0574. | 2026 | 471 | 469 | 0 | 469 | 205 | 0 | 0 | 0 | 0 | 2897 | 0 | 4042
Southwest | N | GREENE | US 65 S | 7P2212D | 5.187 | 10.374 | 0 | Pavement improvements from Pomme de Terre River to Rte. KK. | 2030 | 12 | 1 | 171 | 172 | 0 | 0 | 0 | 0 | 0 | 0 | 628 | 812
Southwest | Y | GREENE | MO 744 E | 8P3220 | 1.801 | 10.913 | 4 | Interchange and bridge improvement on Kearney Street at Rte. 65 in Springfield. Project involves twin bridges A1648, A1649 and A2364. | 2030 | 80 | 1400 | 10396 | 11796 | 0 | 0 | 6939 | 6939 | 0 | 0 | 36308 | 55123
Southwest | Y | GREENE | MO 744 E | 8P3237 | 0.143 | 0.691 | 0 | Replace signals on Kearney St at National Ave, Summit Ave, Grant Ave, Broadway Ave and Delaware Ave, on Bus. 65 at Patterson Ave and Cedarbrook Ave, on Rte. FF at Rte. MM in Battlefield and on Rte. CC at Cheyenne Rd in Christian County. | 2028 | 180 | 75 | 630 | 705 | 0 | 0 | 18 | 18 | 0 | 0 | 2499 | 3402
Southwest | Y | GREENE | RT D E | 8S0745 | 2.738 | 13.424 | 0 | Pavement resurfacing on Sunshine Street from 0.1 mile west of Bus. 65 (Glenstone Avenue) to Blackman Road in Springfield. | 2026 | 74 | 213 | 0 | 213 | 0 | 0 | 0 | 0 | 0 | 1798 | 0 | 2085
Southwest | Y | GREENE | RT D E | 8S3133 | 4.533 | 16.583 | 0 | Add intersection turn lanes, pedestrian signals and raised medians at various locations on Sunshine Street from Bus. 65 (Glenstone Avenue) to 0.3 mile east of County Road 199. | 2026 | 1079 | 381 | 0 | 381 | 253 | 0 | 0 | 0 | 0 | 2183 | 0 | 3896
Southwest | Y | GREENE | RT D E | 8S3153 | 2.583 | 12.683 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan on Sunshine Street from Bus. 65 (Glenstone Avenue) to Blackman Road in Springfield. $626,000 Transportation Alternatives and $156,500 Springfield funds. | 2026 | 1377 | 397 | 0 | 397 | 53 | 0 | 0 | 0 | 0 | 3436 | 0 | 5263
Southwest | Y | GREENE | RT D E | 8S3215 | 5.547 | 11.094 | 2 | Pavement resurfacing and replace guardrail from east of Blackman Road to Rte. 125 east of Springfield. Project involves bridges A3055 and A3056. | 2027 | 50 | 5 | 174 | 179 | 0 | 0 | 0 | 0 | 0 | 0 | 1505 | 1734
Southwest | Y | GREENE | RT D E | SU0148 | 0.032 | 0.16 | 0 | Replace signals at Oak Grove Avenue and Ventura Avenue in Springfield. | 2029 | 20 | 10 | 170 | 180 | 0 | 0 | 11 | 11 | 0 | 0 | 892 | 1103
Southwest | N | GREENE | RT F S | SR0083 | 0.064 | 0.128 | 1 | Bridge replacement over Sac River. Project involves bridge K0646. | 2027 | 370 | 100 | 521 | 621 | 0 | 34 | 0 | 34 | 0 | 0 | 3077 | 4102
Southwest | Y | GREENE | RT FF S | SU0018 | 3.054 | 6.108 | 0 | Pavement resurfacing from Weaver Road in Battlefield to Haseltine Road. | 2028 | 22 | 2 | 66 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 554 | 644
Southwest | Y | GREENE | RT FF S | SU0189 | 0.131 | 0.32 | 0 | Intersection improvement at Weaver Road in Battlefield. | 2028 | 120 | 150 | 900 | 1050 | 0 | 0 | 106 | 106 | 0 | 0 | 3700 | 4976
Southwest | Y | GREENE | CST GASCONADE ST W | SU0169 | 0.209 | 0.853 | 3 | Bridge rehabiliitation over Rte. 65, Rte. H (Glenstone Avenue) over I-44 and Rte. 125 over BNSF Railway. Project involves bridges A2040, A7501 and A8269. | 2027 | 70 | 2 | 116 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 726 | 914
Southwest | Y | GREENE | RT J S | 8S3211 | 5.504 | 11.008 | 0 | Pavement resurfacing and add rumble stripes from Rte. D to 0.3 mile north of Rte. 60 east of Springfield. | 2027 | 46 | 9 | 116 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 1198 | 1369
Southwest | Y | GREENE | RT J S | SU0077 | 0.319 | 0.638 | 2 | Replace box culverts south of County Road 150 and south of County Road 168. Project involves culverts Y0581 and W0010. | 2027 | 100 | 300 | 361 | 661 | 0 | 20 | 0 | 20 | 0 | 0 | 1890 | 2671
Southwest | N | GREENE | RT K S | SR0023 | 0.507 | 1.014 | 0 | Pavement resurfacing from Rte. 266 to I-44. | 2028 | 10 | 2 | 14 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 111 | 137
Southwest | Y | GREENE | RT MM S | 8S0836B | 1.511 | 3.221 | 0 | Add lanes on Brookline Avenue from I-44 to Rte. 360 (James River Freeway) in Republic. Design, right of way and inspection by Republic. $6,000,000 Cost Share, $2,296,000 STBG-Urban and $2,872,000 Republic funds. | 2027 | 840 | 100 | 329 | 429 | 0 | 568 | 0 | 568 | 0 | 0 | 10039 | 11876
Southwest | Y | GREENE | RT MM S | 8S0836D | 0.353 | 0 | 0 | Relocate Brookline Avenue, add railroad overpass and sidewalks from County Road 160 to Rte. 60 and add lanes from Haile Street to County Road 160 in Republic. $1,744,000 Open Container, $522,982 Republic, $346,867 Transportation Alternatives funds. | 2026 | 3914 | 4709 | 0 | 4709 | 3536 | 0 | 0 | 0 | 0 | 22249 | 0 | 34408
Southwest | Y | GREENE | RP US65N TO IS44W W | SU0297 | 0 | 0.301 | 1 | Bridge rehabilitation over I-44 in Springfield. Project involves bridge A7024. | 2027 | 30 | 178 | 560 | 738 | 0 | 0 | 0 | 0 | 0 | 0 | 3576 | 4344
Southwest | Y | GREENE | RP US65N TO US60W W | SU0298 | 0 | 1.007 | 3 | Bridge painting over Rte. 60, on eastbound Rte. 60 ramp over Rte. 65 and on Rte. 65 ramp over I-44 in Springfield. Project involves bridges A7541, A7542 and A7024. | 2029 | 2 | 2 | 364 | 366 | 0 | 0 | 0 | 0 | 0 | 0 | 1741 | 2109
Southwest | N | GREENE | RT V S | SR0025 | 8.016 | 16.032 | 0 | Pavement resurfacing and safety improvements from Rte. 123 in Walnut Grove to Rte. 160 in Ash Grove. | 2028 | 47 | 10 | 174 | 184 | 0 | 0 | 15 | 15 | 0 | 0 | 1633 | 1879
Southwest | N | HENRY | MO 13 N | SR0130 | 0.217 | 0.434 | 1 | Bridge deck sealing on northbound bridge over the Truman Reservoir 3.1 miles south of Rte. 7. Project involves bridge A5385. | 2027 | 9 | 20 | 134 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 474 | 637
Southwest | N | HENRY | MO 13 S | SR0031 | 7.67 | 16.175 | 0 | Pavement resurfacing from 0.2 mile south of Rte. 7 in Clinton to Rte. 52. | 2026 | 79 | 230 | 0 | 230 | 0 | 0 | 0 | 0 | 0 | 1949 | 0 | 2258
Southwest | N | HENRY | MO 18 E | SR0028 | 2.079 | 4.612 | 0 | Pavement resurfacing on Ohio Street from Montgomery Street to Rte. 13 in Clinton. | 2027 | 8 | 12 | 77 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 644 | 741
Southwest | N | HENRY | MO 18 E | SR0338 | 4.142 | 8.284 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan in Clinton, Windsor and Montrose. | 2026 | 81 | 186 | 0 | 186 | 0 | 14 | 0 | 14 | 0 | 522 | 0 | 803
Southwest | N | HENRY | BU 52 E | 7S3399 | 4.958 | 9.926 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in Deepwater, on Rte. BB in Brownington, on Rte. D in Lowry City and on Rtes. 52, KK and P in Appleton City. | 2026 | 347 | 129 | 0 | 129 | 2 | 0 | 0 | 0 | 0 | 477 | 0 | 955
Southwest | N | HENRY | MO 7 S | SR0024 | 20.929 | 89.654 | 0 | Pavement resurfacing from east of Rte. B to 0.2 mile south of Rte. 18 (Ohio Street) in Clinton. | 2026 | 81 | 299 | 0 | 299 | 0 | 0 | 0 | 0 | 0 | 2424 | 0 | 2804
Southwest | N | HENRY | RT C E | SR0053B | 0.153 | 0.77 | 8 | Bridge rehabilitation on Rte. C and Rte. 7 in Henry County and Rte. 13 in St. Clair County. Project involves bridges A5355, A5357, A5359, A6566, A6567, A6932, B0428 and A3913. | 2027 | 25 | 32 | 127 | 159 | 0 | 0 | 0 | 0 | 0 | 0 | 773 | 957
Southwest | N | HENRY | RT C E | SR0090 | 17.512 | 35.024 | 2 | Pavement resurfacing and add rumble stripes from Rte. 7 to Rte. 65. Upgrade guardrail on bridges over Barker Creek and Brush Creek. Project involves bridges A3691 and A3881. | 2028 | 82 | 10 | 550 | 560 | 0 | 0 | 0 | 0 | 0 | 0 | 4638 | 5280
Southwest | N | HICKORY | MO 64 E | SR0320 | 0.35 | 0.7 | 1 | Bridge rehabilitation over Pomme de Terre Lake. Project involves bridge A0894. | 2029 | 5 | 5 | 551 | 556 | 0 | 0 | 0 | 0 | 0 | 0 | 2576 | 3137
Southwest | N | JASPER | MO 43 N | SR0073 | 0.196 | 0.392 | 2 | Bridge rehabilitations 0.4 mile south of Pine Road over North Fork Spring River and 0.6 mile south of Pecan Road over Spring River. Project involves bridges A2690 and A2691. | 2026 | 198 | 427 | 0 | 427 | 0 | 0 | 0 | 0 | 0 | 2550 | 0 | 3175
Southwest | N | JASPER | MO 43 S | SR0008 | 0.221 | 1.058 | 2 | Bridge replacement on Main Street over CPKC railroad and Turkey Creek and add sidewalk from F Street to Murphy Boulevard in Joplin. Project involves bridges K0415 and J0339. | 2028 | 250 | 500 | 1952 | 2452 | 0 | 0 | 21 | 21 | 0 | 0 | 9515 | 12238
Southwest | N | JASPER | MO 43 S | SR0017 | 2.979 | 14.895 | 2 | Pavement resurfacing from 0.1 mile south of Rte. 171 in Airport Drive to F Street in Joplin. Project involves bridges J0339 and K0415. | 2027 | 57 | 5 | 192 | 197 | 0 | 0 | 0 | 0 | 0 | 0 | 1667 | 1921
Southwest | N | JASPER | IS 44 E | SR0269 | 27.534 | 112.739 | 9 | Pavement resurfacing and bridge rehabilitation 1.3 miles east of Rte. 37 to Rtes. Z and O near Halltown (disconnected sections) and the westbound bridge over MNA Railroad west of Rte. H. Bridges A0976, A8858, A8859, A8862, A8866, A8867, A8868, A8869 and A8879. | 2026 | 414 | 1999 | 0 | 1999 | 0 | 0 | 0 | 0 | 0 | 15387 | 0 | 17800
Southwest | N | JASPER | IS 49 N | SR0053E | 0 | 0.929 | 1 | Bridge rehabilitation on the northbound lanes over Dry Fork Creek near Carytown. Project involves bridge A3580. | 2028 | 4 | 10 | 179 | 189 | 0 | 0 | 0 | 0 | 0 | 0 | 836 | 1029
Southwest | N | JASPER | IS 49 S | SR0342 | 0.927 | 1.854 | 1 | Bridge replacement on the southbound lanes over Dry Fork Creek. Project involves bridge A1341. | 2028 | 0 | 600 | 1499 | 2099 | 0 | 0 | 0 | 0 | 0 | 0 | 5541 | 7640
Southwest | N | JASPER | MO 66 E | 7S2185B | 0.992 | 4.24 | 0 | Rebuild pavement and upgrade signals on 7th Street from Rte. P (Schifferdecker Avenue) to Maiden Lane in Joplin. | 2026 | 1610 | 910 | 0 | 910 | 0 | 50 | 0 | 50 | 0 | 8449 | 0 | 11019
Southwest | N | JASPER | MO 66 E | 7S2185C | 0.975 | 3.998 | 0 | Rebuild pavement, upgrade signals, upgrade pedestrian facilities to comply with ADA Transition Plan on 7th St. from Maiden Lane to Rte. 43 (Main St.) and construct a new culvert from Byers Ave. to Wall Ave. in Joplin. $5,299,000 Joplin, $1,209,000 Open Container funds. | 2026 | 2515 | 2028 | 0 | 2028 | 0 | 138 | 0 | 138 | 0 | 17128 | 0 | 21809
Southwest | N | JASPER | MO 66 E | 7S2185D | 1.015 | 4.612 | 1 | Rebuild pavement, upgrade signals, and upgrade pedestrian facilities to comply with the ADA Transition Plan on 7th Street from Rte. 43 (Main Street) to St. Louis Avenue in Joplin. Project includes bridge A5961. $692,936 Joplin and $846,000 Open Container funds. | 2026 | 2821 | 1820 | 0 | 1820 | 50 | 9 | 0 | 9 | 0 | 11278 | 0 | 15978
Southwest | N | JASPER | MO 66 E | 7S2185E | 0.988 | 4.899 | 0 | Rebuild pavement and upgrade signals on 7th Street from St. Louis Avenue to Loop 49 (Range Line Road) in Joplin. $648,000 Open Container funds. | 2026 | 1635 | 1120 | 0 | 1120 | 50 | 0 | 0 | 0 | 0 | 10355 | 0 | 13160
Southwest | N | JASPER | MO 66 E | 7S2185F | 0.992 | 4.24 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan on 7th Street from Rte. P (Schifferdecker Avenue) to Maiden Lane Avenue in Joplin. | 2026 | 626 | 506 | 0 | 506 | 0 | 50 | 0 | 50 | 0 | 2165 | 0 | 3347
Southwest | N | JASPER | MO 66 E | 7S2185G | 0.988 | 4.899 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan on 7th Street from St. Louis Avenue to Loop 49 (Range Line Road) in Joplin. | 2026 | 737 | 280 | 0 | 280 | 50 | 0 | 0 | 0 | 0 | 1207 | 0 | 2274
Southwest | N | JASPER | MO 96 E | 7S3506B | 1.12 | 5.229 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan on Central Avenue from I-49 to Garrison Avenue in Carthage. | 2026 | 625 | 414 | 0 | 414 | 0 | 50 | 0 | 50 | 0 | 1643 | 0 | 2732
Southwest | N | JASPER | MO 96 E | SR0060 | 1.12 | 5.198 | 0 | Rebuild pavement and upgrade signals on Central Avenue from I-49 to Rte. 571 (Garrison Street) in Carthage. $399,000 Open Container funds. | 2026 | 990 | 1171 | 0 | 1171 | 0 | 240 | 0 | 240 | 0 | 10117 | 0 | 12518
Southwest | N | JASPER | RT BB S | SR0137 | 0.021 | 0.042 | 1 | Bridge replacement 1 mile south of Rte. N. Project involves bridge A1884. | 2026 | 150 | 317 | 0 | 317 | 2 | 0 | 0 | 0 | 0 | 1104 | 0 | 1573
Southwest | N | JASPER | RT FF E | 7S3059 | 0.4 | 2 | 0 | Add railroad overpass on 32nd Street at CPKC railroad in Joplin. $3,159,000 Open Container funds. | 2028 | 260 | 324 | 3536 | 3860 | 0 | 0 | 2627 | 2627 | 0 | 0 | 20728 | 27475
Southwest | N | JASPER | RT H E | SR0142 | 0.022 | 0.044 | 1 | Bridge replacement over Duval Creek 0.7 mile west of Rte. Y. Project involves bridge S0834. | 2026 | 90 | 374 | 0 | 374 | 2 | 0 | 0 | 0 | 0 | 1086 | 0 | 1552
Southwest | N | JASPER | RT M E | SR0074 | 0.019 | 0.038 | 1 | Bridge rehabilitation 0.7 mile east of Rte. 43 over Duval Creek. Project involves bridge A2862. | 2026 | 41 | 72 | 0 | 72 | 3 | 0 | 0 | 0 | 0 | 427 | 0 | 543
Southwest | N | JASPER | RP MO249N TO MO171N N | SR0319B | 0 | 0.581 | 1 | Bridge painting over Rte. 171 and Missouri & Northern Arkansas Railroad in Carterville. Project involves bridge A6149. | 2030 | 2 | 2 | 53 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 557
Southwest | N | JASPER | CST OAK ST W | SR0314 | 0.072 | 0.144 | 1 | Upgrade pedestrian facilities to comply with the ADA Transition Plan on Oak Street over I-49 in Carthage. Project involves bridge A3561. | 2026 | 134 | 107 | 0 | 107 | 0 | 0 | 0 | 0 | 0 | 415 | 0 | 656
Southwest | N | JASPER | RT P E | SR0337 | 1.262 | 2.858 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan in Joplin, Carl Junction, Jasper, Sarcoxie, Diamond, and Mount Vernon. | 2026 | 100 | 237 | 0 | 237 | 0 | 11 | 0 | 11 | 0 | 679 | 0 | 1027
Southwest | N | LAWRENCE | MO 39 S | SR0019 | 2.632 | 7.137 | 0 | Pavement resurfacing from west of Lewis Shaw Avenue to Rte. 60 in Aurora. | 2027 | 14 | 20 | 110 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 993 | 1137
Southwest | N | LAWRENCE | IS 44 E | SR0344 | 27.218 | 111.473 | 9 | Bridge rehabilitation at various locations from 1.25 miles east of Rte. 37 to Rtes. Z and O near Halltown. Project involves bridges A0684, A0981, A0981, A8813, A8858, A8862, A8867, A8869 and A8879. | 2026 | 0 | 227 | 0 | 227 | 0 | 0 | 0 | 0 | 0 | 1056 | 0 | 1283
Southwest | N | LAWRENCE | BU 60 E | SR0022 | 3.528 | 7.268 | 0 | Pavement resurfacing from west of Cowan Drive to Rte. 60 in Aurora. | 2027 | 15 | 8 | 90 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 746 | 859
Southwest | N | LAWRENCE | US 60 E | SR0084 | 0.098 | 0.196 | 2 | Bridge replacement over Missouri & Northern Arkansas Railroad near Aurora and on Rte. H over Missouri & Northern Arkansas Railroad near Hoberg. Project involves bridges K0947 and A0872. | 2028 | 192 | 500 | 1860 | 2360 | 0 | 0 | 29 | 29 | 0 | 0 | 6964 | 9545
Southwest | N | LAWRENCE | RT H S | SR0312 | 14.38 | 29.02 | 0 | Pavement resurfacing and add rumble stripes from I-44 to Bus. 60 in Monett. $773,000 Open Container funds. | 2026 | 148 | 337 | 0 | 337 | 0 | 0 | 0 | 0 | 0 | 3296 | 0 | 3781
Southwest | N | LAWRENCE | RT K S | SR0211 | 0.171 | 0.342 | 1 | Bridge replacement over Honey Creek. Project involves bridge K0865. | 2027 | 250 | 188 | 333 | 521 | 0 | 47 | 0 | 47 | 0 | 0 | 1903 | 2721
Southwest | N | LAWRENCE | RT P S | 7S3494 | 5.59 | 11.18 | 0 | Pavement resurfacing and add rumble stripes from Rte. 39 to Bus. 60 in Verona. | 2027 | 43 | 9 | 110 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 1140 | 1302
Southwest | N | MCDONALD | MO 43 S | 7S3379 | 0.33 | 0.66 | 1 | Bridge replacement and streambank stabilization over Elk River. Project involves bridge A0826. | 2026 | 731 | 714 | 0 | 714 | 2 | 0 | 0 | 0 | 0 | 4087 | 0 | 5534
Southwest | N | MCDONALD | IS 49 N | SR0053C | 0.139 | 0.823 | 3 | Bridge rehabilitation over Indian Creek Road in Anderson and northbound over Goodwin Hollow Road in Pineville. Project involves bridges A5812, A5813 and A6378. | 2029 | 4 | 5 | 294 | 299 | 0 | 0 | 0 | 0 | 0 | 0 | 1531 | 1834
Southwest | N | MCDONALD | IS 49 S | SR0016 | 6.843 | 28.715 | 0 | Pavement resurfacing from Rte. 59 near Goodman to 2.1 miles south of Rte. 76. | 2027 | 155 | 1 | 482 | 483 | 0 | 0 | 0 | 0 | 0 | 0 | 4211 | 4849
Southwest | N | MCDONALD | IS 49 S | SR0181 | 16.005 | 0 | 0 | Job Order Contracting for pavement repair from Rte. 59 to Arkansas State line. | 2026 | 5 | 29 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 154
Southwest | N | MCDONALD | MO 59 S | SR0172 | 0.213 | 0.426 | 0 | Repair and stabilize drainage 0.5 mile north of Rte. DD near Noel. | 2026 | 29 | 42 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 187 | 0 | 258
Southwest | N | MCDONALD | BU 71 S | 7P3529 | 0.641 | 1.869 | 0 | Replace signals on Bus. 71 in Anderson and Pineville, Rte. 52 in Butler, Rte. 54 in El Dorado Springs, Rte. 65 in Buffalo, Rte. 43 in Joplin, Rte. 60 and Loop 49 in Neosho, Rte. 39 in Aurora and Rte. 59 in Goodman and Anderson. | 2026 | 1067 | 646 | 0 | 646 | 0 | 248 | 0 | 248 | 0 | 4610 | 0 | 6571
Southwest | N | MCDONALD | PVT BLANKENSHIP PARK W | SR0144 | 0.029 | 0.01 | 1 | Bridge replacement at Blankenship Park west of Main Street in Southwest City. Project involves bridge T1041. | 2030 | 10 | 1 | 50 | 51 | 0 | 0 | 4 | 4 | 0 | 0 | 147 | 212
Southwest | N | MCDONALD | RT H E | SR0143 | 0.025 | 0.05 | 1 | Bridge replacement over Goodin Hollow 0.3 mile west of Bus. 71 near Pineville. Project involves bridge R0305. | 2026 | 100 | 343 | 0 | 343 | 2 | 0 | 0 | 0 | 0 | 1138 | 0 | 1583
Southwest | N | NEWTON | MO 43 S | SR0075B | 0.055 | 0.094 | 3 | Culvert replacement and ditch grading from Grand Avenue to Osage Street in Seneca. Project involves culverts T1060, T1061 and T1062. | 2027 | 0 | 146 | 158 | 304 | 0 | 2 | 0 | 2 | 0 | 0 | 866 | 1172
Southwest | N | NEWTON | IS 44 E | SR0128 | 18.725 | 78.228 | 6 | Pavement improvements from 0.4 mile east of Loop 49 (Range Line Road) in Joplin to 1.5 miles east of Rte. 37 near Sarcoxie. Involves bridges A0540, A0541, A0542, A0543, A0544 and A0862. | 2027 | 14 | 502 | 1587 | 2089 | 0 | 0 | 0 | 0 | 0 | 0 | 13810 | 15913
Southwest | N | NEWTON | IS 44 E | SR0177 | 69.112 | 0 | 0 | Job Order Contracting for pavement repair from the Oklahoma State line to Rte. 360 in Greene County. | 2026 | 5 | 85 | 0 | 85 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 490
Southwest | N | NEWTON | LP 49 S | SR0185 | 0.103 | 0.309 | 1 | Bridge improvement over Shoal Creek south of Saginaw. Project involves bridge K0765. | 2030 | 125 | 200 | 2022 | 2222 | 0 | 0 | 51 | 51 | 0 | 0 | 8935 | 11333
Southwest | N | NEWTON | BU 60 E | 7S3390 | 6.996 | 20.677 | 1 | Pavement resurfacing from Rtes. 60 and 59 north junction 2.2 miles west of Granby to Rtes. 60 and 59 south junction in Neosho. Project involves bridge J0623. | 2027 | 209 | 1 | 194 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 1693 | 2097
Southwest | N | NEWTON | BU 60 E | SR0113 | 1.149 | 5.736 | 0 | Rebuild pavement from Stadium Drive to north of Daugherty Road in Neosho. | 2028 | 101 | 135 | 626 | 761 | 0 | 0 | 0 | 0 | 0 | 0 | 4239 | 5101
Southwest | N | NEWTON | US 60 E | 7P3386 | 41.772 | 87.121 | 3 | Pavement resurfacing and bridge rehabilitation from the Oklahoma State line to Rte. 37 in Monett. Project involves bridges A0333, A0334 and A4961. $289,000 Open Container funds. | 2026 | 560 | 1776 | 0 | 1776 | 0 | 0 | 0 | 0 | 0 | 15089 | 0 | 17425
Southwest | N | NEWTON | RT B S | 7S3496 | 2.628 | 5.256 | 0 | Pavement resurfacing and add shoulders and rumble stripes from Rte. 60 in Granby to Rte. 86. | 2028 | 12 | 2 | 67 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 588 | 669
Southwest | N | NEWTON | RT E S | 7S3497 | 5.266 | 10.532 | 0 | Pavement resurfacing and add shoulders and rumble stripes from Rte. J east of Diamond to Rte. 60 in Granby. | 2028 | 14 | 2 | 136 | 138 | 0 | 0 | 10 | 10 | 0 | 0 | 1083 | 1245
Southwest | N | NEWTON | PVT NN-2 N | SR0075 | 0.023 | 0.034 | 2 | Culvert replacement at Rte. H 0.1 mile south of Raven Road and at Rte. NN 0.1 mile north of Freeburg Road. Project involves culverts T1059 and T1063. | 2026 | 252 | 85 | 0 | 85 | 0 | 2 | 0 | 2 | 0 | 510 | 0 | 849
Southwest | N | POLK | MO 123 S | SR0055 | 0.036 | 0.072 | 3 | Culvert replacement at Spring Creek and culvert rehabilitation on Rte. 83 at Mile Creek and on Rte. O at Ashlock Creek. Project involves culverts H0406, L0341 and P0984. | 2027 | 15 | 574 | 268 | 842 | 0 | 0 | 0 | 0 | 0 | 0 | 1005 | 1862
Southwest | N | POLK | MO 13 N | SR0049 | 0.09 | 0.178 | 1 | Bridge replacement on northbound lanes over Brush Creek in Humansville. Project involves bridge A0063. | 2026 | 337 | 538 | 0 | 538 | 0 | 0 | 0 | 0 | 0 | 2721 | 0 | 3596
Southwest | N | POLK | MO 13 N | SR0183 | 0.06 | 0.12 | 1 | Bridge rehabilitation on the northbound lanes over Dry Sac River 1 mile north of Rte. AE. Project involves bridge A2681. | 2026 | 125 | 341 | 0 | 341 | 2 | 0 | 0 | 0 | 0 | 1866 | 0 | 2334
Southwest | N | POLK | MO 83 S | SR0035 | 14.148 | 28.296 | 0 | Pavement resurfacing and add rumble stripes from Rte. V to Rte. 32 in Bolivar. | 2028 | 129 | 2 | 311 | 313 | 0 | 0 | 0 | 0 | 0 | 0 | 2767 | 3209
Southwest | N | POLK | RT N E | SR0138 | 0.21 | 0.42 | 1 | Bridge replacement over Saddler Branch west of Humansville. Project involves bridge A1878. | 2027 | 186 | 85 | 215 | 300 | 0 | 2 | 0 | 2 | 0 | 0 | 1220 | 1708
Southwest | N | POLK | RT U S | SR0026 | 5.111 | 10.269 | 0 | Pavement resurfacing and add rumble stripes from Rte. 13 in Bolivar to end of state maintenance. $333,000 Open Container funds. | 2028 | 44 | 2 | 94 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 975 | 1115
Southwest | N | POLK | RT Z E | 7S3368B | 0.018 | 0.036 | 1 | Culvert replacement over Pratter Branch 0.2 mile west of Rock Prairie. Project involves culvert W0507. | 2027 | 68 | 36 | 86 | 122 | 0 | 2 | 0 | 2 | 0 | 0 | 489 | 681
Southwest | N | ST. CLAIR | MO 13 S | 7P3034B | 1.27 | 2.588 | 0 | Pavement improvement on the southbound lanes from SE 1100 Road to NE 201 Road. | 2030 | 10 | 1 | 199 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 1117 | 1327
Southwest | N | STONE | MO 13 S | SR0132 | 0.363 | 0.726 | 1 | Bridge rehabilitation over Table Rock Lake. Project involves bridge A0585. | 2026 | 107 | 243 | 0 | 243 | 0 | 0 | 0 | 0 | 0 | 1527 | 0 | 1877
Southwest | N | STONE | MO 13 S | SR0317 | 0.643 | 1.286 | 2 | Bridge washing over Table Rock Lake in Kimberling City and on Rte. 39 over Table Rock Lake in Shell Knob. Project involves bridges A0585 and A0260. | 2029 | 1 | 1 | 25 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 541 | 568
Southwest | N | STONE | US 160 E | 7P3533C | 9.238 | 19.431 | 0 | Pavement resurfacing and add rumble stripes from Rte. 13 to 0.4 mile east of Rte. 65. | 2027 | 399 | 2 | 217 | 219 | 0 | 0 | 0 | 0 | 0 | 0 | 2252 | 2870
Southwest | N | STONE | MO 76 E | SR0050 | 1.024 | 2.508 | 14 | Bridge painting at various locations in the rural Southwest District. Project involves bridges A2728, A2729, A3020, A3070, A3477, A3564, A3821, A4258, A4820, A5812, A5813, X0793, A0588 and A0337. | 2028 | 190 | 50 | 1072 | 1122 | 0 | 0 | 0 | 0 | 0 | 0 | 5678 | 6990
Southwest | N | TANEY | US 160 E | 7P3507 | 0.228 | 0.828 | 0 | Replace signals at Rte. 39 and Hadley Street in Aurora, replace signals at Rte. 76 and Main Street in Branson and replace signals and add right turn lane at Rte. 160 and Coy Boulevard in Forsyth. | 2027 | 175 | 84 | 253 | 337 | 0 | 63 | 0 | 63 | 0 | 0 | 1325 | 1900
Southwest | N | TANEY | US 160 E | SR0011 | 0.092 | 0.184 | 1 | Bridge replacement over Beaver Creek. Project involves bridge L0382. | 2027 | 200 | 572 | 1084 | 1656 | 0 | 55 | 0 | 55 | 0 | 0 | 5481 | 7392
Southwest | N | TANEY | US 160 E | SR0121 | 0.085 | 0.17 | 1 | Bridge replacement over Swan Creek in Forsyth. Project involves bridge J0952. | 2027 | 944 | 735 | 1517 | 2252 | 0 | 65 | 0 | 65 | 0 | 0 | 8143 | 11404
Southwest | N | TANEY | MO 165 S | SR0228 | 8.413 | 18.394 | 0 | Pavement resurfacing and add rumble stripes from 76 Country Boulevard in Branson to Rte. 265 near Hollister. | 2027 | 5 | 74 | 270 | 344 | 0 | 0 | 0 | 0 | 0 | 0 | 2296 | 2645
Southwest | N | TANEY | MO 248 E | 7P3533B | 6.668 | 13.601 | 1 | Pavement resurfacing and add rumble stripes from Rte. 160 to Shepherd of the Hills Expressway in Branson. Project involves bridge A5431. | 2027 | 50 | 2 | 137 | 139 | 0 | 0 | 0 | 0 | 0 | 0 | 1419 | 1608
Southwest | N | TANEY | BU 65 S | SR0039 | 2.614 | 9.943 | 0 | Pavement resurfacing from Rte. 76 to Birch Street in Hollister. | 2029 | 25 | 5 | 207 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 1654 | 1891
Southwest | N | TANEY | BU 65 S | SR0057 | 0.233 | 0.484 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan on Bus. 65 in Hollister and Bus. 13 in Branson West. | 2026 | 80 | 83 | 0 | 83 | 0 | 2 | 0 | 2 | 0 | 283 | 0 | 448
Southwest | N | TANEY | BU 65 S | SR0122 | 0.044 | 0.088 | 1 | Bridge replacement over Missouri and Northern Arkansas Railroad in Hollister. Project involves bridge J0710. | 2027 | 553 | 900 | 765 | 1665 | 0 | 55 | 0 | 55 | 0 | 0 | 3729 | 6002
Southwest | N | TANEY | US 65 N | SR0215 | 0.104 | 0.414 | 2 | Bridge painting on northbound bridge and rehabilitation on southbound bridge over Missouri & Northern Arkansas Railroad in Branson. Project involves bridges A3065 and A3066. | 2027 | 5 | 110 | 502 | 612 | 0 | 0 | 0 | 0 | 0 | 0 | 2951 | 3568
Southwest | N | TANEY | US 65 N | SR0341 | 0 | 0.204 | 1 | Bridge rehabilitation over Missouri & Northern Arkansas Railroad in Branson. Project involves bridge A3065N. | 2027 | 0 | 88 | 217 | 305 | 0 | 0 | 0 | 0 | 0 | 0 | 1282 | 1587
Southwest | N | TANEY | US 65 S | SR0091 | 0.401 | 2.118 | 0 | Intersection improvements at Rte. 265. $3,223,000 Open Container funds. | 2027 | 600 | 158 | 623 | 781 | 0 | 0 | 0 | 0 | 0 | 0 | 3537 | 4918
Southwest | N | TANEY | US 65 S | SR0270 | 17.014 | 73.588 | 0 | Pavement resurfacing and replace guardrail from 0.9 mile north of Rte. 76 north junction (Ozark Mountain Highroad) to Arkansas State line. | 2027 | 50 | 200 | 1169 | 1369 | 0 | 0 | 0 | 0 | 0 | 0 | 9311 | 10730
Southwest | N | TANEY | US 65 S | SR0325 | 0.104 | 0.208 | 1 | Bridge improvement on the southbound bridge over Emery Creek. Project involves bridge A0930. | 2030 | 50 | 279 | 2867 | 3146 | 0 | 0 | 2 | 2 | 0 | 0 | 9030 | 12228
Southwest | N | TANEY | US 65 S | SR0346 | 17.144 | 74.106 | 0 | Pavement resurfacing and add pavement friction at various locations from 0.9 mile north of Rte. 76 north junction (Ozark Mountain Highroad) to Arkansas State line. | 2027 | 0 | 100 | 504 | 604 | 0 | 0 | 0 | 0 | 0 | 0 | 3963 | 4567
Southwest | N | TANEY | MO 76 E | SR0326 | 0.322 | 0.644 | 0 | Urgent slide repair west of Lake Shore Drive. $1,135,670 Emergency Relief funds, MO24-1 flood event. | 2026 | 80 | 1608 | 0 | 1608 | 0 | 2 | 0 | 2 | 0 | 5629 | 0 | 7319
Southwest | N | TANEY | CST 76 COUNTRY BLVD E | 8O2373 | 4.504 | 14.355 | 0 | Payment to Branson for Phase I multimodal improvements on 76 Country Boulevard from Rte. 376 to 6th Street in Branson. | 2026 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 929
Southwest | N | TANEY | CST 76 COUNTRY BLVD E | 8O2373B | 4.335 | 13.384 | 0 | Payment to Branson for road relinquishment of Rte. 76 from Shepherd of the Hills Expressway to Sunshine Street. $3,746,574 over 10 years from SFY 2019 through SFY 2028. | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2832 | 402 | 513 | 3747
Southwest | N | TANEY | RT BB S | SR0040 | 3.584 | 7.168 | 0 | Pavement resurfacing and add rumble stripes from Bus. 65 in Hollister to Layton Road. | 2028 | 29 | 5 | 103 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 675 | 812
Southwest | N | TANEY | RT F E | SR0038 | 3.218 | 6.495 | 0 | Pavement resurfacing and add rumble stripes from 0.1 mile east of Rte. 65 to Rte. 160 in Merriam Woods. | 2027 | 56 | 2 | 122 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 1264 | 1444
Southwest | N | VARIOUS | Various | 5B0800W | 0 | 0 | 38 | Payback beginning in SFY 2008 for Safe and Sound bridges in the rural Southwest District. | 2033 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 89750 | 7768 | 31072 | 128649
Southwest | Y | VARIOUS | Various | 5B0800X | 0 | 0 | 4 | Payback beginning in SFY 2008 for Safe and Sound bridges in the urban Southwest District. | 2033 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 4330 | 292 | 1168 | 5797
Southwest | N | VARIOUS | Various | SR0176 | 0 | 0 | 0 | On-call work zone enforcement at various locations in the rural Southwest District. | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 0 | 110
Southwest | N | VARIOUS | Various | SR0182 | 0 | 0 | 0 | Operations and management of Ozarks Traffic ITS in the rural Southwest District. | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464 | 0 | 464
Southwest | N | VARIOUS | Various | SR0194 | 0 | 0 | 0 | Job Order Contracting for concrete repairs in the rural Southwest District. | 2026 | 30 | 202 | 0 | 202 | 0 | 0 | 0 | 0 | 0 | 1020 | 0 | 1252
Southwest | N | VARIOUS | Various | SR0195 | 0 | 0 | 1 | Job Order Contracting for bridge repairs at various locations in the rural Southwest District. | 2026 | 8 | 402 | 0 | 402 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 2410
Southwest | N | VARIOUS | Various | SR0217 | 0 | 0 | 0 | Operations and management of Ozarks Traffic ITS in the rural Southwest District. | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464 | 464
Southwest | N | VARIOUS | Various | SR0219 | 0 | 0 | 0 | On-call work zone enforcement at various locations in the rural Southwest District. | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100
Southwest | N | VARIOUS | Various | SR0272 | 0 | 0 | 0 | Job Order Contracting for guard cable and guardrail repair in the rural Southwest District. | 2026 | 20 | 1087 | 0 | 1087 | 0 | 0 | 0 | 0 | 0 | 3570 | 0 | 4677
Southwest | N | VARIOUS | Various | SR0285 | 0 | 0 | 2 | Bridge improvements at various locations in Bates, Jasper and Newton Counties. Potential Design-Build project. | 2030 | 50 | 100 | 5500 | 5600 | 0 | 0 | 328 | 328 | 0 | 0 | 41644 | 47622
Southwest | N | VARIOUS | Various | SR0347 | 0 | 0 | 0 | Job Order Contracting for ADA Transition Plan Improvements at various locations in the rural Southwest District. | 2026 | 0 | 160 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 510
Southwest | N | VARIOUS | Various | SR0348 | 0 | 0 | 0 | Job Order Contracting ADA compliance repairs at various locations in the rural Southwest District. | 2028 | 0 | 2 | 160 | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 212 | 374
Southwest | N | VARIOUS | Various | SR0358 | 0 | 0 | 0 | On-call work zone enforcement at various locations in the rural Southwest District. | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 100
Southwest | N | VARIOUS | Various | SR0360 | 0 | 0 | 0 | Operations and management of Ozarks Traffic ITS in the rural Southwest District. | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464 | 464
Southwest | N | VARIOUS | Various | SR0361 | 0 | 0 | 0 | Job Order Contracting for guard cable and guardrail repair in the rural Southwest District. | 2028 | 0 | 2 | 1105 | 1107 | 0 | 0 | 0 | 0 | 0 | 0 | 3787 | 4894
Southwest | Y | VARIOUS | Various | SU0196 | 0 | 0 | 0 | On-call work zone enforcement at various locations in the urban Southwest District. | 2026 | 0 | 14 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 214
Southwest | Y | VARIOUS | Various | SU0198 | 0 | 0 | 1 | Job Order Contracting for bridge repairs at various locations in the urban Southwest District. | 2026 | 8 | 42 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 250
Southwest | Y | VARIOUS | Various | SU0199 | 0 | 0 | 0 | Job Order Contracting for concrete repairs in the urban Southwest District. | 2026 | 10 | 122 | 0 | 122 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 732
Southwest | Y | VARIOUS | Various | SU0200 | 0 | 0 | 0 | Operations and management of Ozarks Traffic ITS in the urban Southwest District. | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1204 | 0 | 1204
Southwest | Y | VARIOUS | Various | SU0218 | 0 | 0 | 0 | Operations and management of Ozarks Traffic ITS in the urban Southwest District. | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1279 | 1279
Southwest | Y | VARIOUS | Various | SU0220 | 0 | 0 | 0 | On-call work zone enforcement at various locations in the urban Southwest District. | 2027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200
Southwest | Y | VARIOUS | Various | SU0273 | 0 | 0 | 0 | Job Order Contracting for guard cable and guardrail repair in the urban Southwest District. | 2026 | 8 | 302 | 0 | 302 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1810
Southwest | Y | VARIOUS | Various | SU0349 | 0 | 0 | 0 | Job Order Contracting for ADA Transition Plan Improvements at various locations in the urban Southwest District. | 2026 | 0 | 120 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 320
Southwest | Y | VARIOUS | Various | SU0354 | 0 | 0 | 0 | Job Order Contracting for ADA compliance repairs at various locations in the urban Southwest District. | 2028 | 0 | 5 | 85 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 212 | 302
Southwest | Y | VARIOUS | Various | SU0359 | 0 | 0 | 0 | On-call work zone enforcement at various locations in the urban Southwest District. | 2028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200
Southwest | N | VERNON | MO 43 S | 7P3518 | 3.498 | 7.819 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan in Bronaugh, on Spur 71 (Main Street) in Milo, Rte. F in Moundville, Loop 49 in Nevada, Rte. H in Richards, Rte. AA in Schell City and Rte. EE in Walker. | 2026 | 458 | 319 | 0 | 319 | 2 | 0 | 0 | 0 | 0 | 719 | 0 | 1498
Southwest | N | VERNON | MO 43 S | SR0162 | 24.219 | 48.438 | 0 | Pavement resurfacing from Rte. 54 to Rte. 160 in Barton County. | 2027 | 239 | 22 | 803 | 825 | 0 | 0 | 0 | 0 | 0 | 0 | 7005 | 8069
Southwest | N | VERNON | IS 49 N | SR0064 | 0.269 | 0.48 | 2 | Bridge rehabilitation over Rte. K in Nevada. Project involves twin bridges A1775. | 2026 | 167 | 358 | 0 | 358 | 0 | 0 | 0 | 0 | 0 | 2137 | 0 | 2662
Southwest | N | VERNON | IS 49 S | SR0063 | 0.261 | 0.69 | 2 | Bridge rehabilitation over Missouri and Northern Arkansas Railroad in Nevada. Project involves twin bridges A1774. | 2026 | 289 | 615 | 0 | 615 | 0 | 0 | 0 | 0 | 0 | 3697 | 0 | 4601
Southwest | N | VERNON | IS 49 S | SR0180 | 55.938 | 0 | 0 | Job Order Contracting for pavement repair from Rte. 54 in Vernon County to I-44 in Jasper County. | 2026 | 5 | 65 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 370
Southwest | N | VERNON | IS 49 S | SR0274 | 0.18 | 0.36 | 4 | Bridge rehabilitation on southbound lanes over Little Osage River, Little Osage River Overflow and Douglas Branch. Project involves bridges A2629, A2614, A2630 and A2631. | 2026 | 70 | 1070 | 0 | 1070 | 0 | 0 | 0 | 0 | 0 | 4649 | 0 | 5789
Southwest | N | VERNON | US 54 E | SR0340 | 0.075 | 0.3 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan at Cottey College in Nevada. | 2026 | 20 | 71 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 185 | 0 | 276
Southwest | N | VERNON | RT BB S | SR0139 | 0.04 | 0.08 | 1 | Bridge replacement over Birch Creek in Nevada. Project involves bridge A1448. | 2027 | 90 | 200 | 223 | 423 | 0 | 0 | 0 | 0 | 0 | 0 | 1330 | 1843
Southwest | N | VERNON | RT E E | SR0140 | 0.155 | 0.31 | 1 | Bridge replacement and replace guardrail over McCarty Creek southeast of Nevada. Project involves bridge T0685. | 2026 | 122 | 363 | 0 | 363 | 2 | 0 | 0 | 0 | 0 | 1194 | 0 | 1681
Southwest | N | VERNON | RT K E | SR0161 | 2.645 | 5.67 | 0 | Pavement resurfacing from I-49 near Nevada to County Road 1800. | 2027 | 26 | 12 | 121 | 133 | 0 | 0 | 0 | 0 | 0 | 0 | 1023 | 1182
Southwest | N | WEBSTER | IS 44 E | SR0178 | 20.757 | 0 | 0 | Job Order Contracting for pavement repair in Webster County. | 2026 | 5 | 45 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 250
Southwest | N | WEBSTER | US 60 E | SR0112 | 3.857 | 15.802 | 0 | Corridor improvements in Seymour. | 2029 | 1357 | 350 | 4912 | 5262 | 0 | 0 | 928 | 928 | 0 | 0 | 27615 | 35162
Southwest | N | WEBSTER | US 60 E | SR0187 | 0.056 | 0.318 | 2 | Bridge rehabilitation over Rte. PP, BNSF Railway and Front Street in Webster County. Project involves twin bridges A2627. | 2027 | 210 | 189 | 880 | 1069 | 0 | 0 | 0 | 0 | 0 | 0 | 5453 | 6732
Southwest | N | WEBSTER | RT B S | SR0030 | 6.676 | 13.352 | 0 | Pavement resurfacing from Rte. AD to Bus. 60 in Rogersville and add rumble stripes from Rte. AD to Shagbark Lane. | 2028 | 38 | 5 | 138 | 143 | 0 | 0 | 0 | 0 | 0 | 0 | 1310 | 1491
Southwest | N | WEBSTER | RT FF S | 7P3533D | 1.403 | 2.806 | 0 | Pavement resurfacing on Rtes. FF and PP from Rte. 60 west junction to Rte. 60 east junction in Fordland. | 2028 | 9 | 1 | 27 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 224 | 261
Southwest | N | WEBSTER | RT O S | SR0166 | 3.07 | 6.14 | 0 | Pavement resurfacing from Hazelwood Road to Rte. 60 and on Brentlinger Drive from beginning of route to Rte. FF in Fordland. | 2027 | 36 | 2 | 60 | 62 | 0 | 21 | 0 | 21 | 0 | 0 | 521 | 640
Southwest | N | WEBSTER | RT PP E | SR0032 | 5.844 | 11.691 | 0 | Pavement resurfacing and add rumble stripes from Rte. KK to Rte. FF in Fordland. | 2028 | 51 | 2 | 110 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 1146 | 1309
Southwest | N | WEBSTER | RT Y E | SR0366 | 0.411 | 0.822 | 1 | Urgent bridge construction over the Niangua River. Potential FEMA funding. Project replaces culvert P0959. | 2026 | 0 | 1658 | 0 | 1658 | 0 | 65 | 0 | 65 | 0 | 4066 | 0 | 5789
Southeast | N | BOLLINGER | MO 34 E | SE0057 | 15.2 | 30.4 | 3 | Pavement resurfacing from Rte. B to Rte. 72. Project involves bridges B0500, B0498 and B0495. | 2026 | 95 | 295 | 0 | 295 | 0 | 0 | 0 | 0 | 0 | 4632 | 0 | 5022
Southeast | N | BOLLINGER | MO 34 E | SE0067 | 0.2 | 0.4 | 0 | Intersection improvements at the north intersection of Rte. 51 in Marble Hill. | 2028 | 30 | 20 | 177 | 197 | 0 | 0 | 84 | 84 | 0 | 0 | 1504 | 1815
Southeast | N | BOLLINGER | RT FF E | SE0098 | 7.318 | 14.636 | 0 | Pavement resurfacing from Rte. H to Rte. 51 and on Spur N from Rte. N to end of state maintenance. | 2026 | 23 | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 829 | 0 | 932
Southeast | N | BOLLINGER | RT UU E | SE0064 | 7.524 | 15.048 | 0 | Pavement resurfacing from Rte. B to Rte. 34. | 2028 | 10 | 5 | 97 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 935 | 1047
Southeast | N | BUTLER | MO 142 E | SE0226 | 0.2 | 0.4 | 1 | Bridge replacement over Cane Creek. Project involves bridge S0523. | 2029 | 4 | 10 | 250 | 260 | 0 | 0 | 18 | 18 | 0 | 0 | 999 | 1281
Southeast | N | BUTLER | US 160 W | SE0060 | 0.1 | 0.2 | 0 | Add roundabout at Rte. C and Rte. V. | 2026 | 101 | 211 | 0 | 211 | 0 | 385 | 0 | 385 | 0 | 2346 | 0 | 3043
Southeast | N | BUTLER | MO 51 N | SE0118 | 0.164 | 0.328 | 1 | Bridge replacement over St. Francis River. Project involves bridge J0092. | 2027 | 192 | 398 | 620 | 1018 | 0 | 5 | 0 | 5 | 0 | 0 | 3569 | 4784
Southeast | N | BUTLER | MO 53 S | SE0061 | 2.043 | 4.086 | 0 | Add turn lane from Rte. 142 to Rte. UU. | 2027 | 200 | 100 | 251 | 351 | 0 | 4065 | 0 | 4065 | 0 | 0 | 3013 | 7629
Southeast | N | BUTLER | BU 67 N | SE0106 | 0 | 0.1 | 1 | Bridge rehabilitation over Pike Creek. Project involves bridge A0595. | 2027 | 26 | 20 | 162 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 821 | 1029
Southeast | N | BUTLER | US 67 S | SE0126 | 6.126 | 26.457 | 0 | Pavement resurfacing on northbound lane from Rte. 60 to County Road 402 and on southbound lane from County Road 521 to Rte. 60. | 2029 | 6 | 40 | 516 | 556 | 0 | 0 | 0 | 0 | 0 | 0 | 5063 | 5625
Southeast | N | BUTLER | US 67 S | SE0140 | 0.6 | 1.2 | 3 | Bridge replacement over Harviell Drainage Ditch, Hart Drainage Ditch and Neelyville Drainage Ditch. Project involves bridges F0665, K0982 and K0983. | 2027 | 250 | 100 | 336 | 436 | 0 | 21 | 0 | 21 | 0 | 0 | 3548 | 4255
Southeast | N | BUTLER | W OR 67 S | SE0091 | 2.415 | 4.83 | 0 | Pavement resurfacing from Rte. M to Rte. 67. | 2029 | 23 | 1 | 68 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 315 | 407
Southeast | N | BUTLER | RT AA S | 9S3677 | 0.4 | 0.8 | 2 | Bridge replacement over Drainage Ditch 1 and 10. Project involves bridges X0789 and X0790. | 2026 | 164 | 94 | 0 | 94 | 14 | 0 | 0 | 0 | 0 | 1461 | 0 | 1733
Southeast | N | BUTLER | RT EE N | SE0109 | 0.2 | 0.4 | 1 | Bridge rehabilitation over Cane Creek Overflow. Project involves bridge N0884. | 2028 | 6 | 2 | 65 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 464 | 537
Southeast | N | BUTLER | RT HH S | SE0210 | 0.2 | 0.4 | 1 | Bridge replacement over Stilcamp Drainage Ditch. Project involves bridge P0256. | 2029 | 1 | 1 | 200 | 201 | 0 | 0 | 5 | 5 | 0 | 0 | 917 | 1124
Southeast | N | BUTLER | RT HH S | SE0211 | 0.2 | 0.4 | 1 | Bridge replacement over Ackerman Drainage Ditch. Project involves bridge P0258. | 2029 | 1 | 1 | 190 | 191 | 0 | 0 | 5 | 5 | 0 | 0 | 911 | 1108
Southeast | N | BUTLER | RT M E | 9S3453 | 0.131 | 0.262 | 0 | Increase sight distance at County Road 459. | 2026 | 189 | 140 | 0 | 140 | 349 | 0 | 0 | 0 | 0 | 898 | 0 | 1576
Southeast | N | BUTLER | RT MM E | SE0114 | 0.2 | 0.4 | 1 | Bridge redeck over Harviell Drainage Ditch. Project involves bridge N0686. | 2026 | 126 | 52 | 0 | 52 | 11 | 0 | 0 | 0 | 0 | 466 | 0 | 655
Southeast | N | BUTLER | RT PP E | SE0066 | 2.76 | 12.995 | 0 | Pavement resurfacing from roundabout to Bus. 60. | 2028 | 11 | 5 | 230 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 2116 | 2362
Southeast | N | BUTLER | RT U E | 9S3779 | 11.77 | 23.54 | 0 | Pavement resurfacing from Rte. CC to Rte. 25. | 2026 | 17 | 177 | 0 | 177 | 0 | 0 | 0 | 0 | 0 | 1436 | 0 | 1630
Southeast | N | BUTLER | RT W S | 9S3781 | 4.141 | 8.338 | 0 | Pavement resurfacing from Rte. O to Bus. 60. | 2026 | 8 | 93 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 829 | 0 | 930
Southeast | N | BUTLER | RT WW S | SE0131 | 0.93 | 2.992 | 0 | Replace signals at Rte. WW and Henry Street in Poplar Bluff at Bus. 60 and 9th Street in Poplar Bluff and at Rte. 160 and Rte. Y in Doniphan. | 2027 | 132 | 50 | 318 | 368 | 0 | 556 | 0 | 556 | 0 | 0 | 2206 | 3262
Southeast | N | CAPE GIRARDEAU | MO 25 S | 9P3772 | 0.2 | 0.4 | 1 | Bridge replacement over Drainage Ditch 25. Project involves bridge H0431. | 2026 | 52 | 61 | 0 | 61 | 0 | 6 | 0 | 6 | 0 | 735 | 0 | 854
Southeast | N | CAPE GIRARDEAU | MO 25 S | SE0072 | 0.2 | 0.4 | 0 | Add roundabout at Rte. 74 and Rte. A. | 2030 | 79 | 75 | 405 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 3846 | 4405
Southeast | N | CAPE GIRARDEAU | MO 25 S | SE0117 | 15.638 | 31.276 | 3 | Pavement resurfacing from Rte. 77 to Rte. 91. Project involves bridge G0853, G0854 and H0429. | 2026 | 103 | 358 | 0 | 358 | 0 | 0 | 0 | 0 | 0 | 5158 | 0 | 5619
Southeast | N | CAPE GIRARDEAU | MO 25 S | SE0128 | 11.183 | 23.276 | 2 | Pavement resurfacing from Rte. 61 to Rte. 77 and add turn lanes at Rte. Z and County Roads 325, 324 and 318. Project involves bridges J0056 and H0613. | 2027 | 74 | 100 | 340 | 440 | 0 | 672 | 0 | 672 | 0 | 0 | 3599 | 4785
Southeast | N | CAPE GIRARDEAU | MO 34 E | 9P3812 | 0.4 | 0.8 | 1 | Bridge replacement over Dillard Creek. Project involves bridge J0883. | 2028 | 174 | 40 | 221 | 261 | 0 | 0 | 40 | 40 | 0 | 0 | 2507 | 2982
Southeast | N | CAPE GIRARDEAU | IS 55 N | 9P3122 | 1.08 | 1.992 | 3 | Bridge rehabilitation northbound over BNSF Railway and Rte. 74 and Rte. 61 over I-55. Add roundabout at Rte. 61 and Silver Springs Road. Project involves bridges A0628, A0513 and A0514. | 2027 | 1137 | 156 | 700 | 856 | 0 | 100 | 0 | 100 | 0 | 0 | 6069 | 8162
Southeast | N | CAPE GIRARDEAU | IS 55 N | SE0201 | 4.693 | 19.13 | 0 | Drainage upgrades from Rte. K to Bloomfield Road and from County Road 434 to Exit 105. | 2029 | 5 | 10 | 235 | 245 | 0 | 0 | 0 | 0 | 0 | 0 | 1579 | 1829
Southeast | N | CAPE GIRARDEAU | IS 55 S | 9I3838 | 12.381 | 58.872 | 3 | Pavement resurfacing on southbound lanes from Rte. 61 to Rte. 74 and on northbound lanes from Rte. M to Rte. 61. Project involves bridges A0516, A0476 and A0476. $200,000 Strategic Highway Research Program. | 2026 | 249 | 770 | 0 | 770 | 0 | 0 | 0 | 0 | 0 | 18726 | 0 | 19745
Southeast | N | CAPE GIRARDEAU | US 61 S | 9S3782 | 1.4 | 5.184 | 0 | Pavement resurfacing from Rte. 177 to Drury Lane. | 2026 | 28 | 115 | 0 | 115 | 0 | 0 | 0 | 0 | 0 | 1142 | 0 | 1285
Southeast | N | CAPE GIRARDEAU | US 61 S | 9S3810 | 0.3 | 0.6 | 1 | Bridge replacement over Erlide Creek. Project involves bridge G0027. | 2026 | 51 | 38 | 0 | 38 | 0 | 9 | 0 | 9 | 0 | 665 | 0 | 763
Southeast | N | CAPE GIRARDEAU | US 61 S | SE0071 | 0.2 | 1 | 0 | Add intersection turn lanes and upgrade signals at Donna Drive. | 2027 | 13 | 200 | 410 | 610 | 0 | 346 | 0 | 346 | 0 | 0 | 1786 | 2755
Southeast | N | CAPE GIRARDEAU | US 61 S | SE0247 | 2.145 | 10.791 | 0 | Payment to Jackson to add corridor lighting on Rte. 61 from south of K Land Drive to Old Orchard Road. $926,552 Cost Share funds. | 2026 | 0 | 8 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 927 | 0 | 935
Southeast | N | CAPE GIRARDEAU | MO 74 E | 9P3862 | 0.25 | 1.041 | 0 | Payback to Cape Girardeau for eastbound intersection modification at Minnesota Avenue and construct westbound intersection at Minnesota Avenue. Design, right of way and construction by Cape Girardeau. $296,000 Cost Share funds. | 2026 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 296 | 0 | 306
Southeast | N | CAPE GIRARDEAU | MO 74 E | SE0304 | 0.2 | 1.082 | 0 | Upgrade pedestrian facilities at Rte. 177. | 2028 | 0 | 1 | 22 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 131
Southeast | N | CAPE GIRARDEAU | RT BB E | 9S3776 | 0.2 | 0.4 | 1 | Bridge rehabilitation over Caney Creek. Project involves bridge R0071. | 2026 | 51 | 161 | 0 | 161 | 5 | 0 | 0 | 0 | 0 | 757 | 0 | 974
Southeast | N | CAPE GIRARDEAU | RT D S | 9S3773 | 0.2 | 0.4 | 1 | Bridge replacement over Cane Creek. Project involves bridge P0714. | 2027 | 65 | 20 | 74 | 94 | 0 | 10 | 0 | 10 | 0 | 0 | 1020 | 1189
Southeast | N | CAPE GIRARDEAU | RT K E | 9S3847 | 2.6 | 5.2 | 0 | Roadway widening from County Road 319 to 0.2 mile west of I-55 in Cape Girardeau and add roundabout at Notre Dame Drive. $3,991,000 Open Container funds and $585,560 repurposed earmarks DEMO ID MO234. | 2026 | 419 | 1075 | 0 | 1075 | 0 | 336 | 0 | 336 | 0 | 12750 | 0 | 14580
Southeast | N | CAPE GIRARDEAU | RT N E | SE0044 | 0.023 | 0.046 | 1 | Bridge replacement over Whitewater River. Project involves bridge S0291. | 2028 | 54 | 20 | 344 | 364 | 0 | 0 | 26 | 26 | 0 | 0 | 1358 | 1802
Southeast | N | CAPE GIRARDEAU | RT N E | SE0045 | 0.09 | 0.18 | 1 | Bridge replacement over Small Creek. Project involves bridge S0532. | 2028 | 51 | 20 | 292 | 312 | 0 | 0 | 26 | 26 | 0 | 0 | 1177 | 1566
Southeast | N | CAPE GIRARDEAU | RT OO E | SE0030 | 0.026 | 0.052 | 1 | Bridge replacement over Whitewater River. Project involves bridge N0690. | 2026 | 395 | 577 | 0 | 577 | 20 | 0 | 0 | 0 | 0 | 3028 | 0 | 4020
Southeast | N | CAPE GIRARDEAU | RT P S | SE0310 | 12.376 | 24.752 | 0 | Pavement preservation treatment from Rte. 25 to Rte. 91. | 2028 | 0 | 5 | 65 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 546 | 616
Southeast | N | CAPE GIRARDEAU | RT Z E | 9S3738 | 0.35 | 0.7 | 2 | Bridge replacement over Hubble Creek and Hubble Creek Overflow. Project involves bridges T0788 and T0842. | 2026 | 427 | 188 | 0 | 188 | 42 | 0 | 0 | 0 | 0 | 3776 | 0 | 4433
Southeast | N | CARTER | BU 60 E | SE0022 | 2.067 | 4.134 | 0 | Pavement resurfacing on Bus. 60 in Van Buren. | 2028 | 3 | 4 | 81 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 725 | 813
Southeast | N | CARTER | US 60 W | SE0236 | 0 | 0.4 | 1 | Bridge improvement over Cane Creek. Project involves bridge A1195. | 2029 | 25 | 10 | 288 | 298 | 0 | 0 | 0 | 0 | 0 | 0 | 2053 | 2376
Southeast | N | CARTER | RT D S | SE0149 | 2.536 | 5.072 | 0 | Pavement resurfacing and add rumble stripes from 0.5 mile north of County Road 123 to Bus. 60. | 2026 | 30 | 119 | 0 | 119 | 0 | 0 | 0 | 0 | 0 | 1291 | 0 | 1440
Southeast | N | CARTER | RT N E | SE0051 | 0.141 | 0.282 | 1 | Bridge replacement over Middle Brushy Creek. Project involves bridge G0770. | 2029 | 109 | 20 | 317 | 337 | 0 | 0 | 7 | 7 | 0 | 0 | 1493 | 1946
Southeast | N | CHRISTIAN | RT T E | SE0014 | 8.383 | 16.766 | 0 | Pavement resurfacing from Rte. UU to Rte. 76 in Douglas County. | 2028 | 6 | 5 | 112 | 117 | 0 | 0 | 0 | 0 | 0 | 0 | 1022 | 1145
Southeast | N | DENT | MO 72 E | 9P3843 | 33.763 | 67.526 | 0 | Pavement resurfacing from the east intersection of Rte. 32 to the west intersection of Rte. 21. | 2027 | 40 | 18 | 599 | 617 | 0 | 0 | 0 | 0 | 0 | 0 | 5268 | 5925
Southeast | N | DOUGLAS | MO 14 E | 9P3808 | 12.552 | 25.299 | 0 | Pavement resurfacing and add rumble stripes from Rte. Z to Rte. 5. $2,933,000 Open Container funds. | 2027 | 24 | 80 | 503 | 583 | 0 | 0 | 0 | 0 | 0 | 0 | 6199 | 6806
Southeast | N | DOUGLAS | MO 14 E | SE0013 | 31.367 | 62.734 | 3 | Pavement resurfacing from Bus. 5 to Rte. 181. Project involves bridges H0344, J0437 and J0664. | 2029 | 19 | 22 | 434 | 456 | 0 | 0 | 0 | 0 | 0 | 0 | 4042 | 4517
Southeast | N | DOUGLAS | BU 5 S | SE0016 | 2.362 | 5.57 | 0 | Pavement resurfacing on Bus. 5 loop in Ava. | 2028 | 3 | 4 | 88 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 782 | 877
Southeast | N | DOUGLAS | MO 5 S | SE0297 | 0.2 | 0.4 | 0 | Intersection improvements at Rte. Y. | 2028 | 0 | 10 | 365 | 375 | 0 | 0 | 99 | 99 | 0 | 0 | 1919 | 2393
Southeast | N | DOUGLAS | MO 76 E | SE0012 | 33.111 | 66.222 | 1 | Pavement resurfacing from Rte. 5 to Rte. 181. Project involves bridge P0351. | 2029 | 18 | 25 | 450 | 475 | 0 | 0 | 0 | 0 | 0 | 0 | 4186 | 4679
Southeast | N | DOUGLAS | MO 76 E | SE0025 | 0.047 | 0.094 | 1 | Bridge rehabilitation over Indian Creek. Project involves bridge T0972. | 2027 | 43 | 20 | 149 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 1108 | 1320
Southeast | N | DOUGLAS | MO 76 E | SE0289 | 0.2 | 0.4 | 1 | Bridge replacement over Clifty Creek. Project involves bridge T0609. | 2030 | 0 | 20 | 320 | 340 | 0 | 0 | 30 | 30 | 0 | 0 | 1887 | 2257
Southeast | N | DUNKLIN | MO 153 S | SE0070 | 0.1 | 0.2 | 1 | Bridge replacement over Drainage Slough. Project involves bridge J0854. | 2027 | 24 | 57 | 105 | 162 | 0 | 27 | 0 | 27 | 0 | 0 | 544 | 757
Southeast | N | DUNKLIN | BU 25 S | SE0144 | 1.405 | 2.863 | 0 | Add center turn lane from Rte. 25 to Broadwater Road. | 2027 | 48 | 312 | 350 | 662 | 0 | 820 | 0 | 820 | 0 | 0 | 2122 | 3652
Southeast | N | DUNKLIN | US 412 E | 9P3766 | 0.239 | 0.956 | 1 | Payment to ARDOT for bridge repair on St. Francis River bridge. Project involves bridge A4554. | 2026 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 396 | 0 | 399
Southeast | N | DUNKLIN | MO 53 S | SE0221 | 0.2 | 0.4 | 1 | Bridge replacement over Lost Creek. Project involves bridge K0682. | 2029 | 10 | 17 | 265 | 282 | 0 | 0 | 18 | 18 | 0 | 0 | 1305 | 1615
Southeast | N | DUNKLIN | US 62 E | SE0155 | 1 | 2 | 1 | Bridge replacement over the St. Francis River. Project involves bridge H0927. $9,820,000 ARDOT funds. | 2026 | 1800 | 1862 | 0 | 1862 | 50 | 0 | 0 | 0 | 0 | 15928 | 0 | 19640
Southeast | N | DUNKLIN | MO 84 E | 9P3839 | 2.086 | 5.431 | 0 | Pavement resurfacing from Rte. O to Rte. 412 in Kennett. | 2026 | 11 | 105 | 0 | 105 | 0 | 0 | 0 | 0 | 0 | 958 | 0 | 1074
Southeast | N | DUNKLIN | MO 84 E | SE0132 | 1.2 | 3.95 | 0 | Replace signals at Kennett Street and Main Street in Kennett, Rte. 61 and Cape Rock Drive in Cape Girardeau and at Rte. 62 and Rte. 105 in Charleston. | 2027 | 103 | 50 | 239 | 289 | 0 | 960 | 0 | 960 | 0 | 0 | 1716 | 3068
Southeast | N | DUNKLIN | RT DD W | SE0095 | 0.367 | 0.737 | 4 | Bridge painting over Saint Francis River, Black River and over Rte. 60 at Marble Hill Road and Rte. T in Butler County. Project involves bridges A2382, A3723, A3266 and A3681. | 2027 | 16 | 30 | 144 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 1416 | 1606
Southeast | N | DUNKLIN | RT MM N | SE0130 | 0.2 | 0.4 | 1 | Bridge replacement over Lateral Ditch 1. Project involves bridge N0626. | 2028 | 8 | 107 | 260 | 367 | 0 | 0 | 21 | 21 | 0 | 0 | 1128 | 1524
Southeast | N | DUNKLIN | RT NN S | SE0308 | 16.24 | 32.48 | 0 | Pavement preservation from Rte. 412 to the Arkansas State line. | 2028 | 0 | 5 | 86 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 864 | 955
Southeast | N | DUNKLIN | RT UU E | SE0065 | 0.4 | 0.8 | 2 | Bridge replacement over Lateral Ditch 78 and Lateral Ditch 79. Project involves bridges P0663 and P0664. | 2027 | 30 | 206 | 245 | 451 | 0 | 40 | 0 | 40 | 0 | 0 | 1413 | 1934
Southeast | N | DUNKLIN | RT Z S | 9S3774 | 0.2 | 0.4 | 1 | Bridge replacement over Main Drainage Ditch. Project involves bridge S0924. | 2026 | 60 | 112 | 0 | 112 | 0 | 5 | 0 | 5 | 0 | 1326 | 0 | 1503
Southeast | N | HOWELL | MO 137 S | 9S3801 | 0.223 | 0.446 | 1 | Bridge replacement over BNSF Railway. Project involves bridge K0789. | 2026 | 428 | 703 | 0 | 703 | 0 | 1231 | 0 | 1231 | 0 | 3468 | 0 | 5830
Southeast | N | HOWELL | MO 142 E | 9S3684 | 0.2 | 0.4 | 1 | Bridge replacement over Myatt Creek. Project involves bridge P0058. | 2027 | 120 | 50 | 355 | 405 | 0 | 11 | 0 | 11 | 0 | 0 | 1656 | 2192
Southeast | N | HOWELL | MO 142 E | 9S3846 | 26.175 | 52.35 | 0 | Pavement resurfacing from Rte. E to Bus. 63 in Thayer. | 2027 | 31 | 16 | 312 | 328 | 0 | 0 | 0 | 0 | 0 | 0 | 2871 | 3230
Southeast | N | HOWELL | US 160 E | SE0006 | 0.593 | 2.895 | 0 | Pavement resurfacing from County Road 6070 to Rte. 63. | 2026 | 6 | 40 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 357 | 0 | 403
Southeast | N | HOWELL | MO 17 S | 9S3692 | 17.865 | 35.73 | 0 | Pavement resurfacing from Rte. 63 to Arkansas State line. | 2026 | 57 | 547 | 0 | 547 | 0 | 0 | 0 | 0 | 0 | 4702 | 0 | 5306
Southeast | N | HOWELL | US 63 S | SE0004 | 4.705 | 9.41 | 0 | Pavement resurfacing from south of Rte. 60 to north of Rte. P. | 2026 | 44 | 151 | 0 | 151 | 0 | 0 | 0 | 0 | 0 | 1518 | 0 | 1713
Southeast | N | HOWELL | RT CC E | SE0306 | 10.381 | 20.762 | 0 | Add rumble stripes from Rte. AD to Rte. 63. $955,000 Open Container funds. | 2028 | 0 | 10 | 320 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 2243 | 2573
Southeast | N | HOWELL | RT DD E | SE0009 | 3.726 | 7.452 | 0 | Pavement resurfacing from Rte. 137 to end of state maintenance. | 2026 | 7 | 45 | 0 | 45 | 0 | 0 | 0 | 0 | 0 | 408 | 0 | 460
Southeast | N | HOWELL | RT JJ S | SE0011 | 12.994 | 25.988 | 0 | Pavement resurfacing from Rte. 160 to Arkansas State line (two disconnected sections). | 2029 | 8 | 9 | 185 | 194 | 0 | 0 | 0 | 0 | 0 | 0 | 1713 | 1915
Southeast | N | HOWELL | RT JJ S | SE0034 | 0.061 | 0.122 | 1 | Bridge replacement over South Fork Spring River. Project involves bridge P0797. | 2027 | 73 | 50 | 284 | 334 | 0 | 17 | 0 | 17 | 0 | 0 | 1281 | 1705
Southeast | N | HOWELL | RT WW S | SE0008 | 3.777 | 7.554 | 0 | Pavement resurfacing from Rte. 17 to end of state maintenance. | 2026 | 7 | 47 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 421 | 0 | 475
Southeast | N | HOWELL | RT ZZ E | 9S3845 | 7.579 | 15.158 | 0 | Pavement resurfacing from Rte. 63 to end of state maintenance. | 2026 | 9 | 98 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 832 | 0 | 939
Southeast | N | IRON | MO 21 S | 9P3570 | 6.81 | 13.62 | 0 | Pavement resurfacing from Rte. 32 to Rte. N. | 2027 | 22 | 10 | 216 | 226 | 0 | 0 | 0 | 0 | 0 | 0 | 1990 | 2238
Southeast | N | IRON | MO 32 E | SE0038 | 0.085 | 0.17 | 1 | Bridge replacement over Reid Creek. Project involves bridge G0269. | 2029 | 42 | 20 | 431 | 451 | 0 | 0 | 34 | 34 | 0 | 0 | 1650 | 2177
Southeast | N | IRON | MO 32 E | SE0039 | 0.059 | 0.118 | 1 | Bridge replacement over Richardson Creek. Project involves bridge G0270. | 2029 | 42 | 20 | 219 | 239 | 0 | 0 | 18 | 18 | 0 | 0 | 933 | 1232
Southeast | N | IRON | MO 32 E | SE0040 | 0.326 | 0.652 | 1 | Bridge replacement over Keesling Creek. Project involves bridge G0272. | 2029 | 33 | 20 | 322 | 342 | 0 | 0 | 17 | 17 | 0 | 0 | 1257 | 1649
Southeast | N | IRON | MO 32 E | SE0148 | 8.22 | 16.44 | 0 | Pavement preservation treatment, add shoulders, curve widening and curve relocation from Rte. KK to Rte. Z. | 2028 | 112 | 50 | 742 | 792 | 0 | 0 | 39 | 39 | 0 | 0 | 5753 | 6696
Southeast | N | IRON | MO 49 S | SE0240 | 0.2 | 0.4 | 1 | Bridge improvement over Union Pacific Railroad. Project involves bridge G0878. | 2029 | 20 | 40 | 495 | 535 | 0 | 0 | 33 | 33 | 0 | 0 | 1854 | 2442
Southeast | N | IRON | RT E E | SE0241 | 0.2 | 0.4 | 1 | Bridge improvement over Marble Creek. Project involves bridge T0222. | 2029 | 20 | 30 | 507 | 537 | 0 | 0 | 33 | 33 | 0 | 0 | 1864 | 2454
Southeast | N | IRON | RT M E | SE0120 | 0.2 | 0.4 | 1 | Bridge box culvert extension over Mill Dam Creek. Project involves bridge X0524. | 2027 | 47 | 30 | 54 | 84 | 0 | 8 | 0 | 8 | 0 | 0 | 447 | 586
Southeast | N | IRON | RT U E | SE0239 | 0.2 | 0.4 | 1 | Bridge improvement over Branch East Fork Cedar Creek. Project involves bridge F0989. | 2029 | 5 | 15 | 326 | 341 | 0 | 0 | 33 | 33 | 0 | 0 | 1159 | 1538
Southeast | N | LACLEDE | MO 95 S | 9S3696 | 28.66 | 57.32 | 1 | Pavement and bridge resurfacing from Rte. 32 to Rte. 60. Project involves bridge A2113. | 2026 | 35 | 526 | 0 | 526 | 0 | 0 | 0 | 0 | 0 | 4367 | 0 | 4928
Southeast | N | MADISON | BU 67 S | SE0018 | 3.908 | 7.816 | 0 | Pavement resurfacing from Rte. 72 to County Road 205. | 2028 | 5 | 7 | 133 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 1085 | 1230
Southeast | N | MADISON | E OR 67 S | SE0017 | 0.695 | 1.39 | 0 | Pavement resurfacing from Rte. 72 to end of state maintenance. | 2028 | 3 | 1 | 16 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 132 | 152
Southeast | N | MADISON | US 67 S | SE0069 | 1.4 | 5.598 | 0 | Add J-turns at Rte. A and Rte. C. | 2026 | 29 | 219 | 0 | 219 | 0 | 0 | 0 | 0 | 0 | 1885 | 0 | 2133
Southeast | N | MADISON | MO 72 E | SE0043 | 2.253 | 4.478 | 0 | Pavement resurfacing from Rte. 67 to Rte. OO. | 2028 | 13 | 5 | 80 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 935 | 1033
Southeast | N | MADISON | MO 72 W | SE0085 | 0.2 | 0.4 | 1 | Bridge replacement over Turkey Creek. Project involves bridge G0328. | 2026 | 290 | 252 | 0 | 252 | 0 | 41 | 0 | 41 | 0 | 2208 | 0 | 2791
Southeast | N | MADISON | RT C E | SE0035 | 0.048 | 0.096 | 1 | Bridge replacement over Leatherwood Creek. Project involves bridge T0763. | 2027 | 59 | 105 | 313 | 418 | 0 | 13 | 0 | 13 | 0 | 0 | 1505 | 1995
Southeast | N | MADISON | RT C E | SE0160 | 0.07 | 0.14 | 0 | Slope repairs 0.1 mile west of Saint Francis River. | 2029 | 106 | 1 | 102 | 103 | 5 | 0 | 0 | 0 | 0 | 0 | 1115 | 1329
Southeast | N | MADISON | RT E E | SE0293 | 0.2 | 0.4 | 1 | Bridge rehabilitation over Marble Creek. Project involves bridge N0271. | 2030 | 0 | 20 | 270 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 1627 | 1917
Southeast | N | MADISON | RT E E | SE0298 | 16.1 | 32.2 | 0 | Pavement preservation treatment from Iron County line to Rte. 67. | 2028 | 0 | 5 | 77 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 656 | 738
Southeast | N | MADISON | RT M S | SE0036 | 0.088 | 0.176 | 1 | Bridge replacement over Shetley Creek. Project involves bridge T0092. | 2027 | 69 | 90 | 333 | 423 | 0 | 13 | 0 | 13 | 0 | 0 | 1551 | 2056
Southeast | N | MADISON | RT M S | SE0037 | 0.046 | 0.092 | 1 | Bridge replacement over Big Creek. Project involves bridge T0093. | 2027 | 59 | 80 | 299 | 379 | 0 | 13 | 0 | 13 | 0 | 0 | 1377 | 1828
Southeast | N | MISSISSIPPI | IS 57 N | 9I3730 | 1.728 | 5.475 | 0 | Pavement resurfacing in the northbound lane from east of Rte. B to west of Rte. 105 and from Rte. 105 to Rte. 60 and on I-55 in the southbound lane from 0.6 mile north of Rte. O to the Arkansas State line. | 2028 | 20 | 50 | 750 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 14678 | 15498
Southeast | N | MISSISSIPPI | IS 57 N | SE0332 | 0 | 3.6 | 0 | Rebuild pavement from Big Lake Bayou to the Mississippi River. | 2026 | 0 | 380 | 0 | 380 | 0 | 0 | 0 | 0 | 0 | 4081 | 0 | 4461
Southeast | N | MISSISSIPPI | IS 57 S | 9I3583 | 0.5 | 2 | 1 | Payment to IDOT for bridge painting on Mississippi River "Cairo bridge". Project involves bridge A2000. | 2026 | 6 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 22000 | 0 | 22007
Southeast | N | MISSISSIPPI | IS 57 S | SE0187 | 0.5 | 2 | 1 | Payment to IDOT for deck overlay and joint repairs on Mississippi River "Cairo bridge". Project involves bridge A2000. | 2029 | 1 | 1 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 6605
Southeast | N | MISSISSIPPI | US 60 E | 9S3707 | 4.841 | 9.682 | 0 | Add rumble stripes from Rte. EE to Mississippi River Bridge. | 2030 | 22 | 1 | 106 | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 884 | 1013
Southeast | N | MISSISSIPPI | US 60 E | SE0183 | 0.456 | 0.912 | 1 | Payment to IDOT for end of life study on bridge over the Mississippi River at Cairo. Project involves bridge K0950. | 2026 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 1501
Southeast | N | MISSISSIPPI | MO 77 S | SE0062 | 0.8 | 1.6 | 4 | Bridge replacement over Lateral Ditch 3, Main Ditch, Lateral Ditch 4 and Lateral Ditch 7. Project involves bridges T0418, T0419, T0542 and T0543. | 2027 | 250 | 536 | 867 | 1403 | 0 | 80 | 0 | 80 | 0 | 0 | 4868 | 6601
Southeast | N | MISSISSIPPI | MO 80 E | SE0077 | 0.4 | 0.8 | 2 | Bridge replacement over Drainage Ditch 23 and Drainage Ditch 29. Project involves bridges F0786 and F0788. | 2027 | 16 | 249 | 374 | 623 | 0 | 20 | 0 | 20 | 0 | 0 | 1879 | 2538
Southeast | N | MISSISSIPPI | RT B S | SE0303 | 8.91 | 17.822 | 0 | Pavement preservation treatment from Rte. 62 to Rte. 80. | 2028 | 0 | 5 | 64 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 524 | 593
Southeast | N | MISSISSIPPI | RT BB S | SE0266 | 7.514 | 15.028 | 0 | Pavement preservation treatment from Rte. 80 to Rte. P. | 2028 | 0 | 5 | 51 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 326 | 382
Southeast | N | NEW MADRID | US 61 S | 9S3798 | 0.752 | 1.504 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in Bernie, Campbell and Portageville. | 2026 | 63 | 105 | 0 | 105 | 0 | 5 | 0 | 5 | 0 | 1542 | 0 | 1715
Southeast | N | NEW MADRID | US 61 S | SE0234 | 1 | 2 | 0 | Intersection improvement at Rte. 80. | 2027 | 50 | 100 | 350 | 450 | 0 | 17 | 0 | 17 | 0 | 0 | 2320 | 2837
Southeast | N | NEW MADRID | RT J N | SE0059 | 3.97 | 7.94 | 0 | Pavement resurfacing from Rte. 62 to Rte. 153. | 2026 | 11 | 46 | 0 | 46 | 0 | 0 | 0 | 0 | 0 | 442 | 0 | 499
Southeast | N | NEW MADRID | RT ZZ W | SE0107 | 0.2 | 0.4 | 1 | Bridge replacement over Drainage Ditch 52. Project involves bridge T0783. | 2027 | 30 | 62 | 156 | 218 | 0 | 20 | 0 | 20 | 0 | 0 | 731 | 999
Southeast | N | OREGON | MO 142 E | 9P3686 | 0.961 | 1.922 | 1 | Bridge replacement over Eleven Point River and raise roadway from bridge east 0.6 mile. Project involves bridge T0395. | 2027 | 505 | 359 | 758 | 1117 | 0 | 83 | 0 | 83 | 0 | 0 | 4801 | 6506
Southeast | N | OREGON | US 160 E | 9S3802 | 0.2 | 0.4 | 1 | Bridge replacement over Cox Creek. Project involves bridge H0173. | 2026 | 129 | 250 | 0 | 250 | 0 | 10 | 0 | 10 | 0 | 1161 | 0 | 1550
Southeast | N | OREGON | US 160 E | SE0021 | 28.747 | 57.52 | 1 | Pavement resurfacing from Rte. FF to Rte. 21 and add rumble stripes from Rte. C to Rte. 21. Project involves bridge A2910. | 2029 | 51 | 55 | 661 | 716 | 0 | 0 | 0 | 0 | 0 | 0 | 5890 | 6657
Southeast | N | OREGON | US 160 E | SE0041 | 0.041 | 0.082 | 1 | Bridge replacement over Barren Fork Creek. Project involves bridge H0458. | 2028 | 93 | 50 | 498 | 548 | 0 | 0 | 18 | 18 | 0 | 0 | 2076 | 2735
Southeast | N | OREGON | US 160 E | SE0190 | 0.4 | 0.8 | 1 | Bridge replacement over Eleven Point River. Project involves bridge K0272. | 2030 | 0 | 50 | 590 | 640 | 0 | 0 | 27 | 27 | 0 | 0 | 3658 | 4325
Southeast | N | OREGON | US 160 E | SE0290 | 0.2 | 0.4 | 1 | Bridge replacement over Dry Creek. Project involves bridge H0174. | 2030 | 0 | 20 | 370 | 390 | 0 | 0 | 33 | 33 | 0 | 0 | 2186 | 2609
Southeast | N | OREGON | MO 19 S | SE0033 | 0.102 | 0.204 | 1 | Bridge replacement over Eleven Point River. Project involves bridge K0344. | 2027 | 156 | 250 | 960 | 1210 | 0 | 35 | 0 | 35 | 0 | 0 | 4311 | 5712
Southeast | N | OREGON | RT AA E | 9S3809 | 9.179 | 18.358 | 0 | Pavement resurfacing from Rte. 19 to end of state maintenance. | 2026 | 10 | 114 | 0 | 114 | 0 | 0 | 0 | 0 | 0 | 954 | 0 | 1078
Southeast | N | OREGON | CST WALNUT ST E | SE0295 | 0.2 | 0.4 | 1 | Bridge rehabilitation over Warm Fork Spring River and BNSF Railway. Project involves bridge A1476. | 2030 | 0 | 60 | 680 | 740 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 4940
Southeast | N | OZARK | MO 142 E | SE0311 | 9.721 | 19.442 | 0 | Pavement preservation treatment from Rte. 101 to the north intersection of Rte. E. | 2028 | 0 | 5 | 56 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 404 | 465
Southeast | N | OZARK | US 160 E | SE0185 | 1 | 2 | 1 | Bridge replacement over Bull Shoals Lake. Project involves bridge K0817. | 2029 | 500 | 500 | 14161 | 14661 | 0 | 0 | 3050 | 3050 | 0 | 0 | 82181 | 100392
Southeast | N | OZARK | MO 95 S | SE0191 | 0.4 | 0.8 | 1 | Bridge replacement over Brixey Creek. Project involves bridge N0328. | 2030 | 0 | 20 | 185 | 205 | 0 | 0 | 19 | 19 | 0 | 0 | 1730 | 1954
Southeast | N | OZARK | RT N E | SE0192 | 0.4 | 0.8 | 1 | Bridge replacement over Fork Pine Creek. Project involves bridge Y0579. | 2030 | 0 | 10 | 92 | 102 | 0 | 0 | 4 | 4 | 0 | 0 | 685 | 791
Southeast | N | OZARK | RT PP S | SE0015 | 5.308 | 10.616 | 0 | Pavement resurfacing from Rte. H to Rte. 160. | 2028 | 3 | 4 | 77 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 696 | 780
Southeast | N | PEMISCOT | IS 155 N | SE0189 | 0.5 | 2 | 1 | Payment to TDOT for structural repairs at Caruthersville Mississippi River Bridge. Project involves bridge A1700. | 2026 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4797 | 0 | 4798
Southeast | N | PEMISCOT | IS 155 S | SE0171 | 0.584 | 2.338 | 1 | Bridge washing over the Mississippi River. Project involves bridges A1700. | 2028 | 2 | 1 | 20 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 212 | 235
Southeast | N | PEMISCOT | IS 155 S | SE0257 | 0.562 | 2.248 | 1 | Payment to TDOT for bridge rehabilitation over the Mississippi River. Project involves bridge A1700. | 2030 | 0 | 1 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 35005
Southeast | N | PEMISCOT | MO 84 E | SE0167 | 0.2 | 0.4 | 1 | Payment to Pemiscot County for bridge replacement over Drainage Ditch No. 6. Project involves bridge J0291. $822,834 Governor's Cost Share Program funds. | 2026 | 3 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 823 | 0 | 828
Southeast | N | PEMISCOT | RT A E | SE0178 | 0.389 | 0.778 | 0 | Upgrade pedestrian facilities at various locations in New Hamburg and Wardell. | 2028 | 75 | 5 | 144 | 149 | 0 | 2 | 0 | 2 | 0 | 0 | 1879 | 2105
Southeast | N | PEMISCOT | RT A E | SE0220 | 0.2 | 0.4 | 1 | Bridge replacement over Clay Root Bay. Project involves bridge T0697. | 2029 | 5 | 5 | 210 | 215 | 0 | 0 | 22 | 22 | 0 | 0 | 952 | 1194
Southeast | N | PEMISCOT | RT C S | 9S3770 | 0.2 | 0.4 | 1 | Bridge replacement over Drainage Ditch 4. Project involves bridge S0712. | 2026 | 51 | 65 | 0 | 65 | 0 | 2 | 0 | 2 | 0 | 748 | 0 | 866
Southeast | N | PEMISCOT | RT C S | SE0258 | 0.014 | 0.028 | 1 | Bridge replacement over Drainage Ditch 1. Project involves bridge S0715. | 2030 | 0 | 2 | 183 | 185 | 0 | 0 | 25 | 25 | 0 | 0 | 894 | 1104
Southeast | N | PEMISCOT | RT D S | SE0075 | 6.07 | 12.14 | 0 | Pavement resurfacing and add rumble stripes from Rte. U to Rte. 164. | 2026 | 23 | 317 | 0 | 317 | 0 | 0 | 0 | 0 | 0 | 1604 | 0 | 1944
Southeast | N | PEMISCOT | RT DD S | SE0074 | 6.469 | 12.938 | 0 | Pavement resurfacing from Rte. 164 to Arkansas State line. | 2026 | 3 | 90 | 0 | 90 | 0 | 0 | 0 | 0 | 0 | 725 | 0 | 818
Southeast | N | PEMISCOT | RT J E | SE0105 | 4.926 | 9.852 | 0 | Pavement resurfacing from Rte. 84 to Rte. K. | 2026 | 6 | 79 | 0 | 79 | 0 | 0 | 0 | 0 | 0 | 545 | 0 | 630
Southeast | N | PEMISCOT | RT Z S | SE0222 | 0.2 | 0.4 | 1 | Bridge replacement over Main Ditch 1. Project involves bridge N0186. | 2029 | 11 | 20 | 410 | 430 | 0 | 0 | 42 | 42 | 0 | 0 | 1870 | 2353
Southeast | N | PERRY | MO 51 S | SE0246 | 0.359 | 1.077 | 0 | Payment to Perryville to add roundabout at Alma Avenue. $1,605,000 Cost Share funds. | 2026 | 8 | 7 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 1605 | 0 | 1620
Southeast | N | PERRY | RT C S | SE0056 | 0.017 | 0.034 | 1 | Bridge replacement over Apple Creek. Project involves bridge P0803. | 2026 | 278 | 268 | 0 | 268 | 0 | 21 | 0 | 21 | 0 | 2346 | 0 | 2913
Southeast | N | PERRY | RT C S | SE0283 | 0.2 | 0.4 | 1 | Bridge replacement over Cinque Hommes Creek. Project involves bridge A0901. | 2030 | 0 | 10 | 456 | 466 | 0 | 0 | 5 | 5 | 0 | 0 | 3046 | 3517
Southeast | N | PERRY | RT E S | SE0284 | 0.2 | 0.4 | 1 | Bridge rehabilitation over Bois Brule Creek. Project involves bridge N0661. | 2030 | 0 | 5 | 195 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 1076 | 1276
Southeast | N | PERRY | RT K S | 9S3671 | 0.2 | 0.4 | 1 | Bridge replacement over Apple Creek. Project involves bridge N0877. | 2026 | 117 | 151 | 0 | 151 | 0 | 6 | 0 | 6 | 0 | 1107 | 0 | 1381
Southeast | N | PERRY | RT NN E | 9S3771 | 0.2 | 0.4 | 1 | Bridge replacement over Saline Creek. Project involves bridge N0062. | 2026 | 138 | 138 | 0 | 138 | 0 | 2 | 0 | 2 | 0 | 1576 | 0 | 1854
Southeast | N | PERRY | RT O E | SE0279 | 0.2 | 0.4 | 1 | Bridge replacement over Apple Creek. Project involves bridge N0606. | 2030 | 0 | 10 | 314 | 324 | 0 | 0 | 5 | 5 | 0 | 0 | 2036 | 2365
Southeast | N | PERRY | RT T E | 9S3670 | 0.2 | 0.4 | 1 | Bridge replacement over Saline Creek. Project involves bridge S0734. | 2026 | 303 | 279 | 0 | 279 | 0 | 28 | 0 | 28 | 0 | 2269 | 0 | 2879
Southeast | N | REYNOLDS | MO 34 E | SE0003 | 9.214 | 18.428 | 0 | Pavement resurfacing from Rte. 21 to near Wayne County line. | 2026 | 25 | 194 | 0 | 194 | 0 | 0 | 0 | 0 | 0 | 1705 | 0 | 1924
Southeast | N | RIPLEY | MO 142 E | 9S3685 | 0.2 | 0.4 | 1 | Bridge replacement over Drainage Ditch 2. Project involves bridge T0758. | 2026 | 124 | 130 | 0 | 130 | 8 | 0 | 0 | 0 | 0 | 1078 | 0 | 1340
Southeast | N | RIPLEY | MO 142 E | SE0031 | 0.038 | 0.076 | 1 | Bridge replacement over Harris Creek. Project involves bridge S0814. | 2026 | 163 | 159 | 0 | 159 | 14 | 0 | 0 | 0 | 0 | 986 | 0 | 1322
Southeast | N | RIPLEY | MO 142 E | SE0032 | 0.043 | 0.086 | 1 | Bridge replacement over Logan Creek. Project involves bridge S0889. | 2027 | 64 | 65 | 320 | 385 | 0 | 17 | 0 | 17 | 0 | 0 | 1415 | 1881
Southeast | N | RIPLEY | US 160 E | 9S3806 | 9.126 | 23.564 | 1 | Pavement and bridge resurfacing from south intersection of Rte. 21 to Rte. JJ. Project involves bridge A3087. | 2026 | 37 | 631 | 0 | 631 | 0 | 0 | 0 | 0 | 0 | 6331 | 0 | 6999
Southeast | N | RIPLEY | RT W S | 9S3817 | 0.2 | 0.4 | 1 | Bridge replacement over Drainage Ditch 1. Project involves bridge P0676. | 2026 | 180 | 173 | 0 | 173 | 7 | 0 | 0 | 0 | 0 | 1092 | 0 | 1452
Southeast | N | RIPLEY | RT W S | 9S3848 | 0.2 | 0.4 | 1 | Bridge replacement over Drainage Ditch 3. Project involves bridge P0677. | 2026 | 181 | 173 | 0 | 173 | 7 | 0 | 0 | 0 | 0 | 1095 | 0 | 1456
Southeast | N | SCOTT | US 61 S | 9S3777 | 11.03 | 22.876 | 0 | Pavement resurfacing from Rte. 77 to Rte. Y. | 2027 | 31 | 50 | 280 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 3367 | 3728
Southeast | N | SCOTT | US 61 S | SE0235 | 1.284 | 0 | 0 | Upgrade pedestrian signals and pavement markings at Tanner Street, Lake Street and Pine Street. | 2027 | 25 | 50 | 140 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 855 | 1070
Southeast | N | SCOTT | MO 77 S | SE0213 | 0.2 | 0.4 | 1 | Bridge replacement over Drainage Ditch 1. Project involves bridge J0384. | 2030 | 2 | 5 | 322 | 327 | 0 | 0 | 36 | 36 | 0 | 0 | 1467 | 1832
Southeast | N | SCOTT | MO 91 S | SE0278 | 0.2 | 0.4 | 1 | Bridge replacement over Drain Ditch 1. Project involves bridge S0615. | 2030 | 0 | 20 | 184 | 204 | 0 | 0 | 15 | 15 | 0 | 0 | 1174 | 1393
Southeast | N | SCOTT | MO 91 S | SE0280 | 0.2 | 0.4 | 1 | Bridge replacement over Drainage Ditch 4. Project involves bridge S0616. | 2030 | 0 | 20 | 180 | 200 | 0 | 0 | 15 | 15 | 0 | 0 | 1103 | 1318
Southeast | N | SCOTT | RT A E | 9S3827 | 9.02 | 18.163 | 1 | Pavement resurfacing from Rte. 77 to Rte. 61. Project involves bridge A6451. | 2027 | 11 | 25 | 127 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 1337 | 1500
Southeast | N | SCOTT | RT C E | 9S3727 | 0.228 | 0.456 | 1 | Bridge replacement over St. Johns Drainage Ditch. Project involves bridge N0761. | 2026 | 124 | 282 | 0 | 282 | 10 | 0 | 0 | 0 | 0 | 1291 | 0 | 1707
Southeast | N | SCOTT | RT N N | SE0143 | 0.1 | 0.2 | 0 | Intersection improvements at Rte. K. | 2027 | 15 | 30 | 50 | 80 | 0 | 136 | 0 | 136 | 0 | 0 | 692 | 923
Southeast | N | SCOTT | RT N S | 9S3811 | 10.09 | 20.18 | 0 | Pavement resurfacing from Rte. E to Rte. D. | 2027 | 10 | 20 | 106 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 1113 | 1249
Southeast | N | SCOTT | RT O S | SE0281 | 0.2 | 0.4 | 1 | Bridge replacement over North Cut Ditch. Project involves bridge N0257. | 2030 | 0 | 10 | 314 | 324 | 0 | 0 | 11 | 11 | 0 | 0 | 2108 | 2443
Southeast | N | SCOTT | RT Y E | SE0150 | 0.5 | 1 | 0 | Add roundabout at Rte. BB. | 2026 | 135 | 160 | 0 | 160 | 12 | 0 | 0 | 0 | 0 | 2037 | 0 | 2344
Southeast | N | SCOTT | RT Y E | SE0267 | 0.2 | 0.4 | 1 | Bridge replacement over Drainage Ditch 2. Project involves bridge L0299. | 2030 | 0 | 20 | 270 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 1645 | 1935
Southeast | N | SCOTT | RT Y E | SE0288 | 0.2 | 0.4 | 1 | Bridge replacement over Drainage Ditch 1. Project involves bridge L0300. | 2030 | 0 | 10 | 250 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 1422 | 1682
Southeast | N | SCOTT | RT ZZ E | SE0285 | 0.2 | 0.4 | 1 | Bridge replacement over Drainage Ditch 1. Project involves bridge L0270. | 2030 | 0 | 5 | 145 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 842 | 992
Southeast | N | SHANNON | MO 19 S | 9P3814 | 0.259 | 0.518 | 1 | Bridge replacement over Spring Valley Creek. Project involves bridge J0420. | 2026 | 1022 | 1317 | 0 | 1317 | 0 | 440 | 0 | 440 | 0 | 7142 | 0 | 9921
Southeast | N | SHANNON | MO 99 S | SE0193 | 0.2 | 0.4 | 1 | Bridge replacement over Spring Creek. Project involves bridge K0274. | 2030 | 0 | 20 | 288 | 308 | 0 | 0 | 23 | 23 | 0 | 0 | 2101 | 2432
Southeast | N | SHANNON | RT JJ S | SE0194 | 0.2 | 0.4 | 1 | Bridge replacement over Castro Valley. Project involves bridge N0185. | 2030 | 0 | 20 | 260 | 280 | 0 | 0 | 10 | 10 | 0 | 0 | 1608 | 1898
Southeast | N | ST. FRANCOIS | MO 221 S | 9S3853 | 0.082 | 0.246 | 1 | Box culvert replacement over Brewers Creek. Project involves bridge Y0935. | 2026 | 68 | 130 | 0 | 130 | 0 | 27 | 0 | 27 | 0 | 1124 | 0 | 1349
Southeast | N | ST. FRANCOIS | MO 32 E | 9P3852 | 6.954 | 13.908 | 2 | Pavement and bridge resurfacing from High Street in Bismark to the south intersection of Bus. 32. Project involves bridges A2668 and A2670. | 2027 | 34 | 16 | 341 | 357 | 0 | 0 | 0 | 0 | 0 | 0 | 3133 | 3524
Southeast | N | ST. FRANCOIS | BU 67 S | 9S3851 | 0.911 | 1.863 | 0 | Pavement resurfacing from Rte. 8. to Main Street through Park Hills. | 2027 | 12 | 24 | 78 | 102 | 0 | 94 | 0 | 94 | 0 | 0 | 794 | 1002
Southeast | N | ST. FRANCOIS | US 67 N | SE0195 | 0 | 0.834 | 1 | Bridge replacement over Rte. 8. Project involves bridge A0654. | 2030 | 0 | 10 | 330 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 1990 | 2330
Southeast | N | ST. FRANCOIS | US 67 S | SE0068 | 0.4 | 1.615 | 1 | Interchange improvements and bridge replacement at Rte. 32 in Leadington. Project involves bridge A0144. | 2029 | 751 | 500 | 1567 | 2067 | 0 | 0 | 64 | 64 | 0 | 0 | 13014 | 15896
Southeast | N | ST. FRANCOIS | US 67 S | SE0233 | 1.2 | 4.876 | 0 | Intersection improvements at Hildebrecht Road. | 2027 | 75 | 75 | 222 | 297 | 0 | 0 | 0 | 0 | 0 | 0 | 1836 | 2208
Southeast | N | ST. FRANCOIS | MO 8 E | SE0010 | 6.85 | 14.12 | 0 | Pavement resurfacing and intersection improvements from the Washington County line to RR Bridge (Bus. 67) and add shoulders from east of Rte. P to RR Bridge (Bus. 67). | 2028 | 43 | 50 | 700 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 5038 | 5831
Southeast | N | ST. FRANCOIS | RT D S | SE0050 | 0.52 | 1.04 | 0 | Rebuild pavement and add turn lanes from Rte. EE to Rte. 32. | 2027 | 132 | 400 | 514 | 914 | 0 | 312 | 0 | 312 | 0 | 0 | 2492 | 3850
Southeast | N | ST. FRANCOIS | RT D S | SE0305 | 9.255 | 18.51 | 0 | Add rumble stripes from Rte. K to Rte. EE. $1,989,000 Open Container funds. | 2028 | 0 | 10 | 337 | 347 | 0 | 0 | 0 | 0 | 0 | 0 | 2110 | 2457
Southeast | N | ST. FRANCOIS | RT K E | SE0019 | 6.953 | 14.094 | 0 | Pavement resurfacing from Rte. 47 to Rte. D. | 2028 | 9 | 9 | 140 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 1299 | 1457
Southeast | N | ST. FRANCOIS | RT K E | SE0154 | 0.135 | 0.299 | 0 | Intersection improvements at North Wood Drive. | 2029 | 26 | 20 | 201 | 221 | 0 | 0 | 724 | 724 | 0 | 0 | 1727 | 2698
Southeast | N | ST. FRANCOIS | RT K E | SE0294 | 0.2 | 0.4 | 1 | Bridge rehabilitation over Big River. Project involves bridge A0968. | 2030 | 0 | 40 | 440 | 480 | 0 | 0 | 0 | 0 | 0 | 0 | 2688 | 3168
Southeast | N | ST. FRANCOIS | RT N S | SE0232 | 9.481 | 18.962 | 1 | Pavement resurfacing and add rumble stripes from Rte. 32 to Rte. 21. Project involves bridge K0401. | 2027 | 40 | 100 | 557 | 657 | 0 | 0 | 0 | 0 | 0 | 0 | 4308 | 5005
Southeast | N | ST. FRANCOIS | RT OO S | 9S3490 | 16.76 | 33.52 | 0 | Pavement resurfacing and add rumble stripes from 0.1 mile south of Rte. 32 in Farmington to Rte. 72 in Fredericktown. | 2028 | 214 | 100 | 588 | 688 | 0 | 0 | 0 | 0 | 0 | 0 | 5263 | 6165
Southeast | N | STE. GENEVIEVE | MO 32 E | 9S3854 | 0.8 | 2 | 0 | Drainage improvements 0.2 mile east of Rte. 61 and at Siebert Road. | 2027 | 150 | 10 | 166 | 176 | 0 | 135 | 0 | 135 | 0 | 0 | 1326 | 1787
Southeast | N | STE. GENEVIEVE | IS 55 S | SE0175 | 198.084 | 0 | 0 | Job Order Contracting for concrete pavement repair at various locations from the Jefferson County line to the Arkansas State line and all of I-57 and all of I-155. | 2026 | 2 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 522
Southeast | N | STE. GENEVIEVE | IS 55 S | SE0200 | 198.084 | 0 | 0 | Job Order Contracting for concrete pavement repair from the Jefferson County line to the Arkansas State line and all of I-57 and all of I-155. | 2027 | 0 | 2 | 20 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 537
Southeast | N | STE. GENEVIEVE | IS 55 S | SE0238 | 198.084 | 0 | 0 | Job Order Contracting for concrete pavement repair from the Jefferson County line to the Arkansas State line and all of I-57 and all of I-155. | 2028 | 0 | 1 | 21 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 552
Southeast | N | STE. GENEVIEVE | US 61 S | 9P3855 | 0.9 | 1.8 | 0 | Widen intersection at Rte. Y. | 2026 | 65 | 240 | 0 | 240 | 0 | 258 | 0 | 258 | 0 | 944 | 0 | 1507
Southeast | N | STE. GENEVIEVE | US 61 S | SE0264 | 0.2 | 0.552 | 0 | Intersection improvements at Rte. M. | 2028 | 0 | 10 | 130 | 140 | 0 | 0 | 187 | 187 | 0 | 0 | 903 | 1230
Southeast | N | STE. GENEVIEVE | US 61 S | SE0286 | 0.2 | 0.4 | 1 | Bridge replacement over Union Pacific Railroad. Project involves bridge J0134. | 2030 | 0 | 20 | 360 | 380 | 0 | 0 | 5 | 5 | 0 | 0 | 2150 | 2535
Southeast | N | STE. GENEVIEVE | RT JJ E | SE0282 | 0.2 | 0.4 | 1 | Bridge rehabilitation over Terre bleue Creek. Project involves bridge R0022. | 2030 | 0 | 10 | 170 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 1003 | 1183
Southeast | N | STE. GENEVIEVE | RT N S | SE0026 | 0.064 | 0.128 | 1 | Bridge replacement over Little Saline Creek. Project involves bridge P0631. | 2026 | 221 | 200 | 0 | 200 | 0 | 20 | 0 | 20 | 0 | 1289 | 0 | 1730
Southeast | N | STE. GENEVIEVE | RT Z E | SE0094 | 0.38 | 0.76 | 4 | Bridge painting over I-55 at Rte. Z, Rte. M, County Road Eisenbeis Bottom and Rte. 32. Project involves bridges A2460, A2420, A2417 and A2406. | 2027 | 17 | 50 | 202 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 1534 | 1803
Southeast | N | STE. GENEVIEVE | RT Z E | SE0100 | 4.321 | 8.642 | 1 | Add rumble stripes from Rte. N to Rte. 61. Project involves bridge A2460. | 2027 | 50 | 40 | 110 | 150 | 0 | 20 | 0 | 20 | 0 | 0 | 1442 | 1662
Southeast | N | STODDARD | MO 114 E | 9S3725 | 0.457 | 0.914 | 2 | Bridge replacement over Drainage Ditch 5 and bridge rehabilitation over Little River Drainage Ditch. Project involves bridges J0740 and F0565. | 2027 | 330 | 75 | 360 | 435 | 0 | 14 | 0 | 14 | 0 | 0 | 2765 | 3544
Southeast | N | STODDARD | MO 114 E | 9S3726 | 0.229 | 0.458 | 1 | Bridge replacement over Dexter Creek. Project involves bridge K0031. | 2027 | 187 | 100 | 149 | 249 | 25 | 0 | 0 | 0 | 0 | 0 | 1946 | 2407
Southeast | N | STODDARD | MO 114 E | 9S3775 | 0.2 | 0.4 | 1 | Bridge replacement over Union Pacific Railroad. Project involves bridge K0032. | 2027 | 315 | 200 | 460 | 660 | 25 | 0 | 0 | 0 | 0 | 0 | 3409 | 4409
Southeast | N | STODDARD | US 60 E | SE0063 | 6.937 | 13.874 | 0 | Pavement resurfacing from Rte. F to Rte. 25. | 2028 | 12 | 10 | 240 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 3707 | 3969
Southeast | N | STODDARD | MO 91 S | 9S3824 | 6.59 | 13.18 | 1 | Pavement resurfacing from Rte. 25 to Rte. P. Project involves bridge A2214. | 2027 | 11 | 14 | 81 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 885 | 991
Southeast | N | STODDARD | RT AA S | SE0141 | 4.006 | 17.753 | 0 | Upgrade pedestrian facilities to comply with the ADA Transition Plan at various locations in Bloomfield, Park Hills, Arcadia and Jackson. | 2026 | 115 | 110 | 0 | 110 | 0 | 2 | 0 | 2 | 0 | 1501 | 0 | 1728
Southeast | N | STODDARD | RT AB E | SE0093 | 0.2 | 0.4 | 1 | Bridge replacement over Drainage Ditch 24. Project involves bridge N0380. | 2028 | 61 | 50 | 244 | 294 | 0 | 0 | 8 | 8 | 0 | 0 | 1843 | 2206
Southeast | N | STODDARD | RT J E | SE0097 | 19.093 | 38.186 | 0 | Pavement resurfacing from Rte. T to Rte. 25. | 2028 | 13 | 10 | 230 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 2055 | 2308
Southeast | N | STODDARD | RT N S | SE0307 | 15.103 | 30.206 | 0 | Pavement preservation treatment from Rte. 91 to Rte. 60. | 2028 | 0 | 5 | 61 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 627 | 693
Southeast | N | STODDARD | RT PP E | SE0125 | 10.034 | 20.068 | 1 | Pavement resurfacing from Rte. 51 to Rte. M. Project involves bridge B0543. | 2029 | 16 | 5 | 133 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 1329 | 1483
Southeast | N | STODDARD | RT T S | SE0309 | 19.549 | 39.098 | 0 | Pavement preservation treatment from Rte. 51 to Rte. 60. | 2028 | 0 | 5 | 86 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 860 | 951
Southeast | N | STODDARD | RT W E | SE0124 | 8.732 | 17.464 | 1 | Pavement resurfacing from Rte. Z to Rte. 61. Project involves bridge A0158. | 2028 | 5 | 5 | 143 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 1355 | 1508
Southeast | N | STODDARD | RT Y E | SE0199 | 0.2 | 0.4 | 1 | Bridge replacement over Drainage Ditch 30. Project involves bridge X0829. | 2030 | 0 | 20 | 200 | 220 | 0 | 0 | 34 | 34 | 0 | 0 | 1169 | 1423
Southeast | N | STODDARD | RT Y E | SE0203 | 0.2 | 0.4 | 1 | Bridge replacement over Drainage Ditch 24. Project involves bridge X0830. | 2030 | 0 | 10 | 220 | 230 | 0 | 0 | 34 | 34 | 0 | 0 | 1335 | 1599
Southeast | N | STODDARD | RT Y E | SE0204 | 0.2 | 0.4 | 1 | Bridge replacement over Drainage Ditch 34. Project involves bridge X0832. | 2030 | 5 | 10 | 260 | 270 | 0 | 0 | 34 | 34 | 0 | 0 | 1222 | 1531
Southeast | N | STODDARD | RT Y E | SE0205 | 0.2 | 0.4 | 1 | Bridge replacement over Drainage Ditch 35. Project involves bridge X0833. | 2030 | 5 | 10 | 230 | 240 | 0 | 0 | 34 | 34 | 0 | 0 | 1267 | 1546
Southeast | N | STODDARD | RT Y E | SE0287 | 0.2 | 0.4 | 1 | Bridge replacement over Drainage Ditch 37. Project involves bridge X0838. | 2030 | 0 | 20 | 260 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 1531 | 1811
Southeast | N | STODDARD | RT ZZ N | SE0119 | 0.2 | 0.4 | 1 | Bridge replacement over Main Drainage Ditch. Project involves bridge N0899. | 2027 | 5 | 118 | 180 | 298 | 0 | 20 | 0 | 20 | 0 | 0 | 892 | 1215
Southeast | N | TEXAS | MO 137 S | 9S3693 | 23.966 | 47.932 | 0 | Pavement resurfacing from Rte. 17 to Bus. 63. | 2027 | 32 | 8 | 315 | 323 | 0 | 0 | 0 | 0 | 0 | 0 | 2847 | 3202
Southeast | N | TEXAS | MO 17 S | SE0296 | 0.2 | 0.4 | 1 | Bridge rehabilitation over Jacks Fork River. Project involves bridge A7022. | 2030 | 0 | 20 | 200 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 1264 | 1484
Southeast | N | TEXAS | US 60 W | SE0229 | 0 | 2 | 1 | Bridge replacement over Beeler Creek. Project involves bridge H0296. | 2029 | 50 | 50 | 1212 | 1262 | 0 | 0 | 16 | 16 | 0 | 0 | 5468 | 6796
Southeast | N | TEXAS | US 63 S | 9P3820 | 2.669 | 7.456 | 0 | Pavement resurfacing from Rte. E to Rte. B. | 2027 | 43 | 15 | 149 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 1447 | 1654
Southeast | N | TEXAS | US 63 S | SE0230 | 1 | 2.321 | 1 | Bridge replacement over Potters Creek. Project involves bridge K0996. | 2029 | 50 | 80 | 1863 | 1943 | 0 | 0 | 12 | 12 | 0 | 0 | 6671 | 8676
Southeast | N | TEXAS | RT B E | 9S3803 | 23.209 | 46.418 | 0 | Pavement resurfacing from Rte. 63 to end of state maintenance. | 2026 | 28 | 295 | 0 | 295 | 0 | 0 | 0 | 0 | 0 | 2514 | 0 | 2837
Southeast | N | TEXAS | RT K S | SE0042 | 4.95 | 9.9 | 0 | Pavement resurfacing from Rte. KK to Rte. 17. | 2026 | 3 | 68 | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 557 | 0 | 628
Southeast | N | TEXAS | RT M S | SE0197 | 0.2 | 0.4 | 1 | Bridge replacement over Roubidoux Creek. Project involves bridge P0222. | 2030 | 0 | 40 | 360 | 400 | 0 | 0 | 31 | 31 | 0 | 0 | 2204 | 2635
Southeast | N | TEXAS | RT VV E | SE0007 | 9.826 | 19.652 | 0 | Pavement resurfacing from Rte. 137 to end of state maintenance in Dent County. | 2026 | 28 | 114 | 0 | 114 | 0 | 0 | 0 | 0 | 0 | 1104 | 0 | 1246
Southeast | N | VARIOUS | Various | 5B0800Z | 0 | 0 | 83 | Payback beginning in SFY 2008 for Safe and Sound bridges in the Southeast District. | 2033 | 0 | 0 | 0 | 0 | 99 | 0 | 0 | 0 | 82535 | 6166 | 24664 | 113464
Southeast | N | VARIOUS | Various | SE0133 | 0 | 0 | 0 | Upgrade signals at various locations in the Southeast District. | 2026 | 76 | 127 | 0 | 127 | 0 | 0 | 0 | 0 | 0 | 653 | 0 | 856
Southeast | N | VARIOUS | Various | SE0170 |  | 0 | 0 | On-call work zone enforcement at various locations in the Southeast District. | 2026 | 1 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 42
Southeast | N | VARIOUS | Various | SE0173 | 0 | 0 | 0 | Job Order Contracting for ADA Transition Plan Improvements at various locations in the Southeast District. | 2026 | 3 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 115
Southeast | N | VARIOUS | Various | SE0174 | 0 | 0 | 0 | Job Order Contracting for concrete pavement repair at various locations on all major highways except interstates in the Southeast District. | 2026 | 2 | 20 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 522
Southeast | N | VARIOUS | Various | SE0176 | 0 | 0 | 0 | Job Order Contracting for guard cable and guardrail repair for St. Francois, Ste. Genevieve, Madison, Perry, Cape Girardeau, Wayne, Bollinger, Stoddard, Scott, Butler, New Madrid, Mississippi, Pemiscot and Dunklin Counties. | 2026 | 6 | 168 | 0 | 168 | 0 | 0 | 0 | 0 | 0 | 2250 | 0 | 2424
Southeast | N | VARIOUS | Various | SE0177 | 0 | 0 | 0 | Job Order Contracting for guard cable and guardrail repair for Wright, Douglas, Ozark, Texas, Howell, Shannon, Reynolds, Iron, Carter, Oregon and Ripley Counties. | 2026 | 1 | 38 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 539
Southeast | N | VARIOUS | Various | SE0179 | 0 | 0 | 0 | Job Order Contracting for erosion control repairs at various locations. | 2026 | 20 | 95 | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 1115
Southeast | N | VARIOUS | Various | SE0196 |  | 0 | 0 | On-call work zone enforcement at various locations in the Southeast District. | 2027 | 1 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 43
Southeast | N | VARIOUS | Various | SE0208 | 0 | 0 | 0 | Job Order Contracting for ADA compliance repairs at various locations in the Southeast District. | 2027 | 0 | 3 | 12 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 118
Southeast | N | VARIOUS | Various | SE0209 | 0 | 0 | 0 | Job Order Contracting for ADA compliance repairs at various locations in the Southeast District. | 2028 | 0 | 1 | 14 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 106 | 121
Southeast | N | VARIOUS | Various | SE0231 | 0 | 0 | 0 | Job Order Contracting for concrete pavement repair at various locations on all major highways except interstates in the Southeast District. | 2027 | 0 | 2 | 20 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 537
Southeast | N | VARIOUS | Various | SE0249 | 0 | 0 | 0 | Job Order Contracting for concrete pavement repair at various locations on all major highways except interstates in the Southeast District. | 2028 | 0 | 1 | 21 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 552
Southeast | N | VARIOUS | Various | SE0250 |  | 0 | 0 | Job Order Contracting for erosion control repairs at various locations. | 2027 | 0 | 20 | 95 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 1030 | 1145
Southeast | N | VARIOUS | Various | SE0251 |  | 0 | 0 | Job Order Contracting for erosion control repairs at various locations. | 2028 | 0 | 5 | 110 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 1061 | 1176
Southeast | N | VARIOUS | Various | SE0252 | 0 | 0 | 0 | Job Order Contracting for guard cable and guardrail repair for St. Francois, Ste. Genevieve, Madison, Perry, Cape Girardeau, Wayne, Bollinger, Stoddard, Scott, Butler, New Madrid, Mississippi, Pemiscot and Dunklin Counties. | 2027 | 0 | 6 | 168 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 2318 | 2492
Southeast | N | VARIOUS | Various | SE0253 | 0 | 0 | 0 | Job Order Contracting for guard cable and guardrail repair for St. Francois, Ste. Genevieve, Madison, Perry, Cape Girardeau, Wayne, Bollinger, Stoddard, Scott, Butler, New Madrid, Mississippi, Pemiscot and Dunklin Counties. | 2028 | 0 | 2 | 172 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 2387 | 2561
Southeast | N | VARIOUS | Various | SE0254 | 0 | 0 | 0 | Job Order Contracting for guard cable and guardrail repair for Wright, Douglas, Ozark, Texas, Howell, Shannon, Reynolds, Iron, Carter, Oregon and Ripley Counties. | 2027 | 0 | 1 | 38 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 554
Southeast | N | VARIOUS | Various | SE0255 | 0 | 0 | 0 | Job Order Contracting for guard cable and guardrail repair for Wright, Douglas, Ozark, Texas, Howell, Shannon, Reynolds, Iron, Carter, Oregon and Ripley Counties. | 2028 | 0 | 1 | 38 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 569
Southeast | N | VARIOUS | Various | SE0256 |  | 0 | 0 | On-call work zone enforcement at various locations in the Southeast District. | 2028 | 0 | 1 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 43
Southeast | N | WAYNE | MO 34 E | 9P3816 | 0.2 | 0.4 | 1 | Bridge rehabilitation over Clark Creek. Project involves bridge A1300. | 2026 | 122 | 200 | 0 | 200 | 2 | 0 | 0 | 0 | 0 | 1262 | 0 | 1586
Southeast | N | WAYNE | MO 34 E | SE0049 | 12.245 | 24.49 | 0 | Pavement resurfacing from Wayne County line to Rte. 49 north. | 2029 | 18 | 16 | 330 | 346 | 0 | 0 | 0 | 0 | 0 | 0 | 3095 | 3459
Southeast | N | WAYNE | US 67 N | SE0083 | 0.2 | 0.4 | 1 | Bridge replacement over Otter Creek. Project involves bridge L0210. | 2026 | 612 | 486 | 0 | 486 | 10 | 0 | 0 | 0 | 0 | 3302 | 0 | 4410
Southeast | N | WAYNE | US 67 S | 9P3822 | 7.42 | 29.04 | 0 | Pavement resurfacing in the southbound lane from 0.2 mile south of Rte. A to 0.9 mile north of Rte. F, from 0.4 mile north of Rte. 49 to 0.3 mile south of County Road 521 and in the northbound lane from 0.7 mile north of Rte. 172 to 0.2 mile south of Rte. F. | 2027 | 53 | 50 | 366 | 416 | 0 | 0 | 0 | 0 | 0 | 0 | 5825 | 6294
Southeast | N | WAYNE | RT A E | 9S3815 | 0.2 | 0.4 | 1 | Bridge rehabilitation over Otter Creek. Project involves bridge A0518. | 2027 | 93 | 5 | 93 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 823 | 1014
Southeast | N | WAYNE | RT A E | SE0147 | 0.087 | 0.174 | 1 | Bridge replacement over Small Creek. Project involves bridge S0497. | 2027 | 138 | 5 | 98 | 103 | 0 | 6 | 0 | 6 | 0 | 0 | 697 | 944
Southeast | N | WRIGHT | MO 38 E | 9S3689 | 0.2 | 0.4 | 1 | Bridge replacement over Dove Creek. Project involves bridge A1812. | 2026 | 108 | 683 | 0 | 683 | 0 | 6 | 0 | 6 | 0 | 2430 | 0 | 3227
Southeast | N | WRIGHT | MO 38 E | SE0237 | 0.2 | 0.4 | 1 | Bridge improvement over Whetstone Creek. Project involves bridge A2360. | 2029 | 10 | 5 | 219 | 224 | 0 | 0 | 0 | 0 | 0 | 0 | 1486 | 1720
Southeast | N | WRIGHT | MO 5 S | SE0291 | 0.2 | 0.4 | 1 | Bridge replacement over BNSF Railway. Project involves bridge A0327. | 2030 | 0 | 20 | 320 | 340 | 0 | 0 | 28 | 28 | 0 | 0 | 1935 | 2303
Southeast | N | WRIGHT | MO 5 S | SE0292 | 0.2 | 0.4 | 1 | Bridge replacement over Woods Fork. Project involves bridge J0754. | 2030 | 0 | 60 | 580 | 640 | 0 | 0 | 54 | 54 | 0 | 0 | 3660 | 4354
Southeast | N | WRIGHT | US 60 E | SE0023 | 20.001 | 40.305 | 1 | Pavement and bridge resurfacing on the eastbound lane east of Rte. C to east of Cabool. Project involves bridge A2647. | 2028 | 37 | 45 | 879 | 924 | 0 | 0 | 0 | 0 | 0 | 0 | 7940 | 8901
Southeast | N | WRIGHT | US 60 E | SE0139 | 316.582 | 0 | 0 | Erosion control repairs at various locations along Rtes. 60 and 67 in the Southeast District. | 2027 | 3 | 20 | 90 | 110 | 0 | 20 | 0 | 20 | 0 | 0 | 1030 | 1163
Southeast | N | WRIGHT | US 60 W | SE0024 | 23.619 | 47.238 | 0 | Pavement resurfacing on the westbound lane from Rte. 95 to Webster County line. | 2028 | 48 | 56 | 1139 | 1195 | 0 | 0 | 0 | 0 | 0 | 0 | 10274 | 11517
Southeast | N | WRIGHT | MO 95 S | SE0145 | 1.622 | 3.488 | 1 | Add intersection turn lanes and improvements. Project involves bridge A3457. | 2027 | 603 | 496 | 1152 | 1648 | 0 | 2874 | 0 | 2874 | 0 | 0 | 11816 | 16941
Southeast | N | WRIGHT | RT A E | 9S3805 | 6.002 | 12.004 | 0 | Pavement resurfacing from Bus. 60 in Mansfield to Rte. K. | 2026 | 8 | 91 | 0 | 91 | 0 | 0 | 0 | 0 | 0 | 775 | 0 | 874
Southeast | N | WRIGHT | RT AF S | 9S3691 | 0.2 | 0.4 | 1 | Bridge replacement over Beaver Creek. Project involves bridge N0675. | 2026 | 485 | 390 | 0 | 390 | 6 | 0 | 0 | 0 | 0 | 2623 | 0 | 3504
Southeast | N | WRIGHT | RT AM E | SE0312 | 4.037 | 8.074 | 0 | Pavement preservation treatment from Rte. 95 to the end of state maintenance. | 2028 | 0 | 5 | 37 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 181 | 223
Southeast | N | WRIGHT | RT C S | SE0313 | 17.376 | 34.752 | 0 | Pavement preservation treatment from Rte. 60 to Rte. 14. | 2028 | 0 | 5 | 75 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 698 | 778
Southeast | N | WRIGHT | RT PP S | SE0005 | 2.427 | 4.854 | 0 | Pavement resurfacing from Rte. C to end of state maintenance. | 2026 | 5 | 30 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 273 | 0 | 308
Southeast | N | WRIGHT | RT U S | 9S3818 | 0.2 | 0.4 | 1 | Bridge replacement over BNSF Railway. Project involves bridge H0290. | 2026 | 183 | 353 | 0 | 353 | 0 | 22 | 0 | 22 | 0 | 1643 | 0 | 2201
Southeast | N | WRIGHT | RT V E | 9S3804 | 7.287 | 14.574 | 0 | Pavement resurfacing from Rte. F to Rte. 5. | 2026 | 9 | 92 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 786 | 0 | 887
Statewide | N | BENTON | US 65 S | ST0093 | 45.073 | 92.363 | 0 | Construct passing lanes from Warsaw to Buffalo. | 2029 | 10 | 828 | 5216 | 6044 | 0 | 0 | 9606 | 9606 | 0 | 0 | 22340 | 38000
Statewide | N | BOONE | US 63 S | ST0092 | 1.306 | 3.41 | 0 | Roadway improvements in Columbia. $4,200,000 SFY 2025 General Revenue. | 2026 | 5 | 295 | 0 | 295 | 0 | 0 | 0 | 0 | 0 | 4200 | 0 | 4500
Statewide | N | BOONE | IS 70 E | ST0017 | 13.621 | 57.354 | 1 | Safety and capacity improvements from the Missouri River near Rocheport to Columbia. Design-Build. Involves bridge L0286. $15,727,618 INFRA Grant, $900,000 Wildlife Crossing Pilot Program, $50,000 MO Dept. of Conservation, and $50,000 Design Bridge Consultant Budget. | 2026 | 8500 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 432868 | 0 | 441370
Statewide | N | BUTLER | US 67 S | ST0062 | 7.695 | 15.39 | 0 | Roadway improvements from County Road 352 to Arkansas State line. | 2026 | 1 | 4201 | 0 | 4201 | 5000 | 0 | 0 | 0 | 0 | 39664 | 0 | 48866
Statewide | N | CALLAWAY | IS 70 E | ST0018 | 45.378 | 189.036 | 2 | Safety and capacity improvements from Kingdom City to Warrenton. Project involves bridges A0096 and A0865. | 2027 | 5500 | 5000 | 501 | 5501 | 0 | 13374 | 0 | 13374 | 0 | 0 | 556018 | 580393
Statewide | N | CAMDEN | US 54 E | ST0156 | 4.109 | 11.816 | 0 | Intersection improvements at Rte. 54 and Rte. 5. Funding currently restricted. Contingent upon release of funds. | 2026 | 0 | 944 | 0 | 944 | 0 | 200 | 0 | 200 | 0 | 2856 | 0 | 4000
Statewide | Y | CASS | IS 49 S | ST0091 | 0.83 | 3.745 | 0 | Interchange and roadway improvements at Rte. 58 in Belton. | 2028 | 200 | 800 | 2400 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 23400
Statewide | N | CHARITON | RT UU E | ST0154 | 27.204 | 54.408 | 0 | Pavement resurfacing in Carroll and Chariton Counties. Includes Rtes. M, UU and WW. | 2026 | 0 | 190 | 0 | 190 | 0 | 0 | 0 | 0 | 0 | 2682 | 0 | 2872
Statewide | N | CLINTON | RT BB S | ST0081 | 0.259 | 0.518 | 0 | Scoping and enginering study over I-35 in Cameron. |  | 995 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000
Statewide | N | COOPER | IS 70 E | ST0017B | 25 | 50 | 0 | Safety and capacity improvements from Boonville to the Missouri River near Rocheport. | 2026 | 1000 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 120000 | 0 | 125000
Statewide | N | COOPER | RT B S | ST0017C | 0.103 | 0.157 | 0 | Construct roundabout at Americana in Boonville. $1,177,836 Cost Share and $1,181,437 Boonville funds. | 2026 | 119 | 115 | 0 | 115 | 0 | 10 | 0 | 10 | 0 | 2119 | 0 | 2363
Statewide | Y | FRANKLIN | IS 44 E | ST0115 | 0.481 | 2.146 | 0 | Interchange and pavement improvements at Rte. 50. Potential Design-Build project. | 2027 | 5 | 2000 | 5075 | 7075 | 0 | 0 | 0 | 0 | 0 | 0 | 58220 | 65300
Statewide | N | GREENE | RT CC E | ST0165 | 19.262 | 38.558 | 0 | Pavement resurfacing from Rte. 13 to Rte. 65, on Rte. JJ from Rte. 215 in Polk County to Rte. BB in Greene County and on Rte. Y from Rte. 13 in Polk County to end of state maintenance. | 2026 | 0 | 131 | 0 | 131 | 0 | 0 | 0 | 0 | 0 | 1695 | 0 | 1826
Statewide | N | HOWARD | RT E E | ST0152 | 24.354 | 48.708 | 0 | Pavement resurfacing from east of Park Road to end of state maintenance, Rte. V from Rte. 3 to Rte. 5. Potential Rte. V from Rte. 179 to end of state maintenance and SP 240 from Rte. 40 to 3rd Street. | 2026 | 0 | 156 | 0 | 156 | 0 | 0 | 0 | 0 | 0 | 2161 | 0 | 2317
Statewide | N | JASPER | IS 44 E | ST0089 | 51.246 | 209.276 | 1 | Safety, capacity, and pavement improvements at various locations from I-49 north junction in Fidelity to 2 miles west of Rte. A east of Conway. Design-Build. Involves bridge A0713. $902,000 Open Container, $407,968 Springfield STBG-Urban, and $101,992 Springfield funds. | 2026 | 631 | 16369 | 0 | 16369 | 0 | 18 | 0 | 18 | 0 | 453897 | 0 | 470915
Statewide | N | JASPER | RT N E | ST0083 | 9.993 | 19.986 | 0 | Road improvements on Baseline Road. Funding currently restricted. Contingent upon release of funds. | 2026 | 0 | 500 | 0 | 500 | 0 | 200 | 0 | 200 | 0 | 1997 | 0 | 2697
Statewide | N | JOHNSON | RT CC N | ST0167 | 7.115 | 14.23 | 0 | Pavement resurfacing from Rte. E to Rte. 23. | 2026 | 0 | 42 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 588 | 0 | 630
Statewide | N | LACLEDE | IS 44 W | ST0119 | 4.681 | 9.606 | 0 | Rebuild pavement and resurfacing 3.7 miles west of Rte. 133 to 2.1 miles east of Rte. F. Potential Design-Build project. | 2027 | 5 | 492 | 6391 | 6883 | 0 | 0 | 0 | 0 | 0 | 0 | 44625 | 51513
Statewide | N | LAFAYETTE | IS 70 E | ST0016 | 13.5 | 55.066 | 1 | Safety and capacity improvements from Rte. H east of Odessa to Concordia. | 2027 | 6500 | 2850 | 3750 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 149900 | 163000
Statewide | N | LAFAYETTE | IS 70 E | ST0016C | 42.689 | 173.581 | 1 | Safety and capacity improvements from Concordia to Boonville. Project involves bridge L0945. $1,087,200 Congressionally Directed Spending Demo ID MO261. | 2027 | 0 | 2250 | 2750 | 5000 | 0 | 10 | 0 | 10 | 0 | 0 | 577735 | 582745
Statewide | N | LAWRENCE | RT O S | ST0166 | 14.55 | 29.1 | 0 | Pavement resurfacing from I-44 to Rte. 174 and on Rte. V from beginning of state maintenance to Rte. 39. Potential pavement resurfacing on Rte. EE from Rte. 39 to Rte. 76 in Barry County. | 2026 | 0 | 69 | 0 | 69 | 0 | 0 | 0 | 0 | 0 | 891 | 0 | 960
Statewide | N | LEWIS | CRD 524 (250TH ST) E | ST0064 | 1.395 | 0 | 0 | Pavement resurfacing on 250th Street and Heritage Avenue near Highland High School in Lewis County. $2,366,000 Lewis County funds. Funding currently restricted. Contingent upon release of funds. | 2026 | 0 | 490 | 0 | 490 | 0 | 2 | 0 | 2 | 0 | 4240 | 0 | 4732
Statewide | N | NEW MADRID | US 60 E | ST0160 | 0.589 | 1.998 | 0 | Add roundabouts and connections for future outer road and on and off ramps at the intersection of Ingram Road. Funding currently restricted. Contingent upon release of funds. | 2026 | 0 | 600 | 0 | 600 | 0 | 50 | 0 | 50 | 0 | 4350 | 0 | 5000
Statewide | N | NEWTON | IS 44 E | ST0089B | 1.877 | 8.04 | 0 | Add lanes from Rte. 43 (Main Street) to Loop 49 (Rangeline Road) in Joplin. | 2027 | 0 | 1560 | 2560 | 4120 | 0 | 5 | 0 | 5 | 0 | 0 | 21016 | 25141
Statewide | N | NEWTON | IS 44 W | ST0157 | 2.481 | 2.481 | 0 | Add westbound climbing lane at Rte. 43. Funding currently restricted. Contingent upon release of funds. | 2026 | 0 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 9915 | 0 | 11915
Statewide | N | PEMISCOT | RT K E | ST0161 | 35.46 | 70.92 | 0 | Pavement resurfacing on Rtes. K, BB, CC, M and Y in Pemiscot County, Rtes. AD and ZZ in New Madrid County and Rte. Z in Dunklin County. | 2026 | 0 | 343 | 0 | 343 | 0 | 0 | 0 | 0 | 0 | 2889 | 0 | 3232
Statewide | N | PETTIS | US 65 S | ST0090 | 0.212 | 0.739 | 0 | Payment to Sedalia for intersection and road improvements at Rte. B. | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4700 | 0 | 4700
Statewide | N | PHELPS | IS 44 E | ST0122 | 0.636 | 1.947 | 0 | Capacity and safety improvements at Rte. V in Rolla. Potential Design-Build project. | 2027 | 5 | 1 | 1166 | 1167 | 0 | 5 | 0 | 5 | 0 | 0 | 16635 | 17812
Statewide | N | PHELPS | IS 44 E | ST0123 | 0.377 | 1.516 | 0 | Capacity and safety improvements at Rte. 68 in St. James. Potential Design-Build project. | 2027 | 5 | 546 | 461 | 1007 | 0 | 200 | 0 | 200 | 0 | 0 | 3289 | 4501
Statewide | N | PHELPS | IS 44 W | ST0121 | 10.4 | 24.445 | 0 | Rebuild pavement on westbound lanes from east of Rte. 63 to Sugar Tree Road. Potential Design-Build project. | 2027 | 5 | 871 | 3074 | 3945 | 0 | 0 | 0 | 0 | 0 | 0 | 51070 | 55020
Statewide | Y | PLATTE | IS 29 S | ST0094 | 94.281 | 455.559 | 0 | Corridor improvements on I-29, I-35 and Rte. 169 in Platte, Clay and Jackson Counties. | 2027 | 500 | 1750 | 2646 | 4396 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 34896
Statewide | Y | PLATTE | CST NW LP COOKINGHAM DR W | ST0159 | 0.388 | 1.846 | 0 | Payment to Ambassador Building Community Improvement District to add roundabouts at I-29. Funding currently restricted. Contingent upon release of funds. | 2026 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4498 | 0 | 4500
Statewide | N | RANDOLPH | BU 63 S | ST0155 | 1.564 | 3.128 | 0 | Intersection improvements between East Burkhart Street and Rte. M in Moberly. Funding currently restricted. Contingent upon release of funds. | 2027 | 0 | 200 | 152 | 352 | 0 | 0 | 0 | 0 | 0 | 0 | 1748 | 2100
Statewide | Y | RAY | RT Y S | ST0168 | 6.003 | 12.006 | 0 | Pavement resurfacing from Rte. 10 to King Road and from Rte. N to North Brightwell Road in Platte County. | 2026 | 0 | 48 | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 677 | 0 | 725
Statewide | N | SCHUYLER | RT D E | ST0164 | 42.766 | 85.532 | 0 | Pavement resurfacing from Rte. U in Schuyler County to Rte. 15 in Scotland County and on J, U, and V in Schuyler County. | 2026 | 0 | 290 | 0 | 290 | 0 | 0 | 0 | 0 | 0 | 4127 | 0 | 4417
Statewide | Y | ST. LOUIS | IS 44 E | ST0117 | 7.937 | 49.904 | 0 | Rebuild pavement from Rte. 141 to Rte. 109. | 2027 | 5 | 4030 | 3322 | 7352 | 0 | 0 | 0 | 0 | 0 | 0 | 40320 | 47677
Statewide | N | SULLIVAN | RT PP E | ST0153 | 25.991 | 51.982 | 0 | Pavement resurfacing in Sullivan County. Includes Rtes. E, W and PP. | 2026 | 0 | 195 | 0 | 195 | 0 | 0 | 0 | 0 | 0 | 2750 | 0 | 2945
Statewide | Y | VARIOUS | IS 70 | ST0137 |  | 0 | 0 | Solar panel installation at various locations. $12,228,452 Infrastructure for Rebuilding America Grant funds. | 2026 | 1500 | 1157 | 0 | 1157 | 0 | 0 | 0 | 0 | 0 | 9571 | 0 | 12228
Statewide | Y | VARIOUS | IS 70 | ST0151 |  | 0 | 0 | Scoping for traffic and safety management improvements related to traffic incident management, emergency response enhancements, work zone speed safety management and data driven analysis for Improve I-70. $6,911,850 Infrastructure for Rebuilding America Grant. |  | 0 | 2300 | 3689 | 5989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5989
Statewide | N | VARIOUS | Various | ST0138 |  | 0 | 0 | Guardrail improvements at various locations in the Northwest District. $3,800,000 private entity funds. | 2026 | 5 | 271 | 0 | 271 | 0 | 0 | 0 | 0 | 0 | 3800 | 0 | 4076
Statewide | N | VARIOUS | Various | ST0139 |  | 0 | 0 | Guardrail improvements at various locations in Audrain, Lincoln, Monroe, Montgomery, Pike, Randolph, Ralls, and Warren Counties. $1,952,000 private entity funds. | 2026 | 5 | 184 | 0 | 184 | 0 | 0 | 0 | 0 | 0 | 1952 | 0 | 2141
Statewide | N | VARIOUS | Various | ST0139B |  | 0 | 0 | Guardrail improvements at various locations in Adair, Clark, Knox, Lewis, Macon, Marion, Schuyler, and Shelby Counties. $1,311,000 private entity funds. | 2026 | 0 | 110 | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 1311 | 0 | 1421
Statewide | Y | VARIOUS | Various | ST0143 |  | 0 | 0 | Guardrail improvements at various locations in the urban Southwest District. $161,000 private entity funds. | 2026 | 5 | 55 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 161 | 0 | 221
Statewide | N | VARIOUS | Various | ST0143B |  | 0 | 0 | Guardrail improvements at various locations in the rural Southwest District in Barton, Bates, Benton, Cedar, Dade, Dallas, Henry, Hickory, Polk, St. Clair, and Vernon counties. $2,239,000 private entity funds. | 2026 | 0 | 699 | 0 | 699 | 0 | 0 | 0 | 0 | 0 | 2239 | 0 | 2938
Statewide | N | VARIOUS | Various | ST0143C |  | 0 | 0 | Guardrail improvements at various locations in the rural Southwest District in Barry, Christian, Greene, Jasper, Lawrence, McDonald, Newton, Stone, Taney, and Webster counties. $1,778,000 private entity funds. | 2026 | 0 | 556 | 0 | 556 | 0 | 0 | 0 | 0 | 0 | 1778 | 0 | 2334
Statewide | N | VARIOUS | Various | ST0145 |  | 0 | 0 | Safety Circuit Rider statewide liaison for state fiscal year 2026. | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 70
Statewide | N | VERNON | RT AA S | ST0162 | 16.73 | 33.46 | 0 | Pavement resurfacing from Rte. M to Rte. 54 and on Rte. J from Rte. F to Rte. 52 in Bates County. | 2026 | 0 | 119 | 0 | 119 | 0 | 0 | 0 | 0 | 0 | 1539 | 0 | 1658
Statewide | N | WARREN | RA IS70W WRIGHT CITY W | ST0125 | 1.205 | 0 | 0 | Construct additional truck parking at existing eastbound and westbound facilities at Wright City, Boonville and Mineola. Design-Build project. $33,407,308 Infrastructure for Rebuilding America Grant. | 2026 | 1000 | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 30907 | 0 | 33407