## Right of Way and Construction
District No. | County | Route | Project No. | Length | Lane Miles | Bridge Count | MPO | TIP No. | Description | Federal Advanced Construction Label | Federal Funds | State Funds | Local Funds | Estimate Total | Future Cost | Anticipated Federal Funds | Let With | Previous Engineering | Current Year Engineering | Engineering 2028 Total | Engineering 2029 Total | Engineering 2030 Total | Engineering 2031 Total | Previous Right of Way | Current Year Right of Way | Right of Way 2028 Total | Right of Way 2029 Total | Right of Way 2030 Total | Right of Way 2031 Total | Previous Construction | Current Year Construction | Construction 2028 Total | Construction 2029 Total | Construction 2030 Total | Construction 2031 Total | Previous Year FFOS | Current Year FFOS | FFOS 2028 Total | FFOS 2029 Total | FFOS 2030 Total | FFOS 2031 Total | Previous Payback | Current Year Payback | Payback 2028 Total | Payback 2029 Total | Payback 2030 Total | Payback 2031 Total
1 | ANDREW | US 169 S | NW0072 | 0.293 | 0.45 | 0 | Y | RR-2024-01 | Add roundabout at Woodbine Road and County Line Road 0.5 mile north of I-29 near St. Joseph. $1,083,000 Open Container Funds. | Federal | 3686 | 410 | 0 | 4216 | 0 | SAFETY |  | 120 | 50 | 381 | 0 | 0 | 0 | 0 | 674 | 0 | 0 | 0 | 0 | 0 | 0 | 2991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | ANDREW | IS 29 S | NW0184 | 12.286 | 51.458 | 0 | Y |  | Pavement improvements from Bus 71 to Rte. O. | Federal | 11302 | 1256 | 0 | 12558 | 0 | NHPP |  | 0 | 2 | 10 | 50 | 170 | 718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | ANDREW | RT B E | NW0047 | 0.296 | 0.592 | 1 | N |  | Bridge rehabilitation over One Hundred and Two River 0.8 mile west of Bolckow. Project involves bridge A1251. | Federal | 1341 | 335 | 0 | 1776 | 0 | NHPP |  | 100 | 114 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 1557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | ANDREW | RT O E | NW0080 | 18.926 | 37.852 | 0 | Y | RR-2027-02 | Pavement resurfacing in Andrew County (Rte. O and Rte. W), Buchanan County (Rte. FF, Rte. O, and Rte. W). | Adv. CN | 6604 | 1651 | 0 | 8273 | 0 | AC-STBG |  | 18 | 40 | 120 | 520 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7575 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | ATCHISON | US 136 E | NW0125 | 0.228 | 0.456 | 1 | N |  | Bridge washing over the Missouri River at Brownsville, Nebraska. Project involves bridge L0098. | Federal | 140 | 35 | 0 | 177 | 0 | NHPP |  | 2 | 5 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | ATCHISON | US 275 N | NW0055 | 0.22 | 0.44 | 2 | N |  | Bridge replacement over the West Fork of High Creek and over High Creek near Rte. T. Project involves bridges J0221 and J0222. | Federal | 3547 | 887 | 0 | 4484 | 0 | NHPP |  | 50 | 200 | 402 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 3798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | ATCHISON | IS 29 N | NW0060 | 16.257 | 66.671 | 0 | N |  | Pavement resurfacing from the Iowa State line to Rte. 111 near Rock Port. | Federal | 12831 | 1426 | 0 | 14452 | 0 | NHPP |  | 195 | 150 | 928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | ATCHISON | IS 29 S | NW0150 | 107.892 | 442.494 | 0 | Y | RR-2025-02 | Job Order Contracting for pavement repair from the Iowa State line to Platte County line. Includes I-229 in Andrew and Buchanan Counties. | Adv. CN | 497 | 55 | 0 | 553 | 0 | AC-NHPP |  | 1 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | BUCHANAN | IS 229 S | NW0134 | 3.746 | 14.138 | 10 | Y | RR-2025-03 | Bridge removal and construct roadway Highland Ave to Rte 36, bridge rehabilitation I-229 flyover to Rte 36, and Rte 36 over 6th St, and replacement Rte 36 over 9th St. Potential Design-Build. Bridges A2225, A2227, A2226, A2229, A2228, A2230, A2231, A2232, L0319, L0320. | Federal | 110105 | 12234 | 0 | 123940 | 0 | NHPP |  | 1601 | 1700 | 8083 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 112456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | BUCHANAN | IS 29 S | NW0118 | 0.031 | 0.183 | 1 | Y | SE-2024-03 | Bridge improvements over Rte. 36. Project involves twin bridges A0179. | Federal | 5126 | 570 | 0 | 5711 | 0 | NHPP |  | 15 | 5 | 10 | 50 | 175 | 323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | BUCHANAN | US 36 E | NW0063 | 10.989 | 22.19 | 0 | Y | RR-2025-01 | Pavement resurfacing on eastbound lane from 0.7 miles east of Rte. AC (Riverside Road) to 0.7 miles east of Rte. 31, near St. Joseph. | Federal | 3521 | 880 | 0 | 4476 | 0 | NHPP |  | 75 | 40 | 282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | BUCHANAN | RT AC S | 1S3030 | 0.054 | 0.134 | 1 | Y | BR-2022-02 | Bridge replacement over Rte. 36 in St. Joseph, add sidewalk on west side of bridge. Project involves bridge A2822. $1,177,000 Open Container Funds. $1,000,000 in Community Project funds from Federal Transportation Bill Earmark. | Federal | 9338 | 2334 | 0 | 12514 | 0 | NHPP |  | 842 | 1205 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 10462 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | BUCHANAN | RT DD E | NW0048 | 0.053 | 0.106 | 1 | N |  | Bridge rehabilitation over Bee Creek near Faucett. Project involves bridge A2581. | Federal | 755 | 189 | 0 | 988 | 0 | NHPP |  | 44 | 70 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | CALDWELL | US 36 E | NW0169 | 19.376 | 38.855 | 0 | N |  | Pavement resurfacing on eastbound lanes from Rte. 13 ramp in Hamilton to 0.4 mile west of Rte. C in Livingston County. | Federal | 5183 | 1296 | 0 | 6479 | 0 | NHPP |  | 0 | 1 | 25 | 100 | 315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | CALDWELL | US 36 W | NW0116 | 0.376 | 23.289 | 0 | N |  | Reconstruct shoulder on westbound lanes from east of Rte. 13 to 1.2 miles east of I-35 and on ramps at Rte. 36 and Rte. 69 in Cameron. | Federal | 2325 | 581 | 0 | 2921 | 0 | NHPP |  | 15 | 10 | 90 | 203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2603 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | CARROLL | US 24 E | NW0126 | 0.412 | 0.824 | 1 | N |  | Bridge deck sealing over the Grand River. Project involves bridge A4613. | Federal | 1094 | 274 | 0 | 1372 | 0 | NHPP |  | 4 | 10 | 30 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | CARROLL | RT DD E | NW0078 | 24.766 | 49.532 | 0 | N |  | Pavement resurfacing in Carroll County (Rte. DD), Clinton County (Rte. A and Rte. M), and DeKalb County (Rte. M). | Adv. CN | 2818 | 704 | 0 | 3534 | 0 | AC-STBG |  | 12 | 10 | 50 | 229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3233 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | CHARITON | MO 11 N | NW0082 | 31.137 | 65.169 | 0 | N |  | Pavement resurfacing from Rte. 24 to Husk Road, E. Locking Street to Rte. 11, and on Helm Street from Rte. 36 to Bus. 36. | Adv. CN | 5079 | 1270 | 0 | 6361 | 0 | AC-STBG |  | 12 | 20 | 90 | 417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | CLINTON | IS 35 N | NW0153 | 7.744 | 33.811 | 0 | Y |  | Pavement resurfacing from 1 mile north of Rte. 116 to 0.33 miles south of PP. | Federal | 7246 | 805 | 0 | 8053 | 0 | NHPP |  | 2 | 100 | 544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | DAVIESS | MO 13 N | NW0081 | 24.069 | 48.138 | 0 | N |  | Pavement resurfacing on Rte. 13 from Rte. 136, near Bethany, to Rte. 6 near Gallatin. | Federal | 4451 | 1113 | 0 | 5576 | 0 | NHPP |  | 12 | 20 | 80 | 359 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 5094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | DAVIESS | MO 13 S | NW0105 | 0.384 | 0.768 | 19 | N |  | Bridge rehabilitation on various routes in Daviess, Grundy, Harrison, Linn, Mercer, Putnam, and Sullivan Counties. Project involves various bridges. | Federal | 1251 | 313 | 0 | 1654 | 0 | NHPP | NW0106 | 90 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | DAVIESS | MO 190 W | NW0053 | 12.444 | 24.888 | 0 | N |  | Pavement resurfacing from Rte. 146 to Rte. F in Jamesport. | Adv. CN | 991 | 248 | 0 | 1294 | 0 | AC-STBG |  | 55 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | DAVIESS | IS 35 N | NW0032 | 9.413 | 38.206 | 0 | N |  | Pavement repair from Rte. C near Pattonsburg to Rte. 69. | Federal | 4055 | 450 | 0 | 4555 | 0 | NHPP |  | 50 | 80 | 305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | DAVIESS | IS 35 N | NW0155 | 0.376 | 1.252 | 2 | N |  | Bridge preventative maintenance on northbound lanes over the Grand River and southbound lanes over Granite Avenue. Project involves bridges A1756 and A1758. | Federal | 1036 | 115 | 0 | 1152 | 0 | NHPP |  | 1 | 1 | 10 | 15 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | DAVIESS | IS 35 S | NW0178 | 14.917 | 61.036 | 0 | N |  | Pavement improvements from Rte. 69 to north of Grand Avenue. | Federal | 12849 | 1428 | 0 | 14277 | 0 | NHPP |  | 0 | 15 | 25 | 55 | 155 | 845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | DAVIESS | MO 6 W | NW0062 | 11.015 | 24.769 | 0 | N |  | Pavement resurfacing from Rte. V to Rte. F in Jamesport and from 4th Street, in Trenton, to No Creek in Grundy County. | Federal | 3432 | 858 | 0 | 4347 | 0 | NHPP |  | 57 | 273 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4017 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | DAVIESS | RT BB E | NW0070 | 0.162 | 0.324 | 1 | N |  | Bridge replacement over I-35 3.6 miles north of Cameron. Project involves bridge R0237. | Adv. CN | 2654 | 663 | 0 | 3352 | 0 | AC-STBG |  | 35 | 1 | 100 | 175 | 213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | DEKALB | US 36 W | NW0156 | 1.011 | 2.022 | 0 | N |  | Road realignment on the westbound lanes from 0.5 miles west of Watson Road to Taylor Road 0.7 miles east of Rte. 31. | Federal | 5222 | 580 | 0 | 5952 | 0 | SAFETY |  | 150 | 250 | 379 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 5144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | GENTRY | MO 48 E | NW0113 | 0.032 | 0.064 | 2 | N |  | Bridge replacement over 3rd fork Platte River 1.6 miles east of King City and Elm Grove Branch 3 miles east of King City. Project involves bridges J0083 and J0084. | Federal | 2463 | 616 | 0 | 3104 | 0 | NHPP |  | 25 | 10 | 100 | 150 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | GRUNDY | MO 6 W | NW0062B | 12.575 | 25.633 | 0 | N |  | Pavement resurfacing from Rte. F to 4th Street in Trenton. | Federal | 5406 | 1351 | 0 | 6757 | 0 | NHPP |  | 0 | 200 | 447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | GRUNDY | US 65 N | NW0086 | 36.804 | 73.608 | 0 | N |  | Pavement resurfacing from Arctic Street to Rte. 6 in Trenton. | Federal | 17524 | 4381 | 0 | 21918 | 0 | NHPP |  | 13 | 20 | 150 | 150 | 1370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | GRUNDY | US 65 S | NW0088 | 18.582 | 37.311 | 0 | N |  | Pavement resurfacing from Rte. 6, in Trenton, to 1.3 miles north of Rte. 190 in Chillicothe. | Federal | 10259 | 2565 | 0 | 12844 | 0 | NHPP |  | 20 | 20 | 75 | 100 | 807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11822 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | HARRISON | US 136 E | NW0075 | 0.044 | 0.088 | 1 | N |  | Bridge replacement over I-35 in Bethany. Project involves bridge A0698. $1,000,000 in Community Project funds from Federal Transportation Bill Earmark. | Federal | 5050 | 1263 | 0 | 6338 | 0 | NHPP |  | 25 | 35 | 140 | 490 | 367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5281 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | HARRISON | IS 35 S | NW0052 | 8.192 | 34.148 | 0 | N |  | Pavement resurfacing from the Iowa State line to Rte. N near Eagleville. | Federal | 6164 | 685 | 0 | 7109 | 0 | NHPP |  | 260 | 459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | HARRISON | IS 35 S | NW0151 | 81.382 | 333.184 | 0 | N |  | Job Order Contracting for pavement repair from the Iowa State line to the Clay County line. | Adv. CN | 695 | 77 | 0 | 773 | 0 | AC-NHPP |  | 1 | 1 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | HARRISON | US 69 N | NW0057 | 0.165 | 0.33 | 1 | N |  | Bridge replacement over Zadie Branch 1 mile west of I-35. Project involves bridge L0267. $792,000 from Iowa DOT. | Federal | 715 | 0 | 642 | 1667 | 0 | NHPP |  | 300 | 293 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1064 | 0 | 0 | 0 | 0 | 150 | 642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | HARRISON | RT N E | NW0058 | 0.124 | 0.248 | 1 | N |  | Bridge rehabilitation over East Fork Big Creek 1.6 miles east of I-35. Project involves bridge A2402. | Federal | 1443 | 361 | 0 | 1844 | 0 | NHPP |  | 40 | 100 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | HOLT | MO 111 S | NW0056 | 0.279 | 0.558 | 1 | N |  | Bridge replacement over the Tarkio River near Craig. Project involves bridge T0104. | Adv. CN | 2082 | 520 | 0 | 2772 | 0 | AC-STBG |  | 170 | 173 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 2404 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | HOLT | MO 118 E | NW0059 | 0.033 | 0.066 | 1 | N |  | Bridge rehabilitation over I-29 near Mound City. Project involves bridge A1766. | Federal | 1768 | 442 | 0 | 2300 | 0 | NHPP |  | 90 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | HOLT | US 159 N | 1P3383 | 0.462 | 0.924 | 1 | N |  | Payment to Nebraska DOT for bridge rehabilitation over the Missouri River near Rulo Nebraska. Project involves bridge A7698. | Federal | 800 | 200 | 0 | 1004 | 0 | NHPP |  | 4 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 997 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | HOLT | US 159 S | NW0119 | 0.021 | 0.042 | 1 | N |  | Bridge improvements over Little Tarkio Creek 6.5 miles east of I-29. Project involves bridge A2583. $500,000 in Community Project funds from Federal Transportation Bill Earmark. | Federal | 1421 | 355 | 0 | 1791 | 0 | NHPP |  | 15 | 5 | 1 | 12 | 50 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1607 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0
1 | HOLT | IS 29 N | NW0050 | 15.091 | 61.416 | 0 | N |  | Pavement resurfacing from Rte. 118 to Rte. W. | Federal | 13234 | 1470 | 0 | 14849 | 0 | NHPP |  | 145 | 50 | 944 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | HOLT | IS 29 N | NW0061 | 16.633 | 67.778 | 0 | N |  | Pavement resurfacing from Rte. 59 to Rte. 118 near Mound City. | Federal | 12688 | 1410 | 0 | 14328 | 0 | NHPP |  | 230 | 50 | 200 | 888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12960 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | HOLT | IS 29 N | NW0067 | 0.156 | 0.624 | 2 | N |  | Bridge rehabilitation over Little Tarkio Creek 1.6 miles south of Rte. 59 near Craig. Project involves bridge A1909. $500,000 in Community Project funds from Federal Transportation Bill Earmark. | Federal | 5904 | 656 | 0 | 6586 | 0 | NHPP |  | 26 | 5 | 20 | 200 | 445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5890 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | HOLT | IS 29 N | NW0167 | 0.708 | 2.609 | 5 | N |  | Pavement replacement at bridge approaches and under overpass bridges at various locations in Holt County. Projects involves bridges A2705, A1912, A2706, A1393, A1767. | Federal | 3974 | 442 | 0 | 4416 | 0 | NHPP |  | 0 | 377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | HOLT | US 59 S | NW0019 | 0.1 | 0.2 | 0 | N |  | Repair slide and shoulder repairs 1.1 miles south of Rte. 111 near Oregon. | Adv. CN | 3390 | 847 | 0 | 4602 | 0 | AC-STBG |  | 345 | 5 | 269 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3963 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | HOLT | RT B S | NW0139 | 0.524 | 1.048 | 10 | N |  | Bridge painting on various bridges in Atchison, Holt, Worth, Harrison, Mercer, Daviess, and Chariton Counties. Project includes bridges A1834, A1907, A2708, L0344, A1766, A0448, A2291, A1589, A2635, and A1906. | Federal | 2802 | 700 | 0 | 3504 | 0 | NHPP |  | 2 | 40 | 70 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | LINN | US 36 E | NW0138 | 28.588 | 112.693 | 0 | N |  | Pavement resurfacing from County Road 227 to west of Atlantic Loop. Rte. 11 from Husk Road to north of E. Locking Street. On Park Circle from Rte. 11 to west of Inglewood. On Rte. U from 0.1 mile north of Lilac Road to Rte. 5 0.16 miles south of Lilac Road. | Federal | 20704 | 5176 | 0 | 25890 | 0 | NHPP |  | 10 | 40 | 60 | 1590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | LINN | US 36 W | NW0117 | 0 | 0.082 | 2 | N |  | Bridge rehabilitation over Big Turkey Creek and Big Turkey Creek Overflow 1 mile east of Laclede. Project involves bridges A0793 and A0845. | Federal | 1104 | 276 | 0 | 1400 | 0 | NHPP |  | 20 | 5 | 15 | 50 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | LINN | US 36 W | NW0127 | 0.392 | 1.568 | 0 | N |  | Construct J-turns at the intersection with Rte. 129 near Bucklin. | Federal | 3226 | 358 | 0 | 3769 | 0 | SAFETY | NW0128 | 185 | 371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | LINN | US 36 W | NW0128 | 0.94 | 3.76 | 0 | N |  | Construct J-turns at Rte. F east of Brookfield. | Federal | 3135 | 348 | 0 | 3718 | 0 | SAFETY | NW0127 | 235 | 306 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 3152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | LINN | MO 5 N | NW0054 | 32.475 | 65.152 | 0 | N |  | Pavement resurfacing from Rte. 36 to Rte. 6 north near Milan. | Adv. CN | 6996 | 1749 | 0 | 8790 | 0 | AC-STBG |  | 45 | 100 | 549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | LIVINGSTON | US 36 E | NW0120 | 0.968 | 3.87 | 0 | N |  | Construct J-turns at the intersection with Mitchell Road in Chillicothe. $1,182,000 Open Container funds. | Federal | 3703 | 411 | 0 | 4174 | 0 | SAFETY | NW0074 | 60 | 530 | 0 | 0 | 0 | 0 | 0 | 185 | 0 | 0 | 0 | 0 | 0 | 3399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | LIVINGSTON | US 36 W | NW0074 | 0.55 | 2.202 | 0 | N |  | Roadway realignment in the westbound lane 0.4 miles west of Rte. B to 0.2 miles east of Rte. B. Project also includes turn lanes in eastbound and westbound lanes. | Federal | 3146 | 786 | 0 | 4092 | 0 | NHPP | NW0120 | 150 | 327 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 3605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | LIVINGSTON | RT DD E | NW0132 | 0.05 | 0.1 | 1 | N |  | Bridge replacement over Shoal Creek Drain Ditch 0.8 mile west of Rte. C in Livingston County. Project involves bridge P0932. | Federal | 2188 | 547 | 0 | 2745 | 0 | NHPP |  | 10 | 40 | 80 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2381 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | MERCER | US 136 E | 1S3396 | 0.11 | 0.22 | 1 | N |  | Section 14 streambank protection at bridge over Weldon Fork. Corps of Engineers to design and administer project. Cost shown represents MoDOT's share. Payment to Corps for design work. Project involves bridge A2634. | Adv. CN | 189 | 47 | 0 | 278 | 0 | AC-STBG |  | 42 | 16 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | NODAWAY | US 71 S | NW0085 | 18.23 | 32.447 | 0 | Y |  | Pavement improvements on the southbound lanes from Bus. 71, in Maryville, to 0.8 miles north of Rte. A (Nodaway County), and from 0.4 miles north of Rte. 48 to I-29 off ramp (Andrew County). | Federal | 14568 | 3642 | 0 | 18222 | 0 | NHPP |  | 12 | 1 | 16 | 68 | 237 | 1043 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | NODAWAY | RT C E | NW0147 | 0.128 | 0.256 | 1 | N |  | Bridge replacement over Moss Branch. Project involves bridge S0360. | Federal | 1115 | 279 | 0 | 1399 | 0 | NHPP |  | 5 | 10 | 25 | 80 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | NODAWAY | RT F S | NW0106 | 0.329 | 0.658 | 13 | N |  | Bridge rehabilitation on various routes in Gentry, Harrison, Nodaway, and Worth Counties. Project involves various bridges. | Federal | 1166 | 291 | 0 | 1551 | 0 | NHPP | NW0105 | 94 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1345 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | SULLIVAN | BU 5 N | NW0079 | 23.308 | 46.616 | 0 | N |  | Pavement resurfacing on Rte. 129 from Rte. 11 to Rte. 36 (Linn County), and on Bus. 5, and Rte. E in Milan (Grundy County). | Adv. CN | 2482 | 620 | 0 | 3119 | 0 | AC-STBG |  | 17 | 9 | 32 | 191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | VARIOUS | Various | 5B0800O | 0 | 0 | 0 | Y | BR-33 | Payback beginning in SFY 2008 for Safe and Sound bridges in the Northwest District. | Federal | 0 | 44865 | 0 | 179449 | 15,001 - 25,000 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 169 | 0 | 0 | 0 | 0 | 0 | 134415 | 8973 | 8973 | 8973 | 8973 | 8973
1 | VARIOUS | Various | NW0130 |  |  | 0 | Y |  | On-call work zone enforcement at various locations in the Northwest District. | Federal | 37 | 4 | 0 | 43 | 0 | SAFETY |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | VARIOUS | Various | NW0131 |  |  | 0 | Y | RR-2025-02 | Job Order Contracting for guardrail and guard cable repair on various major routes in the Northwest District. | Adv. CN | 1762 | 440 | 0 | 2204 | 0 | AC-NHPP |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | VARIOUS | Various | NW0141 | 0 | 0 | 0 | Y |  | On-call work zone enforcement at various locations in the Northwest District. | Federal | 41 | 4 | 0 | 46 | 0 | SAFETY |  | 1 | 1 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | VARIOUS | Various | NW0170 |  |  | 0 | Y | RR-2025-02 | Job Order Contracting for guardrail and guard cable repair on various major routes in the Northwest District. | Adv. CN | 1870 | 468 | 0 | 2338 | 0 | AC-NHPP |  | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | VARIOUS | Various | NW0171 | 0 | 0 | 0 | Y |  | On-call work zone enforcement at various locations in the Northwest District. | Federal | 39 | 4 | 0 | 43 | 0 | SAFETY |  | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | WORTH | US 169 S | NW0142 | 17.372 | 34.744 | 0 | N |  | Pavement improvement from Rte. 46, near Grant City, to Rte. 136 in Gentry County. | Adv. CN | 2975 | 744 | 0 | 3726 | 0 | AC-STBG |  | 7 | 2 | 7 | 11 | 38 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3444 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | ADAIR | MO 6 E | NE0142 | 0.201 | 0.402 | 1 | N |  | Bridge replacement over abandoned railroad 0.3 mile east of Rte. B in Kirksville. Project involves bridge A2901. | Federal | 644 | 161 | 0 | 902 | 0 | NHPP |  | 95 | 56 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | ADAIR | MO 6 E | NE0254 | 0.86 | 1.72 | 0 | N |  | Pavement resurfacing from east of Baltimore Street to 0.2 mile west of Rte. 63 in Kirksville. | Federal | 174 | 43 | 0 | 225 | 0 | NHPP | NE0024 | 8 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | ADAIR | BU 63 S | NE0100 | 3.179 | 10.234 | 0 | N |  | Pavement improvement from 0.4 mile south of Rte. 63 to Rte. 11 in Kirksville. | Adv. CN | 2907 | 727 | 0 | 3648 | 0 | AC-STBG |  | 14 | 5 | 25 | 242 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | ADAIR | US 63 S | NE0213 | 16.916 | 34.418 | 0 | N |  | Pavement improvement from 0.5 mile north of Rte. D to north of Rte. DD in Macon County. | Federal | 5345 | 1336 | 0 | 6699 | 0 | NHPP |  | 18 | 25 | 50 | 472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | AUDRAIN | MO 22 E | NE0151 | 1.322 | 2.644 | 1 | N |  | Bridge replacement over CPKC railroad 0.2 mile west of Rte. 151 west junction near Sturgeon and rebuild pavement on Rtes. 22 and 151. Project involves bridge K0672. | Federal | 8922 | 2230 | 0 | 11652 | 0 | NHPP |  | 450 | 958 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 10194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | AUDRAIN | US 54 E | NE0251 | 13.863 | 27.726 | 0 | N |  | Roadway improvement from Farber to Curryville in Audrain, Ralls, and Pike Counties. $24,892,433 BUILD Grant. | Federal | 24892 | 1500 | 0 | 28424 | 0 | NHPP |  | 2250 | 500 | 400 | 400 | 608 | 0 | 0 | 0 | 499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23767 | 0 | 2000 | 450 | 692 | 0 | 21750 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | AUDRAIN | US 54 E | NE0253 | 3.29 | 6.579 | 0 | N |  | Roadway improvement from east of Rte. 19 to 0.3 mile west of Rte. AA near Farber. $4,900,000 Community Project Funding. | Federal | 6449 | 1612 | 0 | 8361 | 0 | NHPP |  | 300 | 200 | 150 | 200 | 474 | 0 | 0 | 0 | 0 | 226 | 0 | 0 | 0 | 0 | 0 | 0 | 6811 | 0 | 0 | 0 | 0 | 0 | 4900 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | AUDRAIN | US 54 W | NE0216 | 0 | 0.046 | 1 | N |  | Bridge improvement over Beaverdam Creek 0.6 mile north of Rte. HH near Mexico. Project involves bridge H0594. | Federal | 2056 | 514 | 0 | 2780 | 0 | NHPP |  | 210 | 50 | 50 | 197 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | AUDRAIN | RT J E | NE0112 | 17.913 | 35.887 | 0 | N |  | Pavement preservation treatment from Bus. 54 in Mexico to 0.1 mile west of Rte. 54 at Basinger Corner. | Adv. CN | 590 | 148 | 0 | 746 | 0 | AC-STBG |  | 8 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 686 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | CLARK | US 136 E | NE0155 | 0.016 | 0.032 | 1 | N |  | Bridge improvement over drainage ditch 3 miles west of Rte. 61 near Alexandria. Project involves bridge F0955. | Federal | 1271 | 318 | 0 | 1874 | 0 | NHPP |  | 285 | 10 | 108 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | CLARK | US 61 S | 2P3353 | 13.161 | 91.426 | 0 | N |  | Pavement improvements from the Iowa State line to 0.5 mile north of Rte. B in Lewis County near LaGrange (nine disconnected sections). Project includes southbound and northbound lanes on Rte. 27 from the Iowa State line to the Rte. 61 interchange. | Federal | 5960 | 1490 | 0 | 7614 | 0 | NHPP |  | 164 | 10 | 10 | 461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6969 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | CLARK | US 61 S | NE0048 | 14.779 | 29.558 | 0 | N |  | Pavement resurfacing on southbound lanes from Rte. 27 to 1.2 miles north of Rte. B in Lewis County near Canton (seven disconnected sections), from Iowa State line to Rte. 27, and Rte. 27 from north of the Fox River to Rte. 61. | Federal | 3945 | 986 | 0 | 5201 | 0 | NHPP |  | 270 | 387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | KNOX | MO 11 S | NE0024 | 42.609 | 85.218 | 0 | N |  | Pavement resurfacing from Rte. 15 near Baring to Rte. 129 in Linn County (three disconnected sections). | Adv. CN | 4368 | 1092 | 0 | 5612 | 0 | AC-STBG | NE0254 | 152 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | KNOX | MO 15 S | NE0101 | 32.044 | 64.088 | 0 | N |  | Pavement preservation treatment from Rte. 6 north junction at Edina to Rte. 168 in Shelbyville in Shelby County. | Adv. CN | 1052 | 263 | 0 | 1321 | 0 | AC-STBG |  | 6 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | KNOX | MO 15 S | NE0208 | 0.031 | 0.062 | 1 | N |  | Bridge improvement over Rock Creek 0.4 mile south of Rte. 6 near Edina. Project involves bridge H0771. | Federal | 1812 | 453 | 0 | 2315 | 0 | NHPP | NE0215 | 50 | 200 | 232 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1831 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | KNOX | MO 6 E | NE0215 | 0.088 | 0.176 | 1 | N |  | Bridge improvement over South Fork South Fabius River 0.2 mile north of Rte. 6 near Edina. Project involves bridge H0770. | Federal | 4323 | 1081 | 0 | 5619 | 0 | NHPP | NE0208 | 215 | 350 | 549 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 4495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | KNOX | RT BB S | NE0148 | 0.025 | 0.05 | 1 | N |  | Bridge improvement over North River 1.1 miles south of Rte. 15. Project involves bridge P0989. | Adv. CN | 1218 | 305 | 0 | 1765 | 0 | AC-STBG |  | 242 | 20 | 113 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | KNOX | RT F E | NE0149 | 0.016 | 0.032 | 1 | N |  | Bridge improvement over Little Fabius River 3.3 miles west of Rte. 15 near Hurdland. Project involves bridge P0400. | Adv. CN | 870 | 217 | 0 | 1249 | 0 | AC-STBG |  | 162 | 10 | 77 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | KNOX | RT K E | NE0156 | 0.249 | 0.498 | 1 | N |  | Bridge replacement over Middle Fabius River 0.5 mile east of Rte. V near Colony. Project involves bridge X0617. | Federal | 1940 | 485 | 0 | 2775 | 0 | NHPP |  | 350 | 249 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | LEWIS | MO 16 E | NE0026 | 16.709 | 33.418 | 0 | N |  | Pavement improvement from Rte. 6 to Rte. B in Canton. | Adv. CN | 3059 | 765 | 0 | 3883 | 0 | AC-STBG |  | 59 | 50 | 283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | LEWIS | RT H S | NE0150 | 0.06 | 0.12 | 1 | N |  | Bridge improvement over Middle Fabius River 2.3 miles south of Rte. Y near Lewistown. Project involves bridge R0153. | Federal | 2551 | 638 | 0 | 3591 | 0 | NHPP |  | 402 | 50 | 10 | 199 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | LINCOLN | MO 147 S | NE0124 | 0.015 | 0.03 | 1 | N |  | Bridge improvement over Little Sugar Creek 0.9 mile north of Rte. 47 near Troy. Project involves bridge L0844. | Adv. CN | 662 | 166 | 0 | 1064 | 0 | AC-STBG |  | 235 | 10 | 10 | 10 | 10 | 55 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | LINCOLN | MO 47 S | NE0023 | 0.213 | 0.426 | 1 | N |  | Bridge improvement over Cuivre River 1.3 miles east of Rte. 61 near Troy. Project involves bridge A5595. | Federal | 663 | 166 | 0 | 852 | 0 | NHPP |  | 23 | 1 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | LINCOLN | US 61 N | NE0256 | 0 | 0.198 | 0 | N |  | Demolition of structures on state right of way south of Rtes. K and V. | Adv. CN | 90 | 22 | 0 | 124 | 0 | AC-STBG |  | 12 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 102 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | LINCOLN | US 61 S | NE0004 | 2.948 | 8.684 | 0 | N |  | Add interchange with roundabouts and outer roads from 0.2 mile north of Rtes. V and K to 0.1 mile south of Creech Lane. $1,484,000 Open Container funds. | Federal | 20080 | 5020 | 0 | 28902 | 0 | NHPP |  | 2700 | 1975 | 0 | 0 | 0 | 0 | 1102 | 0 | 0 | 0 | 0 | 0 | 0 | 23125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | LINCOLN | US 61 S | NE0144 | 2.404 | 8.5 | 0 | N |  | Safety and intersection improvements at Rte. B and Rte. E near Troy. | Federal | 21816 | 5454 | 0 | 29220 | 0 | NHPP |  | 1950 | 150 | 1649 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 0 | 24371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | LINCOLN | US 61 S | NE0235 | 8.963 | 38.181 | 0 | N |  | Pavement resurfacing from 1.3 mile north of Rte. 47 near Troy to Big Creek on northbound and southbound lanes. | Federal | 9914 | 2479 | 0 | 12468 | 0 | NHPP |  | 75 | 866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | LINCOLN | US 61 S | NE0236 | 7.874 | 25.448 | 0 | N |  | Pavement improvement from just south of Rte. E to north of Cuivre River on southbound lanes and from north of Cuivre River to Rte. V near Troy on northbound lanes. $3,000,000 District Operations funds. | Federal | 7028 | 1757 | 0 | 8885 | 0 | NHPP |  | 100 | 25 | 594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8166 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | LINCOLN | MO 79 S | NE0086 | 17.063 | 34.126 | 0 | N |  | Pavement improvement from Pike County line to Rte. 47 in Winfield. | Adv. CN | 3154 | 788 | 0 | 4003 | 0 | AC-STBG |  | 61 | 5 | 5 | 244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | LINCOLN | RT C E | NE0089 | 10.881 | 22.246 | 0 | N |  | Pavement improvement and add rumble stripes from Elm Tree Road to Main Street in Old Monroe. $860,000 Open Container funds. | Adv. CN | 2517 | 629 | 0 | 3171 | 0 | AC-STBG | NE0237 | 25 | 25 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | LINCOLN | RT C E | NE0219 | 0.114 | 0.228 | 1 | N |  | Bridge rehabilitation over Cuivre River 0.1 mile east of Front Street in Moscow Mills. Project involves bridges A1658. | Federal | 738 | 184 | 0 | 982 | 0 | NHPP |  | 60 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | LINCOLN | CST EAST CHERRY ST E | NE0196 | 0.051 | 0.102 | 1 | N |  | Bridge improvement over Rte. 61 in Troy. Project involves bridge A2605. | Federal | 1190 | 297 | 0 | 1697 | 0 | NHPP | NE0266 | 210 | 25 | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | LINCOLN | RT J S | NE0237 | 11.625 | 23.316 | 0 | N |  | Pavement improvement and add rumble stripes from Rte. H in Troy to I-70 north Outer Road in Wright City. $569,000 Open Container funds. | Adv. CN | 2149 | 537 | 0 | 2786 | 0 | AC-STBG | NE0089 | 100 | 5 | 172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | LINCOLN | CST OLD CAP AU GRIS RD W | NE0266 | 0.05 | 0.1 | 1 | N |  | Bridge improvement over Rte. 61 on Old Cap Au Gris Road in Troy. Project involves bridge A2606. | Adv. CN | 878 | 219 | 0 | 1097 | 0 | AC-STBG | NE0196 | 0 | 75 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MACON | MO 149 S | NE0158 | 0.01 | 0.02 | 1 | N |  | Culvert improvement over Little Walnut Creek 0.1 mile south of Rte. 156 near Gifford. Project involves culvert X0936. | Federal | 1196 | 299 | 0 | 1855 | 0 | NHPP |  | 360 | 10 | 10 | 99 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MACON | RT UU S | 2S3315 | 0.277 | 0.554 | 1 | N |  | Bridge improvement over BNSF Railway 0.5 mile north of Rte. 36 near Callao. Project involves bridge W0401. | Adv. CN | 2750 | 688 | 0 | 3756 | 0 | AC-STBG |  | 318 | 150 | 296 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 2942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MARION | MO 168 E | NE0065 | 6.68 | 13.36 | 0 | N |  | Pavement resurfacing and add rumble stripes from 0.2 mile east of Rte. JJ to Rte. 61 in Hannibal. | Adv. CN | 1159 | 290 | 0 | 1582 | 0 | AC-STBG |  | 131 | 102 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MARION | US 24 E | NE0108 | 0.43 | 0.86 | 1 | N |  | Payment to IDOT for bridge replacement study on the Quincy Memorial Bridge over the Mississippi River. Project involves bridge L0099. | Federal | 3201 | 800 | 0 | 4005 | 0 | NHPP |  | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MARION | US 24 E | NE0231 | 0.433 | 0.866 | 1 | N |  | Payment to IDOT for bridge replacement on the Quincy Memorial Bridge over the Mississippi River at Quincy. Project involves bridge L0099. | Federal | 84003 | 21001 | 0 | 105005 | 0 | NHPP |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MARION | US 24 E | NE0245 | 0.145 | 0.29 | 1 | N |  | Bridge improvement over South Fabius River 1.2 miles south of Rte. 6 near Taylor. Project involves bridge A2021. | Federal | 523 | 131 | 0 | 684 | 0 | NHPP |  | 30 | 25 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 571 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MARION | US 24 E | NE0268 | 14.787 | 64.207 | 0 | N |  | Pavement improvement on eastbound and westbound lanes from 0.3 mile north of Rte. F and Rte. 24 to 3.0 miles east of Rte. 61 near Taylor and on Rte. 61 0.5 mile north of Rte. 24. | Federal | 25408 | 6352 | 0 | 31760 | 0 | NHPP |  | 0 | 50 | 50 | 1971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MARION | US 24 W | NE0109 | 0 | 0.914 | 1 | N |  | Payment to IDOT for rehabilitation on Quincy Bayview Bridge over the Mississippi River. Project involves bridge A4274. | Federal | 4002 | 1000 | 0 | 5005 | 0 | NHPP |  | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MARION | US 24 W | NE0233 | 0.695 | 3.746 | 0 | N |  | Intersection safety improvement at southbound Rte. 61, westbound Rte. 24, and Rte. F. | Federal | 6183 | 687 | 0 | 7020 | 0 | SAFETY |  | 150 | 350 | 507 | 0 | 0 | 0 | 0 | 0 | 284 | 0 | 0 | 0 | 0 | 0 | 5729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MARION | BU 61 S | NE0064 | 2.951 | 5.902 | 0 | N |  | Pavement resurfacing from 0.1 mile north of Rte. BB to 0.1 mile north of Rtes. 24 and 61 in Palmyra and on Rte. 168 (two disconnected sections). | Adv. CN | 419 | 105 | 0 | 554 | 0 | AC-STBG | NE0063 | 30 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MARION | US 61 S | NE0008 | 0 | 0 | 0 | N |  | Signal and striping safety upgrades at various locations in Hannibal, Troy, Warrenton, Kirksville, Macon, and Moberly. | Federal | 406 | 45 | 0 | 471 | 0 | SAFETY |  | 20 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MARION | IS 72 E | NE0200 | 0.394 | 1.6 | 1 | N |  | Bridge washing on the Mark Twain Memorial Bridge over the Mississippi River at Hannibal. Project involves bridge A5054. $127,500 IDOT funds. | Federal | 165 | 0 | 127 | 294 | 0 | NHPP |  | 2 | 1 | 1 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 271 | 0 | 0 | 0 | 0 | 0 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MARION | IS 72 E | NE0232 | 0.394 | 1.6 | 1 | N |  | Bridge improvement on the Mark Twain Memorial Bridge over the Mississippi River at Hannibal. Project involves bridge A5054. $4,080,255 IDOT funds. | Federal | 6477 | 0 | 4080 | 10558 | 0 | NHPP |  | 1 | 85 | 900 | 50 | 604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8918 | 0 | 0 | 0 | 0 | 0 | 4080 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MARION | RT W W | NE0069 | 3.338 | 6.676 | 0 | N |  | Pavement resurfacing from Rte. 61 north junction to Rte. 61 south junction and on Rte. 61 outer road from Rte. W to 0.3 mile south of Rte. W in Hannibal. | Adv. CN | 583 | 146 | 0 | 734 | 0 | AC-STBG |  | 5 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MONROE | MO 15 S | NE0214 | 0.068 | 0.136 | 1 | N |  | Bridge rehabilitation over Middle Fork Salt River 0.3 mile south of Rte. 24 in Paris. Project involves bridge A4396. | Federal | 841 | 210 | 0 | 1176 | 0 | NHPP |  | 125 | 114 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MONROE | RT AA E | NE0153 | 0.086 | 0.172 | 1 | N |  | Bridge improvement over Elk Fork Salt River 3.3 miles south of Rte. 24 near Madison. Project involves bridge R0548. | Adv. CN | 1054 | 264 | 0 | 1498 | 0 | AC-STBG |  | 180 | 25 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MONTGOMERY | IS 70 E | 2I3226Z | 4.098 | 19.899 | 0 | N |  | Payback for MTFC loan to add eastbound and westbound climbing lanes, replace westbound bridge over Loutre River Overflow from 1.1 miles east of Rte. N to 0.3 mile west of Rte. 161 near Mineola. Total cost of $3,878,000 with payments from 2024 to 2030. | Adv. CN | 2770 | 0 | 0 | 3878 | 0 | AC-NHFP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1662 | 554 | 554 | 554 | 554 | 0
2 | MONTGOMERY | IS 70 E | NE0129 | 38.598 | 162.115 | 0 | N |  | Job Order Contracting for pavement repair from the Callaway County line to the St. Charles County line. | Adv. CN | 507 | 56 | 0 | 565 | 0 | AC-NHPP |  | 2 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MONTGOMERY | IS 70 E | NE0201 | 42.194 | 174.248 | 0 | N |  | Job Order Contracting for guard cable repair on I-70 in Montgomery and Warren Counties, Rte. 61 in Lincoln County, Rte. T in Ralls County, and Rte. 36 in Macon County. | Adv. CN | 1542 | 171 | 0 | 1715 | 0 | AC-NHPP |  | 2 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MONTGOMERY | IS 70 E | NE0263 | 42.194 | 174.248 | 0 | N |  | Job Order Contracting for guard cable repair on I-70 in Montgomery and Warren Counties, Rte. 61 in Lincoln County, Rte. T in Ralls County, and Rte. 36 in Macon County. | Adv. CN | 1631 | 181 | 0 | 1812 | 0 | AC-NHPP |  | 0 | 1 | 1 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MONTGOMERY | IS 70 E | NE0265 | 38.598 | 162.115 | 0 | N |  | Job Order Contracting for pavement repair from the Callaway County line to the St. Charles County line. | Adv. CN | 537 | 60 | 0 | 597 | 0 | AC-NHPP |  | 0 | 1 | 1 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | MONTGOMERY | MO 94 E | NE0259 | 9.953 | 19.906 | 0 | N |  | Pavement preservation treatment from 0.2 mile east of Bluffton Road to Rte. 19 near McKittrick. | Adv. CN | 296 | 74 | 0 | 370 | 0 | AC-STBG |  | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | RALLS | MO 154 E | NE0107 | 12.351 | 24.702 | 0 | N |  | Pavement resurfacing from Rte. 19 south junction to Rte. 54 near Vandalia in Pike County. | Adv. CN | 1207 | 302 | 0 | 1519 | 0 | AC-STBG |  | 10 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | RALLS | US 61 S | NE0244 | 7.89 | 32.401 | 0 | N |  | Pavement resurfacing from just north of Warren Barrett Drive in Hannibal to 0.5 mile south of Rte. 19 near New London on northbound and southbound lanes. | Federal | 10634 | 2659 | 0 | 13493 | 0 | NHPP |  | 200 | 1041 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | RALLS | RT J S | NE0072 | 19.163 | 38.326 | 0 | N |  | Pavement improvement from Rte. 36 to Rte. 154 in Perry (two disconnected sections). | Adv. CN | 3491 | 873 | 0 | 4410 | 0 | AC-STBG |  | 46 | 75 | 315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | RANDOLPH | MO 22 E | 2P3095 | 17.317 | 34.739 | 0 | N |  | Pavement resurfacing and add rumble stripes from 0.1 mile west of Rte. E near Mexico to Rte. F in Boone County. $1,200,000 Open Container funds. | Adv. CN | 2970 | 743 | 0 | 3830 | 0 | AC-STBG |  | 117 | 248 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | RANDOLPH | US 24 E | NE0068 | 0.1 | 0.454 | 0 | N |  | Pavement replacement at Bus. 63 in Moberly. | Federal | 1251 | 313 | 0 | 1604 | 0 | NHPP |  | 40 | 199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | RANDOLPH | US 24 E | NE0170 | 0.025 | 0.05 | 1 | N |  | Bridge improvement over East Fork Salt River 0.5 mile east of Rte. YY near Milton. Project involves bridge L0118. | Federal | 4442 | 1111 | 0 | 6103 | 0 | NHPP |  | 550 | 250 | 565 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 4728 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | RANDOLPH | MO 3 S | NE0194 | 0.03 | 0.06 | 1 | N |  | Bridge improvement over Sweet Spring Creek 2.3 miles south of Rte. 24 near Mount Airy. Project involves bridge J0402. | Federal | 1726 | 431 | 0 | 2212 | 0 | NHPP | NE0272 | 55 | 200 | 75 | 185 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | RANDOLPH | MO 3 S | NE0272 | 0.11 | 0.22 | 1 | N |  | Bridge improvement over Silver Creek 2 miles south of Rte. U near Mount Airy. Project involves bridge J0727. | Federal | 1942 | 486 | 0 | 2428 | 0 | NHPP | NE0194 | 0 | 200 | 100 | 176 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | RANDOLPH | BU 63 S | NE0002 | 0.301 | 0.602 | 0 | N |  | Payment to Moberly for ADA Transition Plan improvements and add center turn lane from Burkhart Street to Carpenter Street. $1,056,161 Cost Share funds. | Adv. CN | 850 | 213 | 0 | 1066 | 0 | AC-STBG |  | 3 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1056 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | RANDOLPH | US 63 N | NE0246 | 0.236 | 2.61 | 0 | N |  | Widen intersection and add acceleration lane at Rte. P and widen intersection at Rte. P and County Road 2790 near Clark. $618,000 Cost Share funds. | Federal | 565 | 141 | 0 | 726 | 0 | NHPP |  | 20 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | RANDOLPH | RT A S | NE0076 | 10.976 | 21.952 | 0 | N |  | Pavement improvement from Bus. 63 to to Howard County Line. | Adv. CN | 1598 | 400 | 0 | 2018 | 0 | AC-STBG | NE0039 NE0077 NE0206 NE0207 | 20 | 15 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | RANDOLPH | RT B W | NE0077 | 18.294 | 36.588 | 0 | N |  | Pavement improvement from Rte. 63 near Clark to Rte. 3 near Roanoke in Howard County. | Adv. CN | 1967 | 492 | 0 | 2486 | 0 | AC-STBG | NE0039 NE0076 NE0206 NE0207 | 27 | 56 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | RANDOLPH | RT EE E | NE0207 | 1.102 | 4.408 | 0 | N |  | Pavement improvement from just east of Bus. 63 to Rte. 63 in Moberly. | Adv. CN | 595 | 149 | 0 | 761 | 0 | AC-STBG | NE0039 NE0076 NE0077 NE0206 | 17 | 15 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | RANDOLPH | RT JJ E | NE0039 | 4.597 | 9.221 | 0 | N |  | Pavement improvement from Rte. C in Huntsville to Rte. 24 in Moberly. | Adv. CN | 864 | 216 | 0 | 1103 | 0 | AC-STBG | NE0076 NE0077 NE0206 NE0207 | 23 | 2 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | RANDOLPH | RT M E | NE0206 | 1.096 | 2.192 | 0 | N |  | Pavement improvement from Bus. 63 to Rte. 63 in Moberly. | Adv. CN | 204 | 51 | 0 | 259 | 0 | AC-STBG | NE0039 NE0076 NE0077 NE0207 | 4 | 2 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | SCHUYLER | RT N S | NE0097 | 7.981 | 15.962 | 0 | N |  | Pavement improvement from Iowa State line to Rte. 136 in Downing. | Adv. CN | 258 | 65 | 0 | 329 | 0 | AC-STBG |  | 6 | 1 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | SCOTLAND | BU 136 E | NE0258 | 0.457 | 0.914 | 0 | N |  | Pavement resurfacing from Monroe Street to Rte. 136 in Memphis. | Federal | 96 | 24 | 0 | 120 | 0 | STBG | NE0098 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | SCOTLAND | US 136 E | NE0271 | 0.065 | 0.13 | 1 | N |  | Bridge improvement over Gunns Branch 0.7 mile east of Rte. MM near Memphis. Project involves bridge K0284. | Federal | 1766 | 441 | 0 | 2207 | 0 | NHPP |  | 0 | 200 | 75 | 188 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1742 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | SCOTLAND | RT MM S | NE0098 | 5.238 | 10.476 | 0 | N |  | Pavement resurfacing from Rte. 136 in Memphis to Rte. M. | Adv. CN | 585 | 146 | 0 | 735 | 0 | AC-STBG | NE0258 | 4 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | SHELBY | MO 168 E | NE0063 | 31.27 | 62.54 | 0 | N |  | Pavement resurfacing from Rte. 15 to Bus. 61 in Palmyra in Marion County and add rumble stripes from Philadelphia to Palmyra. | Adv. CN | 4184 | 1046 | 0 | 5650 | 0 | AC-STBG | NE0064 | 400 | 359 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 4871 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | SHELBY | US 36 E | NE0221 | 0.019 | 0.038 | 1 | N |  | Bridge improvement over Branch of Crooked Creek 1 mile east of Rte. TT near Clarence. Project involves bridge H0590. | Federal | 196 | 49 | 0 | 270 | 0 | NHPP |  | 25 | 10 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | SHELBY | RT C E | NE0067 | 19 | 38 | 0 | N |  | Pavement improvement from Rte. Z to Rte. 168 near Palmyra in Marion County. | Adv. CN | 1976 | 494 | 0 | 2518 | 0 | AC-STBG |  | 48 | 5 | 5 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | VARIOUS | Various | 5B0800Q | 0 | 0 | 1 | N |  | Payback beginning in SFY 2008 for Safe and Sound bridges in the Northeast District. | Federal | 0 | 26400 | 0 | 104930 | 10,001 - 15,000 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 78434 | 5280 | 5280 | 5280 | 5280 | 5280
2 | VARIOUS | Various | NE0134 | 0 | 0 | 0 | N |  | Job Order Contracting for guardrail repair at various locations in the Northeast District. | Adv. CN | 2226 | 557 | 0 | 2787 | 0 | AC-STBG |  | 4 | 183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | VARIOUS | Various | NE0202 | 0 | 0 | 0 | N |  | On-call work zone enforcement at various locations in the Northeast District. | Federal | 11 | 1 | 0 | 14 | 0 | SAFETY |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | VARIOUS | Various | NE0203 | 0 | 0 | 0 | N |  | On-call work zone enforcement at various locations in the Northeast District. | Federal | 11 | 1 | 0 | 14 | 0 | SAFETY |  | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | VARIOUS | Various | NE0260 | 0 | 0 | 0 | N |  | On-call work zone enforcement at various locations in the Northeast District. | Federal | 21 | 2 | 0 | 23 | 0 | SAFETY |  | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | VARIOUS | Various | NE0261 | 0 | 0 | 0 | N |  | On-call work zone enforcement at various locations in the Northeast District. | Federal | 22 | 2 | 0 | 24 | 0 | SAFETY |  | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | VARIOUS | Various | NE0262 | 0 | 0 | 0 | N |  | On-call work zone enforcement at various locations in the Northeast District. | Federal | 23 | 2 | 0 | 25 | 0 | SAFETY |  | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | VARIOUS | Various | NE0264 | 0 | 0 | 0 | N |  | Job Order Contracting for guardrail repair at various locations in the Northeast District. | Adv. CN | 2354 | 589 | 0 | 2943 | 0 | AC-STBG |  | 0 | 1 | 1 | 183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | WARREN | MO 47 S | NE0117 | 21.709 | 43.531 | 0 | N |  | Pavement improvement from 0.1 mile south of Rte. M in Warrenton to Missouri River Bridge near Washington. | Adv. CN | 2141 | 535 | 0 | 2713 | 0 | AC-STBG |  | 37 | 15 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | WARREN | MO 47 S | NE0247 | 0.513 | 1.026 | 0 | N |  | Payment to Warren County R-III School District to add turn lanes and signals at Nina Drive and add turn lanes at Ash Road in Warrenton. $1,416,805 Cost Share funds. $20,000 District Operations funds. | Adv. CN | 1146 | 286 | 0 | 1437 | 0 | AC-STBG |  | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1417 | 0 | 0 | 0 | 0 | 5 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JOHNSON | BU 13 S | 3S3229 | 0.528 | 2.103 | 2 | N |  | Bridge rehabilitation on Holden Street and Bus. 13 (Maguire Street) over Rte. 50 and pavement resurfacing on Rte. 50 from west of Holden Street to Bus. 13 (Maguire Street). Project involves bridges A0143 and A0321. | Adv. CN | 1402 | 351 | 0 | 1818 | 0 | AC-STBG |  | 65 | 15 | 57 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1569 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JOHNSON | MO 131 N | 3P3167 | 16.078 | 32.156 | 0 | N |  | Pavement resurfacing from Rte. 50 to Rte. 2. | Adv. CN | 5114 | 1279 | 0 | 6425 | 0 | AC-STBG |  | 32 | 50 | 50 | 50 | 100 | 186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JOHNSON | MO 2 W | KR0126 | 1.12 | 2.444 | 0 | N |  | Intersection improvements at Rte. 13. $711,000 Open Container funds. | Federal | 2595 | 288 | 0 | 3007 | 0 | SAFETY |  | 124 | 100 | 100 | 40 | 154 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 2439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JOHNSON | BU 50 E | 3P3202 | 1.11 | 2.22 | 0 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan and pavement resurfacing in Knob Noster from Washington Avenue to Sunshine Lane and Rte. J from SE 25 Road to end of state maintenance. | Adv. CN | 2864 | 716 | 0 | 4413 | 0 | AC-STBG |  | 783 | 258 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 3322 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JOHNSON | US 50 E | KR0104 | 0.071 | 0.286 | 1 | N |  | Bridge rehabilitation over South Fork Blackwater River 1 mile west of County Road Northwest 1601 and 0.1 mile east of Rte. Z. Project involves bridge A1223. | Federal | 2660 | 665 | 0 | 4030 | 0 | NHPP |  | 705 | 397 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JOHNSON | US 50 E | KR0242 | 0.079 | 0.158 | 1 | N |  | Bridge rehabilitation over Union Pacific Railroad 0.2 mile east of Vaughn Street. Project involves bridge A2090. | Federal | 1229 | 307 | 0 | 1556 | 0 | NHPP |  | 20 | 15 | 15 | 15 | 15 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JOHNSON | US 50 W | KR0107 | 0 | 0.148 | 2 | N |  | Bridge rehabilitation over Devils Branch and Post Oak Creek 0.6 mile west of County Road 105 and 0.7 mile east of County Road Northwest 191 west of Warrensburg. Project involves bridges A1042 and A1043. | Federal | 3527 | 882 | 0 | 4864 | 0 | NHPP |  | 455 | 873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JOHNSON | US 50 W | KR0403 | 1.462 | 7.159 | 0 | N |  | Add J-turns from west of NW 1511 Road to west of NW 1391 Road. $704,000 Open Container funds. | Federal | 3439 | 382 | 0 | 3836 | 0 | SAFETY |  | 15 | 100 | 378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JOHNSON | MO 58 W | KR0220 | 21.97 | 43.941 | 0 | Y |  | Pavement resurfacing west of SE 1991st Road to Rte. 50. | Adv. CN | 10840 | 2710 | 0 | 13615 | 0 | AC-STBG |  | 65 | 5 | 5 | 200 | 1107 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 12230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JOHNSON | CST N MAGUIRE ST N | KR0450 | 0.102 | 0.3 | 2 | N |  | Payment to Warrensburg for design of North Maguire Street and Holden Street bridge improvements over Rte. 50. Project involves bridges A0321 and A0143. $1,067,000 Cost Share funds. | Federal | 0 | 1072 | 0 | 1077 | 0 | STATE |  | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JOHNSON | RT TT W | KR0296 | 0.262 | 0.524 | 7 | N |  | Culvert improvements at various locations in the rural Kansas City District. Project involves culverts A2384, P0813, L0274, H0722, G0560, J0042, and S0067. | Federal | 1987 | 497 | 0 | 2574 | 0 | NHPP |  | 90 | 5 | 100 | 275 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 2042 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | LAFAYETTE | MO 13 S | KR0076 | 6.877 | 14.078 | 0 | N |  | Pavement and safety improvements from Rte. 20 to I-70 in Higginsville. | Federal | 2984 | 746 | 0 | 3774 | 0 | NHPP |  | 44 | 20 | 50 | 100 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | LAFAYETTE | MO 13 S | KR0351 | 2.067 | 8.334 | 0 | Y |  | Pavement repair from Missouri River to Rte. 24 in Lexington. | Federal | 1240 | 310 | 0 | 1559 | 0 | NHPP |  | 9 | 5 | 5 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | LAFAYETTE | MO 131 S | 3S3179 | 2.149 | 4.298 | 0 | N |  | Pavement resurfacing from I-70 east outer road to Rte. OO. | Adv. CN | 514 | 128 | 0 | 662 | 0 | AC-STBG |  | 20 | 10 | 10 | 10 | 10 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | LAFAYETTE | MO 20 E | 3S3217 | 0.455 | 0.91 | 0 | N |  | Intersection improvements at Rte. 23. $743,000 Open Container funds. | Federal | 4162 | 462 | 0 | 4642 | 0 | SAFETY |  | 18 | 150 | 150 | 250 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 4061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | LAFAYETTE | US 24 E | KR0243 | 0.45 | 0.9 | 1 | N |  | Bridge rehabilitation on Waverly Bridge over Missouri River. Project involves bridge A5910. | Federal | 7842 | 1960 | 0 | 10109 | 0 | NHPP |  | 307 | 100 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9002 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | LAFAYETTE | US 24 W | KR0105 | 0.045 | 0.09 | 1 | N |  | Bridge rehabilitation over Tabo Creek 0.6 mile west of Garr Road. Project involves bridge A2850. | Federal | 2091 | 523 | 0 | 2685 | 0 | NHPP |  | 71 | 20 | 50 | 159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PETTIS | US 50 E | 3P3199 | 3.526 | 16.655 | 0 | N |  | Pavement resurfacing from Rte. 65 to the Sedalia Sub railroad crossing. | Federal | 4829 | 1207 | 0 | 6071 | 0 | NHPP | 3P3192 4P3422 | 35 | 681 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PETTIS | US 50 E | 3P3205 | 0.768 | 3.477 | 2 | N |  | Bridge rehabilitation and upgrade guardrail over Muddy Creek from Sadie Lane to 1.2 miles west of Curry Drive. Project involves bridge A2663. | Federal | 4348 | 1087 | 0 | 5763 | 0 | NHPP |  | 328 | 358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5077 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PETTIS | US 50 E | 4P3422 | 4.245 | 19.222 | 0 | N |  | Pavement resurfacing from Rte. MM to South Warren Avenue. | Federal | 4418 | 1105 | 0 | 5550 | 0 | NHPP | 3P3192 3P3199 | 27 | 980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PETTIS | US 50 E | KR0240 | 0.253 | 1.012 | 0 | N |  | Rebuild pavement from Massachusetts Avenue to Thompson Avenue in Sedalia. | Federal | 1465 | 366 | 0 | 1843 | 0 | NHPP |  | 12 | 25 | 105 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1593 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PETTIS | MO 52 W | KR0248 | 0.009 | 0.018 | 1 | N |  | Bridge replacement 0.1 mile east of Meyers Road. Project involves bridge H0880. | Federal | 952 | 238 | 0 | 1198 | 0 | NHPP |  | 8 | 1 | 10 | 10 | 10 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PETTIS | US 65 S | 3P3192 | 4.729 | 17.593 | 0 | N |  | Pavement resurfacing south of Rte. H to Rte. B. | Federal | 3798 | 949 | 0 | 4773 | 0 | NHPP | 3P3199 4P3422 | 26 | 422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PETTIS | US 65 S | KR0168 | 1.016 | 4.188 | 0 | N |  | Corridor improvements from 0.4 mile south of Rte. HH to North Ohio Avenue in Sedalia. $865,000 Open Container funds. | Federal | 2969 | 330 | 0 | 3632 | 0 | SAFETY |  | 333 | 50 | 241 | 191 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 2793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PETTIS | US 65 S | KR0399 | 2.469 | 12.52 | 0 | N |  | Intersection improvements from Rte. 50 to Sacajawea Road in Sedalia. | Federal | 2491 | 277 | 0 | 2778 | 0 | SAFETY |  | 10 | 75 | 75 | 75 | 75 | 335 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 2120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PETTIS | RT H S | 3S3228 | 0.03 | 0.06 | 1 | N |  | Bridge replacement over Pearl River at Georgetown Road. Project involves bridge W0535. | Adv. CN | 1365 | 341 | 0 | 1879 | 0 | AC-STBG |  | 173 | 103 | 102 | 132 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | SALINE | MO 20 E | KR0252 | 6.792 | 13.706 | 0 | N |  | Pavement resurfacing from Rte. EE to Rte. 65 in Marshall. | Adv. CN | 2047 | 512 | 0 | 2644 | 0 | AC-STBG |  | 85 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | SALINE | MO 240 E | 3P3183 | 5.678 | 11.356 | 0 | N |  | Pavement resurfacing from Rte. 65 to 0.2 mile east of Rte. 41. | Adv. CN | 10890 | 2723 | 0 | 13700 | 0 | AC-STBG |  | 87 | 5 | 5 | 1108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | SALINE | MO 41 S | 3P3175 | 11.367 | 22.734 | 0 | N |  | Pavement resurfacing from Rte. 240 to 0.6 mile north of Arrow Rock Road. | Adv. CN | 1491 | 373 | 0 | 1894 | 0 | AC-STBG | 3P3177 | 30 | 5 | 10 | 131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1718 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | SALINE | MO 41 S | 3P3177 | 13.853 | 27.706 | 0 | N |  | Pavement resurfacing from north of Rte. F to north of Rte. 240. | Adv. CN | 2158 | 540 | 0 | 2730 | 0 | AC-STBG | 3P3175 | 32 | 10 | 10 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | SALINE | US 65 S | KR0122 | 1.783 | 4.103 | 0 | N |  | Upgrade signals from Rte. 20 (Arrow Street) to Fairground Road in Marshall. | Federal | 301 | 33 | 0 | 376 | 0 | SAFETY |  | 42 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | SALINE | US 65 S | KR0257 | 0.018 | 0.036 | 1 | N |  | Bridge rehabilitation over Straddle Creek 0.7 mile east of Golden Avenue. Project involves bridge G0131. | Federal | 520 | 130 | 0 | 670 | 0 | NHPP |  | 20 | 1 | 10 | 10 | 10 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | SALINE | RT E N | KR0106 | 0.072 | 0.144 | 1 | N |  | Bridge rehabilitation over Salt Fork Creek 1.2 miles north of 170th Trail and 0.3 mile south of Mallard Trail. Project involves bridge R0545. | Federal | 1049 | 262 | 0 | 1346 | 0 | NHPP |  | 35 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | SALINE | RT O S | KR0188 | 11.298 | 22.596 | 0 | N |  | Pavement resurfacing from Rte. 41 to Rte. C in Slater. | Adv. CN | 1211 | 303 | 0 | 1539 | 0 | AC-STBG |  | 25 | 10 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | 5B0800R | 0 | 0 | 1 | N |  | Payback beginning in SFY 2008 for Safe and Sound bridges in rural Kansas City District. | Federal | 0 | 23130 | 0 | 111743 | 5,001 - 10,000 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 88463 | 4626 | 4626 | 4626 | 4626 | 4626
3 | VARIOUS | Various | KR0320 | 0 | 0 | 0 | N |  | Job Order Contracting for asphalt pavement repair in the rural Kansas City District. | Adv. CN | 492 | 123 | 0 | 625 | 0 | AC-STBG |  | 10 | 1 | 1 | 1 | 1 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KR0346 | 0 | 0 | 0 | N |  | Job Order Contracting for concrete pavement repair at various major route and interstate locations in the rural Kansas City District. | Adv. CN | 1863 | 466 | 0 | 2331 | 0 | AC-NHPP |  | 2 | 1 | 1 | 1 | 141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KR0348 | 0 | 0 | 0 | N |  | Job Order Contracting for concrete pavement repair at various major route and interstate locations in the rural Kansas City District. | Adv. CN | 1768 | 442 | 0 | 2217 | 0 | AC-NHPP |  | 7 | 5 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KR0349 | 0 | 0 | 0 | N |  | Job Order Contracting for guard cable and guardrail repair at various locations in the rural Kansas City District. | Adv. CN | 1769 | 442 | 0 | 2213 | 0 | AC-STBG |  | 2 | 10 | 141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KR0414 | 0 | 0 | 0 | N |  | On-call work zone enforcement at various locations in the rural Kansas City District. | Federal | 97 | 11 | 0 | 110 | 0 | SAFETY |  | 2 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KR0471 | 0 | 0 | 0 | N |  | On-call work zone enforcement at various locations in the rural Kansas City District. | Federal | 98 | 11 | 0 | 110 | 0 | SAFETY |  | 1 | 1 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KR0499 | 0 | 0 | 0 | N |  | Job Order Contracting for guard cable and guardrail repair at various locations in the rural Kansas City District. | Adv. CN | 1826 | 456 | 0 | 2282 | 0 | AC-STBG |  | 0 | 5 | 5 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KR0501 | 0 | 0 | 0 | N |  | On-call work zone enforcement at various locations in the rural Kansas City District. | Federal | 110 | 12 | 0 | 122 | 0 | SAFETY |  | 0 | 5 | 5 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KR0344 |  |  | 0 | N |  | Job Order Contracting for asphalt pavement repair in the rural Kansas City District. | Federal | 959 | 240 | 0 | 1201 | 0 | NHPP |  | 2 | 1 | 1 | 1 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KR0347 |  |  | 0 | N |  | Job Order Contracting for asphalt pavement repair in the rural Kansas City District. | Federal | 888 | 222 | 0 | 1117 | 0 | NHPP |  | 7 | 5 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CASS | MO 2 E | KU0299 | 0.046 | 0.092 | 0 | Y | 790160 | Culvert replacement over Muddy Creek. $204,090 Cost Share, $215,000 Harrisonville, and $861,000 STBG-Urban funds. | Federal | 1117 | 64 | 215 | 1436 | 0 | NHPP |  | 40 | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1280 | 0 | 0 | 0 | 0 | 0 | 1076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CASS | MO 291 S | KU0267 | 8.736 | 18.099 | 0 | Y | 790156 | Pavement resurfacing from Rte. 58 to Waters Road. | Federal | 8207 | 2052 | 0 | 10737 | 0 | NHPP |  | 478 | 753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CASS | IS 49 N | KU0028 | 3.388 | 16.12 | 2 | Y |  | Rebuild pavement, add lane, widen shoulders, and replace barriers from south of Rte. 58 in Belton to north of 155th Street and bridge rehabilitation at 163rd Street. Project involves bridges A7352 and A7353. | Federal | 71469 | 7941 | 0 | 82710 | 0 | NHPP | 4I3494 ST0091 | 3300 | 1750 | 6396 | 0 | 0 | 0 | 0 | 1362 | 0 | 0 | 0 | 0 | 0 | 0 | 69902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CASS | IS 49 S | KU0283 | 10.18 | 41.83 | 0 | Y |  | Pavement resurfacing from Rte. 7 in Harrisonville to 0.5 mile south of Rte. B in Archie. | Federal | 11262 | 1251 | 0 | 12678 | 0 | NHPP | KU0229 | 165 | 100 | 518 | 732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CASS | W OR 49 S | KU0229 | 1.17 | 2.34 | 0 | Y |  | Pavement improvements from 275th Street to 283rd Street in Harrisonville. | Federal | 0 | 1815 | 0 | 1911 | 0 | STATE | KU0283 | 96 | 50 | 31 | 199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CASS | RT A E | KU0149 | 0.201 | 0.402 | 1 | Y |  | Bridge replacement over I-49. Project involves bridge A3222. | Adv. CN | 4462 | 1115 | 0 | 5742 | 0 | AC-STBG |  | 165 | 15 | 100 | 200 | 640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4622 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CASS | RT B E | KU0148 | 0.123 | 0.246 | 0 | Y |  | Repair slides at South Grand River 0.4 mile east of I-49. | Federal | 331 | 37 | 0 | 386 | 0 | SAFETY |  | 18 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 342 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CASS | RT D S | KU0109 | 0.142 | 0.294 | 1 | Y |  | Bridge rehabilitation over Massey Creek 0.9 mile south of 231st Street and 1.1 miles north of Rte. Y. Project involves bridge A2251. | Federal | 966 | 241 | 0 | 1321 | 0 | NHPP |  | 114 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CASS | RT J N | KU0237 | 6.108 | 12.415 | 0 | Y |  | Add roundabouts at Hubach Hill Road and 203rd Street, add turn lanes at 195th Street and 211th Street, and pavement resurfacing from Rte. 58 to Rte. 49. $2,541,000 Open Container funds. | Federal | 10826 | 1203 | 0 | 13189 | 0 | SAFETY |  | 1160 | 1786 | 0 | 0 | 0 | 0 | 0 | 196 | 0 | 0 | 0 | 0 | 0 | 10047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CASS | RT K S | KU0277 | 6.541 | 13.08 | 0 | Y |  | Pavement resurfacing from Rte. P to Rte. 2 and Spur K from Ohio Street to Rte. K. | Adv. CN | 1397 | 349 | 0 | 1766 | 0 | AC-STBG |  | 20 | 12 | 20 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CLAY | US 169 N | KU0492 | 0.038 | 0.19 | 0 | Y |  | Payment to Smithville to upgrade pedestrian facilities, upgrade traffic signals, and improve the median at Richardson Street. $541,910 in Cost Share funds. | Federal | 0 | 550 | 0 | 550 | 0 | STATE |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CLAY | US 169 S | KU0490 | 0.059 | 0.145 | 1 | Y |  | Bridge rehabilitation over BNSF Railway 0.1 mile south of Rte. 9. Project involves bridge A4643. | Federal | 3509 | 877 | 0 | 4391 | 0 | NHPP |  | 5 | 5 | 5 | 10 | 150 | 289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CLAY | MO 210 E | KU0111 | 0.329 | 1.352 | 2 | Y |  | Bridge replacement over Rte. 269 0.8 mile east of Walker Road and 0.8 mile west of North Brighton Avenue. Project involves bridges A2175 and A2176. | Federal | 7956 | 1989 | 0 | 11293 | 0 | NHPP |  | 1348 | 500 | 500 | 637 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 8303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CLAY | MO 269 S | KU0425 | 0.51 | 2.036 | 1 | Y |  | Bridge rehabilitation over Missouri River. Project involves bridge A5817. | Federal | 7042 | 1761 | 0 | 8873 | 0 | NHPP |  | 70 | 200 | 200 | 814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7589 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CLAY | IS 29 S | 4I3458 | 1.043 | 6.498 | 6 | Y | 590295 | Bridge replacement over Guinotte Avenue, BNSF Railway, and Bedford Avenue and bridge rehabilitation over Missouri River and Front Street. Project involves bridges A7650, A7645, A7646, A7647, L0788, and L0789. | Federal | 235857 | 26206 | 0 | 274332 | 0 | NHFP |  | 12269 | 10500 | 19271 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 232291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CLAY | IS 29 S | KU0061 | 0.324 | 2.172 | 2 | Y |  | Bridge replacement over NE Parvin Road. Project involves bridges L0659 and L0660. | Federal | 14413 | 1601 | 0 | 17364 | 0 | NHFP | KU0025 ST0094 | 1350 | 300 | 890 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 14699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CLAY | MO 291 N | KU0205 | 1.379 | 7.021 | 0 | Y |  | Pavement resurfacing from Leonard Street to Orchard Avenue. | Federal | 1773 | 443 | 0 | 2248 | 0 | NHPP |  | 32 | 50 | 50 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1964 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CLAY | MO 291 S | KU0117 | 0.899 | 2.361 | 0 | Y |  | Upgrade signals at Flintlock Road and corridor improvement from north of 104th Street to west of Overton Avenue. $4,000,000 Community Funded Projects funds. | Federal | 10024 | 2506 | 0 | 12945 | 0 | NHPP |  | 415 | 500 | 897 | 0 | 0 | 0 | 0 | 326 | 0 | 0 | 0 | 0 | 0 | 0 | 10807 | 0 | 0 | 0 | 0 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CLAY | MO 33 S | 4S3507 | 0.061 | 0.152 | 0 | Y |  | Payment to Kearney to add turn lanes, pedestrian signals, traffic signals, sidewalks, and bike lanes at 19th Street. $1,224,582 Cost Share funds. | Adv. CN | 986 | 247 | 0 | 1260 | 0 | AC-STBG |  | 27 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CLAY | IS 35 S | KU0206 | 8.209 | 35.775 | 0 | Y |  | Pavement repair from south of Rte. PP in Haynesville to Fishing River. | Federal | 1494 | 166 | 0 | 1680 | 0 | NHPP |  | 20 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CLAY | IS 435 S | KU0146 | 0.005 | 0.015 | 0 | Y |  | Repair erosion in the median 0.4 mile north of I-35. | Federal | 257 | 29 | 0 | 304 | 0 | SAFETY |  | 18 | 3 | 3 | 15 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CLAY | US 69 N | 4S3482 | 0.895 | 4.082 | 0 | Y | 590277 | Payment to Kansas City to add shared use path, upgrade pedestrian facilities and upgrade drainage from Highland Avenue to Chouteau Trafficway. $2,745,217 Cost Share funds. | Federal | 2201 | 550 | 0 | 2759 | 0 | NHPP |  | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CLAY | US 69 N | KU0281 | 9.45 | 38.248 | 0 | Y |  | Pavement resurfacing from I-35 in Liberty to McCleary Road in Excelsior Springs. | Federal | 9712 | 2428 | 0 | 12148 | 0 | NHPP |  | 8 | 75 | 50 | 655 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CLAY | US 69 S | KU0055 | 0.31 | 0.62 | 0 | Y |  | Add roundabout at Rte. D in Lawson. | Federal | 4591 | 510 | 0 | 5156 | 0 | SAFETY |  | 55 | 655 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 4438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CLAY | MO 9 N | KU0504 | 0 | 4.836 | 0 | Y |  | Pavement resurfacing and replace guardrail on the northbound lane 10th Avenue to North Oak Trafficway. | Federal | 908 | 227 | 0 | 1135 | 0 | NHPP |  | 0 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CLAY | MO 92 E | KU0274 | 7.117 | 15.131 | 0 | Y |  | Pavement resurfacing from Rte. 33 to Rte. 69. | Federal | 2981 | 745 | 0 | 3743 | 0 | NHPP |  | 17 | 1 | 1 | 5 | 263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CLAY | CST BRYANT ST N | KU0123 | 0.031 | 0.062 | 1 | Y |  | Bridge rehabilitation over I-35 0.3 mile east of Poe Avenue and 0.5 mile west of I-435. Project involves bridge L0756. | Federal | 1042 | 260 | 0 | 1665 | 0 | NHPP |  | 363 | 147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CLAY | RT H E | KU0269 | 8.958 | 17.916 | 0 | Y |  | Pavement resurfacing from Liberty city limits to McKee Road. | Adv. CN | 1734 | 433 | 0 | 2187 | 0 | AC-STBG |  | 20 | 5 | 15 | 18 | 128 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 1998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | CLAY | RP IS29S TO IS35N N | KU0025 | 0 | 0.345 | 1 | Y |  | Bridge replacement over I-35 and I-29 0.2 mile south of Davidson Road and 0.5 mile west of Rte. 1. Project involves bridge A1763. | Federal | 17722 | 4430 | 0 | 23133 | 0 | NHPP | KU0061 ST0094 | 981 | 20 | 1401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | MO 12 E | KU0511 | 0.032 | 0.128 | 0 | Y |  | Erosion repair at North Union Street in Independence. | Federal | 390 | 97 | 0 | 487 | 0 | NHPP |  | 0 | 171 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | MO 150 E | KU0140 | 0.52 | 2.486 | 2 | Y |  | Bridge rehabilitation over Union Pacific Railroad and Blue River from Wyandotte Street to 0.8 mile east of Holmes Road. Project involves bridges A5495 and A5496. | Federal | 6131 | 1533 | 0 | 8370 | 0 | NHPP |  | 706 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | MO 150 E | KU0362 | 5.991 | 26.488 | 0 | Y |  | Roadway improvement from State Line Road to CPKC Railroad in Kansas City and on Rte. 78 from Swope Drive to Powahatan Court in Independence. | Federal | 4777 | 1194 | 0 | 5986 | 0 | NHPP |  | 15 | 10 | 10 | 386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | US 24 E | KU0204 | 6.209 | 26.804 | 0 | Y |  | Pavement resurfacing from I-435 to Rte. 291. | Federal | 2842 | 711 | 0 | 3570 | 0 | NHPP |  | 17 | 10 | 47 | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | US 24 E | KU0273 | 5.427 | 24.452 | 0 | Y |  | Pavement resurfacing from Rte. 291 to Rte. 7. | Federal | 4684 | 1171 | 0 | 5877 | 0 | NHPP |  | 22 | 15 | 15 | 10 | 348 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | IS 29 N | KU0426 | 0.302 | 2.172 | 1 | Y |  | Bridge rehabilitation over the Missouri River. Project involves bridge A7650. | Federal | 205 | 23 | 0 | 230 | 0 | NHPP |  | 2 | 1 | 3 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | MO 291 N | 4P3471 | 0.346 | 1.488 | 2 | Y | 690549 | Bridge replacement, bridge rehabilitation, and add pedestrian facilities over Missouri River. Design-Build project. Project involves bridges L0568 and A4757. $1,000 Transportation Alternatives and $1,000 Carbon Reduction Program funds. | Federal | 84193 | 21048 | 0 | 113843 | 0 | NHPP |  | 8402 | 8097 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 97144 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | MO 291 N | KU0272 | 4.79 | 17.448 | 0 | Y |  | Pavement resurfacing from I-470 to Rte. 50, SE Melody Lane north of SE 7th Terrace to SE 5th Terrace and at SE 5th Street, and NE Rice Road from south of NE Columbus Street to NE Deerbrook Street in Lees Summit. | Federal | 3734 | 933 | 0 | 4694 | 0 | NHPP |  | 27 | 25 | 35 | 10 | 285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | MO 291 S | KU0130 | 4.445 | 21.605 | 0 | Y |  | Signal and lighting upgrades from 32nd Street to Salisbury Road and turn lane extension at Hidden Valley Road and Gudgell Street in Independence. | Federal | 623 | 156 | 0 | 813 | 0 | NHPP |  | 34 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 716 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | IS 35 N | KU0263 | 0.179 | 1.068 | 1 | Y |  | Bridge rehabilitation over Southwest Boulevard. Project involves bridge A1701. | Federal | 1202 | 134 | 0 | 1366 | 0 | NHPP |  | 30 | 10 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | IS 35 S | KU0129 | 0.043 | 0.178 | 1 | Y |  | Bridge replacement over I-35 0.1 mile west of Pennsylvania Avenue to Summit Street. Project involves bridge A1122. | Federal | 6543 | 727 | 0 | 7720 | 0 | NHPP |  | 450 | 450 | 450 | 396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | US 40 E | KU0066 | 0.667 | 3.789 | 0 | Y |  | Corridor improvements and signal upgrades from Cliff Avenue to Little Blue Parkway. | Federal | 4040 | 1010 | 0 | 6183 | 0 | NHPP |  | 1113 | 800 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 4250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | US 40 E | KU0479 | 2.972 | 13.027 | 0 | Y |  | Multimodal safety and operational improvements from I-435 to Blue Ridge Boulevard. $2,633,000 Open Container funds. | Federal | 9735 | 1082 | 0 | 11317 | 0 | SAFETY |  | 500 | 1000 | 1150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | US 40 E | KU0497 | 0.042 | 0.126 | 0 | Y |  | Intersection improvements at NW Sni-A-Bar Boulevard. | Federal | 4403 | 489 | 0 | 4892 | 0 | SAFETY |  | 0 | 300 | 350 | 445 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 3787 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | IS 435 S | KU0282 | 8.204 | 58.056 | 0 | Y |  | Pavement resurfacing from 0.3 mile north of Raytown Road to 0.6 mile south of Rte. W. | Federal | 12575 | 1397 | 0 | 14052 | 0 | NHPP | KU0288 | 80 | 1052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | IS 435 S | KU0288 | 1.315 | 9.447 | 0 | Y |  | Pavement resurfacing from Rte. 78 to Rte. 40. | Federal | 2528 | 281 | 0 | 2841 | 0 | NHPP | KU0282 | 32 | 429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | IS 470 W | KU0286 | 13.105 | 66.777 | 0 | Y |  | Pavement resurfacing from 0.2 mile south of 39th Street to 0.2 west of Raytown Road. | Federal | 18944 | 2105 | 0 | 21057 | 0 | NHPP |  | 8 | 1647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | IS 49 S | 4I3494 | 0.619 | 0.121 | 2 | Y | 690552 | Bridge replacement and add auxiliary lanes over Little Blue River 0.6 mile north of 155th Street and 0.6 mile south of Rte. 150. Project involves bridges A0478 and L0530. | Federal | 22028 | 2448 | 0 | 26451 | 0 | NHPP | KU0028 ST0091 | 1975 | 750 | 2185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | US 50 E | KU0171 | 6.08 | 26.487 | 0 | Y |  | Rebuild pavement from 0.8 mile southeast of E. 87th Street to Rte. RA. | Federal | 20217 | 5054 | 0 | 25336 | 0 | NHPP |  | 65 | 1000 | 1000 | 550 | 200 | 1341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | US 50 E | KU0200 | 9.94 | 41.348 | 0 | Y |  | Corridor improvements from Rte. 7 in Lake Lotawana to east of Rte. AA. $2,898,000 Open Container funds. | Federal | 11220 | 1247 | 0 | 12736 | 0 | SAFETY |  | 269 | 360 | 5 | 740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | US 50 E | KU0200B | 9.94 | 41.348 | 0 | Y |  | Corridor improvement on Rte. 50 proposed Outer Road extension between Rte. 7 and Rte. AA. $2,898,000 Open Container funds. | Federal | 10586 | 1176 | 0 | 11762 | 0 | SAFETY |  | 0 | 150 | 150 | 150 | 770 | 0 | 0 | 0 | 0 | 572 | 0 | 0 | 0 | 0 | 0 | 0 | 9970 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | US 50 E | KU0278 | 12.851 | 55.17 | 0 | Y |  | Pavement resurfacing from 0.2 mile west of Rte. RA to 0.3 mile east of Sam Moore Road. | Federal | 10826 | 2707 | 0 | 13553 | 0 | NHPP |  | 20 | 1103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12430 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | MO 7 S | 4S3298B | 0.585 | 3.025 | 0 | Y |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan from Pink Hill Road to 0.1 mile south of Roanoke Drive. | Adv. CN | 354 | 88 | 0 | 495 | 0 | AC-STBG |  | 53 | 38 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | IS 70 E | 4I3211 | 0.1 | 0.6 | 1 | Y | 690499 | Bridge improvements at Union Pacific Railroad over I-70. Project involves bridge L0975. | Federal | 18098 | 2011 | 0 | 21114 | 0 | NHPP |  | 1005 | 750 | 750 | 500 | 1194 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16915 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | IS 70 E | 4I3459 | 0.851 | 4.852 | 2 | Y |  | Bridge rehabilitation over Liberty Street and Mulberry Street from Kansas State line to 0.2 mile west of Broadway Street. Project involves bridges A0507 and A5658. | Federal | 20848 | 2316 | 0 | 23199 | 0 | NHPP |  | 35 | 5 | 5 | 5 | 1838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21311 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | IS 70 E | 4P3323B | 3.921 | 27.141 | 0 | Y | 690591 | Replace median barrier from Manchester Trafficway to Crysler Street. | Federal | 3551 | 394 | 0 | 4214 | 0 | SAFETY |  | 269 | 380 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | IS 70 E | KU0114 | 0.683 | 4.572 | 4 | Y |  | Bridge replacement over Rte. 40 0.1 mile west of Blue Ridge Boulevard and bridge replacement over Sterling Avenue 0.7 mile east of Pittman Road. Potential Design-Build. Project involves twin bridges L0972 and L0973. | Federal | 39443 | 4383 | 0 | 44951 | 0 | NHPP |  | 1125 | 2300 | 3901 | 2291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | IS 70 E | KU0156 | 0.031 | 0.155 | 2 | Y |  | Bridge replacement over 12th Street. Project involves bridges A0244 and A0245. | Federal | 11755 | 1306 | 0 | 14541 | 0 | NHPP | KU0016 | 1480 | 888 | 5 | 744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | IS 70 E | KU0291 | 7.225 | 44.77 | 0 | Y |  | Pavement resurfacing from Kansas State line to 0.2 mile east of Rte. 40. | Federal | 12493 | 1388 | 0 | 14021 | 0 | NHPP |  | 140 | 1008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | IS 70 E | KU0503 | 0.756 | 3.363 | 0 | Y |  | Corridor improvements for eastbound I-70 from Blue Ridge Cutoff to Pittman Road. | Federal | 49821 | 5536 | 0 | 55357 | 0 | NHPP |  | 0 | 25 | 25 | 3365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | IS 70 W | KU0016 | 0.234 | 1.229 | 2 | Y |  | Bridge replacement over 11th Street from south of 9th Street to 12th Street. Project involves bridges A0243. | Federal | 10772 | 1197 | 0 | 13550 | 0 | NHPP | KU0156 | 1581 | 1116 | 5 | 647 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | IS 70 W | KU0284 | 7.87 | 51.432 | 0 | Y |  | Pavement resurfacing from Manchester Trafficway to I-470. | Federal | 14132 | 1570 | 0 | 15767 | 0 | NHPP |  | 65 | 5 | 5 | 5 | 1158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | IS 70 W | KU0486 | 0.27 | 2.244 | 2 | Y |  | Bridge rehabilitation over Union Pacific Railroad at Manchester Trafficway. Project involves bridges A8256 and A8257. | Federal | 2966 | 330 | 0 | 3301 | 0 | NHPP | KU0485 | 5 | 5 | 5 | 5 | 5 | 193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | US 71 N | 4S3415 | 0 | 0.254 | 1 | Y |  | Bridge rehabilitation over 12th Street 0.1 mile south of 10th Street and 0.1 mile north of 13th Street. Project involves bridge A0246. | Federal | 1278 | 320 | 0 | 2083 | 0 | NHPP |  | 485 | 333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | US 71 N | KU0460 | 0.198 | 1.188 | 2 | Y |  | Bridge rehabilitation over Brush Creek. Project involves bridges A4997 and A4998. | Federal | 1353 | 338 | 0 | 1696 | 0 | NHPP |  | 5 | 5 | 5 | 5 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | US 71 N | KU0461 | 0.205 | 0.675 | 2 | Y |  | Bridge rehabilitation over Rte. 71. Project involves bridges A5162 and A5163. | Federal | 1059 | 265 | 0 | 1329 | 0 | NHPP |  | 5 | 5 | 5 | 5 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | US 71 S | KU0321 | 0.56 | 3.652 | 29 | Y |  | Bridge deck sealing in Jackson and Clay Counties. Involves bridges A0053, A1346, A2149, A2443, A2444, A2733, A2745, A4736, A4737, A4739, A4740, A4993, A4994, A5161, A5162, A5164, A5165, A5167, A5169, A7503, A7504, A7647, A7652, A7653, A7654, L0781, L0792, L0981, L0983. | Adv. CN | 527 | 132 | 0 | 669 | 0 | AC-STBG |  | 10 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | MO 9 N | KU0270 | 0.718 | 3.426 | 3 | Y |  | Bridge rehabilitation over Missouri River, 1st Street, and CPKC and Union Pacific Railroad. Project involves bridges A4060, A4059, and A4134. | Federal | 57168 | 14292 | 0 | 72466 | 0 | NHPP |  | 1006 | 1200 | 1200 | 1200 | 1300 | 4956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61604 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | CST EASTWOOD TRFY E | KU0145 | 0.038 | 0.14 | 0 | Y |  | Repair slides on northbound I-435 ramp. | Federal | 540 | 60 | 0 | 608 | 0 | SAFETY |  | 8 | 1 | 1 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | RP IS435N TO US71N N | KU0355 | 0.253 | 2.355 | 0 | Y | 490145 | High friction surface treatment on northbound lanes at Rte. 350, southbound ramp from to Rte. 350 eastbound, and northbound ramp to Rte. 71 northbound. | Federal | 514 | 57 | 0 | 577 | 0 | SAFETY |  | 6 | 2 | 2 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | RP IS470W TO PRYOR RD S | KU0485 | 0.436 | 0.872 | 2 | Y |  | Bridge rehabilitation over Rte. 350 west of Northwest Blue Parkway. Projects involves bridges A7486 and A7487. | Federal | 895 | 224 | 0 | 1124 | 0 | NHPP | KU0486 | 5 | 5 | 5 | 5 | 5 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1031 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | RP STADIUM DR TO IS435S S | 4I3501 | 0.192 | 0.454 | 4 | Y | 690579 | Bridge replacement over Raytown Road and Rock Island Trail 0.5 mile south of I-70. Project involves bridges A2843, A2844, A2852, and A2853. | Federal | 5154 | 1288 | 0 | 7208 | 0 | NHPP |  | 766 | 816 | 370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | JACKSON | RT W E | KU0264 | 4.286 | 21.249 | 0 | Y |  | Rebuild pavement from State Line Road to Holmes Road and pavement resurfacing from Holmes Road to I-435. | Federal | 13946 | 3487 | 0 | 17523 | 0 | NHPP |  | 90 | 1462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15971 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PLATTE | IS 29 S | KU0128 | 0.92 | 3.95 | 1 | Y |  | Add roundabout at interchange and relocate southbound ramp at Rte. HH. Project involves bridge A7784. | Adv. CN | 3770 | 943 | 0 | 5668 | 0 | AC-STBG |  | 950 | 722 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 3991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PLATTE | MO 45 N | KU0446 | 0.067 | 0.134 | 0 | Y |  | Permanent erosion control improvement 0.5 mile east of Rte. P in Weston. | Federal | 364 | 91 | 0 | 465 | 0 | PROTECT |  | 10 | 10 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PLATTE | IS 635 S | KU0488 | 1.39 | 6.128 | 0 | Y |  | Add interchange lighting at Rte. 9 in Riverside. Design, right of way acquisition, and utility relocation by Riverside. $669,422 Cost Share and $528,250 Riverside funds. | Federal | 787 | 0 | 528 | 1319 | 0 | SAFETY |  | 4 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1197 | 0 | 0 | 0 | 0 | 0 | 528 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PLATTE | US 69 N | KU0427 | 0.403 | 1.505 | 1 | Y |  | Bridge rehabilitation over Missouri River. Project involves bridge A8340. | Federal | 2083 | 521 | 0 | 2624 | 0 | NHPP |  | 20 | 100 | 269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PLATTE | MO 92 E | KU0056 | 14.459 | 35.369 | 0 | Y |  | Pavement resurfacing from First Street in Tracy to west of Rte. DD near Smithville. | Federal | 6701 | 1675 | 0 | 8426 | 0 | NHPP |  | 50 | 643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PLATTE | MO 92 E | KU0303 | 1.238 | 3.593 | 0 | Y |  | Payment to Platte City for roadway realignment and add bicycle and pedestrian facilities. $6,667,950 Governor's Cost Share Program funds. | Federal | 0 | 6670 | 0 | 6672 | 0 | STATE |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6668 | 0 | 0 | 0 | 0 | 0 | 6668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PLATTE | MO 92 E | KU0373 | 0.247 | 0.494 | 1 | Y |  | Payment to KDOT for bridge replacement of Centennial Bridge over Missouri River at Leavenworth. Project involves bridge K0941. | Federal | 48867 | 12217 | 0 | 61087 | 0 | NHPP |  | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PLATTE | MO 92 E | KU0374 | 0.687 | 1.371 | 1 | Y |  | Payment to KDOT for roadway widening at Centennial Bridge over the Missouri River. Project involves bridge K0941. | Federal | 9219 | 2305 | 0 | 11527 | 0 | NHPP |  | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11521 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PLATTE | MO 92 E | KU0448 | 0.21 | 0.42 | 1 | Y |  | Right of way acquisition for roadway widening at Centennial Bridge over the Missouri River. | Federal | 0 | 16 | 0 | 22 | 0 | STATE |  | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PLATTE | RT D W | KU0172 | 0.396 | 2.824 | 0 | Y |  | Rebuild pavement from NW Ambassador to NW Prairie View Road and on NW Prairie View Road from North Congress Avenue to south of North Donovan Drive. | Adv. CN | 1506 | 376 | 0 | 1982 | 0 | AC-STBG |  | 100 | 75 | 50 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PLATTE | RT KK E | KU0271 | 4.362 | 8.732 | 0 | Y |  | Pavement resurfacing from Rte. B to Rte. 169. | Adv. CN | 810 | 202 | 0 | 1032 | 0 | AC-STBG |  | 20 | 8 | 5 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PLATTE | CRD OLD PIKE RD E | KU0053 | 0.21 | 0.42 | 1 | Y |  | Bridge replacement over I-29 on Old Pike Road. Project involves bridge A0105. | Adv. CN | 3074 | 769 | 0 | 4471 | 0 | AC-STBG |  | 628 | 570 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 3264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | PLATTE | CST RIVERWAY BLVD N | KU0487 | 0.61 | 0.967 | 0 | Y |  | Payment to Riverside to add roundabouts, modify interchange ramps and extend sidewalks and streets at Riverway Boulevard. $1,500,000 in Cost Share funds. | Adv. CN | 1205 | 301 | 0 | 1516 | 0 | AC-STBG |  | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | RAY | BU 10 E | KU0507 | 5.41 | 10.82 | 0 | Y |  | Pavement resurfacing from Rte. 10 west junction to Rte. 10 east junction. | Adv. CN | 1368 | 342 | 0 | 1710 | 0 | AC-STBG |  | 0 | 10 | 22 | 10 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | RAY | MO 13 N | KU0464 | 0.128 | 0.624 | 0 | Y |  | Upgrade signals at Main Street, South Street, and Walmart Avenue in Richmond. | Federal | 1236 | 137 | 0 | 1413 | 0 | SAFETY |  | 40 | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | RAY | MO 13 S | KU0491 | 0.414 | 1.658 | 1 | Y |  | Bridge rehabilitation over Missouri River. Project involves bridge A5664. | Federal | 21935 | 5484 | 0 | 27424 | 0 | NHPP |  | 5 | 5 | 5 | 5 | 100 | 1663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | RAY | MO 210 W | KU0508 | 8.701 | 17.562 | 0 | Y |  | Pavement resurfacing from west of Rte. 10 to 0.2 mile east of Egypt Road. | Adv. CN | 3906 | 976 | 0 | 4882 | 0 | AC-STBG |  | 0 | 37 | 15 | 20 | 303 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4507 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | RAY | RT A S | KU0480 | 19.109 | 38.218 | 0 | Y |  | Pavement resurfacing and repair from Sader Drive to Rte. 10. | Federal | 3213 | 803 | 0 | 4026 | 0 | NHPP |  | 10 | 10 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3746 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | RAY | RT KK S | KU0506 | 2.181 | 4.362 | 0 | Y |  | Pavement resurfacing from Hunter Lane to Rte. D. | Adv. CN | 327 | 82 | 0 | 409 | 0 | AC-STBG |  | 0 | 16 | 2 | 3 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 364 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | VARIOUS | KU0457 |  |  | 0 | Y |  | Emergency response operations and staffing in the urban Kansas City District. | Federal | 0 | 2134 | 0 | 2135 | 0 | STATE |  | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2131 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | 5B0800S | 0 | 0 | 1 | Y | 990107 | Payback beginning in SFY 2008 for Safe and Sound bridges in urban Kansas City District. | Federal | 0 | 25030 | 0 | 87426 | 10,001 - 15,000 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 62335 | 5006 | 5006 | 5006 | 5006 | 5006
3 | VARIOUS | Various | KU0037 | 0 | 0 | 0 | Y |  | Upgrade signage at various locations in the urban Kansas City District. | Federal | 1418 | 355 | 0 | 1930 | 0 | NHPP |  | 157 | 243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0306 | 0 | 0 | 0 | Y | 990283 | Fence repairs at various locations in the urban Kansas City District. | Federal | 0 | 459 | 0 | 461 | 0 | STATE |  | 2 | 1 | 1 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0334 |  |  | 1 | Y |  | Bridge deck sealing at various locations in the urban Kansas City District. | Federal | 552 | 138 | 0 | 705 | 0 | NHPP |  | 15 | 5 | 5 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0335 |  |  | 0 | Y |  | Job Order Contracting for concrete pavement repair at various locations in the urban Kansas City District. | Federal | 4671 | 1168 | 0 | 5874 | 0 | NHPP |  | 35 | 5 | 5 | 5 | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0336 |  |  | 1 | Y |  | Job Order Contracting for bridge repairs at various locations in the urban Kansas City District. | Federal | 2726 | 682 | 0 | 3423 | 0 | NHPP |  | 15 | 5 | 5 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0338 |  |  | 0 | Y |  | Fence repairs at various primary route locations in the urban Kansas City District. | Federal | 0 | 433 | 0 | 443 | 0 | STATE |  | 10 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0339 |  |  | 0 | Y |  | Job Order Contracting for asphalt pavement repair at various locations in the urban Kansas City District. | Federal | 3725 | 931 | 0 | 4666 | 0 | NHPP |  | 10 | 1 | 1 | 1 | 282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0341 |  |  | 0 | Y |  | On-call work zone enforcement at various locations in the urban Kansas City District. | Federal | 246 | 27 | 0 | 283 | 0 | SAFETY |  | 10 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0342 |  |  | 0 | Y |  | Job Order Contracting for guard cable and guardrail repair at various locations in the urban Kansas City District. | Federal | 5392 | 1348 | 0 | 6750 | 0 | NHPP |  | 10 | 446 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0343 |  |  | 0 | Y |  | Job Order Contracting for lighting repair at various locations in the urban Kansas City District. | Federal | 0 | 2650 | 0 | 2665 | 0 | STATE |  | 15 | 5 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2472 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0381 |  |  | 1 | Y |  | Bridge improvements at various locations in the urban Kansas City District. | Federal | 4002 | 1000 | 0 | 5012 | 0 | NHPP |  | 10 | 5 | 10 | 50 | 150 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4592 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0408 |  |  | 0 | Y |  | ITS operations, staffing, and equipment for the Kansas City Scout ITS at the Transportation Management Center building in the urban Kansas City District. $2,845,805 KDOT funds. | Federal | 0 | 3195 | 2846 | 6041 | 0 | STATE |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6040 | 0 | 0 | 0 | 0 | 0 | 2846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0409 |  |  | 0 | Y |  | Emergency response operations and staffing in the urban Kansas City District. | Federal | 0 | 1996 | 0 | 1996 | 0 | STATE |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0423 |  |  | 0 | Y |  | Job Order Contracting for signage replacement at various locations in the urban Kansas City District. | Adv. CN | 860 | 215 | 0 | 1085 | 0 | AC-STBG |  | 10 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0456 |  |  | 0 | Y |  | ITS operations, staffing, and equipment for the Kansas City Scout Traffic Management Center building in the urban Kansas City District. $2,878,627 KDOT funds. | Federal | 0 | 3320 | 2879 | 6200 | 0 | STATE |  | 1 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6196 | 0 | 0 | 0 | 0 | 0 | 2879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0462 |  |  | 0 | Y |  | Scout intelligent transportation system device replacements and other ITS needs in the urban Kansas City District. | Federal | 0 | 2200 | 0 | 2205 | 0 | STATE |  | 5 | 80 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1928 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0466 | 0 | 0 | 1 | Y | 990270 | Job Order Contracting for bridge repairs at various locations in the urban Kansas City District. | Adv. CN | 2572 | 643 | 0 | 3220 | 0 | AC-STBG |  | 5 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0467 |  |  | 0 | Y |  | Job Order Contracting for signage replacement at various locations in the urban Kansas City District. | Adv. CN | 2648 | 662 | 0 | 3315 | 0 | AC-STBG |  | 5 | 5 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0468 |  |  | 0 | Y |  | Job Order Contracting for asphalt pavement repair at various locations in the urban Kansas City District. | Federal | 3528 | 882 | 0 | 4415 | 0 | NHPP |  | 5 | 5 | 285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0469 |  |  | 0 | Y |  | Job Order Contracting for concrete pavement repair at various locations in the urban Kansas City District. | Federal | 4428 | 1107 | 0 | 5545 | 0 | NHPP |  | 10 | 10 | 375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0470 |  |  | 0 | Y |  | Fence repairs at various primary route locations in the urban Kansas City District. | Federal | 0 | 450 | 0 | 455 | 0 | STATE |  | 5 | 5 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0472 |  |  | 0 | Y |  | On-call work zone enforcement at various locations in the urban Kansas City District. | Federal | 250 | 28 | 0 | 283 | 0 | SAFETY |  | 5 | 5 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0489 |  |  | 0 | Y |  | Job order contracting for median barrier repairs at various locations in the urban Kansas City District. | Federal | 242 | 60 | 0 | 303 | 0 | NHPP |  | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0493 |  |  | 0 | Y |  | Emergency response operations and staffing in the urban Kansas City District. | Federal | 1738 | 435 | 0 | 2173 | 0 | NHPP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0494 |  |  | 0 | Y |  | ITS operations, staffing, and equipment for the Kansas City Scout Traffic Management Center building in the urban Kansas City District. This payment project includes $2,980,000 in KDOT funds. | Federal | 3339 | 0 | 2980 | 6319 | 0 | NHPP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6319 | 0 | 0 | 0 | 0 | 0 | 2980 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0498 |  |  | 0 | Y |  | Job Order Contracting for guard cable and guardrail repair at various locations in the urban Kansas City District. | Federal | 5710 | 1428 | 0 | 7138 | 0 | NHPP |  | 0 | 5 | 5 | 451 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | VARIOUS | Various | KU0500 |  |  | 0 | Y |  | On-call work zone enforcement at various locations in the urban Kansas City District. | Federal | 255 | 28 | 0 | 283 | 0 | SAFETY |  | 0 | 5 | 5 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | MO 124 E | CD0311 | 8.315 | 16.63 | 0 | N |  | Pavement improvement from Rte. B in Hallsville to Rte. 22 in Centralia. | Adv. CN | 1933 | 483 | 0 | 2417 | 0 | AC-STBG |  | 1 | 1 | 1 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | MO 163 N | CD0333 | 0 | 1.15 | 1 | Y | 2026-3 | Bridge rehabilitation over Hinkson Creek. Project involves bridge A1899. | Federal | 2120 | 530 | 0 | 2702 | 0 | NHPP |  | 52 | 446 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 2199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | MO 163 S | CD0190 | 6.173 | 12.346 | 0 | Y | 2025-2 | Pavement resurfacing from Rte. K to Rte. 63 outer road. | Adv. CN | 736 | 184 | 0 | 922 | 0 | AC-STBG |  | 2 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | E OR 63 S | CD0166 | 0.02 | 0.04 | 1 | N |  | Bridge improvement over Bass Creek. Project involves bridge G0742. | Adv. CN | 855 | 214 | 0 | 1072 | 0 | AC-STBG |  | 3 | 40 | 191 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | US 63 S | CD0204 | 0.621 | 2.486 | 0 | N |  | Modify intersection configuration at Rte. CC. | Federal | 2318 | 579 | 0 | 3114 | 0 | NHPP |  | 207 | 362 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 2535 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | US 63 S | CD0286 | 0.059 | 0.118 | 1 | Y | 2026-8 | Bridge improvement over Rocky Fork Creek. Project involves bridge A0661. | Federal | 569 | 142 | 0 | 712 | 0 | NHPP |  | 1 | 1 | 5 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | US 63 S | CD0301 | 2.249 | 8.99 | 0 | N |  | Modify intersection configuration at Rte. 124. $404,000 Open Container funds. | Federal | 5953 | 661 | 0 | 6633 | 0 | SAFETY |  | 19 | 200 | 861 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 5543 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | US 63 S | CD0310 | 18.889 | 77.47 | 0 | Y | 2027-1 | Pavement resurfacing from Randolph County line to Rte. B. | Adv. CN | 8725 | 2181 | 0 | 10907 | 0 | AC-STBG |  | 1 | 30 | 564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | LP 70 E | CD0124 | 2.458 | 10.569 | 0 | Y | 2023-23 | Upgrade pedestrian facilities to comply with the ADA Transition Plan from I-70 Drive to Range Line Street in Columbia. | Federal | 453 | 113 | 0 | 733 | 0 | STBG |  | 72 | 61 | 0 | 0 | 0 | 0 | 95 | 0 | 0 | 0 | 0 | 0 | 0 | 505 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | S OR 70 E | CD0194 | 2.28 | 4.55 | 0 | Y | 2025-5 | Pavement improvement from Rte. 63 Connector to St. Charles Road. | Adv. CN | 635 | 159 | 0 | 797 | 0 | AC-STBG |  | 3 | 1 | 1 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | S OR 70 E | CD0202 | 0.015 | 0.03 | 1 | Y | 2025-6 | Bridge improvement over Hominy Creek and Trail. Project involves bridge H0196. | Adv. CN | 2036 | 509 | 0 | 2547 | 0 | AC-STBG |  | 2 | 10 | 75 | 462 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 1983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | MO 740 E | CD0232 | 0.231 | 1.055 | 1 | Y | 2027-0 | Bridge improvement over Hinkson Creek. Project involves bridges A1256. | Federal | 2528 | 632 | 0 | 3161 | 0 | NHPP |  | 1 | 1 | 1 | 1 | 539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | MO 740 E | CD0368 | 7.879 | 36.179 | 0 | Y | 2027-3 | Pavement improvement from I-70 to east of Rte. 63. Includes Rte. E from north of Blackfoot Road to I-70 and Rte. TT from Fairview Road to Rte. 740. | Adv. CN | 5934 | 1483 | 0 | 7417 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | MO 763 S | CD0390 | 2.03 | 8.606 | 0 | Y | 2027-4 | Pavement improvement from Loop 70 to Rte. 740. | Adv. CN | 789 | 197 | 0 | 986 | 0 | AC-STBG |  | 0 | 1 | 1 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 933 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | MO 763 S | CD0395 | 6.267 | 13.967 | 0 | Y | 2027-5 | Upgrade pedestrian facilities at various locations in Columbia, Lebanon, and Bennett Springs. | Adv. CN | 114 | 28 | 0 | 142 | 0 | AC-STBG |  | 0 | 2 | 4 | 26 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | RT B S | CD0226 | 0.105 | 0.466 | 0 | Y | 2025-8 | Modify intersection configuration at East Brown Station Road. Includes Rte. 763 at University Avenue and Rollins Street. | Federal | 1443 | 160 | 0 | 1623 | 0 | SAFETY |  | 20 | 507 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 1081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | RT B S | CD0330 | 12.155 | 32.648 | 0 | Y | 2027-6 | Pavement improvements from Rte. 124 to Loop 70. | Adv. CN | 6277 | 1569 | 0 | 7847 | 0 | AC-STBG |  | 1 | 1 | 1 | 413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7431 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | RT F S | CD0325 | 13.148 | 26.296 | 0 | N |  | Pavement improvement from west of Rte. 63 to Rte. 124. | Adv. CN | 450 | 113 | 0 | 564 | 0 | AC-STBG |  | 1 | 1 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | RT H E | CD0328 | 8.154 | 16.298 | 0 | N |  | Pavement improvement from Rte. 63 to end of state maintenance and Rte. AB from Rte. 63 to end of state maintenance. | Adv. CN | 324 | 81 | 0 | 406 | 0 | AC-STBG |  | 1 | 1 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | RT M E | CD0191 | 6.538 | 13.076 | 0 | N |  | Pavement resurfacing from end of state maintenance to Rte. DD. | Adv. CN | 530 | 132 | 0 | 664 | 0 | AC-STBG | CD0198 | 2 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | CST MEXICO GRAVEL RD E | CD0287 | 0.038 | 0.076 | 1 | Y | 2026-1 | Bridge improvement over Rte. 63. Project involves bridge A4088. | Federal | 623 | 156 | 0 | 780 | 0 | NHPP |  | 1 | 1 | 5 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | RT MM E | CD0198 | 7.332 | 14.664 | 0 | N |  | Pavement resurfacing from end of state maintenance to Rte. M. Includes Rte. DD from Minor Hill Road to Rte. M. | Adv. CN | 584 | 146 | 0 | 732 | 0 | AC-STBG | CD0191 | 2 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | BOONE | CRD PRATHERSVILLE RD E | CD0288 | 0.129 | 0.258 | 2 | Y | 2026-2 | Bridge improvement over Rte. 63. Project involves bridges A4032 and A4031. | Federal | 1333 | 333 | 0 | 1667 | 0 | NHPP |  | 1 | 1 | 5 | 219 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CALLAWAY | BU 54 E | CD0324 | 4.206 | 9.867 | 0 | N |  | Pavement improvement from Rte. H to just west of roundabout and from north of 13th Street to Rte. 54. | Federal | 1574 | 394 | 0 | 1969 | 0 | NHPP |  | 1 | 1 | 12 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CALLAWAY | US 54 E | CD0276 | 0.045 | 0.19 | 2 | N |  | Bridge improvement over Rte. J. Project involves bridges A3449 and A3450. | Federal | 850 | 213 | 0 | 1064 | 0 | NHPP |  | 1 | 1 | 1 | 20 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CALLAWAY | MO 94 E | CD0294 | 33.52 | 67.04 | 0 | Y |  | Pavement resurfacing from Rte. 63/54 interchange to east of Bluffton. | Adv. CN | 3214 | 804 | 0 | 4043 | 0 | AC-STBG |  | 25 | 202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3816 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CALLAWAY | RT B E | CD0277 | 0.12 | 0.24 | 1 | N |  | Bridge improvement over Rte. 54. Project involves bridge A4777. | Federal | 691 | 173 | 0 | 865 | 0 | NHPP |  | 1 | 1 | 1 | 20 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CALLAWAY | RT C S | CD0250 | 27.857 | 56.047 | 0 | Y |  | Pavement improvement from end of state maintenance to Rte. 94, and Rte. AE from Rte. J to Rte. 54, Rte. OO from end of state maintenance to Rte. AA, and Rte. AA from west of Mortin Drive to Rte. 94. | Adv. CN | 2571 | 643 | 0 | 3215 | 0 | AC-STBG |  | 1 | 1 | 1 | 1 | 1 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3054 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CALLAWAY | RT CC S | CD0313 | 9.62 | 19.24 | 0 | N |  | Pavement improvement from Rte. O to Rte. 94. Includes Rte. AD from Rte. C to end of state maintenance. | Adv. CN | 276 | 69 | 0 | 345 | 0 | AC-STBG | CD0182 | 0 | 2 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CALLAWAY | RT D S | CD0182 | 18.481 | 36.962 | 0 | N |  | Pavement preservation treatment from I-70 to Rte. 94. | Adv. CN | 616 | 154 | 0 | 773 | 0 | AC-STBG | CD0313 | 3 | 3 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 730 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CALLAWAY | RT F E | CD0246 | 0.093 | 0.186 | 1 | N |  | Bridge rehabilitation over Rte. 54. Project involves bridge A2296. | Federal | 2878 | 719 | 0 | 3604 | 0 | NHPP |  | 7 | 741 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CALLAWAY | RT N S | CD0298 | 0.04 | 0.08 | 1 | N |  | Bridge improvement over Loutre River. Project involves bridge X0759. | Federal | 685 | 171 | 0 | 858 | 0 | NHPP |  | 2 | 18 | 134 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CALLAWAY | CRD S SUMMIT DR S | CD0072 | 0.051 | 0.102 | 1 | Y | 2023-01 | Bridge rehabilitation over Rte. 54. Project involves bridge A3521. | Federal | 734 | 183 | 0 | 948 | 0 | NHPP |  | 31 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CALLAWAY | RT TT E | CD0347 | 6.947 | 13.894 | 0 | Y |  | Pavement improvement from Rte. 54 to end of state maintenance, Karen Street from Rte. AA to end of state maintenance, and Platinum Road from end of state maintenance to Rte. AA. | Adv. CN | 204 | 51 | 0 | 255 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CAMDEN | MO 5 S | CD0213 | 19.473 | 52.488 | 0 | N |  | Pavement improvement from Niangua River to south of Laclede County line, including ramps. Includes Rte. 7 from Rte. 5 to Old Rte. 5. | Federal | 4666 | 1167 | 0 | 5864 | 0 | NHPP |  | 31 | 35 | 254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CAMDEN | MO 5 S | CD0256 | 1.225 | 2.45 | 2 | N |  | Bridge improvement over Osage Arm and Niangua Arm of the Lake of the Ozarks. Project involves bridges A7875 and A5998. | Federal | 2910 | 727 | 0 | 3638 | 0 | NHPP | CD0257 | 1 | 1 | 42 | 442 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CAMDEN | US 54 E | CD0181 | 16.326 | 44.051 | 0 | N |  | Pavement resurfacing from east of Little Niangua River near the Hickory County line to west of Niangua River near Camdenton. | Federal | 4764 | 1191 | 0 | 6010 | 0 | NHPP |  | 55 | 282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CAMDEN | US 54 E | CD0211 | 0.234 | 0.651 | 1 | N |  | Bridge improvement over Macks Creek. Project involves bridge A1320. | Federal | 1522 | 380 | 0 | 1904 | 0 | NHPP |  | 2 | 66 | 277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CAMDEN | US 54 E | CD0295 | 7.003 | 25.167 | 0 | N |  | Pavement improvement from Grand Glaize bridge to east of Osage Beach Parkway and Rte. 42 from west of Rte. 54 to east of School of the Osage. Includes several ramps. | Federal | 4814 | 1203 | 0 | 6018 | 0 | NHPP |  | 1 | 9 | 56 | 253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CAMDEN | US 54 E | CD0403 | 117.665 | 476.962 | 0 | Y |  | Signage improvements from Hickory County line to Audrain County line. | Federal | 1707 | 427 | 0 | 2134 | 0 | NHPP |  | 0 | 1 | 1 | 1 | 208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CAMDEN | MO 7 S | CD0260 | 0.088 | 0.176 | 3 | N |  | Bridge painting over Sellars Creek and Murphy Creek. Includes Rte. W in Morgan County over Indian Creek. Project involves bridges A1236, A1237, and R0605. | Federal | 326 | 82 | 0 | 409 | 0 | NHPP |  | 1 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CAMDEN | MO 7 S | CD0278 | 0.848 | 1.696 | 4 | N |  | Bridge improvement over Dry Auglaize Creek and on Rte. N in Camden County over Unknown Creek, and Rte. ZZ in Laclede County over Panther Creek. Project involves bridges A4479, N0878, R0007, and N0950. | Federal | 580 | 145 | 0 | 726 | 0 | NHPP |  | 1 | 1 | 1 | 28 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CAMDEN | RT BB S | CD0320 | 21.077 | 42.154 | 0 | N |  | Pavement improvement from Rte. 7 to Rte. F and Rte. V from Rte. 54 to Rte. 7. | Adv. CN | 614 | 154 | 0 | 769 | 0 | AC-STBG |  | 1 | 1 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CAMDEN | RT MM E | CD0178 | 20.881 | 41.767 | 0 | N |  | Pavement resurfacing from Rte. TT to Lake of Ozarks, Rte. TT from Rte. F to end of state maintenance, Rte. F from Rte. 5 to end of state maintenance, and Rte. O from Rte. 5 to end of state maintenance. | Adv. CN | 3224 | 806 | 0 | 4097 | 0 | AC-STBG |  | 67 | 183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CAMDEN | RT MM E | CD0257 | 1.054 | 2.108 | 2 | N |  | Bridge improvement over Lake of the Ozarks and over Beauty Cove Hollow. Project involves A5677 and A6340. | Federal | 3558 | 889 | 0 | 4448 | 0 | NHPP | CD0256 | 1 | 1 | 57 | 536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3853 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CAMDEN | RT Y E | CD0356 | 3.93 | 6.698 | 0 | N |  | Pavement improvement from end of state maintenance to east of Rte. 54. Includes Outer Road 54E from end of state maintenance west of Rte. Y to end of state maintenance east of Rte. Y, and Outer Road 54W from Rte. Y to end of state maintenance. | Adv. CN | 274 | 69 | 0 | 343 | 0 | AC-STBG |  | 0 | 1 | 2 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | MO 17 S | CD0206 | 29.277 | 58.554 | 0 | N |  | Pavement improvement from Rte. 54 in Cole County to Rte. 42 in Miller County. Includes Rte. PP from Rte. 52 to Rte. A. | Adv. CN | 3559 | 890 | 0 | 4451 | 0 | AC-STBG |  | 2 | 1 | 45 | 188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | MO 179 S | CD0215 | 34.182 | 74.093 | 0 | Y |  | Upgrade pedestrian facilities at various locations in Jefferson City, Lake Ozark, Clarksburg, Pilot Grove, and Dixon. | Adv. CN | 766 | 191 | 0 | 1129 | 0 | AC-STBG | CD0214B | 172 | 223 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | BU 50 E | CD0375 | 0.881 | 4.656 | 0 | Y |  | Safety pedestrian improvements from West Stadium Boulevard to Southwest Boulevard. | Federal | 589 | 65 | 0 | 654 | 0 | SAFETY |  | 0 | 1 | 14 | 67 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | US 50 E | CD0106 | 4.99 | 23.629 | 1 | Y |  | Pavement resurfacing from W of Shamrock Road to E of Stoney Gap Road. Includes westbound Rte. 50 from W of Maries River to E of Mari Osa Delta Lane, E approach slab at Bridge A4188, and from W of Osage River to Moreau River. Includes HFST. $99,000 Open Container Funds. | Federal | 3513 | 878 | 0 | 4415 | 0 | NHPP | CD0212 | 24 | 223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | US 50 E | CD0140 | 0.228 | 0.916 | 2 | Y | 2024-01 | Bridge improvement over Osage River. Project involves bridges A5552 and A0506. | Federal | 2646 | 661 | 0 | 3310 | 0 | NHPP | CD0299 | 3 | 158 | 458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | US 50 E | CD0212 | 3.88 | 7.892 | 0 | Y |  | Pavement repair at Rte. 50/63 interchange. Includes Rte. 63 and ramps. | Federal | 302 | 75 | 0 | 379 | 0 | NHPP | CD0106 | 2 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | US 50 E | CD0299 | 0.14 | 0.28 | 1 | Y | 2026-01 | Bridge improvement over Moreau River. Project involves bridge A0723. | Federal | 754 | 188 | 0 | 945 | 0 | NHPP | CD0140 | 3 | 20 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | US 50 E | CD0365 | 1.841 | 7.486 | 0 | N |  | Safety improvements at Rte. U. | Federal | 3250 | 361 | 0 | 3611 | 0 | SAFETY |  | 0 | 2 | 198 | 466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | US 50 E | CD0374 | 5.685 | 23.385 | 0 | Y |  | Pavement improvement from west of Rte. D to east of Truman Boulevard. | Federal | 3605 | 901 | 0 | 4506 | 0 | NHPP |  | 0 | 1 | 1 | 1 | 1 | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | US 54 E | CD0139 | 0.586 | 2.344 | 1 | Y | 2024-02, 2024-02 | Bridge improvement over the Missouri River. Project involves bridges A4497. | Federal | 5267 | 1317 | 0 | 6588 | 0 | NHPP |  | 4 | 37 | 250 | 861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | US 54 E | CD0219 | 3.933 | 17.961 | 0 | N |  | Modify intersection configuration from west of United Road to east of Rte. E. $4,155,000 Open Container funds. | Federal | 11983 | 1331 | 0 | 14393 | 0 | SAFETY |  | 1079 | 1467 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 11825 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | US 54 E | CD0219B | 4.19 | 18.532 | 0 | N |  | Tree removal for intersection improvement from west of United Road to east of Gray Road. | Federal | 562 | 62 | 0 | 625 | 0 | SAFETY |  | 1 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | US 54 E | CD0259 | 0.349 | 3.403 | 2 | Y | 2026-02 | Bridge washing over Missouri River. Project involves bridges A4497 and L0550. | Federal | 305 | 76 | 0 | 382 | 0 | NHPP | CD0253 | 1 | 1 | 9 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | US 54 E | CD0293 | 18.272 | 82.287 | 0 | Y |  | Pavement improvement from Miller County line to south of Stadium Boulevard. | Federal | 10683 | 2671 | 0 | 13355 | 0 | NHPP |  | 1 | 1 | 1 | 80 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | US 54 E | CD0359 | 0.656 | 3.06 | 0 | N |  | Safety improvements at Rte. D. | Federal | 1529 | 170 | 0 | 1699 | 0 | SAFETY |  | 0 | 5 | 100 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1374 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | RT A W | CD0207 | 0.22 | 0.44 | 1 | N |  | Bridge improvement over Brush Creek. Project involves bridge R0248. | Federal | 1198 | 300 | 0 | 1500 | 0 | PROTECT |  | 2 | 21 | 245 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 1212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | RT AA S | CD0230 | 0.558 | 1.188 | 5 | N |  | Bridge painting over S. Moreau Cr. and on Rte. 179 over Rock Creek in Cole Co. Includes Rte. CC over S. Moreau Cr. in Moniteau Co., Rte. H over Middle River in Callaway Co. and Rte. 8 over I-44 in Phelps Co. Project involves bridges R0445, A1835, X0035, R0417, and A0602. | Federal | 1206 | 302 | 0 | 1521 | 0 | NHPP |  | 13 | 229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | RT B S | CD0258 | 0.478 | 0.956 | 1 | N |  | Bridge rehabilitation over Osage River. Project involves bridge K0656. | Federal | 1622 | 405 | 0 | 2102 | 0 | NHPP |  | 75 | 316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1711 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | RT B S | CD0399 | 19.408 | 38.9 | 0 | Y |  | Pavement improvement from south of Rte. 54 to Rte. 133. | Adv. CN | 4114 | 1029 | 0 | 5143 | 0 | AC-STBG |  | 0 | 2 | 29 | 242 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4870 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | RT D S | CD0400 | 31.526 | 63.132 | 0 | Y |  | Pavement improvement from Rte. 50 to Rte. 54, Outer Road 54 from end of state maintenance to south of Stadium Blvd., Rte. T from Rte. 179 to Rte. 50, Rte. U from Lookout Trail to Rte. C, and Rte. Z from Rte. 179 to Lookout Trail. | Adv. CN | 3184 | 796 | 0 | 3980 | 0 | AC-STBG |  | 0 | 2 | 20 | 189 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | RT J S | CD0184 | 5.738 | 12.106 | 0 | Y |  | Pavement resurfacing from Rte 50 to end of state maintenance, Liberty Rd from Rte M to end of state maintenance, Christy Dr from W/O Veterans Ln to S/O Stadium Blvd, Rte M from Liberty Rd to Rte 50 and Militia Dr from S/O Partnership Parkway to end of state maintenance. | Adv. CN | 730 | 183 | 0 | 920 | 0 | AC-STBG |  | 7 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COLE | RT M E | CD0183 | 7.92 | 15.84 | 0 | Y |  | Pavement improvement from Rte. 50 to Rte. B. | Adv. CN | 868 | 217 | 0 | 1088 | 0 | AC-STBG |  | 3 | 1 | 1 | 3 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COOPER | MO 41 S | CD0394 | 11.779 | 23.558 | 0 | N |  | Pavement improvement from Saline County line to I-70. | Adv. CN | 695 | 174 | 0 | 869 | 0 | AC-STBG |  | 0 | 1 | 1 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 808 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COOPER | IS 70 E | 5I3358Z | 4.8 | 19.492 | 1 | N |  | Payback for MTFC loan to construct new Missouri River bridge at Rocheport. Total cost of $60,739,000 with payments from SFY 2024 to SFY 2030. Project involves bridge L0962. | Adv. CN | 43385 | 0 | 0 | 60739 | 0 | AC-NHFP |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26031 | 8677 | 8677 | 8677 | 8677 | 0
4 | COOPER | IS 70 E | CD0253 | 0.572 | 2.288 | 2 | N |  | Bridge washing over Missouri River. Project involves bridge A8900 and A9100. | Federal | 524 | 58 | 0 | 583 | 0 | NHPP | CD0259 | 1 | 1 | 5 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COOPER | IS 70 E | CD0269 | 77.277 | 317.07 | 0 | Y |  | Job Order Contracting for concrete pavement repair in Cooper, Boone, and Callaway Counties. | Adv. CN | 429 | 107 | 0 | 537 | 0 | AC-STBG |  | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COOPER | MO 87 S | CD0329 | 29.718 | 59.436 | 0 | N |  | Pavement resurfacing from south of I-70 to Rte. O. | Adv. CN | 4362 | 1091 | 0 | 5458 | 0 | AC-STBG |  | 5 | 301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COOPER | RT B S | CD0401 | 23.561 | 47.122 | 0 | N |  | Pavement improvement from I-70 to Rte. 50. | Adv. CN | 2413 | 603 | 0 | 3016 | 0 | AC-STBG |  | 0 | 1 | 1 | 5 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2860 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COOPER | RT E E | CD0402 | 4.097 | 8.194 | 0 | N |  | Pavement improvement from Rte. 135 to Rte. 5. | Adv. CN | 402 | 100 | 0 | 502 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COOPER | RT K S | CD0393 | 5.787 | 11.574 | 0 | N |  | Pavement improvement from Rte. 41 to I-70. | Adv. CN | 276 | 69 | 0 | 345 | 0 | AC-STBG |  | 0 | 1 | 1 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | COOPER | RT M S | CD0189 | 9.017 | 18.034 | 0 | N |  | Pavement resurfacing from Rte. K to Rte. 135. | Adv. CN | 855 | 214 | 0 | 1071 | 0 | AC-STBG |  | 2 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1011 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CRAWFORD | MO 19 S | CD0388 | 0.155 | 0.31 | 0 | N |  | Safety improvements at intersection of Rte. 19, Rte. F, and Rte. CC. Open Container funds $2,691,000. | Federal | 3137 | 349 | 0 | 3486 | 0 | SAFETY | CD0245 | 0 | 25 | 110 | 499 | 0 | 0 | 0 | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 2749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CRAWFORD | MO 8 E | CD0102 | 27.925 | 56.519 | 0 | N |  | Pavement resurfacing from east of Courtois Creek to St. Francois County line. | Federal | 7051 | 1763 | 0 | 8903 | 0 | NHPP |  | 89 | 30 | 378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8406 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CRAWFORD | MO 8 E | CD0362 | 0.079 | 0.158 | 1 | N |  | Bridge improvement over Courtois Creek. Project involves bridge A4263. | Federal | 1048 | 262 | 0 | 1310 | 0 | NHPP |  | 0 | 1 | 3 | 60 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CRAWFORD | MO 8 E | CD0380 | 0.088 | 0.176 | 1 | N |  | Bridge improvement over Yadkin Creek. Project involves bridge A4510. | Federal | 700 | 175 | 0 | 875 | 0 | NHPP |  | 0 | 1 | 1 | 20 | 20 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 752 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CRAWFORD | RT M S | CD0385 | 0.069 | 0.138 | 1 | N |  | Bridge improvement over Crooked Creek. Project involves bridge A8469. | Federal | 86 | 21 | 0 | 107 | 0 | NHPP |  | 0 | 1 | 1 | 1 | 2 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | CRAWFORD | RT N W | CD0037 | 0.068 | 0.136 | 1 | N |  | Bridge rehabilitation over the Meramec River. Project involves bridge A3354. | Federal | 1112 | 278 | 0 | 1441 | 0 | NHPP |  | 51 | 204 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | DALLAS | MO 32 E | CD0355 | 65.517 | 132.339 | 0 | N |  | Pavement improvement from east of Rte. P to west of Rte. 5 and from east of Rte. 5 to Rte. 17. Includes Rte. 64 from Dallas County line to Rte. 5 and Rte. 64A from end of state maintenance to Rte. 64. | Adv. CN | 6185 | 1546 | 0 | 7731 | 0 | AC-STBG |  | 0 | 1 | 80 | 329 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | DENT | MO 19 S | CD0035 | 0.044 | 0.088 | 1 | N |  | Bridge rehabilitation over Spring Creek. Project involves bridge A4433. | Federal | 145 | 36 | 0 | 191 | 0 | NHPP |  | 10 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | DENT | MO 19 S | CD0336 | 0.117 | 0.234 | 0 | N |  | Repair slide 0.3 mile south of County Road 4050. $572,000 Emergency Relief funds, November 2024 flood event. | Federal | 719 | 180 | 0 | 974 | 0 | OTHER |  | 75 | 184 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 714 | 0 | 0 | 0 | 0 | 0 | 572 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | DENT | MO 32 E | CD0235 | 0.168 | 0.336 | 1 | N |  | Bridge replacement over Huzzah Creek. Project involves bridge J0573. | Federal | 3422 | 855 | 0 | 4592 | 0 | NHPP |  | 315 | 427 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 3830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | DENT | MO 32 W | CD0285 | 0.033 | 0.066 | 1 | N |  | Bridge improvement over Dry Creek. Project involves bridge A8446. | Federal | 70 | 17 | 0 | 88 | 0 | NHPP |  | 1 | 1 | 10 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | DENT | RT B E | CD0340 | 0.045 | 0.09 | 1 | N |  | Scour repair and bridge painting at Dry Branch. Project involves bridge A5558. $328,000 Emergency Relief funds, November 2024 flood event. | Federal | 470 | 117 | 0 | 627 | 0 | OTHER |  | 40 | 127 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 459 | 0 | 0 | 0 | 0 | 0 | 328 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | DENT | RT C S | CD0255 | 48.928 | 97.856 | 0 | N |  | Pavement resurfacing from Rte. 72 to Rte. 32, Rte. C from Rte. 19 to SOR I-44, Rte. CC from Rte. 19 to Rte. C, Rte. C from Rte. 133 to Rte. 28 in Pulaski County, and Rte. P from Rte. C to Rte. 19. | Adv. CN | 4438 | 1110 | 0 | 5606 | 0 | AC-STBG |  | 58 | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | DENT | RT FF E | CD0282 | 0.08 | 0.16 | 1 | N |  | Bridge improvement over Dry Fork Creek. Project involves bridge A2060. | Federal | 277 | 69 | 0 | 347 | 0 | NHPP |  | 1 | 1 | 35 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | DENT | RT H E | CD0240 | 0.19 | 0.38 | 4 | N |  | Bridge improvements over Dry Fork Creek and Barnitz Prong Dry Creek and on Rte. 32 over Dry Fork Creek and Pigeon Creek. Project involves bridges A2588, A2587, A4408, and A4261. | Federal | 2486 | 621 | 0 | 3109 | 0 | NHPP |  | 2 | 150 | 448 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2508 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | DENT | RT P S | CD0303 | 7.13 | 14.26 | 0 | N |  | Pavement resurfacing from Rte. 72 to end of state maintenance. Includes Rte. JJ from Rte. N to end of state maintenance. | Adv. CN | 620 | 155 | 0 | 793 | 0 | AC-STBG |  | 18 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | DENT | RT TT E | 5S3566 | 0.178 | 0.237 | 1 | N |  | Bridge improvement over Crooked Creek. Project involves bridge R0808. $1,500,000 - Competitive grant. | Federal | 1944 | 486 | 0 | 2435 | 0 | PROTECT |  | 5 | 1 | 1 | 611 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1807 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | GASCONADE | MO 100 E | CD0396 | 5.115 | 10.357 | 0 | N |  | Pavement improvement from Rte. 19 to Franklin County line. | Adv. CN | 618 | 155 | 0 | 773 | 0 | AC-STBG | CD0397 | 0 | 1 | 4 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 732 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | GASCONADE | MO 19 S | CD0245 | 78.316 | 161.025 | 0 | N |  | Pavement improvement from Gasconade County line to Rte. A in Shannon County. Includes Rte. ZZ from McLeod Street to Rte. 19 and Rte. DD from approximately 0.25 miles west of Rte. 19 to Rte. 19. | Adv. CN | 15160 | 3790 | 0 | 18952 | 0 | AC-STBG | CD0388 | 2 | 1 | 1 | 1227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | GASCONADE | MO 19 S | CD0397 | 17.853 | 35.737 | 0 | N |  | Pavement improvement from Sixth Street to Rte. 50. | Adv. CN | 1742 | 435 | 0 | 2177 | 0 | AC-STBG | CD0396 | 0 | 2 | 14 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2061 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | GASCONADE | RT A S | CD0185 | 21.83 | 43.66 | 0 | N |  | Pavement resurfacing from Rte. 50 to Rte. 28. Includes Rte. Y from Rte. A to Rte. 28. | Adv. CN | 1821 | 455 | 0 | 2302 | 0 | AC-STBG |  | 26 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | GASCONADE | RT T S | CD0315 | 17.436 | 34.872 | 0 | N |  | Pavement improvement from Rte. 50 to end of state maintenance and Rte. V from Rte. 19 to Rte. T. | Adv. CN | 499 | 125 | 0 | 625 | 0 | AC-STBG |  | 1 | 3 | 2 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | HOWARD | BU 240 E | CD0163 | 0.304 | 0.608 | 1 | N |  | Bridge replacement over CPKC railroad. Project involves bridge K0382. | Adv. CN | 3786 | 946 | 0 | 5104 | 0 | AC-STBG | CD0164 | 372 | 842 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 3880 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | HOWARD | BU 240 E | CD0391 | 4.204 | 8.408 | 0 | N |  | Pavement improvement from Commerce St. to Rte. 240. | Adv. CN | 403 | 101 | 0 | 504 | 0 | AC-STBG |  | 0 | 1 | 1 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | HOWARD | MO 240 E | CD0137 | 0.105 | 0.21 | 1 | N |  | Bridge replacement over Salt Creek. Project involves bridge K0045. | Federal | 1003 | 251 | 0 | 1546 | 0 | NHPP |  | 292 | 128 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 1116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | HOWARD | MO 240 E | CD0203 | 0.008 | 0.016 | 1 | N |  | Bridge improvement over Pipes Branch. Project involves bridge H0287. | Federal | 1554 | 389 | 0 | 1945 | 0 | NHPP |  | 2 | 10 | 50 | 356 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 1512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | HOWARD | MO 3 S | CD0164 | 0.037 | 0.074 | 1 | N |  | Bridge replacement over CPKC railroad. Project involves bridge K0962. | Federal | 4402 | 1101 | 0 | 5907 | 0 | NHPP | CD0163 | 404 | 892 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 4591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | HOWARD | MO 3 S | CD0392 | 7.983 | 15.966 | 0 | N |  | Pavement improvement from Roanoke to Rte. 5. | Adv. CN | 1722 | 430 | 0 | 2152 | 0 | AC-STBG |  | 0 | 1 | 1 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | HOWARD | US 40 E | CD0289 | 0.07 | 0.14 | 1 | N |  | Bridge improvement over Moniteau Creek. Project involves bridge G0544. | Federal | 1681 | 420 | 0 | 2102 | 0 | NHPP |  | 1 | 3 | 37 | 327 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | HOWARD | MO 5 S | CD0199 | 0.759 | 1.518 | 0 | N |  | Pavement resurfacing from Locust Street to Rte. 240/87. | Adv. CN | 186 | 47 | 0 | 235 | 0 | AC-STBG |  | 2 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | HOWARD | RT J E | CD0326 | 16.707 | 33.414 | 0 | N |  | Pavement improvements from Rte. Z to Rte. 5, and Rte. DD from Rte. 5 to Rte. P. | Adv. CN | 524 | 131 | 0 | 656 | 0 | AC-STBG |  | 1 | 1 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | HOWARD | RT W E | CD0165 | 0.017 | 0.034 | 1 | N |  | Scour repair over Dry Creek. Project involves bridge N0966. | Federal | 52 | 13 | 0 | 69 | 0 | NHPP |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | HOWARD | RT W E | CD0188 | 7.313 | 14.626 | 0 | N |  | Pavement resurfacing from Rte. 240 to Rte. A. | Adv. CN | 640 | 160 | 0 | 802 | 0 | AC-STBG |  | 2 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | LACLEDE | IS 44 E | CD0158 | 31.38 | 132.314 | 0 | N |  | Pavement improvement 0.6 mile west of Rte. 133 to County Road 8490 in Doolittle. | Federal | 23017 | 2557 | 0 | 25581 | 0 | NHPP |  | 7 | 1 | 1755 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | LACLEDE | IS 44 E | CD0263 | 112.213 | 465.275 | 0 | N |  | Job Order Contracting for asphalt pavement repair in Laclede, Pulaski, Phelps, and Crawford Counties. | Adv. CN | 442 | 110 | 0 | 553 | 0 | AC-STBG |  | 1 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | LACLEDE | IS 44 E | CD0264 | 112.213 | 465.275 | 0 | N |  | Job Order Contracting for concrete pavement repair in Laclede, Pulaski, Phelps, and Crawford Counties. | Adv. CN | 618 | 154 | 0 | 773 | 0 | AC-STBG |  | 1 | 1 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | LACLEDE | IS 44 E | CD0270 | 5.449 | 15.983 | 0 | N |  | Pavement resurfacing and rebuild from 0.6 miles west of Rte. F to 2.1 miles east of Rt. F and east of Swallow Dr. to 0.6 miles west of Rte. 133. Includes I-44 westbound. | Federal | 23672 | 2630 | 0 | 26762 | 0 | NHPP | CD0343 CD0344 ST0119 | 460 | 2357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | LACLEDE | IS 44 E | CD0343 | 0.038 | 0.156 | 2 | N |  | Bridge rehabilitation over Gasconade River Overflow. Project involves bridges L0752 and L0753. | Federal | 956 | 106 | 0 | 1063 | 0 | NHPP | CD0270 CD0344 ST0119 | 1 | 178 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | LACLEDE | IS 44 E | CD0352 | 112.162 | 465.069 | 0 | N |  | Striping upgrades in Laclede, Pulaski, Phelps, and Crawford Counties. | Federal | 771 | 86 | 0 | 857 | 0 | SAFETY |  | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | LACLEDE | IS 44 E | CD0370 | 112.162 | 465.069 | 0 | N |  | Upgrade striping in Laclede, Pulaski, Phelps, and Crawford Counties. | Federal | 794 | 88 | 0 | 882 | 0 | SAFETY |  | 0 | 1 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | LACLEDE | IS 44 W | CD0344 | 0 | 0.106 | 1 | N |  | Bridge rehabilitation over Bear Creek. Project involves bridge L0696. | Federal | 197 | 22 | 0 | 220 | 0 | NHPP | CD0270 CD0343 ST0119 | 1 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | LACLEDE | MO 5 S | CD0387 | 19.807 | 62.98 | 0 | N |  | Pavement improvement from south of Camden County line to Rte. HH in Laclede County. Includes approaches of Rte. 64 and Rte. 32. | Adv. CN | 7434 | 1858 | 0 | 9292 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 96 | 367 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | LACLEDE | RT AD S | CD0221 | 0.233 | 0.466 | 1 | N |  | Bridge improvement over Gasconade River. Project involves bridge R0601. | Adv. CN | 2096 | 524 | 0 | 2622 | 0 | AC-STBG |  | 2 | 1 | 114 | 346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | LACLEDE | CRD DOVE RD E | 5S3562 | 0.096 | 0.192 | 1 | N |  | Bridge rehabilitation over I-44. Project involves bridge A2892. | Adv. CN | 464 | 116 | 0 | 602 | 0 | AC-STBG | CD0056 | 22 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 516 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | LACLEDE | RT J E | CD0056 | 0.093 | 0.186 | 1 | N |  | Bridge rehabilitation over I-44. Project includes bridge A1196. | Federal | 923 | 231 | 0 | 1181 | 0 | NHPP | 5S3562 | 27 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | LACLEDE | RT O E | CD0217 | 0.148 | 0.296 | 1 | N |  | Bridge improvement over Steins Creek. Project involves bridge A2676. | Federal | 1158 | 289 | 0 | 1468 | 0 | NHPP | SE0237 | 21 | 1 | 30 | 207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MARIES | US 63 S | CD0334 | 25.412 | 53.316 | 0 | N |  | Pavement improvement from Osage County line to Phelps County line. | Federal | 6432 | 1608 | 0 | 8041 | 0 | NHPP |  | 1 | 1 | 1 | 439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MARIES | MO 68 E | CD0309 | 11.833 | 23.722 | 0 | N |  | Pavement resurfacing from Rte. 63 to north of Matlock Drive. | Adv. CN | 2622 | 655 | 0 | 3287 | 0 | AC-STBG |  | 10 | 181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MARIES | RT Z E | CD0384 | 0.036 | 0.072 | 1 | N |  | Bridge improvement over Dry Fork Creek. Project involves bridge A2465. | Federal | 583 | 146 | 0 | 729 | 0 | NHPP |  | 0 | 1 | 1 | 10 | 10 | 91 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 616 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MILLER | MO 17 S | CD0234 | 0.266 | 0.532 | 1 | N |  | Bridge improvement over Osage River. Project involves bridge A7536. | Federal | 550 | 137 | 0 | 689 | 0 | NHPP |  | 2 | 1 | 23 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 606 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MILLER | MO 17 S | CD0357 | 30.007 | 60.014 | 0 | N |  | Pavement improvement from Rte. 42 to Loop 44. Includes Rte. EE from Rte. U to Rte. 17. | Adv. CN | 4120 | 1030 | 0 | 5150 | 0 | AC-STBG |  | 0 | 1 | 55 | 217 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4877 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MILLER | MO 42 E | 5P3569 | 19.903 | 39.806 | 0 | N |  | Pavement improvement from Osage Beach to Iberia. | Adv. CN | 3904 | 976 | 0 | 4920 | 0 | AC-STBG |  | 40 | 1 | 1 | 1 | 1 | 203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MILLER | MO 42 E | CD0222 | 0.238 | 0.476 | 2 | N |  | Bridge improvements over Spring Branch and Barren Fork. Project involves bridge A1350 and A1351. | Federal | 2158 | 539 | 0 | 2699 | 0 | NHPP |  | 2 | 1 | 130 | 344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MILLER | MO 42 E | CD0279 | 0.721 | 2.007 | 3 | N |  | Bridge improvement over Tavern Creek and Wiemer Creek, and on Rte. 54 in Camden County over Rte. 5. Project involves bridges A4490, A4492, and A6392. | Federal | 1410 | 353 | 0 | 1764 | 0 | NHPP |  | 1 | 1 | 1 | 77 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MILLER | MO 42 E | CD0348 | 22.459 | 44.918 | 0 | N |  | Pavement improvement from Rte. 17 to Rte. 133, and from Rte. 133 to Rte. 63. | Adv. CN | 2311 | 578 | 0 | 2889 | 0 | AC-STBG |  | 0 | 5 | 24 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MILLER | MO 52 E | CD0233 | 0.288 | 0.576 | 1 | N |  | Bridge rehabilitation over South Fork Moreau Creek. Project involves bridge A3964. | Federal | 335 | 84 | 0 | 423 | 0 | NHPP |  | 4 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 363 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MILLER | US 54 W | CD0377 | 1.262 | 5.83 | 2 | N |  | Bridge improvement over Osage River. Project involves bridges A1479 and A6358. | Federal | 6437 | 1609 | 0 | 8046 | 0 | NHPP |  | 0 | 1 | 1 | 1 | 505 | 845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6693 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MILLER | RT A E | CD0280 | 0.505 | 1.01 | 2 | N |  | Bridge improvement over Tavern Creek and over Osage River on Rte. 17. Project involves bridge N0455 and A7536. | Federal | 501 | 125 | 0 | 627 | 0 | NHPP |  | 1 | 1 | 1 | 9 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MONITEAU | MO 179 S | CD0176 | 22.331 | 44.846 | 0 | Y |  | Pavement improvement from Rte. 87 to 0.1 mile north of West Main Street and to Rte. AA from Rte. 87 to Rte. 179. | Adv. CN | 2098 | 524 | 0 | 2624 | 0 | AC-STBG |  | 2 | 1 | 1 | 1 | 1 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MONITEAU | BU 50 W | CD0214 | 8.477 | 21.876 | 0 | N |  | Upgrade pedestrian facilities at various locations in California, Richland, Belle, Fulton, Camdenton, Crocker, Potosi, St. James, Chamois, and Rolla. | Adv. CN | 486 | 122 | 0 | 1001 | 0 | AC-STBG |  | 388 | 50 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 558 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MONITEAU | US 50 E | CD0272 | 0.025 | 0.05 | 2 | N |  | Bridge improvement over Moreau Creek Branch. Project involves bridges H0154 and H0108. | Federal | 202 | 50 | 0 | 253 | 0 | NHPP |  | 1 | 1 | 1 | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MONITEAU | US 50 W | CD0358 | 0.253 | 0.506 | 0 | N |  | Safety improvement at Rte. 50 and Bus. 50 East. | Federal | 311 | 34 | 0 | 345 | 0 | SAFETY |  | 0 | 1 | 30 | 27 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MONITEAU | MO 87 S | CD0302 | 0.062 | 0.124 | 1 | N |  | Bridge rehabilitation over Moreau Creek. Project involves bridge A1204. | Federal | 381 | 95 | 0 | 495 | 0 | NHPP | CD0229 | 19 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MONITEAU | RT CC S | CD0205 | 22.126 | 44.252 | 0 | N |  | Pavement preservation treatment from Rte. E to Rte. C, and from Rte. C to north of Rte. 52 in Eldon. Includes Rte. M from Rte. 54 interchange to end of state maintenance in Miller County. | Adv. CN | 597 | 149 | 0 | 763 | 0 | AC-STBG |  | 17 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MONITEAU | RT E S | CD0319 | 23.786 | 47.572 | 0 | N |  | Pavement improvement from Rte. 50 to Rte. C, Rte. K from Rte. E to end of state maintenance, and Rte. TT from Rte. 5 to Rte. 5. | Adv. CN | 670 | 168 | 0 | 839 | 0 | AC-STBG |  | 1 | 15 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MONITEAU | RT T S | CD0229 | 0.08 | 0.16 | 1 | N |  | Bridge rehabilitation over Burris Fork. Project involves bridge N0747. | Adv. CN | 144 | 36 | 0 | 186 | 0 | AC-STBG | CD0302 | 6 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MORGAN | MO 135 S | CD0223 | 0.341 | 0.682 | 1 | N |  | Bridge improvement over Flat Creek. Project involves bridge A1838. | Federal | 1570 | 393 | 0 | 1965 | 0 | NHPP |  | 2 | 1 | 70 | 274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MORGAN | MO 5 S | CD0070 | 0.646 | 1.292 | 1 | N |  | Bridge improvement over Gravois Creek. Includes intersection improvement at Rte. J and Rte. 5. Project involves bridge A0146. | Federal | 5279 | 1320 | 0 | 6852 | 0 | NHPP |  | 253 | 541 | 720 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 5313 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MORGAN | MO 5 S | CD0216 | 0.513 | 1.026 | 1 | N |  | Bridge improvement over Straight Fork. Project involves bridge A5253. | Federal | 148 | 37 | 0 | 187 | 0 | NHPP |  | 2 | 5 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MORGAN | US 50 E | CD0266 | 254.995 | 648.687 | 0 | Y |  | Signage upgrades from Pettis County line to Franklin County line and Rte. 5 from Chariton County line to Wright County line. | Federal | 798 | 200 | 0 | 1028 | 0 | NHPP |  | 30 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 919 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MORGAN | US 50 E | CD0281 | 0.36 | 0.72 | 1 | N |  | Bridge improvement over Lamine River. Project involves bridge A1193. | Federal | 2011 | 503 | 0 | 2515 | 0 | NHPP |  | 1 | 1 | 1 | 115 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MORGAN | US 50 E | CD0323 | 11.438 | 22.985 | 0 | N |  | Pavement improvement from west of Hogan Road in Pettis County to west of old Rte. 50 in Moniteau County. | Federal | 3217 | 804 | 0 | 4022 | 0 | NHPP |  | 1 | 1 | 1 | 1 | 1 | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MORGAN | MO 52 E | CD0321 | 17.23 | 34.586 | 0 | N |  | Pavement improvement from Versailles to Eldon. Includes intersection improvements at Rte. 52 and Rte. 5, and Rte. 52 and Jefferson Road. | Adv. CN | 5894 | 1474 | 0 | 7369 | 0 | AC-STBG |  | 1 | 20 | 200 | 409 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 6715 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MORGAN | RT T S | CD0346 | 38.893 | 77.786 | 0 | N |  | Pavement improvement from Rte. 52 to end of state maintenance, Rte. AA from Rte. C to Rte. W, Rte. FF from Rte. 52 to end of state maintenance, Rte. HH from Rte. 5 to Rte. E, and Rte. RA from Rte. 5 to end of state maintenance in Camden County. | Adv. CN | 1112 | 278 | 0 | 1390 | 0 | AC-STBG |  | 0 | 1 | 28 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MORGAN | RT T S | CD0361 | 0.078 | 0.156 | 1 | N |  | Bridge improvement over Gravois Creek. Project involves bridge N0942. | Federal | 85 | 21 | 0 | 106 | 0 | NHPP |  | 0 | 1 | 1 | 1 | 1 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | MORGAN | RT W S | CD0345 | 13.093 | 26.186 | 0 | N |  | Pavement improvement from Versailles city limits in Morgan County to Rte. Y in Miller County. | Adv. CN | 1712 | 428 | 0 | 2140 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2033 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | OSAGE | MO 133 S | CD0275 | 0.024 | 0.048 | 1 | N |  | Bridge improvement over Sugar Creek. Project involves bridge B0368. | Federal | 111 | 28 | 0 | 140 | 0 | NHPP |  | 1 | 1 | 1 | 2 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | OSAGE | US 50 E | CD0273 | 0.085 | 0.17 | 1 | N |  | Bridge improvement over Rte. 50/63. Project involves Bridge A5553. | Federal | 778 | 195 | 0 | 974 | 0 | NHPP | CD0274 | 1 | 1 | 1 | 20 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | OSAGE | US 63 N | CD0274 | 0 | 0.06 | 1 | N |  | Bridge improvement over Rte. 50/63. Project involves bridge A5554. | Federal | 354 | 88 | 0 | 443 | 0 | NHPP | CD0273 | 1 | 1 | 1 | 10 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | OSAGE | US 63 S | CD0108 | 5.951 | 13.175 | 2 | N |  | Corridor improvements from Rte. 50 to north of Rte. T and bridge improvement over the Maries River. Project involves bridge A4322 and A4328. | Federal | 65446 | 16362 | 0 | 85555 | 0 | NHPP |  | 3747 | 2716 | 7292 | 0 | 0 | 0 | 0 | 8701 | 0 | 0 | 0 | 0 | 0 | 0 | 63099 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | OSAGE | MO 89 S | CD0105 | 0.08 | 0.16 | 1 | N |  | Bridge replacement over Indian Creek. Project involves bridge K0214. | Federal | 929 | 232 | 0 | 1234 | 0 | PROTECT |  | 73 | 204 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | OSAGE | RT C E | CD0297 | 0.08 | 0.16 | 1 | N |  | Bridge improvement over Loose Creek. Project involves bridge A1847. | Federal | 886 | 221 | 0 | 1109 | 0 | NHPP |  | 2 | 25 | 173 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 904 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | OSAGE | RT CC S | CD0152 | 4.66 | 9.32 | 0 | N |  | Pavement improvement from Rte. 50 to end of state maintenance. | Adv. CN | 460 | 115 | 0 | 577 | 0 | AC-STBG |  | 2 | 1 | 1 | 1 | 1 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | OSAGE | RT E E | CD0350 | 6.237 | 12.474 | 0 | N |  | Pavement improvement from Rte. 63 to Rte. 89. | Adv. CN | 190 | 48 | 0 | 238 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | OSAGE | RT T S | CD0071 | 0.03 | 0.06 | 1 | N |  | Bridge rehabilitation over Loose Creek. Project involves bridge A1839. | Federal | 452 | 113 | 0 | 592 | 0 | NHPP |  | 27 | 74 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 486 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | OSAGE | RT U S | CD0332 | 8.464 | 16.928 | 0 | N |  | Pavement improvement from Rte. 50 to Rte. E. | Adv. CN | 262 | 66 | 0 | 328 | 0 | AC-STBG |  | 0 | 2 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PHELPS | US 63 S | CD0088 | 30.34 | 85.537 | 0 | N |  | Pavement resurfacing from north of Rolla to south of Rte. CC in Texas County. | Federal | 10521 | 2630 | 0 | 13343 | 0 | NHPP |  | 192 | 662 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PHELPS | US 63 S | CD0214B | 2.921 | 13.269 | 0 | N |  | Upgrade pedestrian facilities at various locations in Rolla and Chamois. | Adv. CN | 496 | 124 | 0 | 657 | 0 | AC-STBG | CD0215 | 37 | 51 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PHELPS | US 63 S | CD0381 | 0.082 | 0.164 | 1 | N |  | Bridge improvement over Beaver Creek. Project involves bridge A7222. | Federal | 129 | 32 | 0 | 161 | 0 | NHPP |  | 0 | 1 | 1 | 1 | 4 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PHELPS | MO 72 E | CD0382 | 0.178 | 0.725 | 3 | N |  | Bridge improvement over Dutro Carter Branch, Little Dry Fork Creek, and Ragan Branch. Project involves bridges A6292, A6293, and A5736. | Federal | 326 | 82 | 0 | 408 | 0 | NHPP |  | 0 | 1 | 1 | 1 | 10 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PHELPS | MO 8 E | CD0236 | 0.063 | 0.252 | 1 | N |  | Bridge improvement over I-44. Project involves bridge A0602. | Federal | 1410 | 353 | 0 | 1765 | 0 | NHPP |  | 2 | 100 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1473 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PHELPS | MO 8 E | CD0290 | 0.044 | 0.088 | 1 | N |  | Bridge improvement over Asher Creek. Project involves bridge A4962. | Federal | 542 | 135 | 0 | 678 | 0 | NHPP |  | 1 | 4 | 40 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PHELPS | RT D E | CD0284 | 0.113 | 0.226 | 1 | N |  | Bridge improvement over Gasconade River. Projects involves bridge A5215. | Federal | 1387 | 347 | 0 | 1735 | 0 | NHPP |  | 1 | 3 | 100 | 239 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PHELPS | RT F E | CD0283 | 0.04 | 0.08 | 1 | N |  | Bridge improvement over Dry Fork Creek. Project involves bridge A2946. | Federal | 1053 | 263 | 0 | 1317 | 0 | NHPP | CD0291 | 1 | 5 | 60 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PHELPS | RT F E | CD0291 | 0.04 | 0.08 | 1 | N |  | Bridge improvement over Norman Creek. Project involves bridge R0522. | Federal | 794 | 199 | 0 | 994 | 0 | NHPP | CD0283 | 1 | 9 | 50 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PHELPS | RT F E | CD0360 | 35.87 | 71.74 | 0 | N |  | Pavement improvement from Rte. 72 to Rte. 68. Includes Rte. O from Rte. 28 to end of state maintenance, Rte. W from end of state maintenance to Rte. P, and Rte. M from Rte. 21 to Rte. 8. | Adv. CN | 1009 | 252 | 0 | 1261 | 0 | AC-STBG |  | 0 | 1 | 14 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1165 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PHELPS | RT H E | CD0363 | 0.03 | 0.06 | 1 | N |  | Bridge improvement over Little Piney Creek. Project involves bridge N0093. | Federal | 1596 | 399 | 0 | 1995 | 0 | NHPP |  | 0 | 2 | 10 | 128 | 237 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 1607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PHELPS | RT HH S | CD0036 | 0.18 | 0.36 | 1 | N |  | Bridge replacement over Spring Creek. Project involves bridge N0668. | Adv. CN | 1647 | 412 | 0 | 2262 | 0 | AC-STBG |  | 203 | 316 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 1723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PHELPS | RT J S | CD0238 | 0.05 | 0.1 | 1 | N |  | Bridge improvement over Spring Creek. Project involves bridge T0878. | Federal | 682 | 171 | 0 | 855 | 0 | NHPP |  | 2 | 40 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 690 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PHELPS | RT K E | CD0160 | 0.14 | 0.28 | 1 | N |  | Bridge improvements over Sherrill Creek. Project involves bridge A0523. | Federal | 1970 | 493 | 0 | 2466 | 0 | NHPP |  | 3 | 10 | 290 | 338 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 1804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PHELPS | RT K E | CD0239 | 0.16 | 0.32 | 1 | N |  | Bridge improvement over Spring Creek. Project involves bridge A0524. | Federal | 435 | 109 | 0 | 546 | 0 | NHPP |  | 2 | 1 | 25 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PULASKI | MO 17 S | CD0306 | 5.608 | 13.574 | 0 | N |  | Pavement resurfacing from south of North Street to Spruce Road. | Adv. CN | 1574 | 393 | 0 | 1968 | 0 | AC-STBG | CD0162 | 1 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PULASKI | MO 17 S | CD0373 | 0.086 | 0.258 | 0 | N |  | Signal improvement at Broadway. | Federal | 653 | 72 | 0 | 725 | 0 | SAFETY |  | 0 | 7 | 30 | 137 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PULASKI | LP 44 E | CD0386 | 0.255 | 1.184 | 0 | N |  | Pavement improvement south of I-44 interchange, including I-44 Spur. | Federal | 825 | 206 | 0 | 1031 | 0 | NHPP |  | 0 | 2 | 9 | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PULASKI | SP 44 E | CD0162 | 5.157 | 18.873 | 0 | N |  | Pavement resurfacing from I-44 to end of state maintenance and on Bus. 44 from Rte. 17 to I-44 Spur. | Adv. CN | 4062 | 1015 | 0 | 5122 | 0 | AC-STBG | CD0306 | 45 | 304 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4773 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PULASKI | MO 7 S | 5P3544 | 0.137 | 0.274 | 1 | N |  | Bridge improvement over the Gasconade River. Project involves bridge A0843. | Federal | 679 | 170 | 0 | 854 | 0 | NHPP |  | 5 | 50 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PULASKI | RT H S | CD0398 | 7.933 | 16.989 | 0 | N |  | Pavement improvement from Rte. 17 to end of state maintenance. Includes Outer Road 44 from Rte. H to end of state maintenance. | Adv. CN | 764 | 191 | 0 | 955 | 0 | AC-STBG |  | 0 | 1 | 6 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 902 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | PULASKI | CRD RIO RD S | CD0364 | 0.011 | 0.022 | 1 | N |  | Bridge improvement over I-44. Project involves bridge A3050. | Federal | 1081 | 270 | 0 | 1351 | 0 | NHPP |  | 0 | 1 | 1 | 95 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | VARIOUS | Various | 5B0800T | 0 | 0 | 1 | Y |  | Payback beginning in SFY 2008 for Safe and Sound bridges in the Central District. | Federal | 0 | 21995 | 0 | 93288 | 5,001 - 10,000 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 107 | 0 | 0 | 0 | 0 | 0 | 71186 | 4399 | 4399 | 4399 | 4399 | 4399
4 | VARIOUS | Various | CD0004 | 0 | 0 | 0 | Y | 2023-19 | Job Order Contracting for guard cable and guardrail repair on various routes in the northern portion of the Central District. | Adv. CN | 2055 | 514 | 0 | 2573 | 0 | AC-STBG |  | 4 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | VARIOUS | Various | CD0005 | 0 | 0 | 0 | N |  | Job Order Contracting for guard cable and guardrail repair on various routes in the southern portion of the Central District. | Adv. CN | 2654 | 664 | 0 | 3322 | 0 | AC-STBG |  | 4 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | VARIOUS | Various | CD0175 | 0 | 0 | 0 | Y | 2025-06, 2025-9 | On-call work zone enforcement at various locations in the Central District. | Federal | 58 | 6 | 0 | 64 | 0 | SAFETY |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | VARIOUS | Various | CD0254 | 0 | 0 | 0 | Y | 2027-7 | On-call work zone enforcement at various locations in the Central District. | Federal | 58 | 6 | 0 | 64 | 0 | SAFETY |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | VARIOUS | Various | CD0267 | 0 | 0 | 0 | Y | 2027-8 | Job Order Contracting for guard cable and guardrail repair on various routes in the northern portion of the Central District. | Adv. CN | 2174 | 543 | 0 | 2718 | 0 | AC-STBG |  | 1 | 1 | 1 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2546 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | VARIOUS | Various | CD0268 | 0 | 0 | 0 | N |  | Job Order Contracting for guard cable and guardrail repair on various routes in the southern portion of the Central District. | Adv. CN | 2807 | 702 | 0 | 3510 | 0 | AC-STBG |  | 1 | 1 | 1 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | VARIOUS | Various | CD0349 | 0 | 0 | 0 | Y | 2027-9 | On-call work zone enforcement at various locations in the Central District. | Federal | 58 | 6 | 0 | 64 | 0 | SAFETY |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | VARIOUS | Various | CD0351 | 0 | 0 | 0 | Y | 2027-10 | Job Order Contracting for guard cable and guardrail repair on various routes in the northern portion of the Central District. | Adv. CN | 2299 | 575 | 0 | 2874 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | WASHINGTON | MO 185 S | CD0034 | 0.04 | 0.08 | 1 | N |  | Bridge rehabilitation over Bates Creek. Project involves bridge A0760. | Federal | 990 | 247 | 0 | 1283 | 0 | NHPP |  | 46 | 38 | 148 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | WASHINGTON | MO 185 S | CD0261 | 0.434 | 0.977 | 8 | Y | 2026-03, 2026-06 | Bridge paint over Bates. Rte. J-Laclede -I-44, Rte. N-Crawford -Meramec, Rte. 163 & Rte. 740 -Hinkson-Boone, Rte. T -Burris Fork-Moniteau, S. Summit Dr -Rte. 54-Callaway, Rt. T -Loose Cr.-Osage. Involves bridges A0760, A1196, A1256, A1899, A3354, A3521, N0747, A1839. | Federal | 2599 | 650 | 0 | 3250 | 0 | NHPP |  | 1 | 34 | 354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | WASHINGTON | MO 21 S | CD0092 | 32.273 | 65.319 | 0 | N |  | Pavement resurfacing from Jefferson County line to Rte. 32 in Iron County. | Adv. CN | 7407 | 1852 | 0 | 9263 | 0 | AC-STBG |  | 4 | 466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | WASHINGTON | MO 47 S | CD0383 | 0.07 | 0.14 | 1 | N |  | Bridge improvement over Old Mines Creek. Project involves bridge A6171. | Federal | 129 | 32 | 0 | 161 | 0 | NHPP |  | 0 | 1 | 1 | 1 | 3 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | WASHINGTON | RT C E | CD0378 | 0.08 | 0.16 | 1 | N |  | Bridge improvement over Hazel Creek. Project involves bridge A5296. | Federal | 143 | 36 | 0 | 179 | 0 | NHPP |  | 0 | 1 | 1 | 1 | 4 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | WASHINGTON | RT C E | CD0379 | 0.408 | 0.816 | 1 | N |  | Bridge improvement over Courtois Creek. Project involves bridge A5646. | Federal | 282 | 70 | 0 | 352 | 0 | NHPP |  | 0 | 1 | 1 | 1 | 10 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | FRANKLIN | MO 100 E | 6S3583B | 0.126 | 0.584 | 0 | Y | 7265N-24 | Replace signals at Rte. AT and on South Woods Mill Road at South Outer Forty Drive in St. Louis County. | Federal | 1122 | 280 | 0 | 1452 | 0 | NHPP |  | 50 | 30 | 95 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 1227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | FRANKLIN | MO 100 E | SL0155 | 3.794 | 11.065 | 1 | Y | 7321K-24 | Pavement resurfacing, upgrade guardrail, signage, signals, and add pavement markings for bike lanes from 0.3 mile west of Rte. KK to Washington Crossing Street and bridge rehabilitation over St. Johns Creek. Project involves bridge J0961. $1,699,000 Open Container funds. | Adv. CN | 5987 | 1497 | 0 | 8055 | 0 | AC-STBG |  | 571 | 201 | 641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | FRANKLIN | MO 100 E | SL0296 | 0.093 | 0.477 | 0 | Y | 7563V-27 | Payment to Washington to add intersection turn lane at International Avenue. | Federal | 190 | 48 | 0 | 239 | 0 | NHPP |  | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 236 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | FRANKLIN | MO 185 S | SL0156 | 5.781 | 11.727 | 2 | Y | 7321L-24 | Pavement resurfacing, upgrade guardrail, signage, signals from west of Springfield Road to south of Rte. K, and bridge rehabilitation over the Meramec River and on Rte. H over Calico Road. Project involves bridges A3967 and A4795. | Adv. CN | 7054 | 1764 | 0 | 9053 | 0 | AC-STBG |  | 235 | 50 | 350 | 699 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | FRANKLIN | MO 30 E | 6S3435B | 0.852 | 1.704 | 2 | Y | 7372K-25 | Bridge replacement and rebuild pavement from 1.3 miles east of Bethel Church Road to 0.1 mile west of Oak Grove Church Road and upgrade pedestrian facilities to comply with the ADA Transition Plan at Bardot Street. Project involves bridges H0994 and H0995. | Federal | 5880 | 1470 | 0 | 8115 | 0 | NHPP |  | 690 | 5 | 464 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6881 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | FRANKLIN | IS 44 E | SL0038 | 15.966 | 66.512 | 1 | Y | 7228N-23 | Pavement resurfacing, replace signage, upgrade guardrail from 0.3 mile west of Rte. 185 to 0.5 mile east of Rte. 30, rest area, weigh scale site improvements, and ramp extensions in St. Clair. Project involves bridge A2049. $13,472,000 General Services Operation funds. | Federal | 21128 | 2347 | 0 | 25197 | 0 | NHPP |  | 1702 | 1600 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 21875 | 0 | 0 | 0 | 0 | 20 | 13452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | FRANKLIN | IS 44 E | SL0048 | 4.754 | 29.469 | 0 | Y | 7228X-23 | Pavement resurfacing and upgrade guardrail from Rte. 100 to Viaduct Street. | Federal | 4928 | 548 | 0 | 6123 | 0 | NHPP |  | 647 | 500 | 361 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | FRANKLIN | IS 44 E | SL0297 | 1.399 | 4.076 | 5 | Y | 7499A | Interchange improvements at Rte. 50, intersection improvements at Rte. AT and Rte. 50, bridge painting at Rte. 50, Rte. AH, and Outer Road I-44, bridge rehabilitation over Birch Creek, and culvert rehabilitation 0.3 mile east of Old Hwy. 50. Design-Build project. | Federal | 51729 | 5748 | 0 | 60913 | 0 | NHPP |  | 3436 | 10240 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 44237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | FRANKLIN | MO 47 S | SL0082 | 12.699 | 29.539 | 2 | Y | 7218A-23 | Safety and capacity improvements from Rte. 100 to I-44 and bridge rehabilitation over the Bourbeuse River (Phase I). Project involves bridges A3961 and A4047. | Federal | 73333 | 18333 | 0 | 95875 | 0 | NHPP |  | 4209 | 3700 | 6367 | 0 | 0 | 0 | 0 | 2060 | 0 | 0 | 0 | 0 | 0 | 0 | 79539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | FRANKLIN | MO 47 S | SL0343 | 1.254 | 3.343 | 0 | Y | 7564A-27 | Pavement resurfacing form Cradwell Street to Rte. 30. | Federal | 407 | 102 | 0 | 509 | 0 | NHPP |  | 0 | 1 | 1 | 10 | 10 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | FRANKLIN | RT A S | SL0049 | 7.547 | 15.964 | 0 | Y | 7228Y-23 | Pavement resurfacing, pavement repair, and upgrade signage from Rte. 100 to 0.1 mile north of Independence Drive. | Adv. CN | 1930 | 483 | 0 | 2767 | 0 | AC-STBG |  | 354 | 159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2254 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | FRANKLIN | RT AB S | SL0050 | 2.037 | 4.074 | 0 | Y | 7228Z-23 | Pavement resurfacing, pavement repair, replace drainage, and upgrade signage from Roller Road to North Outer Road I-44. | Federal | 0 | 618 | 0 | 742 | 0 | STATE |  | 124 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | FRANKLIN | RT K S | SL0059 | 0.232 | 0.464 | 3 | Y | 7229H-23 | Bridge rehabilitation over the Meramec River and bridge replacement over Brush Creek north of Heynes Memorial Annex and 0.8 mile south of Heynes Memorial Annex. Project involves bridges A3871, A8533, and A8534. | Federal | 10311 | 2578 | 0 | 13399 | 0 | NHPP |  | 510 | 80 | 816 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 11943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | FRANKLIN | RT K S | SL0339 | 34.338 | 68.676 | 0 | Y | 7563W-27 | Pavement resurfacing and pavement repairs from Rte. 30 to Rte. 185 and on Rte. H from Rte. 50 to Rte. 185. | Adv. CN | 8596 | 2149 | 0 | 10745 | 0 | AC-STBG |  | 0 | 20 | 25 | 225 | 275 | 633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | FRANKLIN | CRD OLD HIGHWAY 100 E | 6S3627 | 0.035 | 0.07 | 1 | Y | 7220C-22 | Bridge replacement over Dubois Creek 0.2 mile east of Fifth Street. Project involves bridge 4330001. | Federal | 2109 | 527 | 0 | 3027 | 0 | NHPP |  | 391 | 342 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 2284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | FRANKLIN | RT OO S | SL0157 | 3.501 | 7.003 | 0 | Y | 7321M-24 | Pavement resurfacing and upgrade signage and guardrail from Rte. 100 to First Street. | Adv. CN | 686 | 172 | 0 | 1016 | 0 | AC-STBG |  | 158 | 1 | 10 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | FRANKLIN | RT VV S | SL0068 | 0.204 | 0.572 | 4 | Y | 7230O-23 | Culvert rehabilitation over Rohlfing Creek, on Rte. UU over Buesher Creek, on I-44 over branch of the Bourbeuse River, and on Rte. OO over Little Fox Creek. Project involves culverts A4693, L0355, N0351, and N0820. | Federal | 406 | 102 | 0 | 583 | 0 | NHPP |  | 75 | 46 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | FRANKLIN | RT Y N | SL0338 | 9.477 | 18.954 | 0 | Y | 7563X-27 | Pavement resurfacing and pavement repairs from Rte. YY to Rte. 50. | Federal | 0 | 2150 | 0 | 2150 | 0 | STATE |  | 0 | 5 | 5 | 50 | 50 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | FRANKLIN | RT YY E | SL0308 | 25.26 | 50.54 | 0 | Y | 7563Y-27 | Pavement preservation treatment from Rte. 185 to Rte. A, on Rte. 47 from Rte. 30 to south of Rte. FF, and on Rte. FF from Rte. 30 to Rte. 47. | Adv. CN | 771 | 193 | 0 | 964 | 0 | AC-STBG |  | 0 | 1 | 5 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | JEFFERSON | MO 110 E | SL0069 | 0.501 | 1.602 | 3 | Y | 7229P-23 | Bridge rehabilitation over Union Pacific Railroad and Joachim Creek, Rte. 61 over Rock Creek, and Rte. T over Plattin Creek. Project involves bridges A3616, A4588, and A4789. | Federal | 1845 | 461 | 0 | 2541 | 0 | NHPP |  | 235 | 10 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | JEFFERSON | MO 110 E | SL0333 | 6.378 | 13.577 | 0 | Y | 7564C-27 | Pavement resurfacing from Rte. 21 to Rte. CC. | Adv. CN | 2501 | 625 | 0 | 3126 | 0 | AC-STBG |  | 0 | 5 | 10 | 50 | 50 | 197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2814 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | JEFFERSON | MO 30 E | SL0046 | 6.689 | 34.354 | 0 | Y | 7228V-23 | Pavement resurfacing, pavement repairs, upgrade guardrail, and replace signage from 0.2 mile west of Rte. PP to 0.2 mile west of Rte. 141. | Federal | 4507 | 1127 | 0 | 6171 | 0 | NHPP |  | 537 | 408 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 5216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | JEFFERSON | IS 55 S | SL0154 | 0.24 | 1.293 | 6 | Y | 7321J-24 | Bridge rehabilitation at Church Road, Vogel Road, Richardson Road, Rock Creek, and Imperial Main Street. Project involves bridges A5459, A5728, A5729, A5929, A6112, and A6113. | Federal | 1671 | 186 | 0 | 2282 | 0 | NHPP |  | 425 | 1 | 10 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | JEFFERSON | IS 55 S | SL0288 | 3.823 | 23.32 | 0 | Y | 7493C-26 | Median improvements from Rte. M to 0.5 mile north of Rte. Z. | Federal | 11451 | 1272 | 0 | 12728 | 0 | NHPP |  | 5 | 10 | 10 | 250 | 250 | 937 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | JEFFERSON | W OR 55 S | 6S3374 | 0.059 | 0.118 | 1 | Y | 6852U-18 | Bridge rehabilitation on Weier Road over Union Pacific Railroad. Project involves bridge A0955. | Federal | 0 | 1865 | 0 | 2211 | 0 | STATE |  | 346 | 1 | 10 | 75 | 50 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | JEFFERSON | W OR 55 S | SL0268 | 2.226 | 5.267 | 1 | Y | 7446-26 | Add signals at Miller Road, Seckman Road, add ITS equipment from Richarson Road to Miller Road, and from Seckman Road to Imperial Main Street. Project involves bridge A7234. $917,440 Congestion Mitigation and Air Quality Improvement Program funds. | Federal | 850 | 212 | 0 | 1175 | 0 | CMAQ |  | 113 | 18 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 968 | 0 | 0 | 0 | 113 | 0 | 805 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | JEFFERSON | US 61 N | 6S3399 | 10.972 | 45.076 | 3 | Y | 6892R-19 | Pavement resurfacing, upgrade guardrail, and upgrade pedestrian facilities to comply with the ADA Transition Plan from Rte. M to Rte. 67 and replace culverts 0.1 mile south of Schmidt Rd. and south of Hillside Estates Dr. Project involves culverts G0511, G0512 and G0641. | Federal | 12317 | 3079 | 0 | 17090 | 0 | NHPP |  | 1010 | 998 | 0 | 0 | 0 | 0 | 684 | 0 | 0 | 0 | 0 | 0 | 0 | 14398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | JEFFERSON | US 61 S | SL0322 | 10.764 | 46.192 | 0 | Y | 7564D-27 | Safety improvements from Collier Drive to Rte. Z. | Federal | 3681 | 409 | 0 | 4090 | 0 | SAFETY |  | 0 | 50 | 150 | 283 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | JEFFERSON | US 67 S | SL0163 | 14.523 | 62.163 | 2 | Y | 7321Q-24 | Pavement resurfacing, upgrade signage, and guardrail from east of American Legion Drive to St. Francois County line and culvert rehabilitation over Mcmullen Branch and over Joachim Creek. Project involves culverts L0577 and L0579. | Federal | 8030 | 2007 | 0 | 10691 | 0 | NHPP |  | 654 | 1 | 200 | 691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | JEFFERSON | RT AA E | SL0167 | 0.055 | 0.11 | 0 | Y | 7321U-24 | Culvert replacement east of Weaver Road. | Federal | 0 | 847 | 0 | 907 | 0 | STATE |  | 60 | 5 | 27 | 64 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | JEFFERSON | RT B S | SL0153 | 11.175 | 22.456 | 2 | Y | 7321I-24 | Pavement resurfacing, pavement repairs, bridge rehabilitation, upgrade guardrail, signals, signage, lighting, and repair sidewalk from Rte. 30 to Old Rte. 21. Project involves bridge A5081 and A6655. | Adv. CN | 8884 | 2221 | 0 | 11973 | 0 | AC-STBG |  | 868 | 100 | 734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | JEFFERSON | RT FF S | SL0274 | 4.545 | 9.09 | 1 | Y | 7394W-26 | Pavement resurfacing, upgrade guardrail, signage, and repair signals from Rte. 109 to Rte. F and bridge rehabilitation over Labarque Creek. Project involves bridge N0199. | Adv. CN | 2685 | 671 | 0 | 3366 | 0 | AC-STBG |  | 10 | 75 | 102 | 300 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 2858 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | JEFFERSON | RT M E | 6S3652 | 7.309 | 31.186 | 8 | Y | 7220L-22 | Pavement resurfacing, upgrade guardrail, replace signage, and bridge deck sealing from Rte. 21 to west of Metropolitan Boulevard and on Rte. MM from Buckeye Valley Road to Rte. 21. Project involves bridges A5415, A5416, A5417, A5418, A5581, A5582, A5633, and A5634. | Federal | 1938 | 485 | 0 | 2608 | 0 | NHPP |  | 185 | 178 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 2225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | JEFFERSON | RT PP E | SL0319 | 2.158 | 4.432 | 0 | Y | 7564B-27 | Pavement resurfacing from Byrnes Mill Road to Rte. 30. | Adv. CN | 621 | 155 | 0 | 776 | 0 | AC-STBG |  | 0 | 10 | 10 | 10 | 10 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | JEFFERSON | RT T E | SL0254 | 28.269 | 56.728 | 0 | Y | 7394V-26 | Pavement preservation treatment from Rte. JJ to Rte. TT, Rte. TT from Rte. 61 north junction to Rte. T, Rte. BB from Rte. 30 to Rte. 21, and Rte. AJ form Rte. YY to Rte. 50. | Adv. CN | 750 | 187 | 0 | 938 | 0 | AC-STBG |  | 1 | 5 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 861 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | JEFFERSON | RT Z E | SL0165 | 6.092 | 13.017 | 1 | Y | 7321S-24 | Pavement resurfacing, replace signage, upgrade guardrail from Rte. A to Rte. 61, and bridge rehabilitation over Sandy Creek. Project involves bridge A6674. | Adv. CN | 2091 | 523 | 0 | 2747 | 0 | AC-STBG |  | 133 | 1 | 1 | 20 | 31 | 194 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 2356 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | MO 364 E | SL0221B | 137.801 | 717.572 | 0 | Y | 7504A | Upgrade striping on Rte. 364, Rte. 180, Rte. 21, Rte. 267, I-55, Rte. 79, and Rte. K in the St. Louis District. $267,000 Open Container funds. | Federal | 2059 | 229 | 0 | 2288 | 0 | SAFETY |  | 0 | 288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | MO 370 E | 6P3551 | 0.248 | 1.522 | 8 | Y | 7216V-22 | Bridge rehabilitation over Lakeside Park Drive, Cole Creek, New Town Boulevard, and Elm Point Industrial Drive. Project involves bridges A5116, A5123, A5308, A5309, A5322, A5323, A5326, and A5327. | Federal | 7881 | 1970 | 0 | 10171 | 0 | NHPP |  | 320 | 10 | 290 | 768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | MO 370 E | 6P3612 | 0.122 | 0.345 | 3 | Y | 7217J-22 | Bridge rehabilitation over Premier Parkway and Salt River Road over Rte. 370. Project involves bridges A5321, A5493, and A5494. | Federal | 2541 | 635 | 0 | 3263 | 0 | NHPP |  | 87 | 50 | 20 | 193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | US 61 S | SL0083 | 6.044 | 25.121 | 0 | Y | 7229Z-23 | Safety and operational improvements from Dietrich Road to 1.0 mile north of I-64 (Phase I). $5,827,000 Open Container funds. | Federal | 36538 | 9135 | 0 | 50013 | 0 | NHPP |  | 4340 | 200 | 200 | 2510 | 0 | 0 | 0 | 0 | 5503 | 0 | 0 | 0 | 0 | 0 | 0 | 37260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | IS 64 W | SL0342 | 0 | 4.134 | 0 | Y | 7564F-27 | Pavement resurfacing on westbound lanes from east of Phoenix Parkway to 0.6 mile west of Rte. DD, 0.5 mile east of Lake St. Louis Boulevard to 0.2 miles west of Lake St. Louis Boulevard. | Federal | 932 | 103 | 0 | 1035 | 0 | NHPP |  | 0 | 5 | 5 | 10 | 50 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | N OR 64 E | SL0016 | 0.04 | 0.088 | 1 | Y | 7227R-23 | Bridge replacement over Peruque Creek. Project involves bridge J0991. | Federal | 3471 | 868 | 0 | 4514 | 0 | NHPP |  | 175 | 25 | 279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4035 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | N OR 64 W | SL0013 | 10.376 | 23.807 | 0 | Y | 7227O-23 | Pavement resurfacing and upgrade guardrail from Warsen Avenue to Wolfrum Road, Rte. N from Spring Borough Drive to Technology Drive, on South Outer Road 64 from Prospect Road to Hickory Glen Court, and from Rte. N to south of Kent Drive. | Adv. CN | 2754 | 688 | 0 | 3462 | 0 | AC-STBG |  | 20 | 100 | 256 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3086 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | US 67 N | SL0346 | 0.538 | 1.775 | 2 | Y | 7563Z-27 | Payment to IDOT for bridge washing on the Clark Bridge and Martin Luther King Bridge over the Mississippi River. Project includes bridges A4278 and A4856. | Federal | 65 | 16 | 0 | 81 | 0 | NHPP |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | US 67 S | SL0107 | 0.635 | 2.54 | 1 | Y | 7230M-23 | Bridge rehabilitation and upgrade drainage on the Lewis Bridge. Project involves bridge A3047. | Federal | 3772 | 943 | 0 | 4735 | 0 | NHPP |  | 20 | 424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | US 67 S | SL0212 | 73.191 | 331.541 | 0 | Y | 7372H-25 | Upgrade signage from the Mississippi River to Swan Drive in St. Louis County and 0.2 mile north of Big Bend Road in St. Louis County to 0.2 mile south of Rte. V in Jefferson County. $1,657,000 Open Container funds. | Federal | 2909 | 323 | 0 | 3432 | 0 | SAFETY |  | 200 | 125 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | US 67 S | SL0317 | 0.538 | 1.775 | 2 | Y | 7564G-27 | Payment to IDOT for bridge deck sealing on Clark Bridge and Martin Luther King Bridge over the Mississippi River. Project includes bridges A4278 and A4856. | Federal | 111 | 28 | 0 | 139 | 0 | NHPP |  | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | IS 70 E | SL0134 | 0.08 | 0.516 | 4 | Y | 7320W-24 | Bridge rehabilitation over Peruque Creek and Rte. A. Project involves bridges A4236, A4237, L0206, and L0709. | Federal | 2197 | 244 | 0 | 2471 | 0 | NHPP |  | 30 | 100 | 40 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2133 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | IS 70 E | SL0135 | 7.526 | 58.861 | 0 | Y | 7320X-24 | Pavement resurfacing from Mid Rivers Mall Drive to the Missouri River. | Federal | 7143 | 794 | 0 | 7952 | 0 | NHPP |  | 15 | 10 | 75 | 100 | 100 | 534 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | IS 70 E | SL0188 | 4.005 | 30.384 | 11 | Y | 7322R-25 | Bridge washing over the Missouri River on I-70, I-64, Rte. 47, Rte. 364, Rte. 370, Rte. 67, and on Rte. 364 over Creve Coeur Lake. Project involves bridges A3047, A3292, A4017, A4557, A5584, A5585, A7577, A8141, and L0561. | Federal | 2102 | 233 | 0 | 2380 | 0 | NHPP |  | 45 | 40 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2147 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | IS 70 E | SL0305 | 0.04 | 0.385 | 2 | Y | 7499B | Bridge rehabilitation over 5th Street. Project involves bridges A3582 and A3583. | Federal | 3990 | 443 | 0 | 4533 | 0 | NHPP |  | 100 | 294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | S OR 70 E | SL0116 | 12.538 | 27.596 | 0 | Y | 7320Q-24 | Pavement resurfacing and replace guardrail on disconnected sections from Callahan Road to Rte. 79 and on North Outer Road I-70 from 0.5 mile west of Lake St. Louis Boulevard to 0.5 mile east of Rte. 79. | Adv. CN | 11198 | 2800 | 0 | 14608 | 0 | AC-STBG |  | 610 | 200 | 100 | 100 | 100 | 823 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12675 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | MO 79 N | SL0015 | 0.247 | 0.791 | 9 | Y | 7227Q-23 | Bridge rehabilitation at various locations on Rte. T, Rte. N, Rte. 61, I-70, and I-64. Project involves bridges A2348, A4728, A6157, A6755, A6986, A7043, A7103, A8539, and H0141. | Federal | 969 | 242 | 0 | 1321 | 0 | NHPP |  | 110 | 28 | 10 | 3 | 3 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1097 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | MO 79 S | SL0130 | 1.491 | 6.616 | 0 | Y | 7320U-24 | Pavement resurfacing and upgrade guardrail from 0.6 mile north of Salt River Road to 1-70. | Federal | 3318 | 829 | 0 | 4397 | 0 | NHFP |  | 250 | 5 | 5 | 25 | 50 | 281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | MO 94 E | SL0120 | 1.206 | 2.751 | 0 | Y | 7265F-23, 7360C-27 | Add intersection turn lanes and replace signal at Rte. D. $1,917,900 Congestion Mitigation and Air Quality Improvement Program funds. | Federal | 2676 | 669 | 0 | 3790 | 0 | CMAQ | SL0120B | 445 | 336 | 0 | 0 | 0 | 0 | 0 | 656 | 0 | 0 | 0 | 0 | 0 | 2353 | 0 | 0 | 0 | 0 | 0 | 1918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | MO 94 E | SL0120B | 1.216 | 2.928 | 0 | Y | 7383B-25 | Add lanes, shoulder, and modify guardrail from Rte. D to I-64. | Federal | 5976 | 1494 | 0 | 7670 | 0 | NHPP | SL0120 | 200 | 730 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 5740 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | MO 94 E | SL0215 | 77.527 | 297.182 | 0 | Y | 7372T-25 | Pavement preservation treatment on Rte. 94, Rte. 79, Rte. 61, Rte. M in St. Charles County, I-44, Rte. 61, Rte. 67, Rte. 109, Rte. 100, Rte. 340, Rte. P, Rte. CC in St. Louis County, Rte. 100, Rte. 50 in Franklin County, and Rte. 109 in Jefferson County. | Federal | 732 | 183 | 0 | 921 | 0 | NHPP |  | 6 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | MO 94 E | SL0235 | 0.171 | 0.342 | 0 | Y | 7360B-25 | Add intersection turn lanes and signal at Rte. B. $712,890 Congestion Mitigation and Air Quality Improvement Program funds. | Federal | 1306 | 326 | 0 | 1698 | 0 | CMAQ |  | 66 | 102 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 1380 | 0 | 0 | 0 | 0 | 59 | 654 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | MO 94 E | SL0340 | 3.792 | 18.633 | 0 | Y | 7564H-27 | Pavement resurfacing and upgrade signals from I-64 to Rte. 364. | Federal | 6618 | 1654 | 0 | 8272 | 0 | NHPP |  | 0 | 25 | 25 | 125 | 200 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | RT DD S | SL0341 | 9.675 | 21.099 | 0 | Y | 7564J-27 | Pavement Resurfacing from I-64 to Rte. 94. | Federal | 3034 | 759 | 0 | 3793 | 0 | NHPP |  | 0 | 10 | 15 | 50 | 100 | 241 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | RT N E | 6S3342C | 2.485 | 6.317 | 0 | Y | 7564K-27 | Add lanes from Hopewell Road to Hawk Ridge Trail (Partial). Potential Design-Build project. | Adv. CN | 19170 | 4793 | 0 | 23963 | 0 | AC-STBG |  | 0 | 1000 | 2366 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 20497 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | RT N E | SL0337 | 5.975 | 11.95 | 0 | Y | 7564L-27 | Pavement resurfacing from Rte. T to Rte. Z. | Adv. CN | 1720 | 430 | 0 | 2150 | 0 | AC-STBG |  | 0 | 10 | 10 | 10 | 75 | 132 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1913 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | RT P E | 6S3666 | 0.048 | 0.096 | 0 | Y | 7220P-22 | Modify intersection configuration and add signals at Koch Road. | Federal | 1257 | 140 | 0 | 1647 | 0 | SAFETY |  | 250 | 90 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 1243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | RT P E | SL0218 | 19.455 | 39.068 | 0 | Y | 7372W-25 | Pavement preservation treatment from Rte. 61 to Rte. M and on Rte. B from Rte. C to Rte. 94. | Adv. CN | 726 | 181 | 0 | 913 | 0 | AC-STBG |  | 6 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 836 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | Various | SL0104 | 0 | 0 | 0 | Y | 7265Z-23 | Job Order Contracting for guardrail repair at various locations in St. Charles County. | Adv. CN | 1713 | 428 | 0 | 2145 | 0 | AC-STBG |  | 4 | 141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. CHARLES | Various | SL0304 |  |  | 0 | Y | 7564M-27 | Job Order Contracting for guardrail repair at various locations in St. Charles County. | Adv. CN | 1812 | 453 | 0 | 2265 | 0 | AC-STBG |  | 0 | 1 | 1 | 141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | MO 100 E | SL0148 | 5.932 | 28.489 | 0 | Y | 7321E-24 | Pavement resurfacing and replace signals from Westglen Farms Drive to Rte. 141. | Federal | 9932 | 2483 | 0 | 12505 | 0 | NHPP |  | 90 | 300 | 400 | 994 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | MO 100 E | SL0251 | 0.45 | 2.996 | 0 | Y | 7394T-26 | Payment to Manchester to add sidewalk from Rte. 141 to west of Knollhaven Drive. $1,340,362 Cost Share funds. | Federal | 872 | 218 | 0 | 1348 | 0 | NHPP |  | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 255 | 1085 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | MO 109 S | SL0295 | 8.124 | 23.462 | 0 | Y | 7448-27 | Signal optimization from Shepard Road to The Legends Parkway and modify turn lanes at Eureka High School, 5th Street, and I-44. $2,260,000 Congestion Mitigation and Air Quality Improvement Program funds. | Federal | 2208 | 552 | 0 | 2825 | 0 | CMAQ |  | 65 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2260 | 0 | 0 | 0 | 0 | 0 | 2260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | MO 115 S | SL0172 | 1.324 | 5.493 | 0 | Y | 7321Y-24 | Pavement resurfacing, replace signage, upgrade lighting, and guardrail from I-70 to Engler Avenue. | Federal | 2133 | 533 | 0 | 2794 | 0 | NHPP | SL0249 | 128 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2448 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | MO 141 S | SL0025 | 0.22 | 0.842 | 3 | Y | 7228A-23 | Bridge rehabilitation over Rte. 370 at Taussig Avenue, West St. Louis Mills Boulevard, and Rte. 141. Project involves bridges A4919, A4920, and A7015. | Federal | 6236 | 1559 | 0 | 7940 | 0 | NHPP |  | 145 | 263 | 658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6874 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | MO 141 S | SL0026 | 2.821 | 11.698 | 0 | Y | 7228B-23 | Pavement resurfacing, replace signage, and guardrail from Rte. 370 to I-70. | Federal | 3097 | 774 | 0 | 3901 | 0 | NHPP |  | 30 | 263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3608 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | MO 141 S | SL0149 | 1.95 | 11.862 | 0 | Y | 7321F-24 | Pavement resurfacing from I-64 to Milldale Drive. | Federal | 2297 | 574 | 0 | 2932 | 0 | NHPP |  | 61 | 20 | 20 | 20 | 40 | 197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | MO 141 S | SL0234 | 0.342 | 2.045 | 0 | Y | 7360A-25/, 7360AA | Add intersection turn lanes and upgrade signals at Parkway South Middle School, upgrade signals at Springdale Lane, Fiedler Lane, and Romaine Creek Road. $1,046,000 Open Container, $224,484 Congestion Mitigation and Air Quality Improvement Program funds. | Federal | 1288 | 143 | 0 | 1455 | 0 | SAFETY |  | 24 | 156 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 21 | 204 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 170 E | 6I3567 | 0.265 | 2.283 | 11 | Y | 7171U-22 | Bridge rehabilitation over I-64 ramps, Ladue Road, Galleria Parkway, Clayton Road, and Brentwood Boulevard, and bridge replacement at Forest Park Parkway. Project involves bridges A2779, A2780, A2782, A2788, A2790, A8011, A8012, and A8015. | Federal | 16721 | 1858 | 0 | 19686 | 0 | NHPP | 6I3634 | 925 | 1694 | 0 | 0 | 0 | 0 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 16885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 170 E | 6I3572 | 7.51 | 53.032 | 4 | Y | 7171R-22 | Bridge and culvert rehabilitation and upgrade guardrail from Nyflot Avenue to 0.2 mile north of Rte. 340 and sound abatement repairs near East Sherwood Drive. Project involves bridges A2807, A2809, A3176, and culvert A2808. $50,000 District Operation funds. | Federal | 14679 | 1631 | 0 | 17755 | 0 | NHPP |  | 1310 | 1106 | 0 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 15204 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 170 E | SL0261 | 0.213 | 0.852 | 1 | Y | 7394S-26 | Bridge rehabilitation over Norfolk Southern Railway 0.4 mile north of Airport Road. Project involves bridge A2926. | Federal | 12438 | 1382 | 0 | 13825 | 0 | NHPP |  | 5 | 20 | 650 | 700 | 806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 170 E | SL0276 | 7.012 | 48.648 | 0 | Y | 7396V | Pavement resurfacing and upgrade guardrail from I-270 to Woodson Road. | Federal | 17946 | 1994 | 0 | 19990 | 0 | NHPP |  | 50 | 10 | 10 | 180 | 1000 | 2021 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 170 E | SL0330 | 3.908 | 24.772 | 0 | Y | 7564U-27 | Pavement resurfacing from Woodson Road to Eager Road. | Federal | 5996 | 666 | 0 | 6662 | 0 | NHPP |  | 0 | 100 | 150 | 577 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 170 W | SL0260 | 0.108 | 1.388 | 5 | Y | 7396R | Bridge rehabilitation over Norfolk Southern Railway, Airport Road, and Rte. 180 (St. Charles Rock Road). Project involves bridge A2927, A2991, A2992, A3171, and A3172. | Federal | 18581 | 2064 | 0 | 20737 | 0 | NHPP |  | 92 | 500 | 500 | 200 | 200 | 2607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | MO 180 E | 6S3311 | 0.097 | 0.597 | 2 | Y | 6811B-18 | Bridge replacement, ramp extensions, upgrade ITS equipment, and add sidewalk on St. Charles Rock Road at I-70. Project involves bridge L0887. | Federal | 19154 | 4789 | 0 | 25399 | 0 | NHPP |  | 1431 | 4 | 4 | 1256 | 0 | 0 | 25 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 22627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | MO 180 E | SL0241 | 0.013 | 0.059 | 2 | Y | 7396L | Culvert replacement 0.1 mile west of McKelvey Road and culvert rehabilitation on McKelvey Road south of Rte. 180 (St. Charles Rock Road). Project involves culverts A2396 and K0286. | Federal | 1758 | 439 | 0 | 2297 | 0 | NHPP |  | 100 | 20 | 10 | 115 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 1892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | MO 21 S | SL0194 | 1.483 | 4.208 | 9 | Y | 7322W-25 | Bridge washing over the Meramec River on Rte. 21, Rte. 30, Rte. 61, Rte. 109, Rte. 141, Rte. 185, Rte. F, Rte. K, and Rte. O. Project involves bridges A2137, A2187, A2955, A3871, A3967, A3998, A4975, A6474, and K0637. | Federal | 390 | 97 | 0 | 493 | 0 | NHPP | SL0194B | 6 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | MO 267 S | SL0222 | 0.175 | 0.736 | 0 | Y | 7322L-25 | Add pedestrian crossing facilities at Hallmark Lane and on Rte. 366 west of Ravensridge Drive. | Federal | 769 | 85 | 0 | 1004 | 0 | SAFETY |  | 150 | 142 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 270 E | 6I3020D | 1.425 | 6.119 | 1 | Y | 7171D-21 | Add lanes and bridge replacement from Lilac Avenue to 0.1 mile west of Rte. H (Riverview Drive). Project involves bridge A0221. | Federal | 13729 | 1525 | 0 | 16693 | 0 | NHPP | 6I3580B SL0021 | 1389 | 984 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 14270 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 270 E | 6I3580B | 3.592 | 20.056 | 0 | Y | 7394R-26 | Pavement resurfacing and median barrier replacement from west of Rte. 367 to the Mississippi River. | Federal | 3803 | 423 | 0 | 4421 | 0 | NHPP | 6I3020D SL0021 | 195 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 270 E | SL0021 | 2.834 | 17.935 | 3 | Y | 7227W-23 | Bridge replacement over Rte. 367 and Bellefontaine Rd., rebuild pavement, replace median barrier 0.6 mile west of Rte. 367 to 0.4 mile west of Lilac Ave., replace signals and upgrade pedestrian facilities at Bellefontaine Road. Project involves bridges A0241 and J0847. | Federal | 26904 | 2989 | 0 | 32462 | 0 | NHPP | 6I3020D 6I3580B | 2549 | 2197 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 27696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 270 E | SL0021B | 0.089 | 0.493 | 3 | Y | 7322Q-25 | Bridge rehabilitation on I-270 and Dunn Road over BNSF Railway. Project involves bridges J0493 and L0749. | Federal | 3691 | 410 | 0 | 4355 | 0 | NHPP | 6I3580 | 254 | 42 | 22 | 358 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 3658 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 270 E | SL0022 | 0.515 | 4.44 | 4 | Y | 7227X-23 | Bridge rehabilitation over Norfolk Southern Railway, on Rte. 370 over Norfolk Southern Railway, on ramp from Missouri Bottom Road to I-270, and on Missouri Bottom Road over I-270. Project involves bridges A0170, A4277, A4898, and A4899. | Federal | 6331 | 703 | 0 | 7624 | 0 | NHPP |  | 590 | 50 | 483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 270 E | SL0024 | 6.761 | 56.741 | 0 | Y | 7227Z-23 | Pavement resurfacing and median barrier replacement from I-70 to 0.5 mile east of I-170. | Federal | 18441 | 2049 | 0 | 20990 | 0 | NHPP |  | 500 | 1597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 270 E | SL0053 | 0.48 | 3.576 | 12 | Y | 7229C-23 | Bridge rehabilitation over Marshall Road, I-44, Rott Road, Von Talge Road, River Sub Railroad, I-55, and ramp from I-55 to I-255. Project involves bridges A0967, A1026, A1033, A1233, A1234, A1235, A4876, A4877, A5082, and A1006. | Federal | 14657 | 1628 | 0 | 16945 | 0 | NHPP |  | 660 | 1048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 270 E | SL0221 | 127.539 | 837.266 | 0 | Y | 7322K-25 | Upgrade striping on I-270, Rte. 370, Rte. 141, I-70, I-64, Rte. 340, and Outer Road 270 in the St. Louis District. $1,009,000 Open Container funds. | Federal | 2027 | 225 | 0 | 2286 | 0 | SAFETY |  | 34 | 252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 270 E | SL0221C | 109.471 | 773.858 | 0 | Y | 7504B | Upgrade striping at various intersections along I-270, I-70, I-64, Rte. 370, and Rte. 141 in the St. Louis District. $2,400,000 Open Container funds. | Federal | 2444 | 271 | 0 | 2715 | 0 | SAFETY |  | 0 | 315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 270 E | SL0242 | 0.043 | 0.44 | 1 | Y | 7396M | Bridge replacement over West Port Plaza Drive. Project involves bridge A1487. | Federal | 13394 | 1488 | 0 | 14932 | 0 | NHPP |  | 50 | 50 | 400 | 400 | 200 | 889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12943 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | N OR 270 E | 6I3580 | 4.862 | 11.037 | 0 | Y | 7171V-22 | Pavement resurfacing from Rte. 367 to west of Rte. H (Riverview Drive), South Outer Road 270 from 0.1 mile west of Rafterty Lane to Rafterty Lane, 0.3 mile west to 0.5 mile east of Lilac Avenue, and on Rte. H (Riverview Drive) from 0.5 mile north of I-270 to I-270. | Federal | 2306 | 577 | 0 | 3125 | 0 | NHPP | SL0021B | 242 | 10 | 10 | 229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2634 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | N OR 270 E | SL0169 | 7.655 | 16.456 | 0 | Y | 7321W-24 | Pavement resurfacing and pavement repairs on various outer roads from Rte. 340 (Olive Boulevard) to I-55. | Adv. CN | 3521 | 880 | 0 | 4601 | 0 | AC-STBG |  | 200 | 25 | 20 | 269 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4087 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | MO 340 E | SL0151 | 3.826 | 19.726 | 0 | Y | 7321H-24 | Pavement resurfacing, upgrade signals, guardrail, and ITS equipment from Lea Oak Drive to Rte. 100 (Manchester Road). | Federal | 7270 | 1817 | 0 | 9427 | 0 | NHPP |  | 340 | 864 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8223 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | MO 340 E | SL0181 | 0.341 | 1.96 | 0 | Y | 7324A-24 | Payment to Olivette for intersection improvements at Dielman Industrial Drive and Price Road. $631,500 Cost Share funds. | Federal | 158 | 39 | 0 | 647 | 0 | NHPP |  | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 442 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | MO 364 E | SL0030 | 0.88 | 6.88 | 2 | Y | 7228F-23 | Bridge rehabilitation at Page Avenue over I-270. Project involves twin bridges A1243. | Federal | 8486 | 2121 | 0 | 11127 | 0 | NHPP |  | 520 | 5 | 5 | 5 | 627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | MO 367 S | SL0117 | 3.264 | 15.307 | 2 | Y | 7265D-23 | Pavement resurfacing, add median island, sidewalk, and drainage from I-270 to Longridge Drive. Project involves bridges A6636 and A6751. | Federal | 11017 | 1224 | 0 | 13120 | 0 | SAFETY |  | 879 | 2021 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 10200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | MO 370 E | 6P3615 | 0.146 | 0.9 | 5 | Y | 7217K-22 | Bridge rehabilitation over Cowmire Creek, Ferguson Lane, and Missouri Bottom Road. Project involves bridges A4886, A4895, A4896, and A5006. | Federal | 5389 | 1347 | 0 | 7032 | 0 | NHPP |  | 296 | 25 | 100 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 44 E | 6S3443 | 1.184 | 3.795 | 19 | Y | 6991T-20 | Bridge replacement at various locations from Rte. 67 to Nebraska Ave. and bridge rehabilitation at Edwards Street. Potential Design-Build. Project involves bridges A1715, A1720, A1721, A1723, A1725, A1726, A1728, A1729, A1730, A1732, A1736, A2092, A2257, A2322 and A3263. | Federal | 65089 | 7232 | 0 | 75732 | 0 | NHPP |  | 3411 | 100 | 100 | 925 | 4274 | 0 | 0 | 0 | 0 | 265 | 0 | 0 | 0 | 0 | 0 | 0 | 66657 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 44 E | SL0054 | 0.238 | 0.829 | 6 | Y | 7229D-23 | Bridge rehabilitation at Central Avenue, Lewis Road, Antire Road, Maritz Street, Bowles Avenue, and Mraz Lane. Potential Design-Build project. Project involves bridges A1797, A3638, A3856, A3996, A4288, and L0761. | Federal | 10463 | 1162 | 0 | 13075 | 0 | NHPP |  | 1450 | 200 | 200 | 200 | 745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 44 E | SL0277 | 0.181 | 1.112 | 8 | Y | 7394Q-26 | Bridge rehabilitation over Fox Creek, Rte. 109, Williams Creek, Rte. 141, culvert rehabilitation 0.5 mile east of Lone Elk Park, and 0.6 mile west of Rte. 141. Project involves bridge A0775, A4285, J0255, L0704, L0932, and culverts L0705 and J0254. | Federal | 16011 | 1779 | 0 | 18790 | 0 | NHPP | ST0117 | 1000 | 1370 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 44 E | SL0323 | 1.635 | 13.529 | 0 | Y | 7564S-27 | High friction surface treatment and add signage from Rte. 67 (Lindbergh Boulevard) to Sappington Road. | Federal | 1411 | 157 | 0 | 1568 | 0 | SAFETY |  | 0 | 40 | 40 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1379 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 44 W | SL0194B | 0.967 | 5.057 | 7 | Y | 7322X-25 | Bridge washing over the Meramec River on I-44, Rte. 30, and Rte. 231. Project involves bridges A1796, A2014, A4932, A8231, A8683, and L0611. | Federal | 517 | 57 | 0 | 584 | 0 | NHPP | SL0194 | 10 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 495 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | US 50 E | SL0136 | 0.148 | 0.148 | 1 | Y | 7320Y-24 | Bridge replacement over I-255. Project involves bridge A1316. | Federal | 4231 | 1058 | 0 | 5609 | 0 | NHPP |  | 320 | 100 | 100 | 75 | 25 | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 55 N | 6I3565 | 0.437 | 3.832 | 9 | Y | 7171O-22 | Bridge painting over 2nd Street, Union Pacific Railroad, River Des Peres, Green Park Road, and Gravois Creek. Project involves bridges A0591, A0607, A1057, A1076, A1085, and A1276. | Federal | 7993 | 888 | 0 | 9037 | 0 | NHPP |  | 156 | 70 | 559 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 55 S | SL0196 | 0.279 | 2.859 | 2 | Y | 7322Z-25 | Bridge rehabilitation over the Meramec River. Project involves bridge A0609. | Federal | 8713 | 968 | 0 | 9691 | 0 | NHPP |  | 10 | 20 | 30 | 20 | 587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 64 E | SL0137 | 9.13 | 53.66 | 0 | Y | 7320Z-24 | Pavement resurfacing and upgrade guardrail from Rte. 94 to Rte. 340. | Federal | 6262 | 696 | 0 | 7078 | 0 | NHPP |  | 120 | 75 | 75 | 100 | 200 | 402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 64 E | SL0138 | 7.612 | 63.553 | 0 | Y | 7321A-24 | Pavement resurfacing and median barrier replacement from Rte. 340 to 0.3 mile east of Spoede Road. | Federal | 10430 | 1159 | 0 | 11989 | 0 | NHPP | SL0168 SL0168B | 400 | 791 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | N OR 64 E | SL0168 | 4.775 | 10.61 | 0 | Y | 7321V-24 | Pavement resurfacing, replace guardrail, and signage from Mason Road to Conway Road, on South Outer Road 64 from Mason Road to Jennifer Lane, and from Clayton Road to Rolling Rock Lane. | Adv. CN | 2199 | 550 | 0 | 2849 | 0 | AC-STBG | SL0138 SL0168B | 100 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | N OR 64 E | SL0168B | 1.641 | 3.4 | 0 | Y | 7564T-27 | Pavement resurfacing and replace signage from west of Marsally Drive to Spoede Road, and on South Outer Road 64 from 0.3 mile west of Carole Lane to Spoede Road. | Federal | 0 | 546 | 0 | 546 | 0 | STATE | SL0138 SL0168 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 483 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | US 67 S | SL0233 | 9.152 | 50.489 | 0 | Y | 7360E-25 | Signal optimization from Old James Town Road to Missouri Bottom Road and Blake Drive to Old St. Charles Road. $2,801,437 Congestion Mitigation and Air Quality Improvement Program funds. | Federal | 2611 | 653 | 0 | 3502 | 0 | CMAQ |  | 238 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3064 | 0 | 0 | 0 | 0 | 206 | 2595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 70 E | 6I3617 | 1.911 | 13.466 | 0 | Y | 7171Y-22 | Upgrade lighting at the I-270 interchange. | Federal | 5004 | 556 | 0 | 5921 | 0 | SAFETY | 6I3654 | 361 | 5 | 10 | 338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5207 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 70 E | 6I3654 | 0.2 | 1.203 | 1 | Y | 7216J-22 | Bridge replacement over I-270. Project involves bridge A0093. | Federal | 14835 | 1648 | 0 | 17618 | 0 | NHFP | 6I3617 | 1135 | 1 | 1 | 996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 70 E | 6I3660B | 2.77 | 17.896 | 0 | Y | 7564V-27 | Modify interchange configuration from Rte. 67 (Lindbergh Boulevard) to Rte. 115 (Natural Bridge Road) (Partial). Potential Design-Build project. | Federal | 44016 | 4891 | 0 | 48907 | 0 | NHPP |  | 0 | 1500 | 1500 | 3494 | 0 | 0 | 0 | 0 | 773 | 0 | 0 | 0 | 0 | 0 | 0 | 41640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 70 E | SL0058 | 6.971 | 57.359 | 25 | Y | 7229G-23 | Corridor improvements from the Missouri River to Rte. 67. Potential Design-Build project. Project involves various bridges. | Federal | 46724 | 5192 | 0 | 57466 | 0 | NHPP |  | 5550 | 25 | 20 | 3155 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 48695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 70 E | SL0216 | 18.778 | 96.382 | 0 | Y | 7372U-25 | Pavement repair on I-70, I-270, I-255, Salt Mill Road in St. Louis County, Rte. 61 in Jefferson County, and North Outer Road 70 in St. Louis City. | Adv. CN | 1342 | 336 | 0 | 1680 | 0 | AC-STBG |  | 2 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 70 E | SL0256 | 11.681 | 80.09 | 0 | Y | 7395A-26 | Pavement preservation treatment from Fee Fee Road to Springdale Avenue and on I-270 form 0.6 mile west of Rte. 67 to Rte. 367. | Adv. CN | 761 | 190 | 0 | 952 | 0 | AC-STBG |  | 1 | 5 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | IS 70 E | SL0320 | 13.149 | 60.073 | 0 | Y | 7564P-27 | Pavement resurfacing, upgrade median barrier, and guardrail from 0.2 mile west of Goodfellow Boulevard to Biddle Street. | Federal | 25284 | 2809 | 0 | 28093 | 0 | NHPP | SL0320B | 0 | 200 | 550 | 275 | 1929 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | S OR 70 E | SL0249 | 1.31 | 3.076 | 0 | Y | 7394P-26 | Pavement resurfacing, replace signage, upgrade lighting, and guardrail from 0.2 mile west of Airflight Drive to Rte. 115 (Natural Bridge Road). | Federal | 1438 | 359 | 0 | 1897 | 0 | NHPP | SL0172 | 100 | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | RT AC S | 6S3648 | 3.295 | 16.9 | 0 | Y | 7220K-22 | Pavement resurfacing and repair pedestrian facilities from Lindbergh Boulevard to 0.1 mile south of I-270. $30,000 Strategic Highway Research Program funds. | Federal | 9499 | 2375 | 0 | 13004 | 0 | NHPP | SL0247 | 1130 | 1420 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 10404 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | RT AC S | SL0247 | 0.228 | 1.203 | 0 | Y | 7394O-26 | Upgrade signals at Leisurewood Court, Hambletonian Drive, Parker Road, Pohlman Road, West Florissant Avenue, and Netherton Drive. $745,000 Open Container funds. | Federal | 1598 | 178 | 0 | 1926 | 0 | SAFETY | 6S3648 | 150 | 253 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | RT D E | SL0027 | 3.191 | 16.66 | 0 | Y | 7228C-23 | Pavement resurfacing and replace signage from Rte. 67 (Lindbergh Boulevard) to 0.1 mile east of I-170. | Federal | 3537 | 884 | 0 | 4591 | 0 | NHPP |  | 170 | 518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | RT D E | SL0232 | 7.643 | 39.499 | 0 | Y | 7360D-25 | Signal optimization from Schuetz Road to Ogden Avenue. $2,169,690 Congestion Mitigation and Air Quality Improvement Program funds. | Federal | 2026 | 506 | 0 | 2712 | 0 | CMAQ |  | 180 | 159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2373 | 0 | 0 | 0 | 0 | 160 | 2010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | CST FROST AVE E | SL0243 | 0.112 | 0.516 | 0 | Y | 7394N-26 | Pavement resurfacing, replace signals, upgrade pedestrian facilities on Frost Avenue, and Airport Road under I-170. | Adv. CN | 1373 | 343 | 0 | 1754 | 0 | AC-STBG |  | 38 | 70 | 227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | RP IS270E TO IS70W W | SL0086 | 0.055 | 0.372 | 2 | Y | 7230C-23 | Bridge replacement at the I-270 and I-70 interchange. Project involves bridges A3764 and A3766. | Federal | 39914 | 9979 | 0 | 52223 | 0 | NHPP |  | 2330 | 130 | 90 | 3027 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | RP IS270W TO IS170E E | SL0264 | 2.729 | 8.401 | 18 | Y | 7394A-26 | Bridge washing on I-270, I-70, I-170, I-55, I-44, I-64, Rte. 100, Rte. 141, and Rte. 370. Project involves bridge A2926, A3764, A3766, A4650, A4651, A4652, A4653, A4881, A4882, A5093, A5411, A5412, A5682, A6370, A6371, A8013, A8014, and A8375. | Federal | 1050 | 262 | 0 | 1317 | 0 | NHPP |  | 5 | 10 | 10 | 50 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | RP IS64E TO IS170W W | 6I3634 | 0.237 | 0.508 | 2 | Y | 7216C-22 | Bridge rehabilitation on ramps between I-170 and I-64. Project involves bridges A8013 and A8014. | Federal | 1091 | 273 | 0 | 1701 | 0 | NHPP | 6I3567 | 337 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | RP IS64W TO LONG RD S | SL0070 | 0.066 | 0.066 | 1 | Y | 7229Q-23 | Bridge replacement over I-64. Project involves bridge A2170. | Federal | 3406 | 852 | 0 | 4438 | 0 | NHPP |  | 180 | 50 | 20 | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | RP MO141S TO IS44E E | SL0209 | 1.136 | 3.253 | 7 | Y | 7372Q-25 | Bridge deck sealing at various locations in the St. Louis District on Rte. 141, Outer Road 44, Rte. 231, I-64, Rte. 61, TR Hughes Boulevard, and Lake St. Louis Boulevard. Project involves bridges A8375, A7577, A4932, A8501, A6157, A7043, and H0141. | Adv. CN | 1026 | 256 | 0 | 1307 | 0 | AC-STBG |  | 25 | 129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | RT N S | SL0327 | 0.173 | 1.014 | 0 | Y | 7564W-27 | Replace signals at I-70. | Adv. CN | 563 | 141 | 0 | 704 | 0 | AC-STBG |  | 0 | 20 | 20 | 5 | 5 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | CST NORTH HANLEY RD S | SL0023 | 0.079 | 0.359 | 1 | Y | 7227Y-23 | Bridge rehabilitation over I-70. Project involves bridge A6175. | Federal | 938 | 235 | 0 | 1258 | 0 | NHPP | SL0278 | 85 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1052 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | CST NORTH HANLEY RD S | SL0278 | 0.079 | 0.359 | 0 | Y | 7394L-26 | Pavement resurfacing, upgrade pedestrian facilities, and replace signals at I-70. | Federal | 582 | 146 | 0 | 798 | 0 | NHPP | SL0023 | 70 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 607 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | RP RTNS TO IS70E E | SL0329 | 0.2 | 0.728 | 0 | Y | 7564X-27 | Pavement repairs, replace lighting, and add guardrail east of Rte. N. | Federal | 192 | 48 | 0 | 240 | 0 | NHPP |  | 0 | 22 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | RT U S | 6S3655 | 2.29 | 10.642 | 0 | Y | 7216P-22 | Pavement resurfacing and upgrade pedestrian facilities from West Florissant Avenue to Woodrow Avenue. | Federal | 5562 | 1390 | 0 | 7682 | 0 | NHPP |  | 730 | 75 | 450 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 6377 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS | CST WEST PORT PLAZA DR N | SL0141 | 0.037 | 0.148 | 1 | Y | 7321D-24 | Bridge rehabilitation over Rte. D. Project involves bridge A3547. | Adv. CN | 4228 | 1057 | 0 | 5455 | 0 | AC-STBG |  | 170 | 50 | 100 | 45 | 23 | 424 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | MO 100 E | SL0252 | 6.519 | 33.359 | 0 | Y | 7395F-26 | Upgrade signals from McCausland Avenue to 4th Street. | Adv. CN | 1097 | 274 | 0 | 1546 | 0 | AC-STBG |  | 175 | 25 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | MO 115 N | SL0124 | 4.181 | 20.571 | 0 | Y | 7320R-24 | Pavement resurfacing and safety improvements from east of Dardenne Road to Salisbury Street. | Federal | 6655 | 1664 | 0 | 8669 | 0 | NHPP |  | 350 | 200 | 150 | 531 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7438 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | CST 11TH ST S | SL0286 | 0.625 | 1.256 | 2 | Y | 7394Y-26 | Pavement resurfacing, upgrade signals, signage, lighting, sidewalk from 0.1 mile north of Rte. 115 to Destrehan Street, upgrade striping on Rte. 115, and replace fencing over I-70. Project involves bridges A6238 and A6239. | Federal | 2798 | 699 | 0 | 3697 | 0 | NHPP |  | 200 | 50 | 25 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | IS 270 W | SL0316 | 0.516 | 2.217 | 2 | Y | 7564N-27 | Payment to IDOT for bridge painting over the Mississippi River. Project involves bridges A9300 and A8000. | Federal | 2701 | 300 | 0 | 3001 | 0 | NHPP |  | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | MO 30 E | SL0192 | 6.009 | 41.625 | 0 | Y | 7322U-25 | Pavement resurfacing, safety, and intersection improvements from St. Louis City limits to Emmet Street. | Federal | 12093 | 1344 | 0 | 13842 | 0 | SAFETY |  | 405 | 550 | 595 | 1263 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | MO 366 E | SL0126 | 5.06 | 21.373 | 0 | Y | 7320S-24 | Pavement resurfacing from Creighton Drive to Broadway Street. | Federal | 3941 | 985 | 0 | 5176 | 0 | NHPP |  | 250 | 100 | 100 | 334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | IS 44 E | SL0195 | 3.591 | 22.845 | 8 | Y | 7322Y-25 | Bridge washing from north of Biddle St. to Washington Ave, Gratiot St. to Park Ave, on I-64 Clayton Ave. to west of Compton Ave, 21st St. to 1st St., and on Rte. H I-70 to west of Hall St. Project involves bridges A1501, A1516, A3162, A3594, A7165, L0361, and L0815. | Federal | 1365 | 152 | 0 | 1527 | 0 | NHPP |  | 10 | 5 | 5 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | IS 44 E | SL0205 | 0.583 | 5.143 | 2 | Y | 7372E-25 | Bridge preventative maintenance north of Gratiot Street to Park Avenue. Project involves bridges A3162 and L0361. | Federal | 1137 | 126 | 0 | 1298 | 0 | NHPP | SL0205B | 35 | 40 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | IS 44 E | SL0263 | 0.488 | 2.847 | 1 | Y | 7395E-26 | Bridge rehabilitation from north of Biddle Street to Washington Avenue. Project involves bridge L0815. | Federal | 41979 | 4664 | 0 | 46743 | 0 | NHPP |  | 100 | 1000 | 1000 | 2000 | 2614 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40029 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | IS 44 W | SL0262 | 0.583 | 5.143 | 2 | Y | 7395K-26 | Bridge painting from Gratiot Street to Park Avenue. Project involves bridge A3162 and L0361. | Federal | 45162 | 5018 | 0 | 50230 | 0 | NHPP |  | 50 | 1000 | 1000 | 1000 | 3023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | IS 55 S | SL0205B | 0.209 | 1.672 | 1 | Y | 7395H-26 | Bridge preventative maintenance over the Mississippi River. Project involves bridge A1500. $281,520 IDOT funds. | Federal | 388 | 0 | 281 | 709 | 0 | NHPP | SL0205 | 40 | 45 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 | 0 | 0 | 0 | 0 | 281 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | IS 64 E | 6I3441 | 0.85 | 5.096 | 3 | Y | 6991P-20 | Bridge rehabilitation over Vandeventer Avenue ramp to westbound I-64, Sarah Street, upgrade median barrier, drainage, and lighting from Sarah Street to 0.1 west of Grand Boulevard. Project involves bridges A3651, A3893, and L0669. | Federal | 8293 | 921 | 0 | 9301 | 0 | NHPP | 6I3502 6I3503 6I3574 SL0087 | 87 | 620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8594 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | IS 64 E | 6I3502 | 0.571 | 1.721 | 1 | Y | 6991Q-20 | Bridge replacement over Vandeventer Avenue and Clayton Avenue. Project involves bridge L0667. | Federal | 50665 | 5629 | 0 | 64075 | 0 | NHPP | 6I3441 6I3503 6I3574 SL0087 | 6761 | 4191 | 0 | 0 | 0 | 0 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 52103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | IS 64 E | SL0087 | 1.629 | 6.312 | 4 | Y | 7230D-23 | Bridge replacement at Market St., modify interchange configuration at Grand Blvd. and Forest Park Ave., add roundabout at Bernard St. and Spruce St. and add bicycle/pedestrian trails from Grand Blvd. to Compton Ave. Project involves bridge A0549, A3636, A0835, and A0832. | Federal | 28193 | 3133 | 0 | 35126 | 0 | NHPP | 6I3441 6I3502 6I3503 6I3574 | 3800 | 2439 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 27887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | IS 64 E | SL0129 | 3.221 | 25.465 | 0 | Y | 7320T-24 | Pavement preservation treatment and repairs from McCausland Avenue to Sarah Street. | Federal | 801 | 89 | 0 | 893 | 0 | NHPP |  | 3 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 768 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | IS 64 W | 6I3574 | 1.049 | 3.263 | 1 | Y | 7171S-22 | Bridge rehabilitation from west of Compton Avenue to west of Clayton Avenue. Project involves bridge A3594. | Federal | 31854 | 3539 | 0 | 39119 | 0 | NHPP | 6I3441 6I3502 6I3503 SL0087 | 3726 | 2282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | IS 70 E | SL0084 | 0.527 | 2.261 | 1 | Y | 7230A-23 | Bridge rehabilitation on the Stan Musial Veterans Memorial Bridge over the Mississippi River. Project involves bridge A6500. $8,045,000 IDOT funds. | Federal | 9606 | 0 | 8045 | 17804 | 0 | NHPP |  | 153 | 1050 | 1058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15543 | 0 | 0 | 0 | 0 | 500 | 7545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | IS 70 E | SL0318 | 1.007 | 5.473 | 4 | Y | 7564R-27 | Bridge washing on I-70, I-55, and I-255 over the Mississippi River. Project involves bridges A1500, A1850, A4936, and A6500. | Federal | 1087 | 121 | 0 | 1208 | 0 | NHPP |  | 0 | 5 | 5 | 5 | 5 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | N OR 70 W | SL0320B | 0.264 | 3.046 | 0 | Y | 7564Q-27 | Pavement resurfacing, replace guardrail, signage from Rte. 367 to Kingshighway Boulevard, and on South Outer Road 70 from east of Union Boulevard to Kingshighway Boulevard. | Adv. CN | 441 | 110 | 0 | 551 | 0 | AC-STBG | SL0320 | 0 | 10 | 10 | 20 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | CST DR MARTIN LUTHER KING BRG E | SL0189 | 0.538 | 1.775 | 2 | Y | 7322S-26 | Payment to IDOT to add navigation lighting on the Martin Luther King Bridge and Clark Bridge over the Mississippi River. Project involves bridges A4278 and A4856. | Federal | 257 | 64 | 0 | 321 | 0 | NHPP |  | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | RP GRAND BLVD TO IS64W W | 6I3503 | 0 | 0.15 | 1 | Y | 6991R-20 | Bridge rehabilitation at I-64. Project involves bridge A3740. | Federal | 776 | 194 | 0 | 1177 | 0 | NHPP | 6I3441 6I3502 6I3574 SL0087 | 207 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 903 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | RT H S | SL0065 | 3.545 | 9.358 | 0 | Y | 7229M-23 | Pavement resurfacing, modify lighting from I-270 to Hall Street, and replace signal at St. Louis Riverfront Trail. | Federal | 2508 | 627 | 0 | 3239 | 0 | NHPP |  | 104 | 248 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | CST WEBER RD E | 6S3442 | 0.132 | 0.627 | 3 | Y | 6991U-20 | Bridge replacement on Weber Road, Loughborough Avenue over I-55, ramp realignment on northbound I-55 ramp to Idaho Avenue, and on ramp at Loughborough Avenue. Project involves bridges A0918 and A1077. | Federal | 13219 | 3305 | 0 | 17569 | 0 | NHPP |  | 1045 | 10 | 1036 | 0 | 0 | 0 | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 15403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | ST. LOUIS CITY | CST WEST FLORISSANT AVE S | 6S3552 | 0.557 | 2.617 | 4 | Y | 7219H-22 | Bridge rehabilitation over Terra West Belt Railroad and I-70, Rte. 366 and Rte. 30 over the River Des Peres Drainage Channel, and Rte. 115 over Terra West Belt Railroad. Project involves bridges A0482, A3208, A7167, and A7168. | Federal | 3902 | 975 | 0 | 4942 | 0 | NHPP |  | 65 | 95 | 369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | 5B0800U | 0 | 0 | 1 | Y | 4772-08 | Payback beginning in SFY 2008 for Safe and Sound bridges in the St. Louis District. | Federal | 0 | 6550 | 0 | 27338 | 2,001 - 5,000 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 20758 | 1310 | 1310 | 1310 | 1310 | 1310
5 | VARIOUS | Various | 6P3510E |  |  | 0 | Y | 7500 | Upgrade pedestrian facilities to comply with the ADA Transition Plan throughout the St. Louis District. | Adv. CN | 6273 | 1568 | 0 | 8132 | 0 | AC-STBG |  | 291 | 691 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0096B | 0 | 0 | 0 | Y | 7265P-23 | Emergency response operations and staffing in the St. Louis District. | Federal | 0 | 2856 | 0 | 2860 | 0 | STATE |  | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0096C | 0 | 0 | 0 | Y | 7265Q-23 | ITS operations, MoDOT staff, equipment maintenance, and operations at the Traffic Management Center building in the St. Louis District. | Federal | 0 | 933 | 0 | 937 | 0 | STATE |  | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 932 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0096D | 0 | 0 | 0 | Y | 7265R-23 | ITS operations, contract staffing, and professional services at the Traffic Management Center building in the St. Louis District. | Adv. CN | 3610 | 903 | 0 | 4517 | 0 | AC-STBG |  | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0096E | 0 | 0 | 0 | Y | 7265S-23 | ITS asset management and operations at various locations in the St. Louis District. | Federal | 0 | 2524 | 0 | 2528 | 0 | STATE |  | 4 | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0096F | 0 | 0 | 0 | Y | 7265T-23 | ITS system preservation, repairs, and upgrades throughout the St. Louis District. | Federal | 0 | 2339 | 0 | 2343 | 0 | STATE |  | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2338 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0096G | 0 | 0 | 0 | Y | 7265U-23 | Advanced Traffic Management System maintenance contract throughout the St. Louis District. | Federal | 0 | 601 | 0 | 605 | 0 | STATE |  | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0096H | 0 | 0 | 0 | Y | 7265V-23 | ITS network support throughout the St. Louis District. | Adv. CN | 441 | 110 | 0 | 555 | 0 | AC-STBG |  | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0098 | 0 | 0 | 1 | Y | 7265W-23 | Job Order Contracting for bridge repairs at various locations in the St. Louis District. | Adv. CN | 1884 | 471 | 0 | 2359 | 0 | AC-STBG |  | 4 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0102 | 0 | 0 | 0 | Y | 7265X-23 | Job Order Contracting for guardrail repair at various locations in St. Louis City and St. Louis County. | Adv. CN | 3767 | 942 | 0 | 4713 | 0 | AC-STBG |  | 4 | 309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0191 | 0 | 0 | 0 | Y | 7322J-25 | On-call work zone enforcement at various locations in the St. Louis District. | Federal | 1216 | 135 | 0 | 1353 | 0 | SAFETY |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0204 |  |  | 0 | Y | 7372D-25 | Replace ITS dynamic message signs and communications equipment at various locations in the St. Louis District. | Federal | 1917 | 479 | 0 | 2406 | 0 | NHPP |  | 10 | 332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0219B |  |  | 0 | Y | 7372X-25 | Emergency response operations and staffing in the St. Louis District. | Federal | 0 | 3005 | 0 | 3007 | 0 | STATE |  | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3003 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0219C |  |  | 0 | Y | 7372Y-25 | ITS operations, MoDOT staff, equipment maintenance, and operations at the Traffic Management Center building in the St. Louis District. | Federal | 0 | 992 | 0 | 994 | 0 | STATE |  | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0219D |  |  | 0 | Y | 7372Z-25 | ITS operations, contract staffing, and professional services at the Traffic Management Center building in the St. Louis District. | Adv. CN | 3796 | 949 | 0 | 4747 | 0 | AC-STBG |  | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0219E |  |  | 0 | Y | 7373A-25 | ITS asset management and operations at various locations in the St. Louis District. | Federal | 0 | 2550 | 0 | 2552 | 0 | STATE |  | 2 | 1 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2415 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0219F |  |  | 0 | Y | 7373B-25 | ITS system preservation, repairs, and upgrades throughout the St. Louis District. | Federal | 0 | 2231 | 0 | 2233 | 0 | STATE |  | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2229 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0219G |  |  | 0 | Y | 7373C-25 | Advanced Traffic Management System maintenance contract throughout the St. Louis District. | Federal | 0 | 662 | 0 | 664 | 0 | STATE |  | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0219H |  |  | 0 | Y | 7373D-25 | ITS network support throughout the St. Louis District. | Adv. CN | 466 | 116 | 0 | 584 | 0 | AC-STBG |  | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0220B |  |  | 0 | Y | 7373E-25 | Emergency response operations and staffing in the St. Louis District. | Federal | 0 | 3161 | 0 | 3163 | 0 | STATE |  | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0220C |  |  | 0 | Y | 7373F-25 | ITS operations, MoDOT staff, equipment maintenance, and operations at the Traffic Management Center building in the St. Louis District. | Federal | 0 | 1027 | 0 | 1029 | 0 | STATE |  | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0220D |  |  | 0 | Y | 7373G-25 | ITS operations, contract staffing, and professional services at the Traffic Management Center building in the St. Louis District. | Adv. CN | 3990 | 997 | 0 | 4989 | 0 | AC-STBG |  | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4984 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0220E |  |  | 0 | Y | 7373H-25 | ITS asset management and operations at various locations in the St. Louis District. | Federal | 0 | 2624 | 0 | 2626 | 0 | STATE |  | 2 | 1 | 1 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2488 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0220F |  |  | 0 | Y | 7373I-25 | ITS system preservation, repairs, and upgrades throughout the St. Louis District. | Federal | 0 | 2349 | 0 | 2351 | 0 | STATE |  | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0220G |  |  | 0 | Y | 7373J-25 | Advanced Traffic Management System maintenance contract throughout the St. Louis District. | Federal | 0 | 663 | 0 | 665 | 0 | STATE |  | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0220H |  |  | 0 | Y | 7373K-25 | ITS network support throughout the St. Louis District. | Adv. CN | 466 | 117 | 0 | 585 | 0 | AC-STBG |  | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0255 |  |  | 0 | Y | 7395B-26 | Pavement repair at various locations in the St. Louis District. | Adv. CN | 1381 | 345 | 0 | 1727 | 0 | AC-STBG |  | 1 | 2 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1576 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0257B |  |  | 0 | Y | 7394M-26 | Emergency response operations and staffing in the St. Louis District. | Federal | 0 | 3325 | 0 | 3326 | 0 | STATE |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0257C |  |  | 0 | Y | 7394C-26 | ITS operations, MoDOT staff, equipment maintenance, and operations at the Traffic Management Center building in the St. Louis District. | Federal | 0 | 1064 | 0 | 1065 | 0 | STATE |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0257D |  |  | 0 | Y | 7394B-26 | ITS operations, contract staffing, and professional services at the Transportation Management Center in the St. Louis District. | Adv. CN | 3994 | 999 | 0 | 4994 | 0 | AC-STBG |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0257E |  |  | 0 | Y | 7394K-26 | ITS asset management maintenance and operations at various locations in the St. Louis District. | Federal | 0 | 2699 | 0 | 2700 | 0 | STATE |  | 1 | 1 | 1 | 1 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0257F |  |  | 0 | Y | 7395D-26 | ITS system preservation, repairs, and upgrades throughout the St. Louis District. | Federal | 0 | 2707 | 0 | 2708 | 0 | STATE |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0257G |  |  | 0 | Y | 7395J-26 | Advanced Traffic Management System maintenance contract throughout the St. Louis District. | Federal | 0 | 664 | 0 | 665 | 0 | STATE |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0257H |  |  | 0 | Y | 7395I-26 | ITS network support throughout the St. Louis District. | Adv. CN | 467 | 117 | 0 | 585 | 0 | AC-STBG |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0258 |  |  | 0 | Y | 7394D-26 | On-call work zone enforcement at various locations in the St. Louis District. | Federal | 1802 | 200 | 0 | 2003 | 0 | SAFETY |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0265 |  |  | 0 | Y | 7395G-26 | Safety improvements at various locations in the St. Louis District. | Federal | 4699 | 522 | 0 | 5226 | 0 | SAFETY |  | 5 | 400 | 330 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0266 |  |  | 0 | Y | 7394E-26 | Upgrade striping at various locations in the St. Louis District. | Federal | 3992 | 443 | 0 | 4445 | 0 | SAFETY |  | 10 | 25 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0270 |  |  | 0 | Y | 7394J-26 | Job Order Contracting for asphalt pavement repair at various locations in the St. Louis District. | Adv. CN | 2656 | 664 | 0 | 3330 | 0 | AC-STBG |  | 10 | 10 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3090 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0271 |  |  | 0 | Y | 7394I-26 | Job Order Contracting for concrete pavement repair at various locations in the St. Louis District. | Adv. CN | 3536 | 884 | 0 | 4430 | 0 | AC-STBG |  | 10 | 10 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0272 |  |  | 0 | Y | 7394H-26 | Job Order Contracting for fence repair at various locations in the St. Louis District. | Federal | 0 | 726 | 0 | 731 | 0 | STATE |  | 5 | 5 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0273 |  |  | 0 | Y | 7394G-26 | Job Order Contracting for guard cable repair at various locations in the St. Louis District. | Adv. CN | 888 | 222 | 0 | 1115 | 0 | AC-STBG |  | 5 | 5 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1030 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0279 |  |  | 0 | Y | 7394F-26 | Upgrade striping at various intersections in the St. Louis District. $960,000 Open Container funds. | Federal | 4150 | 461 | 0 | 4621 | 0 | SAFETY |  | 10 | 50 | 294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0283 |  |  | 0 | Y | 7394X-26 | Repair signals, flashers, signage, and lighting at various location in the St. Louis District. | Federal | 501 | 125 | 0 | 671 | 0 | NHPP |  | 45 | 40 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0301 |  |  | 1 | Y | 7563K-27 | Job Order Contracting for bridge repairs at various locations in the St. Louis District. | Adv. CN | 1993 | 498 | 0 | 2491 | 0 | AC-STBG |  | 0 | 1 | 1 | 155 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0302 |  |  | 0 | Y | 7563L-27 | Job Order Contracting for guardrail repair at various locations in St. Louis City and St. Louis County. | Adv. CN | 3983 | 996 | 0 | 4979 | 0 | AC-STBG |  | 0 | 1 | 1 | 309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0303 |  |  | 0 | Y | 7563M-27 | Job Order Contracting for guardrail repair at various locations in Franklin and Jefferson Counties. | Adv. CN | 1812 | 453 | 0 | 2265 | 0 | AC-STBG |  | 0 | 1 | 1 | 141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0306 |  |  | 0 | Y | 7563N-27 | Pavement preservation treatment at various locations in the St. Louis District. | Adv. CN | 778 | 195 | 0 | 973 | 0 | AC-STBG |  | 0 | 1 | 5 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0307 |  |  | 0 | Y | 7563P-27 | Pavement repair at various locations in the St. Louis District. | Adv. CN | 1418 | 355 | 0 | 1773 | 0 | AC-STBG |  | 0 | 1 | 1 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0309 |  |  | 0 | Y | 7563Q-27 | Upgrade striping at various locations in the St. Louis District. | Federal | 2061 | 229 | 0 | 2290 | 0 | SAFETY |  | 0 | 1 | 5 | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0310 |  |  | 0 | Y | 7563R-27 | On-call work zone enforcement at various locations in the St. Louis District. | Federal | 1803 | 200 | 0 | 2003 | 0 | SAFETY |  | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0311 |  |  | 0 | Y | 7563U-27 | Upgrade striping at various intersections in the St. Louis District. $1,556,000 Open Container funds. | Federal | 4130 | 459 | 0 | 4589 | 0 | SAFETY |  | 0 | 10 | 50 | 285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4244 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0325 |  |  | 0 | Y | 7563S-27 | Replace ITS dynamic message signs and communications equipment at various locations in the St. Louis District. | Federal | 1889 | 472 | 0 | 2361 | 0 | NHPP |  | 0 | 150 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0326 |  |  | 0 | Y | 7563T-27 | Add ITS equipment on various interstates in the St. Louis District. | Federal | 1458 | 364 | 0 | 1822 | 0 | NHPP |  | 0 | 100 | 65 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0328B |  |  | 0 | Y | 7563A-27 | Emergency response operations and staffing in the St. Louis District. | Federal | 0 | 3326 | 0 | 3326 | 0 | STATE |  | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0328C |  |  | 0 | Y | 7563B-27 | ITS operations, MoDOT staff, equipment maintenance, and operations at the Traffic Management Center building in the St. Louis District. | Federal | 0 | 1065 | 0 | 1065 | 0 | STATE |  | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0328D |  |  | 0 | Y | 7563C-27 | ITS operations, contract staffing, and professional services at the Transportation Management Center in the St. Louis District. | Adv. CN | 3995 | 999 | 0 | 4994 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0328E |  |  | 0 | Y | 7563D-27 | ITS asset management maintenance and operations at various locations in the St. Louis District. | Federal | 0 | 2777 | 0 | 2777 | 0 | STATE |  | 0 | 1 | 1 | 1 | 1 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0328F |  |  | 0 | Y | 7563F-27 | ITS system preservation, repairs, and upgrades throughout the St. Louis District. | Federal | 0 | 2708 | 0 | 2708 | 0 | STATE |  | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0328G |  |  | 0 | Y | 7563G-27 | Advanced Traffic Management System maintenance contract throughout the St. Louis District. | Federal | 0 | 665 | 0 | 665 | 0 | STATE |  | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0328H |  |  | 0 | Y | 7563H-27 | ITS network support throughout the St. Louis District. | Adv. CN | 468 | 117 | 0 | 585 | 0 | AC-STBG |  | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | VARIOUS | Various | SL0331 |  |  | 0 | Y | 7563J-27 | Upgrade lighting at various locations in the St. Louis District. | Federal | 1702 | 426 | 0 | 2128 | 0 | NHPP |  | 0 | 75 | 199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BARRY | MO 37 S | 7S2182 | 0.678 | 1.447 | 0 | N |  | Rebuild pavement and sidewalk and intersection reconfiguration on Central Ave from Cleveland Ave to Bond St and add roundabout at Broadway St in Monett. Design, right of way acquisition by Monett. $2,163,000 Cost Share, $2,786,196 Monett, and $399,826 Trans. Alt. funds. | Federal | 2614 | 0 | 2786 | 5453 | 0 | STBG |  | 53 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5349 | 0 | 0 | 0 | 0 | 0 | 3186 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BARRY | MO 39 S | SR0336 | 0.276 | 0.552 | 1 | N |  | Bridge rehabilitation over Table Rock Lake in Shell Knob. Project involves bridge A0260. | Federal | 9855 | 2464 | 0 | 12321 | 0 | NHPP |  | 2 | 50 | 50 | 570 | 1585 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BARRY | MO 39 S | SR0356 | 0.198 | 0.396 | 1 | N |  | Bridge improvement over Flat Creek. Project involves bridge K0770. | Federal | 2225 | 556 | 0 | 2791 | 0 | NHPP |  | 10 | 10 | 10 | 150 | 140 | 306 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 2154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BARRY | MO 39 S | SR0388 | 0.015 | 0.03 | 1 | N |  | Bridge replacement over Brantley Branch in Leann. Project involves bridge S0669. | Federal | 1065 | 266 | 0 | 1331 | 0 | NHPP |  | 0 | 100 | 100 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 958 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BARRY | US 60 E | SR0021 | 18.051 | 47.898 | 0 | N |  | Pavement resurfacing, add roundabout at County Road 1100, and add turn lanes at County Roads 1160, 1180, 1200, 1235, 2000, and 2210 from Rte. 37 in Monett to Rte. 14 in Marionville. | Federal | 10471 | 2618 | 0 | 15125 | 0 | NHPP |  | 1671 | 2333 | 0 | 0 | 0 | 0 | 365 | 0 | 0 | 0 | 0 | 0 | 0 | 10756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BARRY | MO 86 E | SR0120 | 0.128 | 0.256 | 1 | N |  | Bridge rehabilitation over Table Rock Lake. Project involves bridge A0581. | Federal | 3023 | 756 | 0 | 4339 | 0 | NHPP |  | 560 | 330 | 296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BARRY | MO 86 E | SR0343 | 0.259 | 0.518 | 1 | N |  | Bridge replacement over Table Rock Lake near Chain-o-Lakes. Project involves bridge A0581. | Federal | 49918 | 12479 | 0 | 62597 | 0 | NHPP |  | 200 | 1000 | 1000 | 1000 | 4654 | 9325 | 0 | 0 | 0 | 0 | 1386 | 0 | 0 | 0 | 0 | 0 | 0 | 44032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BARRY | MO 97 S | SR0133 | 0.099 | 0.198 | 1 | N |  | Bridge replacement over Capps Creek 0.2 mile south of County Road 2040. Project involves bridge L0573. | Federal | 1364 | 341 | 0 | 2554 | 0 | NHPP |  | 849 | 154 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 1544 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BARRY | RT BB E | 7S3493 | 5.754 | 11.508 | 0 | N |  | Pavement resurfacing from Rte. 37 to County Road 2060. | Adv. CN | 506 | 126 | 0 | 660 | 0 | AC-STBG | 7S3390 7S3494 SR0019 SR0022 | 28 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 565 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BARTON | US 160 E | SR0002 | 0.059 | 0.118 | 1 | N |  | Bridge replacement over North Fork Spring River north of Golden City. Project involves bridge H0901. | Federal | 2270 | 567 | 0 | 3273 | 0 | NHPP |  | 436 | 410 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BARTON | MO 43 S | SR0284 | 0.082 | 0.164 | 3 | N |  | Bridge rehabilitation and guardrail over BNSF Railway, East Fork of Dry Wood Creek, and South Fork of Little North Fork. Project involves bridges A2533, A2870, and A2936. | Federal | 1617 | 404 | 0 | 2141 | 0 | NHPP |  | 120 | 301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1720 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BARTON | IS 49 S | 7I3426 | 0.046 | 0.092 | 1 | N |  | Bridge improvement on the southbound lanes over the North Fork Spring River. Project involves bridge G0578. | Federal | 4170 | 463 | 0 | 4903 | 0 | NHPP |  | 270 | 350 | 605 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BARTON | IS 49 S | SR0245 | 30.591 | 134.93 | 11 | N |  | Pavement improvements from 3.7 miles north of Rte. 160 on northbound lanes and from Rte. 160 on southbound lanes near Lamar to I-44 in Fidelity. Project involves bridges A2022, A3401, A3404, A3562, A3565, A4029, A4495, A4928, A4929, and B0565. | Federal | 21388 | 2376 | 0 | 24047 | 0 | NHPP | SR0252 | 283 | 410 | 2212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BARTON | IS 49 S | SR0464 | 0.038 | 0.152 | 2 | N |  | Bridge rehabilitation over Rte. 160 in Lamar. Project involves twin bridges A2700. | Federal | 3803 | 423 | 0 | 4226 | 0 | NHPP |  | 0 | 100 | 134 | 549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3443 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BARTON | RT V E | SR0096 | 0.702 | 1.404 | 1 | N |  | Bridge replacement and road realignment over Little Dry Wood Creek 4.4 miles west of I-49. Project involves bridge P0343. | Federal | 2979 | 745 | 0 | 3954 | 0 | NHPP |  | 230 | 269 | 486 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 2954 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BATES | MO 18 E | SR0308 | 14.137 | 28.274 | 0 | N |  | Pavement resurfacing from Rte. Y near Merwin to I-49 in Adrian. | Adv. CN | 1238 | 310 | 0 | 1560 | 0 | AC-STBG | SR0159 SR0309 | 12 | 188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BATES | IS 49 S | SR0428 | 0.03 | 0.06 | 1 | N |  | Bridge improvement on southbound bridge over Muddy Creek. Project involves bridge H0400. | Federal | 2532 | 281 | 0 | 2813 | 0 | NHPP |  | 0 | 30 | 300 | 358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BATES | IS 49 S | SR0458 | 44.817 | 182.924 | 0 | N |  | Job Order Contracting for pavement repair from the Cass County line to Rte. 54 in Vernon County. | Adv. CN | 97 | 11 | 0 | 108 | 0 | AC-NHPP |  | 0 | 8 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BATES | LP 49 S | SR0309 | 4.53 | 9.06 | 0 | N |  | Pavement resurfacing and new shoulders with rumble stripes from Rte. F in Passaic to Rte. 52 in Butler. | Adv. CN | 1058 | 265 | 0 | 1338 | 0 | AC-STBG | SR0159 SR0308 | 15 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BATES | MO 52 E | SR0081 | 0.095 | 0.19 | 1 | N |  | Replace railroad underpass and add sidewalk on Fort Scott Street in Butler. Project involves bridge RB00701. | Adv. CN | 9440 | 2360 | 0 | 12606 | 0 | AC-STBG | SR0453 | 806 | 42 | 42 | 869 | 0 | 0 | 0 | 0 | 829 | 0 | 0 | 0 | 0 | 0 | 0 | 10018 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BATES | MO 52 E | SR0159 | 1.849 | 3.967 | 0 | N |  | Pavement resurfacing and upgrade signal from I-49 north interchange to I-49 south interchange in Butler. | Adv. CN | 626 | 157 | 0 | 795 | 0 | AC-STBG | SR0308 SR0309 | 12 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 694 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BATES | MO 52 E | SR0453 | 0.074 | 0.148 | 0 | N |  | Intersection improvement and replace signal at Fort Scott Street and Loop 49 (Orange Street) in Butler. | Federal | 1651 | 413 | 0 | 2064 | 0 | STBG | SR0081 | 0 | 100 | 100 | 362 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BENTON | US 65 N | SR0109 | 0.146 | 0.422 | 0 | N |  | Add roundabout at Rte. 7 south junction. | Federal | 8080 | 2020 | 0 | 10388 | 0 | NHPP | ST0093 | 288 | 2017 | 0 | 0 | 0 | 0 | 0 | 561 | 0 | 0 | 0 | 0 | 0 | 7522 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BENTON | US 65 S | SR0286 | 15.463 | 64.135 | 0 | N |  | Pavement improvement southbound from 1.5 miles north of Rte. HH to Osage River in Warsaw and northbound from Osage River to 2.5 miles north of Rte. HH. | Federal | 5404 | 1351 | 0 | 6775 | 0 | NHPP |  | 20 | 10 | 10 | 10 | 130 | 548 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BENTON | MO 7 S | SR0318 | 1.971 | 3.942 | 3 | N |  | Bridge rehabilitation over Truman Lake near Warsaw, Long Shoal, and south of Whitakerville. Project involves bridges A3464, A3465, and A3689. | Federal | 5548 | 1387 | 0 | 6955 | 0 | NHPP |  | 20 | 10 | 291 | 806 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BENTON | RT AA E | SR0378 | 0.03 | 0.06 | 1 | N |  | Bridge improvement over Turkey Creek. Project involves bridge N0323. | Federal | 1974 | 494 | 0 | 2528 | 0 | NHPP |  | 60 | 120 | 136 | 326 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1884 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BENTON | RT KK S | SR0108 | 20.648 | 41.296 | 0 | N |  | Pavement resurfacing and add rumble stripes from Rte. 7 to end of route and on Rte. Z from Rte. 13 to Rte. 7. | Adv. CN | 3498 | 875 | 0 | 4488 | 0 | AC-STBG |  | 115 | 461 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3912 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BENTON | RT P E | SR0111 | 9.659 | 19.318 | 0 | N |  | Pavement resurfacing from Rte. ZZ to Rte. 65 and Main Street from 1st Street to 3rd Street in Ionia, and Rte. F from Rte. 52 to end of state maintenance. | Adv. CN | 871 | 218 | 0 | 1114 | 0 | AC-STBG |  | 25 | 2 | 2 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BENTON | RT T N | SR0108B | 9.181 | 18.362 | 1 | N |  | Pavement resurfacing and add rumble stripes from Rte. C to Rte. 65. Project involves bridge A3692. | Adv. CN | 2140 | 535 | 0 | 2713 | 0 | AC-STBG |  | 38 | 2 | 2 | 2 | 58 | 211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | BENTON | RT U S | SR0111B | 5.919 | 11.838 | 0 | N |  | Pavement resurfacing from Whiteman Road to Rte. 52 in Cole Camp. | Adv. CN | 519 | 130 | 0 | 649 | 0 | AC-STBG | SR0090 SR0313 | 0 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 568 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CEDAR | MO 215 N | SR0381 | 0.797 | 1.594 | 1 | N |  | Bridge painting over Stockton Lake. Project involves bridge A2074. | Federal | 8626 | 2156 | 0 | 10782 | 0 | NHPP |  | 0 | 10 | 10 | 10 | 60 | 624 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CEDAR | MO 32 E | SR0059 | 1.555 | 3.11 | 1 | N |  | Road realignment at Rte. CC, County Road 1350, and 2.3 miles west of Bolivar, bridge replacement over Barren Creek, and add turn lanes at Rte. 245 and Rte. 123. Project involves bridge H0021. | Adv. CN | 7380 | 1845 | 0 | 10684 | 0 | AC-STBG | SR0104 | 1100 | 1476 | 0 | 0 | 0 | 0 | 359 | 0 | 0 | 0 | 0 | 0 | 0 | 7749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CEDAR | MO 32 E | SR0442 | 0.223 | 0.223 | 0 | N |  | Pavement resurfacing from 0.2 mile south of Rte. 54 to approximately 0.1 mile north of Rte. 54. | Federal | 81 | 20 | 0 | 101 | 0 | NHPP | SR0028 SR0033 SR0487 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CEDAR | MO 39 S | 7P3485B | 0.036 | 0.072 | 1 | N |  | Bridge replacement over Cedar Creek. Project involves bridge X0190. | Federal | 1735 | 434 | 0 | 2537 | 0 | NHPP | SR0212 | 368 | 312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1857 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CEDAR | US 54 E | SR0033 | 25.066 | 50.216 | 5 | N |  | Pavement resurfacing from 0.1 mile east of Rte. 32 in El Dorado Springs to Rte. MM. Project involves bridge A4691, A5754, J0964, J0965, and J0966. | Federal | 5031 | 1258 | 0 | 6491 | 0 | NHPP | SR0028 SR0442 SR0487 | 202 | 664 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CEDAR | RT N E | SR0212 | 0.129 | 0.258 | 1 | N |  | Bridge rehabilitation over Big Sac River. Project involves bridge L0537. | Federal | 1522 | 380 | 0 | 1988 | 0 | NHPP | 7P3485B | 86 | 366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1536 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CHRISTIAN | US 65 S | SR0105 | 18.991 | 76.643 | 0 | N |  | Add climbing lanes, guard cable, and safety signage at various locations from 3.3 miles north of Rte. EE in Christian County to 0.8 mile north of Rte. 76 in Taney County and add northbound right turn lane at Saddlebrooke Drive. $3,259,000 Open Container funds. | Federal | 8906 | 990 | 0 | 10546 | 0 | SAFETY |  | 650 | 200 | 200 | 1458 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8038 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CHRISTIAN | RT EE E | SR0061 | 3.713 | 7.551 | 0 | N |  | Realign curves at various locations from Rte. 160 in Highlandville to Rte. 65 and add roundabout at Rte. 160. | Federal | 9592 | 1066 | 0 | 12071 | 0 | SAFETY | SR0311 | 1413 | 929 | 0 | 0 | 0 | 0 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 8629 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CHRISTIAN | RT EE E | SR0311 | 3.64 | 7.28 | 0 | N |  | Pavement resurfacing and add rumble stripes at various locations from Rte. 160 in Highlandville to Rte. 65 near Ozark. | Adv. CN | 354 | 89 | 0 | 477 | 0 | AC-STBG | SR0061 | 34 | 14 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CHRISTIAN | RT W S | SR0041 | 7.051 | 14.102 | 0 | N |  | Pavement resurfacing from 0.1 mile south of Timbercrest Road to end of state maintenance. | Adv. CN | 910 | 227 | 0 | 1156 | 0 | AC-STBG | SU0012 | 19 | 3 | 2 | 3 | 1 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1020 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | DADE | US 160 E | SR0104 | 0.573 | 1.146 | 0 | N |  | Road realignment from County Road 203 to Rte. 245. | Federal | 1672 | 186 | 0 | 2195 | 0 | SAFETY | SR0059 | 245 | 275 | 0 | 0 | 0 | 0 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 1583 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | DADE | US 160 E | SR0335 | 0.067 | 0.134 | 1 | N |  | Bridge replacement over Kyle Creek. Project involves bridge J0064. | Federal | 835 | 209 | 0 | 1144 | 0 | NHPP |  | 100 | 50 | 154 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 835 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | DADE | RT H S | SR0302 | 0.294 | 0.588 | 1 | N |  | Bridge rehabilitation over Stockton Lake. Project involves bridge A2929. | Federal | 442 | 110 | 0 | 567 | 0 | NHPP |  | 15 | 15 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | DADE | RT WW E | SR0328 | 0.101 | 0.202 | 1 | N |  | Bridge improvement over Turnback Creek. Project involves bridge N0589. | Adv. CN | 1840 | 460 | 0 | 2400 | 0 | AC-STBG |  | 100 | 50 | 121 | 275 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1852 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | DALLAS | MO 64 E | 7P3542 | 0.427 | 0.854 | 1 | N |  | Bridge replacement over the Niangua River and road realignment near Bennett Spring State Park. Project involves bridge J0782. | Federal | 8703 | 2176 | 0 | 13233 | 0 | NHPP |  | 2170 | 1645 | 0 | 0 | 0 | 0 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 9234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | DALLAS | US 65 N | SR0089 | 0.798 | 1.721 | 0 | N |  | Add roundabouts at Rte. 73 and at Truman Road in Buffalo and add passing lane north of Rte. 73. $3,492,000 Open Container funds. | Federal | 10771 | 1197 | 0 | 12718 | 0 | SAFETY |  | 750 | 160 | 1359 | 0 | 0 | 0 | 0 | 1206 | 0 | 0 | 0 | 0 | 0 | 0 | 9243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | US 160 E | SR0136 | 0.069 | 0.138 | 1 | N |  | Culvert replacement over Hamilton Creek between Thurmond Avenue and Perryman Avenue in Ash Grove. Project involves culvert H0468. | Federal | 634 | 158 | 0 | 948 | 0 | NHPP | SR0083 SR0138 | 130 | 108 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | IS 44 E | SR0244 | 9.219 | 37.916 | 0 | N |  | Pavement improvement 1.2 miles east of Rtes. Z and O near Halltown to east of Rte. 360. | Federal | 6876 | 764 | 0 | 7660 | 0 | NHPP | SR0023 SU0253 | 20 | 183 | 809 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6648 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | IS 44 E | SR0275B | 0.039 | 0.156 | 2 | N |  | Bridge rehabilitation over Pond Creek. Project involves twin bridges A0176. | Federal | 684 | 76 | 0 | 760 | 0 | NHPP |  | 0 | 2 | 5 | 5 | 30 | 93 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 625 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | BU 60 E | SR0034 | 3.324 | 6.615 | 0 | N |  | Pavement resurfacing and add rumble stripes from Rte. B to 0.3 mile east of White Oak Road in Rogersville and from 0.1 mile south of Rte. 60 to Rte. B. | Adv. CN | 555 | 139 | 0 | 728 | 0 | AC-STBG | 7P3533D SR0030 SR0032 | 34 | 1 | 1 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 633 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | US 65 S | 7P2212D | 5.184 | 10.368 | 0 | N |  | Pavement improvements on southbound lane from Pomme de Terre River to Rte. KK (two disconnected sections). | Federal | 640 | 160 | 0 | 813 | 0 | NHPP |  | 13 | 1 | 1 | 1 | 1 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 628 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | RT F S | SR0083 | 0.064 | 0.128 | 1 | N |  | Bridge replacement over Sac River. Project involves bridge K0646. | Adv. CN | 2868 | 717 | 0 | 4089 | 0 | AC-STBG | SR0136 SR0138 | 470 | 527 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 3058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | RT K S | SR0023 | 0.507 | 1.014 | 0 | N |  | Pavement resurfacing from Rte. 266 to I-44. | Adv. CN | 107 | 27 | 0 | 146 | 0 | AC-STBG | SR0244 SU0253 | 12 | 1 | 1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | RT V S | SR0025 | 8.016 | 16.032 | 0 | N |  | Pavement resurfacing and safety improvements from Rte. 123 in Walnut Grove to Rte. 160 in Ash Grove. | Adv. CN | 1533 | 383 | 0 | 1973 | 0 | AC-STBG | SR0026 SR0035 | 57 | 10 | 13 | 158 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 1683 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | HENRY | MO 13 N | SR0130 | 0.217 | 0.434 | 1 | N |  | Bridge deck sealing on northbound bridge over the Truman Reservoir 3.1 miles south of Rte. 7. Project involves bridge A5385. | Federal | 337 | 84 | 0 | 450 | 0 | NHPP |  | 29 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | HENRY | MO 18 E | SR0028 | 2.079 | 4.612 | 0 | N |  | Pavement resurfacing on Ohio Street from Montgomery Street to Rte. 13 in Clinton. | Federal | 558 | 140 | 0 | 718 | 0 | NHPP | SR0033 SR0442 SR0487 | 20 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 621 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | HENRY | RT C E | SR0053B | 0.146 | 0.752 | 8 | N |  | Bridge rehabilitation on Rte. C and Rte. 7 in Henry County and Rte. 13 in St. Clair County. Project involves bridges A5355, A5357, A5359, A6566, A6567, A6932, B0428, and A3913. | Federal | 793 | 198 | 0 | 1048 | 0 | NHPP |  | 57 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 842 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | HENRY | RT C E | SR0090 | 17.512 | 35.024 | 6 | N |  | Pavement resurfacing, add rumble stripes, and upgrade guardrail at various locations from Rte. 7 to Rte. 65. Project involves bridges A3881, A3691, L0413, S0438, A3913, and A4477. | Adv. CN | 3865 | 966 | 0 | 4923 | 0 | AC-STBG | SR0111B SR0313 | 92 | 539 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4292 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | HENRY | RT J S | SR0400 | 0.027 | 0.054 | 1 | N |  | Bridge improvement over Katy Trail in Calhoun. Project involves bridge A2308. | Federal | 4188 | 1047 | 0 | 5235 | 0 | NHPP |  | 0 | 80 | 100 | 100 | 200 | 512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | HENRY | RT PP S | SR0313 | 5.557 | 11.114 | 0 | N |  | Pavement resurfacing from Rte. C near Roseland to Rte. 7 in Tightwad. | Adv. CN | 1390 | 348 | 0 | 1748 | 0 | AC-STBG | SR0090 SR0111B | 10 | 211 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | HICKORY | MO 64 E | SR0320 | 0.35 | 0.7 | 1 | N |  | Bridge rehabilitation over Pomme de Terre Lake. Project involves bridge A0894. | Federal | 3050 | 763 | 0 | 3823 | 0 | NHPP |  | 10 | 5 | 165 | 538 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | JASPER | MO 249 S | SR0246 | 5.156 | 18.415 | 0 | Y |  | Pavement improvement and add pavement friction at various locations from Rte. 171 in Carterville to 20th Street in Joplin on southbound lanes and on northbound lanes 0.3 mile south of Newman Road to Rte. 171 in Carterville. | Federal | 2872 | 718 | 0 | 3610 | 0 | NHPP | SR0247 | 20 | 60 | 371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | JASPER | MO 43 N | SR0389 | 0.119 | 0.238 | 1 | Y |  | Bridge rehabilitation over Center Creek near Airport Drive. Project involves bridge A3659. | Federal | 456 | 114 | 0 | 570 | 0 | NHPP | SR0390 | 0 | 30 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 452 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | JASPER | MO 43 S | SR0008 | 0.221 | 1.058 | 2 | Y |  | Bridge replacement on Main Street over CPKC railroad and Turkey Creek and add sidewalk from F Street to Murphy Boulevard in Joplin. Project involves bridges K0415 and J0339. | Federal | 13858 | 3464 | 0 | 18072 | 0 | NHPP |  | 750 | 496 | 2307 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 14499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | JASPER | MO 43 S | SR0017 | 2.979 | 14.895 | 2 | Y |  | Pavement resurfacing from 0.1 mile south of Rte. 171 in Airport Drive to F Street in Joplin. Project involves bridges J0339 and K0415. | Federal | 1306 | 326 | 0 | 1694 | 0 | NHPP | SR0128 | 62 | 173 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1459 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | JASPER | MO 43 S | SR0277 | 1.32 | 5.71 | 0 | Y |  | Pavement improvement on Hearnes Boulevard from north of Rte. FF (32nd Street) to I-44. | Federal | 934 | 233 | 0 | 1182 | 0 | NHPP | SR0276 | 15 | 22 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1026 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | JASPER | IS 49 N | SR0053E | 0 | 0.929 | 1 | N |  | Bridge rehabilitation on the northbound lanes over Dry Fork Creek near Carytown. Project involves bridge A3580. | Federal | 1033 | 115 | 0 | 1162 | 0 | NHPP | SR0342 | 14 | 56 | 153 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 939 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | JASPER | IS 49 S | SR0342 | 0.927 | 1.854 | 1 | N |  | Bridge replacement on the southbound lanes over Dry Fork Creek. Project involves bridge A1341. | Federal | 5871 | 652 | 0 | 7123 | 0 | NHPP | SR0053E | 600 | 286 | 893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5344 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | JASPER | LP 49 S | SR0248 | 6.589 | 33.763 | 0 | Y |  | Pavement improvement from 10th Street in Webb City to south of 44th Street in Leawood. | Federal | 3971 | 993 | 0 | 4984 | 0 | NHPP | SR0249 | 20 | 135 | 504 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | JASPER | MO 571 S | SR0250 | 1.587 | 4.265 | 0 | N |  | Pavement improvement from south of Rte. E (Fairview Avenue) to I-49 in Carthage. | Federal | 586 | 146 | 0 | 736 | 0 | NHPP |  | 4 | 2 | 16 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | JASPER | MO 66 E | SR0276 | 2.611 | 13.075 | 1 | Y |  | Pavement improvements from east of Loop 49 (Range Line Road) to 0.2 mile west of Rte. 249. Project involves culvert A4391. | Federal | 1504 | 376 | 0 | 1895 | 0 | NHPP | SR0277 | 15 | 38 | 198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | JASPER | MO 96 E | 7S3506B | 1.12 | 5.229 | 0 | N |  | Upgrade pedestrian facilities to comply with the ADA Transition Plan on Central Avenue from I-49 to Garrison Avenue in Carthage. | Adv. CN | 1646 | 411 | 0 | 2734 | 0 | AC-STBG | SR0060 | 627 | 414 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 1643 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | JASPER | MO 96 E | SR0060 | 1.12 | 5.198 | 0 | N |  | Rebuild pavement and upgrade signals on Central Avenue from I-49 to Rte. 571 (Garrison Street) in Carthage. $399,000 Open Container funds. | Federal | 9015 | 2254 | 0 | 12519 | 0 | NHPP | 7S3506B | 1010 | 1152 | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 10117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | JASPER | RT FF E | 7S3059 | 0.4 | 2 | 0 | Y | 19HS-22 | Add railroad overpass on 32nd Street at CPKC railroad in Joplin. | Federal | 21750 | 5438 | 0 | 27772 | 0 | NHPP |  | 584 | 416 | 300 | 2871 | 0 | 0 | 0 | 2550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21051 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | JASPER | RT FF E | SR0247 | 4.692 | 23.883 | 0 | Y |  | Pavement improvement on 32nd Street from Rte. 43 (Main Street) to west of I-49 in Joplin. | Federal | 3390 | 848 | 0 | 4258 | 0 | NHPP | SR0246 | 20 | 99 | 398 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3741 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | JASPER | RT H E | SR0372 | 0.131 | 0.262 | 1 | N |  | Bridge replacement over North Fork Spring River. Project involves bridge T0373. | Federal | 2501 | 625 | 0 | 3226 | 0 | NHPP |  | 100 | 345 | 379 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 2343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | JASPER | RP MO249N TO MO171N N | SR0319B | 0 | 0.581 | 1 | Y |  | Bridge painting over Rte. 171 and Missouri & Northern Arkansas Railroad in Carterville. Project involves bridge A6149. | Federal | 487 | 122 | 0 | 613 | 0 | NHPP |  | 4 | 2 | 28 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | JASPER | CST W FAIRVIEW AVE E | SR0460 | 0.04 | 0.08 | 1 | N |  | Bridge painting and rehabilitation over I-49. Project involves bridge A3564. | Federal | 422 | 105 | 0 | 527 | 0 | NHPP | SR0462 | 0 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | LAWRENCE | MO 39 S | SR0019 | 2.632 | 7.137 | 0 | N | SP1812-18 | Pavement resurfacing from west of Lewis Shaw Avenue to Rte. 60 in Aurora. | Federal | 767 | 192 | 0 | 993 | 0 | NHPP | 7S3390 7S3493 7S3494 SR0022 | 34 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | LAWRENCE | BU 60 E | SR0022 | 3.54 | 7.28 | 0 | N |  | Pavement resurfacing from west of Cowan Drive to Rte. 60 in Aurora. | Federal | 668 | 167 | 0 | 858 | 0 | NHPP | 7S3390 7S3493 7S3494 SR0019 | 23 | 92 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | LAWRENCE | US 60 E | SR0084 | 0.098 | 0.196 | 2 | N |  | Bridge replacement over Missouri & Northern Arkansas Railroad near Aurora and on Rte. H over Missouri & Northern Arkansas Railroad near Hoberg. Project involves bridges K0947 and A0872. | Adv. CN | 7073 | 1768 | 0 | 9533 | 0 | AC-STBG |  | 692 | 1090 | 897 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 6826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | LAWRENCE | RT K S | SR0211 | 0.171 | 0.342 | 1 | N |  | Bridge replacement over Honey Creek. Project involves bridge K0865. | Federal | 1843 | 461 | 0 | 2789 | 0 | NHPP |  | 438 | 325 | 0 | 0 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 1979 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | LAWRENCE | RT N S | SR0431 | 0.039 | 0.078 | 1 | N |  | Bridge improvement over I-44. Project involves bridge R0144. | Federal | 2855 | 714 | 0 | 3569 | 0 | NHPP |  | 0 | 50 | 475 | 457 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 2578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | LAWRENCE | RT P S | 7S3494 | 5.574 | 11.148 | 0 | N |  | Pavement resurfacing and add rumble stripes from Rte. 39 to Bus. 60 in Verona. | Adv. CN | 1018 | 254 | 0 | 1324 | 0 | AC-STBG | 7S3390 7S3493 SR0019 SR0022 | 52 | 118 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1154 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | MCDONALD | IS 49 N | SR0053C | 0.138 | 0.554 | 2 | N |  | Bridge rehabilitation over Indian Creek Road in Anderson. Project involves bridges A5812 and A5813. | Federal | 1467 | 163 | 0 | 1634 | 0 | NHPP |  | 4 | 321 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | MCDONALD | IS 49 N | SR0053F | 0 | 0.351 | 1 | Y |  | Bridge rehabilitation over Goodin Hollow Road near Pineville. Project involves bridge A6378. | Federal | 476 | 53 | 0 | 529 | 0 | NHPP |  | 0 | 104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | MCDONALD | IS 49 N | SR0393 | 0 | 0.114 | 1 | N |  | Bridge rehabilitation over Sugar Fork Creek north of Goodman. Project involves bridge A5630. | Federal | 863 | 96 | 0 | 959 | 0 | NHPP |  | 0 | 50 | 134 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | MCDONALD | IS 49 N | SR0462 | 0.547 | 2.021 | 10 | Y |  | Bridge rehabilitation at various locations in McDonald, Newton, Jasper, and Vernon counties. Project involves bridges A4819, A5725, A5810, A6146, A6650, A6651, A6694, A6695, B0561, and B0562. | Federal | 2931 | 326 | 0 | 3257 | 0 | NHPP | SR0460 | 0 | 706 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | MCDONALD | IS 49 S | SR0016 | 6.843 | 28.715 | 4 | Y |  | Pavement resurfacing from Rte. 59 near Goodman to 2.1 miles south of Rte. 76. Project involves bridges A5560, A5561, A5815, and A5816. | Federal | 3893 | 432 | 0 | 4481 | 0 | NHPP |  | 156 | 456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3869 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | MCDONALD | IS 49 S | SR0457 | 16.005 | 67.417 | 0 | Y | 7I3517 | Job Order Contracting for pavement repair from Rte. 59 to Arkansas State line. | Adv. CN | 142 | 16 | 0 | 158 | 0 | AC-NHPP |  | 0 | 8 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | MCDONALD | MO 59 S | SR0390 | 0.108 | 0.216 | 1 | N |  | Bridge rehabilitation over Elk River in Noel. Project involves bridge A3956. | Federal | 266 | 66 | 0 | 332 | 0 | NHPP | SR0389 | 0 | 35 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 249 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | MCDONALD | MO 90 W | SR0383 | 0.02 | 0.04 | 1 | N |  | Bridge replacement over Trent Creek. Project involves bridge A1828. | Federal | 1826 | 456 | 0 | 2282 | 0 | NHPP |  | 0 | 372 | 293 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1615 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | MCDONALD | PVT BLANKENSHIP PARK W | SR0144 | 0.029 | 0.058 | 1 | N |  | Bridge replacement at Blankenship Park west of Main Street in Southwest City. Project involves bridge T1041. | Adv. CN | 167 | 42 | 0 | 220 | 0 | AC-STBG |  | 11 | 1 | 1 | 1 | 10 | 28 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | MCDONALD | PVT BRIDGE T1002 E | SR0436 | 0.011 | 0.022 | 1 | N |  | Bridge improvement over Beaver Branch south of Goodman. Project involves bridge T1002. | Federal | 759 | 190 | 0 | 949 | 0 | NHPP |  | 0 | 25 | 126 | 129 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | NEWTON | MO 43 S | SR0075B | 0.055 | 0.11 | 3 | N |  | Culvert replacement and ditch grading from Grand Avenue to Osage Street in Seneca. Project involves culverts T1060, T1061, and T1062. | Federal | 0 | 1030 | 0 | 1176 | 0 | STATE | SR0439 | 146 | 162 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | NEWTON | MO 43 S | SR0439 | 0.25 | 0.5 | 0 | N |  | Drainage upgrades from Grand Avenue to Osage Street in Seneca. | Federal | 926 | 232 | 0 | 1238 | 0 | STBG | SR0075B | 80 | 237 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 916 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | NEWTON | IS 44 E | SR0128 | 18.719 | 78.77 | 6 | Y |  | Pavement resurfacing from 0.4 mile east of Loop 49 (Range Line Road) in Joplin to 1.5 miles east of Rte. 37 near Sarcoxie. Project involves bridges A0540, A0541, A0542, A0543, A0544, and A0862. | Federal | 13842 | 1538 | 0 | 15896 | 0 | NHPP | SR0017 | 516 | 1627 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13753 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | NEWTON | IS 44 E | SR0357 | 0.084 | 0.336 | 2 | Y |  | Bridge improvement over CPKC railroad. Project involves twin bridges A0540. | Federal | 6432 | 715 | 0 | 7197 | 0 | NHPP |  | 50 | 50 | 50 | 200 | 200 | 774 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5873 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | NEWTON | IS 44 E | SR0376 | 0.029 | 0.118 | 2 | Y |  | Bridge improvements over Rte. 166. Project involves bridges L0854 and L0855. | Federal | 5891 | 655 | 0 | 6552 | 0 | NHPP |  | 6 | 10 | 20 | 400 | 154 | 710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5252 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | NEWTON | IS 44 E | SR0454 | 69.112 | 286.487 | 0 | Y | 01HS-24 | Job Order Contracting for pavement repair from the Oklahoma State line to Rte. 360 in Greene County. | Adv. CN | 456 | 51 | 0 | 507 | 0 | AC-NHPP |  | 0 | 5 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | NEWTON | IS 49 S | SR0391 | 0.049 | 0.196 | 2 | N |  | Bridge rehabilitation over Rte. 60 in Neosho. Project involves bridge A5546 and A5547. | Federal | 220 | 24 | 0 | 244 | 0 | NHPP | SR0392 | 0 | 10 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | NEWTON | IS 49 S | SR0392 | 0.026 | 0.052 | 1 | N |  | Bridge rehabilitation over Poppy Drive west of Neosho. Project involves bridge A5556. | Federal | 152 | 17 | 0 | 169 | 0 | NHPP | SR0391 | 0 | 8 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | NEWTON | LP 49 S | SR0185 | 0.103 | 0.309 | 1 | Y |  | Bridge improvement over Shoal Creek south of Saginaw. Project involves bridge K0765. | Federal | 9176 | 2294 | 0 | 11795 | 0 | NHPP |  | 325 | 200 | 355 | 474 | 1455 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 8936 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | NEWTON | LP 49 S | SR0249 | 6.481 | 20.098 | 0 | Y |  | Pavement improvement from south of 44th Street in Leawood to I-49. | Federal | 1643 | 411 | 0 | 2074 | 0 | NHPP | SR0248 | 20 | 39 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | NEWTON | BU 60 E | 7S3390 | 6.996 | 20.677 | 1 | N |  | Pavement resurfacing from Rtes. 60 and 59 north junction 2.2 miles west of Granby to Rtes. 60 and 59 south junction in Neosho. Project involves bridge J0623. | Federal | 1362 | 340 | 0 | 1912 | 0 | NHPP | 7S3493 7S3494 SR0019 SR0022 | 210 | 179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | NEWTON | BU 60 E | SR0113 | 1.149 | 5.736 | 0 | N |  | Rebuild pavement from Stadium Drive to north of Daugherty Road in Neosho. | Federal | 3677 | 919 | 0 | 4832 | 0 | NHPP |  | 236 | 10 | 514 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4072 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | NEWTON | US 60 E | SR0355 | 0.124 | 0.248 | 1 | N |  | Bridge improvement over Pineville Road and CPKC railroad. Project involves bridge A0334. | Federal | 1661 | 415 | 0 | 2086 | 0 | NHPP |  | 10 | 10 | 10 | 25 | 50 | 232 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1749 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | NEWTON | RT B S | 7S3496 | 2.628 | 5.256 | 0 | N |  | Pavement resurfacing and add shoulders and rumble stripes from Rte. 60 in Granby to Rte. 86. | Adv. CN | 597 | 149 | 0 | 760 | 0 | AC-STBG |  | 14 | 11 | 2 | 1 | 1 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 671 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | NEWTON | RT E S | 7S3497 | 5.266 | 10.532 | 0 | N |  | Pavement resurfacing and add shoulders and rumble stripes from Rte. J east of Diamond to Rte. 60 in Granby. | Adv. CN | 1056 | 264 | 0 | 1336 | 0 | AC-STBG |  | 16 | 20 | 20 | 108 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 1164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | POLK | MO 123 S | SR0055 | 0.036 | 0.072 | 3 | N |  | Culvert replacement at Spring Creek and culvert rehabilitation on Rte. 83 at Mile Creek and on Rte. O at Ashlock Creek. Project involves culverts H0406, L0341, and P0984. | Adv. CN | 1053 | 263 | 0 | 1905 | 0 | AC-STBG |  | 589 | 340 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 976 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | POLK | MO 123 S | SR0487 | 12.175 | 24.35 | 0 | N |  | Pavement resurfacing from Rte. 32 to Rte. 215 south intersection. | Adv. CN | 1186 | 296 | 0 | 1482 | 0 | AC-STBG | SR0028 SR0033 SR0442 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1386 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | POLK | MO 32 E | SR0213 | 0.198 | 0.455 | 0 | N |  | Payment to Bolivar to add roundabout at Broadway Street and Rte. D and add turn lane on Rte. 83 0.3 mile north of Rte. 13 in Bolivar. Scoping, design, right of way acquisition, and construction by Bolivar. $3,012,500 Cost Share funds. | Adv. CN | 2558 | 640 | 0 | 3213 | 0 | AC-STBG |  | 15 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3013 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | POLK | MO 83 S | SR0035 | 14.148 | 28.296 | 0 | N |  | Pavement resurfacing from Rte. V to Rte. 32 in Bolivar. | Adv. CN | 2729 | 682 | 0 | 3542 | 0 | AC-STBG | SR0025 SR0026 | 131 | 7 | 4 | 289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | POLK | MO 83 S | SR0441 | 0.034 | 0.068 | 1 | N |  | Repair streambank at Dry Fork Creek. Project involves bridge A4754. | Adv. CN | 382 | 96 | 0 | 528 | 0 | AC-STBG |  | 50 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | POLK | RT C E | SR0430 | 0.038 | 0.076 | 1 | N |  | Bridge improvement over Panther Creek. Project involves bridge P0919. | Federal | 1954 | 489 | 0 | 2443 | 0 | NHPP |  | 0 | 50 | 321 | 327 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | POLK | RT N E | SR0138 | 0.21 | 0.42 | 1 | N |  | Bridge replacement over Sadler Branch west of Humansville. Project involves bridge A1878. | Federal | 1193 | 298 | 0 | 1764 | 0 | NHPP | SR0083 SR0136 | 271 | 241 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | POLK | RT U S | SR0026 | 5.111 | 10.269 | 0 | N |  | Pavement resurfacing and add rumble stripes from Rte. 13 in Bolivar to end of state maintenance. $333,000 Open Container funds. | Adv. CN | 878 | 219 | 0 | 1143 | 0 | AC-STBG | SR0025 SR0035 | 46 | 2 | 2 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | POLK | RT Z E | 7S3368B | 0.102 | 0.204 | 1 | N |  | Bridge replacement over Pratter Branch 0.2 mile west of Rock Prairie. Project involves bridge W0507. | Federal | 0 | 569 | 0 | 673 | 0 | STATE |  | 104 | 82 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 485 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | ST. CLAIR | MO 13 N | SR0382 | 0 | 0.398 | 1 | N |  | Bridge rehabilitation over Osage River in Osceola. Project involves bridge A5850. | Federal | 429 | 107 | 0 | 536 | 0 | NHPP |  | 0 | 10 | 10 | 10 | 45 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | ST. CLAIR | MO 13 N | SR0386 | 0 | 0.038 | 1 | N |  | Bridge replacement over Otter Creek. Project involves bridge A0842. | Federal | 2795 | 699 | 0 | 3494 | 0 | NHPP |  | 0 | 500 | 496 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | ST. CLAIR | MO 13 S | 7P3034B | 1.27 | 2.588 | 0 | N |  | Pavement improvement on the southbound lanes from SE 1100 Road to NE 201 Road. | Federal | 1173 | 293 | 0 | 1477 | 0 | NHPP |  | 11 | 2 | 2 | 2 | 2 | 319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1139 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | ST. CLAIR | MO 13 S | SR0207 | 10.133 | 47.502 | 0 | N |  | Pavement improvements at various locations from 0.5 mile north of NE 1000 Road to SE 1300 Road. | Adv. CN | 6669 | 1667 | 0 | 8346 | 0 | AC-NHPP |  | 10 | 211 | 863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7262 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | ST. CLAIR | MO 13 S | SR0282 | 12.313 | 71.327 | 0 | N |  | Pavement improvement on disconnected sections from north of Lowry City to south of Collins. | Federal | 3344 | 836 | 0 | 4195 | 0 | NHPP |  | 15 | 10 | 53 | 1412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2705 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | ST. CLAIR | US 54 E | SR0268 | 22.767 | 45.801 | 0 | N |  | Pavement improvement from Rte. MM in St. Clair County to Rte. D in Preston. | Federal | 4349 | 1087 | 0 | 5446 | 0 | NHPP |  | 10 | 160 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | ST. CLAIR | RT B E | SR0377 | 0.113 | 0.226 | 1 | N |  | Bridge rehabilitation over Truman Reservoir. Project involves bridge A4072. | Federal | 2938 | 734 | 0 | 3712 | 0 | NHPP |  | 40 | 40 | 108 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | ST. CLAIR | RT C E | SR0426 | 0.042 | 0.084 | 1 | N |  | Bridge improvement over Big Muddy Creek. Project involves bridge A3579. | Federal | 3439 | 860 | 0 | 4299 | 0 | NHPP |  | 0 | 100 | 600 | 521 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 3066 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | STONE | MO 13 S | SR0129 | 29.088 | 67.568 | 0 | N |  | Pavement improvement from 0.4 mile north of Finley River to Table Rock Lake in Kimberling City. | Federal | 9460 | 2365 | 0 | 11845 | 0 | NHPP | SU0264 | 20 | 50 | 311 | 1146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | STONE | MO 13 S | SR0317 | 0.643 | 1.286 | 2 | N |  | Bridge washing over Table Rock Lake in Kimberling City and on Rte. 39 over Table Rock Lake in Shell Knob. Project involves bridges A0585 and A0260. | Federal | 457 | 114 | 0 | 573 | 0 | NHPP |  | 2 | 2 | 8 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | STONE | US 160 E | 7P3533C | 9.282 | 19.46 | 0 | N |  | Pavement resurfacing and add rumble stripes from Rte. 13 to 0.4 mile east of Rte. 65. | Adv. CN | 1935 | 484 | 0 | 2820 | 0 | AC-STBG | 7P3533B SR0038 SR0228 | 401 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | STONE | MO 76 E | SR0050 | 0.83 | 1.837 | 11 | Y |  | Bridge painting at various locations in the rural Southwest District. Project involves bridges A2728, A2729, A3020, A3070, A3477, A3821, A4258, A4820, X0793, A0588, and A0337. | Adv. CN | 4827 | 1207 | 0 | 6224 | 0 | AC-STBG | SU0051 | 190 | 1046 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | STONE | MO 76 E | SR0278 | 7.663 | 30.649 | 0 | N |  | Pavement improvements on the Ozark Mountain Highroad from Rte. 376 to 0.2 mile west of Rte. 65. | Federal | 5478 | 1370 | 0 | 6868 | 0 | NHPP |  | 20 | 50 | 50 | 30 | 7 | 637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | STONE | RT AA S | SR0275 | 0.229 | 1.558 | 5 | N |  | Bridge rehabilitation on northbound Rte. 65 over Lake Taneycomo, Rte. 13 over Bus. 13, Rte. 14 over Green Valley Creek, Rte. B over BNSF Railway, and Rte. AA over Wheeler Creek near Elsey. Project involves bridges A2597, A2823, A3069, A7914, and A8329. | Federal | 771 | 193 | 0 | 1051 | 0 | NHPP |  | 87 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | STONE | RT M E | SR0435 | 0.019 | 0.038 | 1 | N |  | Bridge improvement over Spring Creek. Project involves bridge T0608. | Federal | 1390 | 347 | 0 | 1737 | 0 | NHPP |  | 0 | 50 | 210 | 248 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1227 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | TANEY | MO 125 S | SR0334 | 0.098 | 0.196 | 2 | N |  | Repair and extend culverts over Brushy Creek. Project involves culverts T0604 and T0605. | Adv. CN | 2041 | 510 | 0 | 2730 | 0 | AC-STBG |  | 179 | 446 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 2075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | TANEY | US 160 E | 7P3507 | 0.228 | 0.828 | 0 | N |  | Replace signals at Rte. 39 and Hadley Street in Aurora, replace signals at Rte. 76 and Main Street in Branson, and replace signals and add right turn lane at Rte. 160 and Coy Boulevard in Forsyth. | Adv. CN | 1298 | 324 | 0 | 1881 | 0 | AC-STBG |  | 259 | 287 | 0 | 0 | 0 | 0 | 0 | 63 | 0 | 0 | 0 | 0 | 0 | 1272 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | TANEY | US 160 E | SR0011 | 0.092 | 0.184 | 1 | N |  | Bridge replacement over Beaver Creek. Project involves bridge L0382. | Federal | 5252 | 1313 | 0 | 7337 | 0 | NHPP |  | 772 | 1111 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 5399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | TANEY | US 160 E | SR0121 | 0.085 | 0.17 | 1 | N |  | Bridge replacement over Swan Creek in Forsyth. Project involves bridge J0952. | Federal | 7590 | 1897 | 0 | 11166 | 0 | NHPP |  | 1679 | 1346 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 0 | 0 | 0 | 8076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | TANEY | MO 165 S | SR0228 | 8.413 | 18.394 | 0 | N |  | Pavement resurfacing and add rumble stripes from 76 Country Boulevard in Branson to Rte. 265 near Hollister. | Adv. CN | 2146 | 536 | 0 | 2761 | 0 | AC-STBG | 7P3533B 7P3533C SR0038 | 79 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2407 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | TANEY | MO 248 E | 7P3533B | 6.668 | 13.601 | 1 | N |  | Pavement resurfacing and add rumble stripes from Rte. 160 to Shepherd of the Hills Expressway in Branson. Project involves bridge A5431. | Adv. CN | 1228 | 307 | 0 | 1587 | 0 | AC-STBG | 7P3533C SR0038 SR0228 | 52 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | TANEY | BU 65 S | SR0039 | 2.614 | 9.943 | 0 | N |  | Pavement resurfacing from Rte. 76 to Birch Street in Hollister. | Adv. CN | 1466 | 366 | 0 | 1862 | 0 | AC-STBG | SR0040 | 30 | 5 | 5 | 5 | 181 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1636 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | TANEY | BU 65 S | SR0122 | 0.044 | 0.088 | 1 | N |  | Bridge replacement over Missouri and Northern Arkansas Railroad in Hollister. Project involves bridge J0710. | Federal | 4666 | 1166 | 0 | 7285 | 0 | NHPP |  | 1453 | 781 | 0 | 0 | 0 | 0 | 0 | 55 | 0 | 0 | 0 | 0 | 0 | 4996 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | TANEY | US 65 N | SR0215 | 0.104 | 0.414 | 2 | N |  | Bridge rehabilitation over Missouri & Northern Arkansas Railroad in Branson. Project involves bridges A3065 and A3066. | Federal | 3934 | 983 | 0 | 5032 | 0 | NHPP |  | 115 | 807 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | TANEY | US 65 S | SR0091 | 0.401 | 2.118 | 0 | N |  | Add bridge and reconfigure intersection access at Rte. 265. $3,223,000 Open Container funds. | Federal | 4827 | 536 | 0 | 6121 | 0 | SAFETY |  | 758 | 952 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | TANEY | US 65 S | SR0270 | 17.014 | 73.588 | 0 | N |  | Pavement resurfacing and replace guardrail from 0.9 mile north of Rte. 76 north junction (Ozark Mountain Highroad) to Arkansas State line. | Federal | 8270 | 2068 | 0 | 10588 | 0 | NHPP | SR0346 | 250 | 1107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | TANEY | US 65 S | SR0325 | 0.104 | 0.208 | 1 | N |  | Bridge replacement on the southbound bridge over Emory Creek. Project involves bridge A0930. | Federal | 5361 | 1340 | 0 | 7030 | 0 | NHPP |  | 329 | 150 | 150 | 150 | 893 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5358 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | TANEY | US 65 S | SR0346 | 17.144 | 74.106 | 0 | N |  | Pavement resurfacing and add pavement friction at various locations from 0.9 mile north of Rte. 76 north junction (Ozark Mountain Highroad) to Arkansas State line. | Adv. CN | 2862 | 716 | 0 | 3678 | 0 | AC-STBG | SR0270 | 100 | 378 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | TANEY | CST 76 COUNTRY BLVD E | 8O2373B | 4.335 | 13.384 | 0 | N |  | Payment to Branson for road relinquishment of Rte. 76 from Shepherd of the Hills Expressway to Sunshine Street. $3,746,574 over 10 years from SFY 2019 through SFY 2028. | Federal | 0 | 513 | 0 | 3747 | 0 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3234 | 414 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | TANEY | RT BB S | SR0040 | 3.584 | 7.168 | 0 | N |  | Pavement resurfacing and add rumble stripes from Bus. 65 in Hollister to Layton Road. | Adv. CN | 622 | 155 | 0 | 811 | 0 | AC-STBG | SR0039 | 34 | 5 | 5 | 5 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 695 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | TANEY | CST BRANSON LANDING BLVD S | SR0395 | 0.151 | 0.302 | 1 | N |  | Bridge painting over White River in Branson. Project involves bridge A7685. | Federal | 122 | 30 | 0 | 152 | 0 | NHPP |  | 0 | 2 | 6 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | TANEY | RT F E | SR0038 | 3.218 | 6.495 | 0 | N |  | Pavement resurfacing and add rumble stripes from 0.1 mile east of Rte. 65 to Rte. 160 in Merriam Woods. | Adv. CN | 1300 | 325 | 0 | 1683 | 0 | AC-STBG | 7P3533B 7P3533C SR0228 | 58 | 158 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1467 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | 5B0800W | 0 | 0 | 1 | Y |  | Payback beginning in SFY 2008 for Safe and Sound bridges in the rural Southwest District. | Federal | 0 | 38840 | 0 | 136417 | 15,001 - 25,000 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 0 | 97518 | 7768 | 7768 | 7768 | 7768 | 7768
6 | VARIOUS | Various | SR0217 | 0 | 0 | 0 | Y |  | ITS operations and management of the Transportation Management Center of the Ozarks in the rural Southwest District. | Federal | 0 | 464 | 0 | 464 | 0 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | SR0219 | 0 | 0 | 0 | Y |  | On-call work zone enforcement at various locations in the rural Southwest District. | Federal | 90 | 10 | 0 | 100 | 0 | SAFETY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | SR0285 | 0 | 0 | 2 | Y |  | Bridge improvements at various locations in Bates, Cedar, Jasper, McDonald, Newton, and Vernon Counties. Potential Design-Build project. | Federal | 42857 | 10714 | 0 | 53721 | 0 | NHPP |  | 150 | 1000 | 1000 | 1000 | 6695 | 0 | 0 | 0 | 0 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 43775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | SR0348 | 0 | 0 | 0 | Y |  | Job Order Contracting for ADA compliance repairs at various locations in the rural Southwest District. | Adv. CN | 235 | 59 | 0 | 296 | 0 | AC-STBG |  | 2 | 4 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | SR0358 | 0 | 0 | 0 | Y |  | On-call work zone enforcement at various locations in the rural Southwest District. | Federal | 90 | 10 | 0 | 100 | 0 | SAFETY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | SR0360 | 0 | 0 | 0 | Y |  | ITS operations and management of the Traffic Management Center of the Ozarks in the rural Southwest District. | Federal | 0 | 573 | 0 | 573 | 0 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 573 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | SR0361 | 0 | 0 | 0 | Y |  | Job Order Contracting for guard cable and guardrail repair in the rural Southwest District. | Adv. CN | 3805 | 951 | 0 | 4758 | 0 | AC-STBG |  | 2 | 4 | 1075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3677 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | SR0446 | 0 | 0 | 0 | Y |  | ITS operations and management of the Traffic Management Center of the Ozarks in the rural Southwest District. | Federal | 0 | 574 | 0 | 574 | 0 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | SR0447 | 0 | 0 | 0 | Y |  | On-call work zone enforcement at various locations in the rural Southwest District. | Federal | 90 | 10 | 0 | 100 | 0 | SAFETY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VERNON | MO 43 S | SR0162 | 24.219 | 48.438 | 0 | N |  | Pavement resurfacing from Rte. 54 to Rte. 160 in Barton County. | Adv. CN | 4918 | 1230 | 0 | 6409 | 0 | AC-STBG | SR0161 | 261 | 557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5591 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VERNON | IS 49 S | SR0456 | 55.938 | 231.144 | 0 | N |  | Job Order Contracting for pavement repair from Rte. 54 in Vernon County to I-44 in Jasper County. | Adv. CN | 341 | 38 | 0 | 379 | 0 | AC-NHPP |  | 0 | 8 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VERNON | IS 49 S | SR0459 | 0.05 | 0.2 | 2 | N |  | Bridge rehabilitation over Willow Branch. Project involves twin bridges A2628. | Federal | 1700 | 189 | 0 | 1889 | 0 | NHPP |  | 0 | 371 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1518 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VERNON | US 54 E | SR0252 | 5.295 | 23.348 | 0 | N |  | Pavement improvement on Austin Boulevard from Webster Street to I-49, on Centennial Boulevard from Loop 49 to north of I-49, and on Osage Boulevard from I-49 to Austin Boulevard in Nevada. | Federal | 2318 | 580 | 0 | 2908 | 0 | NHPP | SR0245 | 10 | 81 | 293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2524 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VERNON | RT BB S | SR0139 | 0.04 | 0.08 | 1 | N |  | Bridge replacement over Birch Creek in Nevada. Project involves bridge A1448. | Federal | 1090 | 273 | 0 | 1653 | 0 | NHPP |  | 290 | 187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VERNON | RT K E | SR0161 | 2.645 | 5.67 | 0 | N |  | Pavement resurfacing from I-49 near Nevada to County Road 1800. | Adv. CN | 893 | 223 | 0 | 1154 | 0 | AC-STBG | SR0162 | 38 | 111 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VERNON | RT WW S | SR0461 | 0.073 | 0.146 | 1 | N |  | Bridge improvement over the Little Osage River. Project involves bridge A1961. | Federal | 1875 | 469 | 0 | 2344 | 0 | NHPP |  | 0 | 80 | 50 | 308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1906 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | WEBSTER | IS 44 E | SR0455 | 20.786 | 85.497 | 0 | N |  | Job Order Contracting for pavement repair in Webster County. | Adv. CN | 230 | 26 | 0 | 256 | 0 | AC-NHPP |  | 0 | 8 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | WEBSTER | US 60 E | SR0112 | 3.857 | 15.802 | 0 | N |  | Corridor improvements in Seymour. | Federal | 26815 | 6704 | 0 | 35226 | 0 | NHPP |  | 1707 | 350 | 465 | 4183 | 0 | 0 | 0 | 0 | 979 | 0 | 0 | 0 | 0 | 0 | 0 | 27542 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | WEBSTER | US 60 E | SR0187 | 0.056 | 0.318 | 2 | N |  | Bridge rehabilitation over Rte. PP, BNSF Railway, and Front Street in Webster County. Project involves twin bridges A2627. | Federal | 6187 | 1547 | 0 | 8133 | 0 | NHPP |  | 399 | 1433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6301 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | WEBSTER | RT B S | SR0030 | 6.676 | 13.352 | 0 | N |  | Pavement resurfacing from Rte. AD to Bus. 60 in Rogersville and add rumble stripes from Rte. AD to Shagbark Lane. | Adv. CN | 1192 | 298 | 0 | 1533 | 0 | AC-STBG | 7P3533D SR0032 SR0034 | 43 | 15 | 2 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1347 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | WEBSTER | RT FF S | 7P3533D | 1.403 | 2.806 | 0 | N |  | Pavement resurfacing on Rtes. FF and PP from Rte. 60 west junction to Rte. 60 east junction in Fordland. | Adv. CN | 187 | 47 | 0 | 244 | 0 | AC-STBG | SR0030 SR0032 SR0034 | 10 | 1 | 1 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | WEBSTER | RT O S | SR0166 | 3.07 | 6.14 | 0 | N |  | Pavement resurfacing from Hazelwood Road to Rte. 60 and on Brentlinger Drive from beginning of route to Rte. FF in Fordland. | Federal | 0 | 552 | 0 | 611 | 0 | STATE | 8S3211 8S3215 SU0077 | 38 | 59 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 493 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | WEBSTER | RT PP E | SR0032 | 5.844 | 11.691 | 0 | N |  | Pavement resurfacing and add rumble stripes from Rte. KK to Rte. FF in Fordland. | Adv. CN | 1058 | 264 | 0 | 1375 | 0 | AC-STBG | 7P3533D SR0030 SR0034 | 53 | 1 | 1 | 112 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CHRISTIAN | MO 14 E | 8P0583B | 0.56 | 0.746 | 0 | Y | OK2201-24A | Add lanes and add sidewalk on South Street west of 6th Avenue to 14th Avenue in Ozark. STBG-Urban $171,523, Transportation Alternatives $134,836, Ozark $110,299. | Adv. CN | 4374 | 983 | 110 | 7228 | 0 | AC-STBG |  | 1213 | 1137 | 0 | 0 | 0 | 0 | 548 | 0 | 0 | 0 | 0 | 0 | 0 | 4330 | 0 | 0 | 0 | 0 | 0 | 417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CHRISTIAN | MO 14 E | SU0287 | 2.917 | 6.782 | 0 | Y | OK2502 | Pavement improvement from 0.2 mile east of Rte. NN to north of Selmore Boulevard and from 6th Avenue to Rte. W in Ozark. | Adv. CN | 2516 | 629 | 0 | 3149 | 0 | AC-STBG |  | 4 | 10 | 154 | 332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2649 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CHRISTIAN | MO 14 E | SU0288 | 7.51 | 25.706 | 0 | Y | CC2502 | Pavement improvement from 0.2 mile west of Rte. M in Nixa to Finley River Bridge in Ozark. | Federal | 3426 | 856 | 0 | 4292 | 0 | NHPP |  | 10 | 10 | 108 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CHRISTIAN | US 160 E | SU0264 | 3.601 | 8.243 | 0 | Y | CC2501 | Pavement improvement from Rte. 14 in Nixa to 0.4 mile north of Finley River. | Federal | 525 | 131 | 0 | 660 | 0 | NHPP | SR0129 | 4 | 6 | 2 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CHRISTIAN | RT CC E | 8S0736D | 0.805 | 1.692 | 0 | Y | OK2102-23A | Add lanes, sidewalk, and shared use path from Fremont Road to east of 22nd Street in Ozark. Design, right of way acquisition, and utility relocation by Ozark. $2,021,449 Cost Share, $2,128,397 STBG-Urban and $532,099 Ozark funds. | Adv. CN | 4126 | 499 | 532 | 5302 | 0 | AC-STBG |  | 145 | 475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4682 | 0 | 0 | 0 | 0 | 0 | 2660 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | CHRISTIAN | RT W S | SU0012 | 0.995 | 2.006 | 0 | Y | CC2302-23 | Pavement resurfacing from Rte. 14 to south of Timbercrest Road near Ozark. | Adv. CN | 180 | 45 | 0 | 231 | 0 | AC-STBG | SR0041 | 6 | 1 | 2 | 1 | 1 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | MO 125 S | SU0174 | 0.041 | 0.164 | 1 | Y | ST2401-24 | Bridge rehabilitation over I-44 in Strafford. Project involves bridge A5400. | Federal | 844 | 211 | 0 | 1310 | 0 | NHPP |  | 255 | 2 | 148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 905 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | MO 13 S | SU0093 | 1.009 | 4.285 | 0 | Y | SP2302-23 | Capital improvement on Kansas Expressway from Grand Street to Rte. 413 (Sunshine Street) in Springfield. | Federal | 6624 | 1656 | 0 | 9060 | 0 | NHPP | SU0432 | 780 | 2 | 1195 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 7068 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | MO 13 S | SU0432 | 0.14 | 0.56 | 1 | Y | SP2703-27 | Rehabilitate and widen bridge over Fassnight Creek. Project involves bridge A3259. | Federal | 1169 | 292 | 0 | 1461 | 0 | NHPP | SU0093 | 0 | 30 | 155 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | US 160 E | SU0051 | 0.248 | 1.166 | 3 | Y | SP2304-23 | Bridge painting over Rte. 60 (James River Freeway), on Republic Street over Rte. 60, and on Rte. 266 (Chestnut Expressway) over I-44 in Springfield. Project involves bridges A4146, A4184, and A0598. | Federal | 1835 | 459 | 0 | 2378 | 0 | NHPP | SR0050 | 84 | 384 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1910 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | US 160 E | SU0156 | 6.517 | 32.843 | 1 | Y | MO2507-25 | Pavement improvement from Republic Street in Springfield to Rte. 14 in Nixa. Project involves bridge J0930. | Federal | 2521 | 630 | 0 | 3255 | 0 | NHPP |  | 104 | 2 | 325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | US 160 E | SU0289 | 6.015 | 22.3 | 0 | Y | SP2506 | Pavement improvement 0.3 mile west of Rte. AB to 0.4 mile west of I-44. | Federal | 2208 | 552 | 0 | 2764 | 0 | NHPP |  | 4 | 10 | 125 | 271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | US 160 E | SU0373 | 0.304 | 0.995 | 0 | Y |  | Rebuild pavement from 0.4 mile west of I-44 to I-44. | Federal | 1546 | 386 | 0 | 2032 | 0 | STBG |  | 100 | 40 | 203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1689 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | MO 266 E | SU0080 | 0.096 | 0.192 | 0 | Y | SP2306-23 | Add roundabouts at Rte. AB and at Rte. B west of Springfield. $919,000 Open Container funds. | Adv. CN | 3346 | 836 | 0 | 4862 | 0 | AC-STBG |  | 579 | 531 | 0 | 0 | 0 | 0 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 3651 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | MO 360 E | SU0014 | 3.679 | 14.489 | 0 | Y | SP2309-23 | Pavement resurfacing and replacement of rumble stripes from I-44 to Rte. 60 in Springfield. | Federal | 649 | 162 | 0 | 831 | 0 | NHPP |  | 20 | 1 | 1 | 1 | 1 | 177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 630 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | MO 413 S | SU0292 | 4.864 | 28.621 | 0 | Y | SP2513 | Pavement resurfacing on Sunshine Street from Rte. 360 to Rte. 13 (Kansas Expressway) in Springfield. | Federal | 2847 | 712 | 0 | 3569 | 0 | NHPP |  | 10 | 10 | 85 | 355 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | IS 44 E | SU0253 | 2.711 | 11.209 | 0 | Y | SP2504 | Pavement improvement from 0.2 mile east of Rte. 360 to 0.6 mile west of Rte. 266 in Springfield. | Federal | 2358 | 262 | 0 | 2630 | 0 | NHPP | SR0023 SR0244 | 10 | 67 | 271 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2282 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | IS 44 E | SU0452 | 69.261 | 308.222 | 0 | Y | MO2708-27 | Job Order Contracting for pavement repair on I-44, Rte. 65, Rte. 60, Rte. 160, and Rte. 13 in the urban Southwest District. | Adv. CN | 549 | 61 | 0 | 610 | 0 | AC-NHPP |  | 0 | 10 | 85 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | US 60 E | 8P0683G | 1.952 | 8.543 | 0 | Y | GR140318A1 | Capital improvement from 0.5 mile east of Rte. 65 to Rtes. NN and J. | Federal | 27204 | 6801 | 0 | 35656 | 0 | NHPP |  | 1651 | 100 | 100 | 200 | 415 | 3460 | 0 | 0 | 0 | 0 | 2926 | 0 | 0 | 0 | 0 | 0 | 0 | 26804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | US 60 E | SU0078 | 1.059 | 4.76 | 0 | Y | RP2303-23 | Capital improvement from west of County Road 103 to Rte. 360 (James River Freeway) in Republic. | Federal | 13361 | 3340 | 0 | 17851 | 0 | NHPP |  | 1150 | 72 | 20 | 1443 | 0 | 0 | 0 | 0 | 7083 | 0 | 0 | 0 | 0 | 0 | 0 | 8083 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | US 60 E | SU0291 | 0.954 | 4.537 | 0 | Y | SP2508 | Pavement improvement from Rte. 65 to west of Highland Springs Boulevard in Springfield. | Federal | 578 | 145 | 0 | 731 | 0 | NHPP | SU0294 | 8 | 2 | 6 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 641 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | US 60 E | SU0293 | 2.612 | 11.834 | 0 | Y | RP2501 | Pavement improvement from 0.3 mile west of Illinois Street to Rte. 174 in Republic. | Federal | 1431 | 358 | 0 | 1799 | 0 | NHPP |  | 10 | 10 | 28 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | US 60 E | SU0294 | 5.163 | 32.355 | 0 | Y | SP2507 | Pavement improvement from Rte. 13 (Kansas Expressway) to 1.4 miles east of Bus. 65 (Glenstone Avenue) in Springfield. | Federal | 2602 | 651 | 0 | 3273 | 0 | NHPP | SU0291 | 20 | 10 | 96 | 416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2731 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | US 60 E | SU0295 | 4.166 | 18.923 | 0 | Y | RP2502 | Pavement improvement from Rte. 174 in Republic to Rtes. 413/60/360. | Federal | 2317 | 579 | 0 | 2900 | 0 | NHPP |  | 4 | 10 | 69 | 290 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2527 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | BU 65 S | SU0003 | 8.097 | 44.031 | 0 | Y | SP2218-22A | Operational and pedestrian improvements on Glenstone Avenue from Valley Water Mill Road to McClernon Street and from Stewart Avenue to Rte. 60 (James River Freeway) in Springfield. $910,000 Open Container funds. | Federal | 2903 | 323 | 0 | 4212 | 0 | SAFETY |  | 986 | 2 | 5 | 470 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 2549 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | US 65 S | SU0254 | 3.241 | 16.859 | 0 | Y | MO2511 | Pavement improvement from James River in Springfield to 0.2 mile north of Rte. CC in Ozark. | Federal | 3433 | 858 | 0 | 4301 | 0 | NHPP |  | 10 | 122 | 436 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | MO 744 E | 8P3220 | 1.801 | 10.913 | 4 | Y | SP2214-22 | Interchange and bridge improvement on Kearney Street at Rte. 65 in Springfield. Project involves twin bridges A1648, A1649, and A2364. | Federal | 41773 | 10443 | 0 | 53696 | 0 | NHPP |  | 1480 | 1430 | 1221 | 1221 | 5112 | 0 | 0 | 0 | 0 | 6939 | 0 | 0 | 0 | 0 | 0 | 0 | 36293 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | MO 744 E | 8P3237 | 0.127 | 0.611 | 0 | Y | MO2210-22 | Replace signals on Kearney St at National Ave, Summit Ave, Broadway Ave and Delaware Ave, on Bus. 65 at Patterson Ave and Cedarbrook Ave, on Rte. FF at Rte. M in Battlefield, and on Rte. CC at Cheyenne Rd in Christian County. Upgrade signal at Rte. 744 and Grant Ave. | Adv. CN | 2431 | 608 | 0 | 3294 | 0 | AC-STBG |  | 255 | 2 | 521 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 2499 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | RT D E | 8S0745 | 2.738 | 13.424 | 0 | Y | SP1906-19 | Pavement resurfacing on Sunshine Street from 0.1 mile west of Bus. 65 (Glenstone Avenue) to Blackman Road in Springfield. | Federal | 1608 | 402 | 0 | 2085 | 0 | NHPP | 8S3133 8S3153 | 75 | 212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1798 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | RT D E | 8S3133 | 4.533 | 16.583 | 0 | Y | SP1802-22A | Add intersection turn lanes, pedestrian signals and raised medians at various locations on Sunshine Street from Bus. 65 (Glenstone Avenue) to 0.3 mile east of County Road 199. | Federal | 2050 | 513 | 0 | 3896 | 0 | NHPP | 8S0745 8S3153 | 1080 | 380 | 0 | 0 | 0 | 0 | 253 | 0 | 0 | 0 | 0 | 0 | 0 | 2183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | RT D E | 8S3153 | 2.583 | 12.683 | 0 | Y | SP1413-24A | Upgrade pedestrian facilities to comply with the ADA Transition Plan on Sunshine Street from Bus. 65 (Glenstone Avenue) to Blackman Road in Springfield. $626,000 Transportation Alternatives and $156,500 Springfield funds. | Adv. CN | 3066 | 609 | 157 | 5263 | 0 | AC-STBG | 8S0745 8S3133 | 1378 | 396 | 0 | 0 | 0 | 0 | 53 | 0 | 0 | 0 | 0 | 0 | 0 | 3436 | 0 | 0 | 0 | 0 | 0 | 783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | RT D E | 8S3215 | 5.547 | 11.094 | 2 | Y | GR2203-22 | Pavement resurfacing and replace guardrail from east of Blackman Road to Rte. 125 east of Springfield. Add curb blockout to bridge over Pierson Creek. Project involves bridges A3055 and A3056. | Adv. CN | 1470 | 367 | 0 | 1892 | 0 | AC-STBG | 8S3211 SR0166 SU0077 | 55 | 195 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1642 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | RT D E | SU0148 | 0.032 | 0.16 | 0 | Y | SP2401-24 | Replace signals at Oak Grove Avenue and Ventura Avenue in Springfield. | Federal | 879 | 220 | 0 | 1129 | 0 | NHPP |  | 30 | 10 | 10 | 10 | 30 | 110 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 918 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | RT FF N | SU0290 | 1.763 | 6.932 | 0 | Y | BA2501 | Pavement improvement from 0.2 mile south of Rte. 60 (James River Freeway) to south of Weaver Road in Battlefield. | Federal | 716 | 179 | 0 | 899 | 0 | NHPP | SU0018 SU0189 SU0210 | 4 | 2 | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 786 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | RT FF S | SU0018 | 3.054 | 6.108 | 0 | Y | BA2301-23 | Pavement resurfacing from Weaver Road in Battlefield to Haseltine Road. | Adv. CN | 505 | 126 | 0 | 655 | 0 | AC-STBG | SU0189 SU0210 SU0290 | 24 | 2 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 562 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | RT FF S | SU0189 | 0.131 | 0.32 | 0 | Y |  | Intersection improvement at Weaver Road in Battlefield. | Federal | 3425 | 381 | 0 | 4076 | 0 | SAFETY | SU0018 SU0210 SU0290 | 270 | 57 | 495 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 3129 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | CST GASCONADE ST W | SU0169 | 0.176 | 0.454 | 3 | Y | SP2512-25 | Bridge rehabilitation over Rte. 65, Rte. H (Glenstone Avenue) over I-44, and Rte. 125 over BNSF Railway. Project involves bridges A2040, A7501, and A8269. | Federal | 693 | 173 | 0 | 938 | 0 | NHPP |  | 72 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 743 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | RT J S | 8S3211 | 5.504 | 11.008 | 0 | Y | GR2205-22 | Pavement resurfacing and add rumble stripes from Rte. D to 0.3 mile north of Rte. 60 east of Springfield. | Adv. CN | 1039 | 260 | 0 | 1354 | 0 | AC-STBG | 8S3215 SR0166 SU0077 | 55 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | RT J S | SU0077 | 0.319 | 0.638 | 2 | Y | GR2502-25 | Replace box culverts south of County Road 150 and south of County Road 168. Project involves culverts Y0581 and W0010. | Adv. CN | 2541 | 635 | 0 | 3596 | 0 | AC-STBG | 8S3211 8S3215 SR0166 | 400 | 539 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 2637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | RT MM S | 8S0836B | 1.511 | 3.221 | 0 | Y | RP1703-22A | Add lanes on Brookline Avenue from I-44 to Rte. 360 (James River Freeway) in Republic. Design by Republic. $7,712,886 Cost Share, $2,296,000 STBG-Urban, and $342,062 Republic funds. $6,000,000 General Revenue funds restricted and contingent upon the release of funds. | Adv. CN | 11385 | 6000 | 342 | 18667 | 0 | AC-STBG | SU0370 | 940 | 1721 | 0 | 0 | 0 | 0 | 0 | 4100 | 0 | 0 | 0 | 0 | 0 | 11906 | 0 | 0 | 0 | 0 | 0 | 8638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | RT MM S | SU0370 | 1.511 | 3.221 | 0 | Y |  | Add medians, lighting, signing, and striping for additional lanes from I-44 to Rte. 360 (James River Freeway) in Republic. | Federal | 1313 | 146 | 0 | 1509 | 0 | SAFETY | 8S0836B | 50 | 209 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | RP US65N TO IS44W W | SU0297 | 0 | 0.301 | 1 | Y | SP2514-25 | Bridge rehabilitation over I-44 in Springfield. Project involves bridge A7024. | Federal | 3450 | 863 | 0 | 4521 | 0 | NHPP |  | 208 | 639 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3674 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | RP US65N TO US60W W | SU0298 | 0 | 1.007 | 3 | Y | SP2511-25 | Bridge painting over Rte. 60 and on Rte. 65 over I-44 and bridge rehabilitation on eastbound Rte. 60 ramp over Rte. 65 in Springfield. Project involves bridges A7541, A7542, and A7024. | Federal | 1550 | 387 | 0 | 1941 | 0 | NHPP |  | 4 | 2 | 90 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1570 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | GREENE | CST WEAVER RD E | SU0210 | 0.427 | 0.861 | 0 | Y |  | Roadway widening from east of Rte. FF to Cloverdale Lane in Battlefield. $2,287,200 STBG-Urban, $571,800 Battlefield. | Adv. CN | 2242 | 14 | 547 | 2923 | 0 | AC-STBG | SU0018 SU0189 SU0290 | 120 | 157 | 325 | 0 | 0 | 0 | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 2196 | 0 | 0 | 0 | 20 | 282 | 2457 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | 5B0800X | 0 | 0 | 1 | Y | MO1105 | Payback beginning in SFY 2008 for Safe and Sound bridges in the urban Southwest District. | Federal | 0 | 1460 | 0 | 6089 | 301 - 1,000 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 4622 | 292 | 292 | 292 | 292 | 292
6 | VARIOUS | Various | SU0218 | 0 | 0 | 0 | Y | MO2701-24 | ITS operations and management of the Transportation Management Center of the Ozarks in the urban Southwest District. | Federal | 0 | 1279 | 0 | 1279 | 0 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | SU0220 | 0 | 0 | 0 | Y | MO2702-25 | On-call work zone enforcement at various locations in the urban Southwest District. | Federal | 180 | 20 | 0 | 200 | 0 | SAFETY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | SU0354 | 0 | 0 | 0 | Y |  | Job Order Contracting for ADA compliance repairs at various locations in the urban Southwest District. | Adv. CN | 233 | 58 | 0 | 296 | 0 | AC-STBG |  | 5 | 3 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | SU0359 | 0 | 0 | 0 | Y | MO2702-25 | On-call work zone enforcement at various locations in the urban Southwest District. | Federal | 180 | 20 | 0 | 200 | 0 | SAFETY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | SU0444 | 0 | 0 | 0 | Y | MO2701-24 | ITS operations and management of the Traffic Management Center of the Ozarks in the urban Southwest District. | Federal | 0 | 1058 | 0 | 1058 | 0 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | SU0445 | 0 | 0 | 0 | Y | MO2701-24 | ITS operations and management of the Transportation Management Center of the Ozarks in the urban Southwest District. | Federal | 0 | 1137 | 0 | 1137 | 0 | STATE |  | 0 | 0 | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | SU0448 | 0 | 0 | 0 | Y | MO2902-27 | On-call work zone enforcement at various locations in the urban Southwest District. | Federal | 180 | 20 | 0 | 200 | 0 | SAFETY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | SU0449 | 0 | 0 | 0 | Y | MO2703-27 | Job Order Contracting for concrete repairs in the urban Southwest District. | Adv. CN | 615 | 154 | 0 | 769 | 0 | AC-STBG |  | 0 | 3 | 6 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 637 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | SU0450 | 0 | 0 | 1 | Y | MO2704-27 | Job Order Contracting for bridge repairs at various locations in the urban Southwest District. | Adv. CN | 205 | 51 | 0 | 256 | 0 | AC-STBG |  | 0 | 5 | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | SU0451 | 0 | 0 | 0 | Y | MO2705-27 | Job Order Contracting for guard cable and guardrail repair in the urban Southwest District. | Adv. CN | 1484 | 371 | 0 | 1855 | 0 | AC-STBG |  | 0 | 5 | 305 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1545 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | SU0471 | 0 | 0 | 0 | Y | MO2706-27 | Pedestrian safety improvements at various locations in the urban Southwest District. | Federal | 1400 | 155 | 0 | 1555 | 0 | SAFETY |  | 0 | 50 | 100 | 250 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 1103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | VARIOUS | Various | SU0527 | 0 | 0 | 0 | Y | MO2707-27 | Bicycle and pedestrian safety improvements at various locations in the urban Southwest District. | Federal | 653 | 72 | 0 | 725 | 0 | SAFETY |  | 0 | 80 | 120 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 523 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BOLLINGER | MO 34 E | SE0067 | 0.2 | 0.4 | 0 | N |  | Add intersection turn lanes at the north intersection of Rte. 51 in Marble Hill. | Federal | 798 | 200 | 0 | 1048 | 0 | NHPP |  | 50 | 20 | 157 | 0 | 0 | 0 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 739 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BOLLINGER | MO 51 S | SE0224 | 9.9 | 19.8 | 0 | N |  | Pavement resurfacing from south intersection with Rte. 34 in Marble Hill to Rte. 91. | Adv. CN | 1361 | 340 | 0 | 1711 | 0 | AC-STBG |  | 10 | 10 | 75 | 169 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1447 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BOLLINGER | RT UU E | SE0064 | 7.524 | 15.048 | 0 | N |  | Pavement resurfacing from Rte. B to Rte. 34. | Adv. CN | 748 | 187 | 0 | 950 | 0 | AC-STBG |  | 15 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 838 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BUTLER | MO 142 E | SE0226 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Cane Creek. Project involves bridge S0523. | Federal | 895 | 224 | 0 | 1133 | 0 | NHPP |  | 14 | 50 | 50 | 150 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 851 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BUTLER | MO 142 E | SE0375 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Big Hunting Drainage Ditch. Project involves bridge S0565. | Federal | 1422 | 355 | 0 | 1777 | 0 | NHPP |  | 0 | 20 | 20 | 20 | 30 | 125 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BUTLER | US 160 W | SE0060 | 0.1 | 0.2 | 0 | N |  | Add roundabout at Rte. C and Rte. V. | Federal | 3391 | 377 | 0 | 3919 | 0 | SAFETY |  | 151 | 375 | 0 | 0 | 0 | 0 | 0 | 385 | 0 | 0 | 0 | 0 | 0 | 3008 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BUTLER | MO 51 N | SE0118 | 0.164 | 0.328 | 1 | N |  | Bridge replacement over St. Francis River. Project involves bridge J0092. | Federal | 5429 | 1357 | 0 | 7376 | 0 | NHPP |  | 590 | 620 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 6161 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BUTLER | MO 53 S | SE0061 | 2.043 | 4.086 | 0 | N |  | Add turn lane from Rte. 142 to Rte. UU. | Federal | 8182 | 2045 | 0 | 10527 | 0 | NHPP |  | 300 | 200 | 800 | 0 | 0 | 0 | 0 | 2300 | 0 | 0 | 0 | 0 | 0 | 0 | 6927 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BUTLER | BU 67 N | SE0106 | 0 | 0.1 | 1 | N |  | Bridge rehabilitation on northbound lane over Pike Creek. Project involves bridge A0595. | Federal | 903 | 226 | 0 | 1175 | 0 | NHPP |  | 46 | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BUTLER | US 67 S | SE0126 | 6.126 | 26.457 | 0 | N |  | Pavement preservation treatment on northbound lane from Rte. 60 to County Road 402 and on southbound lane from County Road 521 to Rte. 60. | Federal | 3678 | 920 | 0 | 4644 | 0 | NHPP |  | 46 | 80 | 40 | 396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BUTLER | US 67 S | SE0140 | 0.6 | 1.2 | 3 | N |  | Bridge replacement over Harviell Drainage Ditch, Hart Drainage Ditch, and Neelyville Drainage Ditch. Project involves bridges F0665, K0982, and K0983. | Federal | 4892 | 1223 | 0 | 6465 | 0 | NHPP |  | 350 | 485 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 5609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BUTLER | W OR 67 S | SE0091 | 2.415 | 4.83 | 0 | N |  | Pavement resurfacing from Rte. M to Rte. 67. | Federal | 0 | 374 | 0 | 398 | 0 | STATE |  | 24 | 1 | 10 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 306 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BUTLER | RT AA S | SE0316 | 11.677 | 23.354 | 0 | N |  | Pavement resurfacing from Rte. 60 to Rte. 51. | Adv. CN | 1230 | 307 | 0 | 1542 | 0 | AC-STBG |  | 5 | 25 | 50 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1326 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BUTLER | RT EE N | SE0109 | 0.2 | 0.4 | 1 | N |  | Bridge rehabilitation over Cane Creek Overflow. Project involves bridge N0884. | Adv. CN | 439 | 110 | 0 | 557 | 0 | AC-STBG |  | 8 | 9 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BUTLER | RT HH S | SE0210 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Stilcamp Drainage Ditch. Project involves bridge P0256. | Federal | 739 | 185 | 0 | 926 | 0 | NHPP |  | 2 | 10 | 50 | 140 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 719 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BUTLER | RT HH S | SE0211 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Ackerman Drainage Ditch. Project involves bridge P0258. | Federal | 759 | 190 | 0 | 951 | 0 | NHPP |  | 2 | 10 | 50 | 130 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 754 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BUTLER | RT M E | 9S3453 | 0.131 | 0.262 | 0 | N |  | Increase sight distance at County Road 459. | Adv. CN | 850 | 213 | 0 | 1626 | 0 | AC-STBG |  | 214 | 165 | 0 | 0 | 0 | 0 | 349 | 0 | 0 | 0 | 0 | 0 | 0 | 898 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BUTLER | RT MM E | SE0382 | 0.2 | 0.4 | 1 | N |  | Bridge painting over Harviell Drainage Ditch. Project involves bridge N0686. | Adv. CN | 148 | 37 | 0 | 185 | 0 | AC-STBG |  | 0 | 2 | 2 | 5 | 10 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BUTLER | RT PP E | SE0066 | 2.76 | 12.995 | 0 | N |  | Pavement resurfacing from roundabout to Bus. 60. | Adv. CN | 1828 | 457 | 0 | 2301 | 0 | AC-STBG |  | 16 | 30 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2055 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | BUTLER | RT WW S | SE0131 | 0.93 | 2.992 | 0 | N |  | Replace signals at Rte. WW and Henry Street in Poplar Bluff at Bus. 60 and 9th Street in Poplar Bluff and at Rte. 160 and Rte. Y in Doniphan. | Adv. CN | 2902 | 725 | 0 | 3809 | 0 | AC-STBG |  | 182 | 338 | 0 | 0 | 0 | 0 | 0 | 556 | 0 | 0 | 0 | 0 | 0 | 2733 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CAPE GIRARDEAU | MO 177 S | SE0215 | 7.401 | 16.027 | 0 | Y |  | Pavement resurfacing from Rte. 61 to Rte. J. | Adv. CN | 2385 | 596 | 0 | 2991 | 0 | AC-STBG |  | 10 | 10 | 100 | 287 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CAPE GIRARDEAU | MO 25 S | SE0072 | 0.2 | 0.4 | 0 | N |  | Intersection improvements at Rte. 74 and Rte. A. | Federal | 3725 | 414 | 0 | 4293 | 0 | SAFETY |  | 154 | 50 | 20 | 50 | 285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CAPE GIRARDEAU | MO 25 S | SE0128 | 11.183 | 23.276 | 2 | Y |  | Pavement resurfacing from Rte. 61 to Rte. 77, and add turn lanes at Rte. Z, and County Roads 325, 324, and 318. Project involves bridges J0056 and H0613. | Adv. CN | 4656 | 1164 | 0 | 5994 | 0 | AC-STBG |  | 174 | 381 | 0 | 0 | 0 | 0 | 0 | 672 | 0 | 0 | 0 | 0 | 0 | 4767 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CAPE GIRARDEAU | MO 34 E | 9P3812 | 0.4 | 0.8 | 1 | N |  | Bridge replacement over Dillard Creek. Project involves bridge J0883. | Federal | 2270 | 568 | 0 | 3052 | 0 | NHPP |  | 214 | 50 | 171 | 0 | 0 | 0 | 0 | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 2578 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CAPE GIRARDEAU | IS 55 N | 9P3122 | 1.08 | 1.992 | 3 | Y |  | Bridge rehabilitation northbound over BNSF Railway and Rte. 74 and Rte. 61 over I-55. Add roundabout at Rte. 61 and Silver Springs Road. Project involves bridges A0628, A0513, and A0514. | Federal | 5933 | 659 | 0 | 7985 | 0 | NHPP |  | 1293 | 700 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 5892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CAPE GIRARDEAU | IS 55 N | SE0201 | 4.693 | 19.13 | 0 | Y |  | Drainage upgrades from Rte. K to Bloomfield Road and from County Road 434 to Exit 105. | Federal | 1591 | 177 | 0 | 1783 | 0 | NHPP |  | 15 | 15 | 50 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1533 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CAPE GIRARDEAU | US 61 S | SE0071 | 0.2 | 1 | 0 | Y |  | Add intersection turn lanes and upgrade signals at Donna Drive. | Federal | 1805 | 451 | 0 | 2469 | 0 | NHPP |  | 213 | 410 | 0 | 0 | 0 | 0 | 0 | 346 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CAPE GIRARDEAU | MO 74 E | SE0304 | 0.2 | 1.082 | 0 | Y |  | Upgrade pedestrian facilities at Rte. 177. | Federal | 114 | 13 | 0 | 128 | 0 | SAFETY |  | 1 | 5 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CAPE GIRARDEAU | RT B S | SE0351 | 12.736 | 25.472 | 0 | N |  | Pavement resurfacing from Rte. KK to Rte. 72. | Adv. CN | 1258 | 315 | 0 | 1573 | 0 | AC-STBG | SE0385 | 0 | 213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CAPE GIRARDEAU | RT D S | 9S3773 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Cane Creek. Project involves bridge P0714. | Adv. CN | 851 | 213 | 0 | 1159 | 0 | AC-STBG |  | 85 | 74 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 990 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CAPE GIRARDEAU | RT D S | SE0385 | 16.129 | 32.58 | 1 | Y |  | Pavement resurfacing from Rte. KK to Rte. 61. Project involves bridge A2491. | Adv. CN | 1910 | 478 | 0 | 2388 | 0 | AC-STBG | SE0351 | 0 | 294 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2094 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CAPE GIRARDEAU | RP I55N TO MAIN ST W | SE0413 | 0 | 0.2 | 0 | Y |  | Upgrade signals on the northbound ramps at exit 102. | Adv. CN | 170 | 43 | 0 | 213 | 0 | AC-STBG |  | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 163 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CAPE GIRARDEAU | RT K E | SE0407 | 1.593 | 7.333 | 1 | Y |  | Pavement preservation treatment from I-55 to Rte. 61 and safety improvements at the intersection of Silver Springs Road. Project involves bridge A1471. | Federal | 2754 | 688 | 0 | 3442 | 0 | NHPP |  | 0 | 30 | 30 | 234 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CAPE GIRARDEAU | RT N E | SE0044 | 0.023 | 0.046 | 1 | N |  | Bridge replacement over Whitewater River. Project involves bridge S0291. | Federal | 1273 | 318 | 0 | 1665 | 0 | NHPP |  | 74 | 50 | 325 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 1191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CAPE GIRARDEAU | RT N E | SE0045 | 0.09 | 0.18 | 1 | N |  | Bridge replacement over Small Creek. Project involves bridge S0532. | Federal | 1108 | 277 | 0 | 1456 | 0 | NHPP |  | 71 | 55 | 265 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 1040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CAPE GIRARDEAU | RT P S | SE0310 | 12.376 | 24.752 | 0 | N |  | Pavement preservation treatment from Rte. 25 to Rte. 91. | Adv. CN | 476 | 119 | 0 | 600 | 0 | AC-STBG |  | 5 | 10 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CAPE GIRARDEAU | RT Z E | 9S3738 | 0.35 | 0.7 | 2 | N |  | Bridge replacement over Hubble Creek and Hubble Creek Overflow. Project involves bridges T0788 and T0842. | Federal | 3148 | 787 | 0 | 4433 | 0 | NHPP |  | 456 | 159 | 0 | 0 | 0 | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 3776 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CARTER | BU 60 E | SE0022 | 2.067 | 4.134 | 0 | N |  | Pavement resurfacing on Bus. 60 in Van Buren. | Adv. CN | 627 | 157 | 0 | 791 | 0 | AC-STBG |  | 7 | 5 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 703 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CARTER | US 60 W | SE0236 | 0 | 0.4 | 1 | N |  | Bridge improvement on westbound lanes over Cane Creek. Project involves bridge A1195. | Federal | 1825 | 456 | 0 | 2316 | 0 | NHPP |  | 35 | 20 | 25 | 243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1993 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CARTER | RT N E | SE0051 | 0.141 | 0.282 | 1 | N |  | Bridge replacement over Middle Brushy Creek. Project involves bridge G0770. | Adv. CN | 1462 | 365 | 0 | 1956 | 0 | AC-STBG |  | 129 | 20 | 42 | 255 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CARTER | RT U S | SE0350 | 2.148 | 4.296 | 0 | N |  | Pavement preservation treatment from Rte. 21 to Rte. 60. | Adv. CN | 109 | 27 | 0 | 136 | 0 | AC-STBG |  | 0 | 1 | 1 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | CHRISTIAN | RT T E | SE0014 | 8.383 | 16.766 | 0 | N |  | Pavement resurfacing from Rte. UU to Rte. 76 in Douglas County. | Adv. CN | 883 | 221 | 0 | 1115 | 0 | AC-STBG |  | 11 | 5 | 107 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 992 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DENT | MO 72 E | 9P3843 | 33.763 | 67.526 | 0 | N |  | Pavement resurfacing from the east intersection of Rte. 32 to the west intersection of Rte. 21. | Adv. CN | 4571 | 1143 | 0 | 5772 | 0 | AC-STBG |  | 58 | 599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DOUGLAS | MO 14 E | 9P3808 | 12.552 | 25.299 | 0 | N |  | Pavement resurfacing and add rumble stripes from Rte. Z to Rte. 5. $2,933,000 Open Container funds. | Adv. CN | 3976 | 994 | 0 | 5074 | 0 | AC-STBG |  | 104 | 403 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4567 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DOUGLAS | MO 14 E | SE0013 | 31.367 | 62.734 | 3 | N |  | Pavement resurfacing from Bus. 5 to Rte. 181. Project involves bridges H0344, J0437, and J0664. | Adv. CN | 3486 | 872 | 0 | 4399 | 0 | AC-STBG |  | 41 | 21 | 62 | 351 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3924 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DOUGLAS | BU 5 S | SE0016 | 2.362 | 5.57 | 0 | N |  | Pavement resurfacing on Bus. 5 loop in Ava. | Adv. CN | 678 | 169 | 0 | 854 | 0 | AC-STBG |  | 7 | 7 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 759 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DOUGLAS | MO 5 S | SE0297 | 0.2 | 0.4 | 0 | N |  | Intersection improvements at Rte. Y. | Federal | 1412 | 157 | 0 | 1579 | 0 | SAFETY |  | 10 | 75 | 290 | 0 | 0 | 0 | 0 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 1108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DOUGLAS | MO 76 E | SE0012 | 33.111 | 66.222 | 1 | N |  | Pavement resurfacing from Rte. 5 to Rte. 181. Project involves bridge P0351. | Adv. CN | 3819 | 955 | 0 | 4817 | 0 | AC-STBG |  | 43 | 25 | 25 | 25 | 25 | 362 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4312 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DOUGLAS | MO 76 E | SE0025 | 0.047 | 0.094 | 1 | N |  | Bridge rehabilitation over Indian Creek. Project involves bridge T0972. | Federal | 980 | 245 | 0 | 1288 | 0 | NHPP |  | 63 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1076 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DOUGLAS | MO 76 E | SE0289 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Clifty Creek. Project involves bridge T0609. | Federal | 1758 | 439 | 0 | 2217 | 0 | NHPP |  | 20 | 20 | 35 | 86 | 343 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 1684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DUNKLIN | MO 108 E | SE0346 | 5.69 | 11.512 | 0 | N |  | Pavement preservation treatment from Arkansas State line to Rte. 412. | Adv. CN | 239 | 60 | 0 | 299 | 0 | AC-STBG |  | 0 | 5 | 5 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DUNKLIN | MO 153 S | SE0070 | 0.1 | 0.2 | 1 | N |  | Bridge replacement over Drainage Slough. Project involves bridge J0854. | Federal | 638 | 159 | 0 | 878 | 0 | NHPP |  | 81 | 105 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 665 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DUNKLIN | MO 164 E | SE0353 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Lateral Ditch 18. Project involves bridge L0303. | Federal | 1440 | 360 | 0 | 1800 | 0 | NHPP |  | 0 | 20 | 20 | 30 | 30 | 145 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DUNKLIN | BU 25 S | SE0144 | 1.405 | 2.863 | 0 | N |  | Add center turn lane from Rte. 25 to Broadwater Road. | Adv. CN | 2909 | 727 | 0 | 3996 | 0 | AC-STBG |  | 360 | 350 | 0 | 0 | 0 | 0 | 0 | 820 | 0 | 0 | 0 | 0 | 0 | 2466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DUNKLIN | MO 53 S | SE0221 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Lost Creek. Project involves bridge K0682. | Federal | 1125 | 281 | 0 | 1433 | 0 | NHPP |  | 27 | 50 | 50 | 165 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 1123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DUNKLIN | MO 53 S | SE0352 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Lateral Ditch 1. Project involves bridge G0584. | Federal | 1727 | 432 | 0 | 2159 | 0 | NHPP |  | 0 | 20 | 20 | 40 | 40 | 280 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DUNKLIN | MO 84 E | SE0132 | 1.232 | 4.029 | 0 | Y |  | Replace signals at Kennett Street and Main Street in Kennett, Rte. 61, and Cape Rock Drive in Cape Girardeau, and at Rte. 62, Rte. 105 in Charleston, and Rte. 114 and West Street in Sikeston. | Adv. CN | 3920 | 980 | 0 | 5053 | 0 | AC-STBG |  | 153 | 300 | 0 | 0 | 0 | 0 | 0 | 960 | 0 | 0 | 0 | 0 | 0 | 3640 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DUNKLIN | RT DD W | SE0095 | 0.367 | 0.737 | 4 | N |  | Bridge painting over Saint Francis River, Black River, and over Rte. 60 at Marble Hill Road and Rte. T in Butler County. Project involves bridges A2382, A3723, A3266, and A3681. | Adv. CN | 1215 | 304 | 0 | 1565 | 0 | AC-STBG |  | 46 | 144 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DUNKLIN | RT M S | SE0336 | 2.514 | 5.028 | 0 | N |  | Pavement preservation treatment from Rte. 25 to Rte. 153. | Adv. CN | 122 | 31 | 0 | 153 | 0 | AC-STBG |  | 0 | 5 | 5 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DUNKLIN | RT MM N | SE0130 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Lateral Ditch 1. Project involves bridge N0626. | Federal | 1100 | 275 | 0 | 1490 | 0 | NHPP |  | 115 | 50 | 210 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 1095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DUNKLIN | RT MM N | SE0338 | 6.566 | 13.132 | 0 | N |  | Pavement preservation treatment from Rte. U to Rte. J. | Adv. CN | 250 | 62 | 0 | 312 | 0 | AC-STBG |  | 0 | 5 | 5 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DUNKLIN | RT NN S | SE0308 | 16.24 | 32.48 | 0 | N |  | Pavement preservation treatment from Rte. 412 to the Arkansas State line. | Adv. CN | 779 | 195 | 0 | 979 | 0 | AC-STBG |  | 5 | 10 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 885 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | DUNKLIN | RT UU E | SE0065 | 0.4 | 0.8 | 2 | N |  | Bridge replacement over Lateral Ditch 78 and Lateral Ditch 79. Project involves bridges P0663 and P0664. | Federal | 0 | 1657 | 0 | 1893 | 0 | STATE |  | 236 | 245 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 1372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | HOWELL | MO 137 S | 9S3801 | 0.223 | 0.446 | 1 | N |  | Bridge replacement over BNSF Railway. Project involves bridge K0789. | Federal | 6146 | 1537 | 0 | 8325 | 0 | NHPP | 9S3818 | 642 | 589 | 0 | 0 | 0 | 0 | 0 | 1231 | 0 | 0 | 0 | 0 | 0 | 5863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | HOWELL | MO 142 E | 9S3684 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Myatt Creek. Project involves bridge P0058. | Federal | 2140 | 535 | 0 | 2845 | 0 | NHPP | SE0032 SE0034 | 170 | 421 | 0 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 2243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | HOWELL | MO 142 E | 9S3846 | 26.175 | 52.35 | 0 | N |  | Pavement resurfacing from Rte. E to Bus. 63 in Thayer. | Adv. CN | 2616 | 654 | 0 | 3317 | 0 | AC-STBG |  | 47 | 85 | 277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2908 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | HOWELL | US 60 E | SE0139B | 89.221 | 362.279 | 0 | N |  | Erosion control repairs at various locations along Rte. 60 in the Southeast District. | Federal | 923 | 231 | 0 | 1174 | 0 | NHPP |  | 20 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | HOWELL | US 63 S | SE0406 | 4.441 | 18.648 | 0 | N |  | Pavement rehabilitation from 0.1 mile north of Rte. CC to Creamery Road. | Adv. CN | 518 | 129 | 0 | 647 | 0 | AC-STBG |  | 0 | 30 | 67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | HOWELL | RT CC E | SE0306 | 10.381 | 20.762 | 0 | N |  | Add rumble stripes from Rte. AD to Rte. 63. $955,000 Open Container funds. | Federal | 3863 | 429 | 0 | 4302 | 0 | SAFETY |  | 10 | 200 | 348 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 3724 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | HOWELL | RT E S | SE0320 | 9.967 | 19.934 | 0 | N |  | Pavement resurfacing from Rte. 160 to Arkansas State line. | Adv. CN | 1142 | 285 | 0 | 1457 | 0 | AC-STBG |  | 30 | 10 | 50 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | HOWELL | RT JJ S | SE0011 | 12.994 | 25.988 | 0 | N |  | Pavement resurfacing from Rte. 160 to Arkansas State line (two disconnected sections). | Adv. CN | 1890 | 473 | 0 | 2380 | 0 | AC-STBG |  | 17 | 9 | 30 | 201 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | HOWELL | RT JJ S | SE0034 | 0.061 | 0.122 | 1 | N |  | Bridge replacement over South Fork Spring River. Project involves bridge P0797. | Federal | 1320 | 330 | 0 | 1790 | 0 | NHPP | 9S3684 SE0032 | 123 | 284 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 1366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | IRON | MO 143 S | SE0318 | 11.214 | 22.428 | 4 | N |  | Pavement resurfacing from Rte. 49 to Big Creek at Sam A. Baker State Park. Project involves bridges A2411, N0669, R0343, and T0113. | Adv. CN | 1404 | 351 | 0 | 1775 | 0 | AC-STBG |  | 20 | 10 | 10 | 10 | 25 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | IRON | MO 21 S | 9P3570 | 6.81 | 13.62 | 0 | N |  | Pavement resurfacing from Rte. 32 to Rte. N. | Adv. CN | 1634 | 408 | 0 | 2074 | 0 | AC-STBG |  | 32 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1826 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | IRON | MO 32 E | SE0038 | 0.085 | 0.17 | 1 | N |  | Bridge replacement over Reid Creek. Project involves bridge G0269. | Federal | 1754 | 439 | 0 | 2255 | 0 | NHPP |  | 62 | 30 | 40 | 361 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 1729 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | IRON | MO 32 E | SE0039 | 0.059 | 0.118 | 1 | N |  | Bridge replacement over Richardson Creek. Project involves bridge G0270. | Federal | 962 | 240 | 0 | 1264 | 0 | NHPP |  | 62 | 25 | 35 | 159 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 965 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | IRON | MO 32 E | SE0040 | 0.326 | 0.652 | 1 | N |  | Bridge replacement over Keesling Creek. Project involves bridge G0272. | Federal | 1387 | 347 | 0 | 1787 | 0 | NHPP |  | 53 | 40 | 60 | 222 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 1396 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | IRON | MO 32 E | SE0148 | 8.22 | 16.44 | 0 | N |  | Pavement preservation treatment, add shoulders, curve widening, and curve relocation from Rte. KK to Rte. Z. | Adv. CN | 5234 | 1309 | 0 | 6705 | 0 | AC-STBG |  | 162 | 75 | 667 | 0 | 0 | 0 | 0 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 5763 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | IRON | MO 49 S | SE0240 | 0.2 | 0.4 | 1 | N |  | Bridge improvement over Union Pacific Railroad. Project involves bridge G0878. | Federal | 2243 | 561 | 0 | 2864 | 0 | NHPP |  | 60 | 50 | 125 | 320 | 0 | 0 | 0 | 0 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 2230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | IRON | RT E E | SE0241 | 0.2 | 0.4 | 1 | N |  | Bridge improvement over Marble Creek. Project involves bridge T0222. | Federal | 2382 | 595 | 0 | 3027 | 0 | NHPP |  | 50 | 50 | 116 | 341 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 2429 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | IRON | RT M E | SE0120 | 0.2 | 0.4 | 1 | N |  | Bridge box culvert extension over Mill Dam Creek. Project involves bridge X0524. | Federal | 421 | 105 | 0 | 603 | 0 | NHPP |  | 77 | 54 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 464 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | IRON | RT U E | SE0239 | 0.2 | 0.4 | 1 | N |  | Bridge improvement over Logan Creek. Project involves bridge F0989. | Adv. CN | 1159 | 290 | 0 | 1469 | 0 | AC-STBG |  | 20 | 20 | 80 | 226 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 1091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MADISON | BU 67 S | SE0018 | 3.908 | 7.816 | 0 | N |  | Pavement resurfacing from Rte. 72 to County Road 205. | Adv. CN | 865 | 216 | 0 | 1093 | 0 | AC-STBG | SE0017 SE0414 | 12 | 20 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MADISON | E OR 67 S | SE0017 | 0.695 | 1.39 | 0 | N |  | Pavement resurfacing from Rte. 72 to end of state maintenance. | Federal | 0 | 198 | 0 | 202 | 0 | STATE | SE0018 | 4 | 1 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MADISON | US 67 S | SE0139 | 25.245 | 101.449 | 0 | N |  | Erosion control repairs at various locations along Rte. 67 in the Southeast District. | Federal | 244 | 61 | 0 | 308 | 0 | NHPP |  | 3 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MADISON | MO 72 E | SE0043 | 2.253 | 4.478 | 0 | N |  | Pavement preservation treatment from Rte. 67 to Rte. OO. | Federal | 790 | 197 | 0 | 1005 | 0 | NHPP |  | 18 | 5 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 907 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MADISON | MO 72 W | SE0085 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Turkey Creek. Project involves bridge G0328. | Adv. CN | 1981 | 495 | 0 | 2866 | 0 | AC-STBG |  | 390 | 227 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 2208 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MADISON | RT C E | SE0035 | 0.048 | 0.096 | 1 | N |  | Bridge replacement over Leatherwood Creek. Project involves bridge T0763. | Federal | 1026 | 257 | 0 | 1447 | 0 | NHPP | SE0036 SE0037 | 164 | 313 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 957 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MADISON | RT C E | SE0160 | 0.07 | 0.14 | 0 | N |  | Slope repairs 0.1 mile west of Saint Francis River. | Federal | 947 | 237 | 0 | 1296 | 0 | STBG |  | 107 | 1 | 1 | 100 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1082 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MADISON | RT E E | SE0293 | 0.2 | 0.4 | 1 | N |  | Bridge rehabilitation over Marble Creek. Project involves bridge N0271. | Federal | 1480 | 370 | 0 | 1870 | 0 | NHPP |  | 20 | 20 | 20 | 40 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1580 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MADISON | RT E E | SE0298 | 16.1 | 32.2 | 0 | N |  | Pavement preservation treatment from Iron County line to Rte. 67. | Adv. CN | 654 | 164 | 0 | 823 | 0 | AC-STBG |  | 5 | 5 | 79 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MADISON | RT E E | SE0379 | 0.2 | 0.4 | 1 | N |  | Bridge painting over Marble Creek. Project involves bridge N0271. | Adv. CN | 277 | 69 | 0 | 346 | 0 | AC-STBG |  | 0 | 2 | 2 | 5 | 10 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 289 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MADISON | RT M S | SE0036 | 0.088 | 0.176 | 1 | N |  | Bridge replacement over Shetley Creek. Project involves bridge T0092. | Federal | 1415 | 354 | 0 | 1928 | 0 | NHPP | SE0035 SE0037 | 159 | 333 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 1423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MADISON | RT M S | SE0037 | 0.046 | 0.092 | 1 | N |  | Bridge replacement over Big Creek. Project involves bridge T0093. | Federal | 1490 | 373 | 0 | 2002 | 0 | NHPP | SE0035 SE0036 | 139 | 299 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 1551 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MADISON | RT Z E | SE0414 | 3.871 | 7.742 | 0 | N |  | Pavement improvements from Bus. 67 to County Road 258. | Adv. CN | 518 | 130 | 0 | 648 | 0 | AC-STBG | SE0018 | 0 | 25 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 561 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MISSISSIPPI | IS 57 N | 9I3730 | 1.728 | 14.741 | 0 | N |  | Rebuild pavement in the northbound lane from east of Rte. B to west of Rte. 105 and from Rte. 105 to Rte. 60 and on I-55 in the southbound lane from 0.6 mile north of Rte. O to the Arkansas State line. | Federal | 14924 | 1658 | 0 | 16652 | 0 | NHPP |  | 70 | 50 | 700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MISSISSIPPI | IS 57 S | SE0187 | 0.5 | 2 | 1 | N |  | Payment to IDOT for deck overlay and joint repairs on Mississippi River "Cairo bridge". Project involves bridge A2000. | Federal | 5943 | 660 | 0 | 6605 | 0 | NHPP |  | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MISSISSIPPI | IS 57 S | SE0403 | 13.182 | 26.902 | 3 | N |  | Pavement resurfacing on south bound lane from 0.6 mile south of Illinois State line to 2.3 miles south of Rte. 105. Project involves bridges A2093, A2025, and A2027. | Adv. CN | 14501 | 1611 | 0 | 16112 | 0 | AC-NHPP |  | 0 | 20 | 20 | 30 | 30 | 967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MISSISSIPPI | US 60 E | 9S3707 | 4.841 | 9.682 | 0 | N |  | Add rumble stripes from Rte. EE to Mississippi River Bridge. | Federal | 1047 | 116 | 0 | 1186 | 0 | SAFETY |  | 23 | 1 | 1 | 20 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MISSISSIPPI | MO 77 S | SE0062 | 0.8 | 1.6 | 4 | N |  | Bridge replacement over Lateral Ditch 3, Main Ditch, Lateral Ditch 4, and Lateral Ditch 7. Project involves bridges T0418, T0419, T0542, and T0543. | Federal | 3841 | 960 | 0 | 5587 | 0 | NHPP |  | 786 | 867 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 3854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MISSISSIPPI | MO 77 S | SE0345 | 25.574 | 51.148 | 0 | N |  | Pavement preservation treatment from Rte. 62 to end of state maintenance. | Adv. CN | 926 | 232 | 0 | 1158 | 0 | AC-STBG |  | 0 | 5 | 5 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MISSISSIPPI | MO 80 E | SE0077 | 0.4 | 0.8 | 2 | N |  | Bridge replacement over Drainage Ditch 23 and Drainage Ditch 29. Project involves bridges F0786 and F0788. | Federal | 1774 | 444 | 0 | 2483 | 0 | NHPP |  | 265 | 374 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 1824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MISSISSIPPI | MO 80 E | SE0337 | 8.076 | 16.152 | 0 | N |  | Pavement preservation treatment from Rte. 102 to Rte. 77. | Adv. CN | 364 | 91 | 0 | 455 | 0 | AC-STBG |  | 0 | 5 | 5 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 413 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MISSISSIPPI | RT B S | SE0303 | 8.91 | 17.822 | 0 | N |  | Pavement preservation treatment from Rte. 62 to Rte. 80. | Adv. CN | 458 | 115 | 0 | 578 | 0 | AC-STBG |  | 5 | 10 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | MISSISSIPPI | RT BB S | SE0266 | 7.514 | 15.028 | 0 | N |  | Pavement preservation treatment from Rte. 80 to Rte. P. | Adv. CN | 294 | 73 | 0 | 372 | 0 | AC-STBG |  | 5 | 10 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 316 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | NEW MADRID | MO 153 S | SE0366 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 6. Project involves bridge X0037. | Federal | 1143 | 286 | 0 | 1429 | 0 | NHPP |  | 0 | 10 | 10 | 10 | 30 | 200 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 1145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | NEW MADRID | US 61 S | SE0234 | 1 | 2 | 0 | N |  | Add roundabout at Rte. 80. | Federal | 3625 | 403 | 0 | 4178 | 0 | SAFETY |  | 150 | 350 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 3661 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | NEW MADRID | RT A E | SE0376 | 0.3 | 0.6 | 1 | N |  | Bridge rehabilitation over Little River. Project involves bridge A0727. | Adv. CN | 658 | 164 | 0 | 822 | 0 | AC-STBG |  | 0 | 5 | 5 | 5 | 25 | 80 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | NEW MADRID | RT B S | SE0355 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 60. Project involves bridge L0587. | Federal | 882 | 220 | 0 | 1102 | 0 | NHPP |  | 0 | 5 | 5 | 10 | 20 | 89 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 972 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | NEW MADRID | RT D E | SE0354 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Caney Slough. Project involves bridge L0219. | Federal | 788 | 197 | 0 | 985 | 0 | NHPP |  | 0 | 10 | 10 | 20 | 30 | 81 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 833 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | NEW MADRID | RT D E | SE0356 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 14. Project involves bridge L0767. | Federal | 925 | 231 | 0 | 1156 | 0 | NHPP |  | 0 | 10 | 10 | 20 | 30 | 160 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | NEW MADRID | RT D E | SE0359 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 6. Project involves bridge L0769. | Federal | 1742 | 436 | 0 | 2178 | 0 | NHPP |  | 0 | 30 | 30 | 40 | 45 | 235 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 1783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | NEW MADRID | RT D E | SE0360 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 3. Project involves bridge L0766. | Federal | 1422 | 355 | 0 | 1777 | 0 | NHPP |  | 0 | 20 | 20 | 20 | 40 | 220 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 1453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | NEW MADRID | RT D E | SE0361 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 7. Project involves bridge L0770. | Federal | 1038 | 260 | 0 | 1298 | 0 | NHPP |  | 0 | 10 | 15 | 15 | 30 | 170 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 1039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | NEW MADRID | RT D E | SE0362 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 8. Project involves bridge L0771. | Federal | 1353 | 338 | 0 | 1691 | 0 | NHPP |  | 0 | 20 | 20 | 20 | 40 | 200 | 0 | 0 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 1372 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | NEW MADRID | RT D E | SE0363 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 37. Project involves bridge L0225. | Federal | 1181 | 295 | 0 | 1476 | 0 | NHPP |  | 0 | 20 | 20 | 20 | 40 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1196 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | NEW MADRID | RT D E | SE0364 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 42. Project involves bridge L0221. | Federal | 1118 | 279 | 0 | 1397 | 0 | NHPP |  | 0 | 10 | 20 | 20 | 40 | 170 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 1117 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | NEW MADRID | RT D E | SE0365 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 41. Project involves bridge L0222. | Federal | 1004 | 251 | 0 | 1255 | 0 | NHPP |  | 0 | 15 | 15 | 20 | 20 | 150 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 1028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | NEW MADRID | RT ZZ W | SE0107 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 52. Project involves bridge T0783. | Adv. CN | 709 | 177 | 0 | 978 | 0 | AC-STBG |  | 92 | 156 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | OREGON | MO 142 E | 9P3686 | 0.961 | 1.922 | 1 | N |  | Bridge replacement over Eleven Point River and raise roadway from bridge east 0.6 mile. Project involves bridge T0395. | Federal | 8063 | 2016 | 0 | 10943 | 0 | PROTECT |  | 864 | 100 | 758 | 0 | 0 | 0 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 9138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | OREGON | US 160 E | 9S3802 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Cox Creek. Project involves bridge H0173. | Federal | 1449 | 362 | 0 | 2036 | 0 | NHPP |  | 215 | 214 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | OREGON | US 160 E | SE0021 | 28.747 | 57.52 | 1 | N |  | Pavement resurfacing from Rte. FF to Rte. 21 and add rumble stripes from Rte. C to Rte. 21. Project involves bridge A2910. | Adv. CN | 5545 | 1386 | 0 | 7037 | 0 | AC-STBG |  | 106 | 55 | 70 | 609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6197 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | OREGON | US 160 E | SE0041 | 0.041 | 0.082 | 1 | N |  | Bridge replacement over Barren Fork Creek. Project involves bridge H0458. | Federal | 2233 | 558 | 0 | 2934 | 0 | NHPP |  | 143 | 90 | 436 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 2225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | OREGON | US 160 E | SE0190 | 0.4 | 0.8 | 1 | N |  | Bridge replacement over Eleven Point River. Project involves bridge K0272. | Federal | 3958 | 990 | 0 | 4998 | 0 | NHPP |  | 50 | 50 | 150 | 185 | 708 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 3828 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | OREGON | US 160 E | SE0290 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Dry Creek. Project involves bridge H0174. | Federal | 2019 | 505 | 0 | 2544 | 0 | NHPP |  | 20 | 40 | 40 | 45 | 245 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 2122 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | OREGON | MO 19 S | SE0033 | 0.102 | 0.204 | 1 | N |  | Bridge replacement over Eleven Point River. Project involves bridge K0344. | Federal | 4311 | 1078 | 0 | 5795 | 0 | NHPP |  | 406 | 960 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 4394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | OREGON | RT E N | SE0347 | 12.419 | 24.838 | 0 | N |  | Pavement preservation treatment from Rte. 142 to Rte. 19. | Adv. CN | 299 | 75 | 0 | 374 | 0 | AC-STBG |  | 0 | 2 | 4 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | OREGON | CST WALNUT ST E | SE0295 | 0.2 | 0.4 | 1 | N |  | Bridge rehabilitation over Warm Fork Spring River and BNSF Railway. Project involves bridge A1476. | Adv. CN | 4104 | 1026 | 0 | 5190 | 0 | AC-STBG |  | 60 | 60 | 60 | 100 | 460 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | OZARK | MO 142 E | SE0311 | 9.721 | 19.442 | 0 | N |  | Pavement preservation treatment from Rte. 101 to the north intersection of Rte. E. | Adv. CN | 380 | 95 | 0 | 480 | 0 | AC-STBG |  | 5 | 10 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 417 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | OZARK | US 160 E | SE0185 | 1 | 2 | 1 | N |  | Bridge replacement over Bull Shoals Lake. Project involves bridge K0817. | Federal | 91649 | 22912 | 0 | 115561 | 0 | NHPP |  | 1000 | 5500 | 5500 | 12016 | 0 | 0 | 0 | 0 | 2961 | 0 | 0 | 0 | 0 | 0 | 0 | 88584 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | OZARK | MO 181 N | SE0348 | 18.153 | 36.306 | 0 | N |  | Pavement preservation treatment from Rte. H to Rte. 160. | Adv. CN | 776 | 194 | 0 | 970 | 0 | AC-STBG |  | 0 | 2 | 6 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | OZARK | MO 5 N | SE0349 | 8.595 | 17.19 | 0 | N |  | Pavement preservation treatment from Rte. 160 to Arkansas State line. | Adv. CN | 378 | 95 | 0 | 473 | 0 | AC-STBG |  | 0 | 1 | 4 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 422 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | OZARK | MO 95 S | SE0191 | 0.4 | 0.8 | 1 | N |  | Bridge replacement over Brixey Creek. Project involves bridge N0328. | Federal | 1800 | 450 | 0 | 2270 | 0 | NHPP |  | 20 | 20 | 60 | 74 | 344 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 1734 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | OZARK | RT N E | SE0192 | 0.4 | 0.8 | 1 | N |  | Bridge replacement over Fork Pine Creek. Project involves bridge Y0579. | Adv. CN | 608 | 152 | 0 | 770 | 0 | AC-STBG |  | 10 | 10 | 20 | 20 | 116 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 590 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | OZARK | RT PP S | SE0015 | 5.308 | 10.616 | 0 | N |  | Pavement resurfacing from Rte. H to Rte. 160. | Adv. CN | 602 | 151 | 0 | 760 | 0 | AC-STBG |  | 7 | 4 | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | PEMISCOT | IS 155 S | SE0171 | 0.584 | 2.338 | 1 | N |  | Bridge washing over the Mississippi River. Project involves bridges A1700. | Federal | 212 | 24 | 0 | 239 | 0 | NHPP |  | 3 | 1 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | PEMISCOT | IS 155 S | SE0257 | 0.562 | 2.248 | 1 | N |  | Payment to TDOT for bridge rehabilitation over the Mississippi River. Project involves bridge A1700. | Federal | 31504 | 3500 | 0 | 35005 | 0 | NHPP |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | PEMISCOT | IS 55 N | SE0369 | 0 | 31.531 | 3 | N |  | Pavement resurfacing on northbound lane from Arkansas State line to 0.7 mile north of Rte. U. Project involves bridges A0454, A1942, and A1936. | Federal | 16064 | 1785 | 0 | 17849 | 0 | NHPP |  | 0 | 20 | 20 | 30 | 30 | 1067 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16682 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | PEMISCOT | IS 55 S | SE0333 | 3.949 | 11.777 | 0 | N |  | Repair slides and erosion in Pemiscot, New Madrid, Mississippi, Stoddard, and Dunklin counties along I-55, I-57, Rte. B, Rte. 61, Rte. 62, Rte. 60, and Rte. W. $2,892,000 Emergency Relief funds, April 2025 flood event. | Federal | 3150 | 788 | 0 | 4128 | 0 | OTHER |  | 175 | 323 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 3615 | 0 | 0 | 0 | 0 | 0 | 2892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | PEMISCOT | RT A E | SE0220 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Clay Root Bay. Project involves bridge T0697. | Federal | 766 | 192 | 0 | 968 | 0 | NHPP |  | 10 | 30 | 50 | 130 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 726 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | PEMISCOT | RT C S | SE0258 | 0.014 | 0.028 | 1 | N |  | Bridge replacement over Drainage Ditch 1. Project involves bridge S0715. | Federal | 878 | 220 | 0 | 1100 | 0 | NHPP |  | 2 | 5 | 50 | 50 | 80 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | PEMISCOT | RT Z S | SE0222 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Main Ditch 1. Project involves bridge N0186. | Federal | 2420 | 605 | 0 | 3056 | 0 | NHPP |  | 31 | 50 | 100 | 260 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 2574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | PERRY | MO 51 S | SE0395 | 107.283 | 277.789 | 0 | Y |  | Job Order Contracting to replace signage on major highways in St. Francois, Ste. Genevieve, Madison, Perry, Cape Girardeau, Wayne, Bollinger, Stoddard, Scott, Butler, New Madrid, Mississippi, Pemiscot, and Dunklin Counties. | Federal | 472 | 118 | 0 | 590 | 0 | NHPP |  | 0 | 15 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | PERRY | RT C S | SE0283 | 0.2 | 0.4 | 1 | N |  | Bridge rehabilitation over Cinque Hommes Creek. Project involves bridge A0901. | Federal | 1689 | 422 | 0 | 2121 | 0 | NHPP |  | 10 | 20 | 50 | 100 | 161 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1775 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | PERRY | RT C S | SE0380 | 0.2 | 0.4 | 1 | N |  | Bridge painting over Cinque Hommes Creek. Project involves bridge A0901. | Adv. CN | 322 | 81 | 0 | 403 | 0 | AC-STBG |  | 0 | 2 | 2 | 5 | 10 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 343 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | PERRY | RT E S | SE0284 | 0.2 | 0.4 | 1 | N |  | Bridge rehabilitation over Bois Brule Creek. Project involves bridge N0661. | Federal | 1118 | 280 | 0 | 1403 | 0 | NHPP |  | 5 | 5 | 10 | 50 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | PERRY | RT E S | SE0381 | 0.2 | 0.4 | 1 | N |  | Bridge painting over Bois Brule Creek. Project involves bridge N0661. | Adv. CN | 227 | 57 | 0 | 284 | 0 | AC-STBG |  | 0 | 2 | 2 | 5 | 10 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 231 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | PERRY | RT O E | SE0279 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Apple Creek. Project involves bridge N0606. | Federal | 1772 | 443 | 0 | 2225 | 0 | NHPP |  | 10 | 15 | 35 | 90 | 169 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1901 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | RIPLEY | MO 142 E | SE0032 | 0.043 | 0.086 | 1 | N |  | Bridge replacement over Logan Creek. Project involves bridge S0889. | Federal | 1760 | 440 | 0 | 2329 | 0 | NHPP | 9S3684 SE0034 | 129 | 320 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 1863 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | RIPLEY | US 160 E | SE0358 | 11.56 | 28.841 | 0 | N |  | Pavement resurfacing from west of Rte. JJ to Rte. 67. | Federal | 4626 | 1156 | 0 | 5782 | 0 | NHPP |  | 0 | 10 | 60 | 555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5157 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | RIPLEY | MO 21 S | SE0335 | 8.578 | 17.156 | 0 | N |  | Pavement preservation treatment from Rte. 142 to Arkansas State line. | Adv. CN | 213 | 53 | 0 | 266 | 0 | AC-STBG |  | 0 | 1 | 3 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 237 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | RIPLEY | RT T S | SE0344 | 5.642 | 11.284 | 0 | N |  | Pavement preservation treatment from Rte. 160 to Rte. 142. | Adv. CN | 147 | 37 | 0 | 184 | 0 | AC-STBG |  | 0 | 1 | 2 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 164 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SCOTT | E OR 55 S | SE0387 | 2.334 | 4.668 | 0 | N |  | Pavement resurfacing from 0.2 mile south of Rte. M to Rte. PP. | Federal | 0 | 1928 | 0 | 1928 | 0 | STATE |  | 0 | 50 | 75 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SCOTT | US 61 S | 9S3777 | 11.03 | 22.876 | 0 | N |  | Pavement resurfacing from Rte. 77 to Rte. Y. | Adv. CN | 3214 | 804 | 0 | 4099 | 0 | AC-STBG |  | 81 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3738 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SCOTT | US 61 S | SE0235 | 1.38 | 6.277 | 0 | N |  | Upgrade pedestrian signals and pavement markings at Tanner Street, Lake Street, Pine Street, and Smith Street. Add sidewalk from Hunter Street to Smith Street. | Federal | 2525 | 280 | 0 | 2880 | 0 | SAFETY |  | 75 | 400 | 600 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 1780 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SCOTT | MO 77 S | SE0213 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 1. Project involves bridge J0384. | Federal | 1378 | 345 | 0 | 1730 | 0 | NHPP |  | 7 | 10 | 50 | 50 | 209 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 1369 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SCOTT | MO 77 S | SE0416 | 1.5 | 3 | 0 | N |  | Safety improvements from 3.3 miles south of Rte. D to 4.8 miles south of Rte. D. | Federal | 2890 | 321 | 0 | 3211 | 0 | SAFETY |  | 0 | 20 | 50 | 181 | 0 | 0 | 0 | 0 | 505 | 0 | 0 | 0 | 0 | 0 | 0 | 2455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SCOTT | MO 91 S | SE0278 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drain Ditch 1. Project involves bridge S0615. | Federal | 1032 | 258 | 0 | 1310 | 0 | NHPP |  | 20 | 20 | 20 | 22 | 122 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 1091 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SCOTT | MO 91 S | SE0280 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 4. Project involves bridge S0616. | Federal | 866 | 217 | 0 | 1103 | 0 | NHPP |  | 20 | 20 | 20 | 20 | 120 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 888 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SCOTT | RT A E | 9S3827 | 9.02 | 18.163 | 1 | N |  | Pavement resurfacing from Rte. 77 to Rte. 61. Project involves bridge A6451. | Adv. CN | 1168 | 292 | 0 | 1496 | 0 | AC-STBG |  | 36 | 127 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SCOTT | RT A E | SE0178 | 0.577 | 1.784 | 0 | N |  | Upgrade pedestrian facilities at various locations in New Hamburg and Dexter. | Federal | 1576 | 394 | 0 | 2050 | 0 | STBG |  | 80 | 5 | 139 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SCOTT | RT N N | SE0143 | 0.1 | 0.2 | 0 | N |  | Widen intersection at Rte. K. | Adv. CN | 608 | 152 | 0 | 941 | 0 | AC-STBG |  | 45 | 50 | 0 | 0 | 0 | 0 | 136 | 0 | 0 | 0 | 0 | 0 | 0 | 710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SCOTT | RT N S | 9S3811 | 10.09 | 20.18 | 0 | N |  | Pavement resurfacing from Rte. E to Rte. D. | Adv. CN | 950 | 237 | 0 | 1217 | 0 | AC-STBG |  | 30 | 106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1081 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SCOTT | RT O S | SE0281 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over North Cut Ditch. Project involves bridge N0257. | Adv. CN | 1702 | 425 | 0 | 2137 | 0 | AC-STBG |  | 10 | 15 | 40 | 90 | 154 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 1817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SCOTT | RT Y E | SE0267 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 2. Project involves bridge L0299. | Federal | 1079 | 270 | 0 | 1369 | 0 | NHPP |  | 20 | 20 | 25 | 40 | 185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1079 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SCOTT | RT Y E | SE0288 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 1. Project involves bridge L0300. | Federal | 1005 | 251 | 0 | 1266 | 0 | NHPP |  | 10 | 20 | 20 | 40 | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SCOTT | RT ZZ E | SE0285 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 1. Project involves bridge L0270. | Federal | 1034 | 258 | 0 | 1297 | 0 | NHPP |  | 5 | 10 | 20 | 20 | 95 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 1136 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SHANNON | MO 106 E | SE0367 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Jacks Fork. Project involves bridge K0924. | Federal | 7076 | 1769 | 0 | 8845 | 0 | NHPP |  | 0 | 100 | 200 | 200 | 200 | 1264 | 0 | 0 | 0 | 0 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 6772 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SHANNON | MO 106 E | SE0368 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Spring Valley Creek. Project involves bridge K0989. | Federal | 3034 | 758 | 0 | 3792 | 0 | NHPP |  | 0 | 50 | 50 | 50 | 150 | 528 | 0 | 0 | 0 | 0 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 2855 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SHANNON | MO 19 N | SE0415 | 0.3 | 0.6 | 1 | N |  | Bridge replacement over Current River. Project involves bridge G0804. | Adv. CN | 14289 | 3572 | 0 | 17861 | 0 | AC-STBG |  | 0 | 100 | 100 | 100 | 500 | 2329 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 14721 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SHANNON | MO 19 S | 9P3814 | 0.259 | 0.518 | 1 | N |  | Bridge replacement over Spring Valley Creek. Project involves bridge J0420. | Federal | 10802 | 2700 | 0 | 14833 | 0 | NHPP |  | 1331 | 200 | 1208 | 0 | 0 | 0 | 0 | 729 | 0 | 0 | 0 | 0 | 0 | 0 | 11365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SHANNON | MO 99 S | SE0193 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Spring Creek. Project involves bridge K0274. | Adv. CN | 1880 | 470 | 0 | 2370 | 0 | AC-STBG |  | 20 | 40 | 40 | 40 | 168 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 2040 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | SHANNON | RT JJ S | SE0194 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Castro Valley. Project involves bridge N0185. | Adv. CN | 1535 | 384 | 0 | 1939 | 0 | AC-STBG |  | 20 | 20 | 50 | 50 | 276 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1513 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ST. FRANCOIS | MO 221 S | 9S3853 | 0.082 | 0.164 | 1 | N |  | Box culvert replacement over Brewers Creek. Project involves culvert Y0935. | Federal | 988 | 247 | 0 | 1374 | 0 | NHPP |  | 112 | 111 | 0 | 0 | 0 | 0 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 1124 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ST. FRANCOIS | MO 32 E | 9P3852 | 6.954 | 13.908 | 2 | N |  | Pavement resurfacing and bridge rehabilitation over Flat River from High Street in Bismarck to the south intersection of Bus. 32. Project involves bridges A2668 and A2670. | Adv. CN | 3323 | 831 | 0 | 4204 | 0 | AC-STBG |  | 50 | 341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3813 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ST. FRANCOIS | MO 47 S | SE0370 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Three Hill Creek. Project involves bridge T0115. | Federal | 970 | 243 | 0 | 1213 | 0 | NHPP |  | 0 | 10 | 10 | 30 | 30 | 82 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 1019 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ST. FRANCOIS | BU 67 S | 9S3851 | 2.991 | 6.736 | 0 | N |  | Pavement resurfacing from Rte. 67 to Main Street through Park Hills. | Federal | 1101 | 275 | 0 | 1412 | 0 | NHPP |  | 36 | 20 | 85 | 0 | 0 | 0 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 1177 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ST. FRANCOIS | US 67 N | SE0195 | 0 | 0.834 | 1 | N |  | Bridge replacement on northbound lane over Rte. 8. Project involves bridge A0654. | Federal | 2217 | 554 | 0 | 2781 | 0 | NHPP |  | 10 | 40 | 40 | 40 | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2441 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ST. FRANCOIS | US 67 S | SE0068 | 0.4 | 1.615 | 1 | N |  | Interchange and bridge improvements at Rte. 32 in Leadington. Project involves bridge A0144. | Federal | 12333 | 3083 | 0 | 16667 | 0 | NHPP |  | 1251 | 500 | 150 | 987 | 0 | 0 | 0 | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 13717 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ST. FRANCOIS | US 67 S | SE0233 | 1.2 | 4.876 | 0 | N |  | Add J-turns at Hildebrecht Road. | Federal | 2435 | 271 | 0 | 2856 | 0 | SAFETY |  | 150 | 267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2439 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ST. FRANCOIS | MO 8 E | SE0010 | 6.85 | 14.12 | 0 | N |  | Pavement resurfacing and intersection improvements from the Washington County line to RR Bridge (Bus. 67) and add shoulders from east of Rte. P to RR Bridge (Bus. 67). | Federal | 4606 | 1152 | 0 | 5851 | 0 | NHPP |  | 93 | 100 | 600 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 5023 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ST. FRANCOIS | RT D S | SE0050 | 0.52 | 1.04 | 0 | N |  | Rebuild pavement and add turn lanes from Rte. EE to Rte. 32. | Adv. CN | 2735 | 684 | 0 | 4263 | 0 | AC-STBG |  | 532 | 634 | 0 | 0 | 0 | 0 | 312 | 0 | 0 | 0 | 0 | 0 | 0 | 2785 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ST. FRANCOIS | RT D S | SE0305 | 9.255 | 18.51 | 0 | N |  | Add rumble stripes from Rte. K to Rte. EE. $1,989,000 Open Container funds. | Federal | 2493 | 277 | 0 | 2780 | 0 | SAFETY |  | 10 | 100 | 261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ST. FRANCOIS | RT K E | SE0019 | 6.953 | 14.094 | 0 | N |  | Pavement resurfacing from Rte. 47 to Rte. D. | Adv. CN | 1189 | 297 | 0 | 1504 | 0 | AC-STBG |  | 18 | 19 | 121 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ST. FRANCOIS | RT K E | SE0154 | 0.135 | 0.299 | 0 | N |  | Intersection improvements at North Wood Drive. | Adv. CN | 2063 | 516 | 0 | 2625 | 0 | AC-STBG |  | 46 | 20 | 25 | 156 | 0 | 0 | 0 | 0 | 702 | 0 | 0 | 0 | 0 | 0 | 0 | 1676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ST. FRANCOIS | RT K E | SE0294 | 0.2 | 0.4 | 1 | N |  | Bridge rehabilitation over Big River. Project involves bridge A0968. | Federal | 2124 | 531 | 0 | 2695 | 0 | NHPP |  | 40 | 40 | 40 | 80 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ST. FRANCOIS | RT N S | SE0232 | 9.481 | 18.962 | 1 | N |  | Pavement resurfacing and add rumble stripes from Rte. 32 to Rte. 21. Project involves bridge K0401. | Federal | 4938 | 549 | 0 | 5627 | 0 | SAFETY |  | 140 | 50 | 50 | 419 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4968 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ST. FRANCOIS | RT OO S | 9S3490 | 16.76 | 33.52 | 0 | N |  | Pavement resurfacing and add rumble stripes from 0.1 mile south of Rte. 32 in Farmington to Rte. 72 in Fredericktown. $3,027,000 Open Container funds. | Adv. CN | 6176 | 1544 | 0 | 8034 | 0 | AC-STBG |  | 314 | 50 | 50 | 557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7063 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | ST. FRANCOIS | RP WOR67S TO US67S S | SE0331 | 0.571 | 0.967 | 0 | N |  | Payment to Farmington to add roundabout at Woodlawn Drive and Bray Road and add signals at Maple Street and Rte. 67 northbound ramp. Design, right of way, and construction by Farmington. $2,920,880 Cost Share funds. | Adv. CN | 2357 | 589 | 0 | 2951 | 0 | AC-STBG |  | 5 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2921 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STE. GENEVIEVE | MO 32 E | 9S3854 | 0.8 | 2 | 0 | N |  | Drainage improvements 0.2 mile east of Rte. 61 and at Siebert Road. | Adv. CN | 1590 | 397 | 0 | 2147 | 0 | AC-STBG |  | 160 | 100 | 243 | 0 | 0 | 0 | 0 | 135 | 0 | 0 | 0 | 0 | 0 | 0 | 1509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STE. GENEVIEVE | IS 55 S | SE0200 | 198.084 | 812.11 | 0 | Y |  | Job Order Contracting for concrete pavement repair from the Jefferson County line to the Arkansas State line and all of I-57 and all of I-155. | Adv. CN | 468 | 52 | 0 | 522 | 0 | AC-NHPP |  | 2 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STE. GENEVIEVE | IS 55 S | SE0238 | 198.084 | 812.11 | 0 | Y |  | Job Order Contracting for concrete pavement repair from the Jefferson County line to the Arkansas State line and all of I-57 and all of I-155. | Adv. CN | 482 | 54 | 0 | 537 | 0 | AC-NHPP |  | 1 | 1 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STE. GENEVIEVE | IS 55 S | SE0392 | 198.084 | 812.11 | 0 | Y |  | Job Order Contracting for concrete pavement repair from the Jefferson County line to the Arkansas State line and all of I-57 and all of I-155. | Adv. CN | 736 | 82 | 0 | 818 | 0 | AC-NHPP |  | 0 | 1 | 1 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 796 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STE. GENEVIEVE | US 61 S | SE0264 | 0.2 | 0.552 | 0 | N |  | Intersection improvements at Rte. M. | Federal | 1133 | 126 | 0 | 1269 | 0 | SAFETY |  | 10 | 30 | 100 | 0 | 0 | 0 | 0 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 961 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STE. GENEVIEVE | US 61 S | SE0286 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Union Pacific Railroad. Project involves bridge J0134. | Federal | 1836 | 459 | 0 | 2315 | 0 | NHPP |  | 20 | 40 | 40 | 45 | 235 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1930 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STE. GENEVIEVE | RT EE S | SE0386 | 11.365 | 22.787 | 0 | N |  | Pavement resurfacing from Rte. C to Rte. D. | Adv. CN | 1553 | 388 | 0 | 1941 | 0 | AC-STBG |  | 0 | 75 | 187 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1679 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STE. GENEVIEVE | RT JJ E | SE0282 | 0.2 | 0.4 | 1 | N |  | Bridge rehabilitation over Terre bleue Creek. Project involves bridge R0022. | Adv. CN | 915 | 229 | 0 | 1154 | 0 | AC-STBG |  | 10 | 20 | 20 | 20 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 974 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STE. GENEVIEVE | RT Z E | SE0094 | 0.38 | 0.76 | 4 | N |  | Bridge painting over I-55 at Rte. Z, Rte. M, County Road Eisenbeis Bottom, and Rte. 32. Project involves bridges A2460, A2420, A2417, and A2406. | Adv. CN | 1353 | 338 | 0 | 1758 | 0 | AC-STBG |  | 67 | 202 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1489 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STE. GENEVIEVE | RT Z E | SE0100 | 4.321 | 8.642 | 1 | N |  | Add rumble stripes from Rte. N to Rte. 61. Project involves bridge A2460. | Federal | 1359 | 151 | 0 | 1620 | 0 | SAFETY |  | 90 | 110 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | MO 114 E | 9S3725 | 0.457 | 0.914 | 2 | N |  | Bridge replacement over Drainage Ditch 5 and bridge rehabilitation over Little River Drainage Ditch. Project involves bridges J0740 and F0565. | Federal | 2435 | 609 | 0 | 3463 | 0 | NHPP |  | 405 | 360 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 2684 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | MO 114 E | 9S3726 | 0.229 | 0.458 | 1 | N |  | Bridge replacement over Dexter Creek. Project involves bridge K0031. | Adv. CN | 1630 | 408 | 0 | 2350 | 0 | AC-STBG | 9S3775 | 287 | 149 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 1889 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | MO 114 E | 9S3775 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Union Pacific Railroad. Project involves bridge K0032. | Adv. CN | 3016 | 754 | 0 | 4310 | 0 | AC-STBG | 9S3726 | 515 | 460 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 3310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | US 60 E | SE0063 | 6.937 | 13.874 | 0 | N |  | Pavement preservation treatment on eastbound lane from Rte. F to Rte. 25. | Federal | 3071 | 768 | 0 | 3861 | 0 | NHPP |  | 22 | 30 | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | MO 91 S | 9S3824 | 6.59 | 13.18 | 1 | N |  | Pavement resurfacing from Rte. 25 to Rte. P. Project involves bridge A2214. | Adv. CN | 752 | 188 | 0 | 965 | 0 | AC-STBG |  | 25 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 859 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | RT AB E | SE0093 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 24. Project involves bridge N0380. | Adv. CN | 2020 | 505 | 0 | 2636 | 0 | AC-STBG |  | 111 | 50 | 224 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 2243 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | RT AB W | SE0340 | 11.596 | 23.192 | 0 | N |  | Pavement preservation treatment from Rte. 25 to Rte. Y. | Federal | 0 | 530 | 0 | 530 | 0 | STATE |  | 0 | 5 | 5 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | RT F S | SE0372 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Delaware Creek. Project involves bridge T0435. | Federal | 982 | 245 | 0 | 1227 | 0 | NHPP |  | 0 | 10 | 10 | 20 | 40 | 160 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 986 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | RT J E | SE0097 | 19.093 | 38.186 | 0 | N |  | Pavement resurfacing from Rte. T to Rte. 25. | Adv. CN | 1785 | 446 | 0 | 2254 | 0 | AC-STBG |  | 23 | 30 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2001 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | RT J E | SE0371 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Creek. Project involves bridge T0136. | Federal | 777 | 194 | 0 | 971 | 0 | NHPP |  | 0 | 10 | 10 | 20 | 20 | 140 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 770 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | RT N S | SE0307 | 15.103 | 30.206 | 0 | N |  | Pavement preservation treatment from Rte. 91 to Rte. 60. | Adv. CN | 536 | 134 | 0 | 675 | 0 | AC-STBG |  | 5 | 10 | 51 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 609 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | RT O W | SE0339 | 7.068 | 14.136 | 0 | N |  | Pavement preservation treatment from Rte. 25 to Rte. P. | Adv. CN | 294 | 73 | 0 | 367 | 0 | AC-STBG |  | 0 | 5 | 5 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | RT PP E | SE0125 | 10.034 | 20.068 | 1 | N |  | Pavement resurfacing from Rte. 51 to Rte. M. Project involves bridge B0543. | Adv. CN | 1162 | 291 | 0 | 1474 | 0 | AC-STBG |  | 21 | 5 | 5 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1320 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | RT T S | SE0309 | 19.549 | 39.098 | 0 | N |  | Pavement preservation treatment from Rte. 51 to Rte. 60. | Adv. CN | 828 | 207 | 0 | 1040 | 0 | AC-STBG |  | 5 | 10 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | RT W E | SE0124 | 8.732 | 17.464 | 1 | N |  | Pavement resurfacing from Rte. Z to Rte. 61. Project involves bridge A0158. | Adv. CN | 1202 | 301 | 0 | 1513 | 0 | AC-STBG |  | 10 | 20 | 123 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | RT Y E | SE0199 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 30. Project involves bridge X0829. | Federal | 969 | 242 | 0 | 1231 | 0 | NHPP |  | 20 | 10 | 20 | 20 | 150 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 978 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | RT Y E | SE0203 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 24. Project involves bridge X0830. | Federal | 1050 | 263 | 0 | 1323 | 0 | NHPP |  | 10 | 10 | 20 | 30 | 160 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 1060 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | RT Y E | SE0204 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 34. Project involves bridge X0832. | Federal | 1057 | 264 | 0 | 1336 | 0 | NHPP |  | 15 | 10 | 20 | 40 | 190 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 1028 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | RT Y E | SE0205 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 35. Project involves bridge X0833. | Federal | 1018 | 255 | 0 | 1288 | 0 | NHPP |  | 15 | 10 | 20 | 40 | 160 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 1010 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | RT Y E | SE0287 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Drainage Ditch 37. Project involves bridge X0838. | Federal | 1043 | 261 | 0 | 1324 | 0 | NHPP |  | 20 | 20 | 20 | 40 | 180 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 1039 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | RT Z E | SE0357 | 14.561 | 29.122 | 0 | N |  | Pavement resurfacing from Rte. 25 to Rte. W. | Federal | 1750 | 437 | 0 | 2187 | 0 | NHPP |  | 0 | 20 | 20 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1998 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | STODDARD | RT ZZ N | SE0119 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Main Drainage Ditch. Project involves bridge N0899. | Federal | 853 | 213 | 0 | 1189 | 0 | NHPP |  | 123 | 180 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 866 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | TEXAS | MO 137 S | 9S3693 | 23.966 | 47.932 | 0 | N |  | Pavement resurfacing from Rte. 17 to Bus. 63. | Adv. CN | 2463 | 616 | 0 | 3119 | 0 | AC-STBG |  | 40 | 315 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2764 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | TEXAS | MO 17 S | SE0296 | 0.2 | 0.4 | 1 | N |  | Bridge rehabilitation over Jacks Fork River. Project involves bridge A7022. | Federal | 978 | 244 | 0 | 1242 | 0 | NHPP |  | 20 | 5 | 12 | 12 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1065 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | TEXAS | US 60 E | SE0315 | 7.78 | 15.578 | 0 | N |  | Pavement resurfacing in the east bound lane from the north intersection of Rte. 63 to Bus. 63. | Adv. CN | 4683 | 1171 | 0 | 5864 | 0 | AC-STBG | SE0023 | 10 | 200 | 541 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | TEXAS | US 60 W | SE0229 | 0 | 2 | 1 | N |  | Bridge replacement on westbound lanes over Beeler Creek. Project involves bridge H0296. | Federal | 5229 | 1307 | 0 | 6636 | 0 | NHPP |  | 100 | 100 | 200 | 912 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 5309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | TEXAS | US 63 S | 9P3820 | 2.669 | 7.456 | 0 | N |  | Pavement resurfacing from Rte. E to Rte. B. | Federal | 1243 | 311 | 0 | 1612 | 0 | NHPP |  | 58 | 149 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | TEXAS | US 63 S | SE0230 | 1 | 2.321 | 1 | N |  | Bridge replacement over Potters Creek. Project involves bridge K0996. | Federal | 5254 | 1314 | 0 | 6698 | 0 | NHPP |  | 130 | 200 | 400 | 1682 | 0 | 0 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0 | 0 | 4275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | TEXAS | US 63 S | SE0421 | 11.645 | 32.375 | 0 | N |  | Safety improvements from 2.9 miles north of Rte. E to Rte. RA. | Federal | 1442 | 160 | 0 | 1602 | 0 | SAFETY |  | 0 | 40 | 80 | 128 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1354 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | TEXAS | RT M S | SE0197 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Roubidoux Creek. Project involves bridge P0222. | Federal | 2024 | 506 | 0 | 2570 | 0 | NHPP |  | 40 | 40 | 40 | 40 | 240 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 2140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | VARIOUS | Various | 5B0800Z | 0 | 0 | 1 | N |  | Payback beginning in SFY 2008 for Safe and Sound bridges in the Southeast District. | Federal | 0 | 30830 | 0 | 119630 | 10,001 - 15,000 | STATE |  | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 88701 | 6166 | 6166 | 6166 | 6166 | 6166
7 | VARIOUS | Various | SE0196 |  |  | 0 | Y |  | On-call work zone enforcement at various locations in the Southeast District. | Federal | 37 | 4 | 0 | 43 | 0 | SAFETY |  | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | VARIOUS | Various | SE0208 | 0 | 0 | 0 | Y |  | Job Order Contracting for ADA compliance repairs at various locations in the Southeast District. | Adv. CN | 90 | 22 | 0 | 115 | 0 | AC-STBG |  | 3 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | VARIOUS | Various | SE0209 | 0 | 0 | 0 | Y |  | Job Order Contracting for ADA compliance repairs at various locations in the Southeast District. | Adv. CN | 94 | 23 | 0 | 118 | 0 | AC-STBG |  | 1 | 2 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | VARIOUS | Various | SE0231 | 0 | 0 | 0 | Y |  | Job Order Contracting for concrete pavement repair at various locations on all major highways except interstates in the Southeast District. | Adv. CN | 416 | 104 | 0 | 522 | 0 | AC-STBG |  | 2 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | VARIOUS | Various | SE0249 | 0 | 0 | 0 | Y |  | Job Order Contracting for concrete pavement repair at various locations on all highways except interstates in the Southeast District. | Adv. CN | 429 | 107 | 0 | 537 | 0 | AC-STBG |  | 1 | 1 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | VARIOUS | Various | SE0250 |  |  | 0 | Y |  | Job Order Contracting for erosion control repairs at various locations. | Adv. CN | 448 | 112 | 0 | 580 | 0 | AC-STBG |  | 20 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | VARIOUS | Various | SE0251 |  |  | 0 | Y |  | Job Order Contracting for erosion control repairs at various locations. | Adv. CN | 472 | 118 | 0 | 595 | 0 | AC-STBG |  | 5 | 15 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | VARIOUS | Various | SE0252 | 0 | 0 | 0 | Y |  | Job Order Contracting for guard cable and guardrail repair for St. Francois, Ste. Genevieve, Madison, Perry, Cape Girardeau, Wayne, Bollinger, Stoddard, Scott, Butler, New Madrid, Mississippi, Pemiscot, and Dunklin Counties. | Adv. CN | 1934 | 484 | 0 | 2424 | 0 | AC-STBG |  | 6 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | VARIOUS | Various | SE0253 | 0 | 0 | 0 | Y |  | Job Order Contracting for guard cable and guardrail repair for St. Francois, Ste. Genevieve, Madison, Perry, Cape Girardeau, Wayne, Bollinger, Stoddard, Scott, Butler, New Madrid, Mississippi, Pemiscot, and Dunklin Counties. | Adv. CN | 1992 | 498 | 0 | 2492 | 0 | AC-STBG |  | 2 | 4 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2318 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | VARIOUS | Various | SE0254 | 0 | 0 | 0 | N |  | Job Order Contracting for guard cable and guardrail repair for Wright, Douglas, Ozark, Texas, Howell, Shannon, Reynolds, Iron, Carter, Oregon, and Ripley Counties. | Adv. CN | 430 | 108 | 0 | 539 | 0 | AC-STBG |  | 1 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | VARIOUS | Various | SE0255 | 0 | 0 | 0 | N |  | Job Order Contracting for guard cable and guardrail repair for Wright, Douglas, Ozark, Texas, Howell, Shannon, Reynolds, Iron, Carter, Oregon, and Ripley Counties. | Adv. CN | 442 | 111 | 0 | 554 | 0 | AC-STBG |  | 1 | 1 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | VARIOUS | Various | SE0256 |  |  | 0 | Y |  | On-call work zone enforcement at various locations in the Southeast District. | Federal | 38 | 4 | 0 | 43 | 0 | SAFETY |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | VARIOUS | Various | SE0383 | 0 | 0 | 0 | Y |  | Job Order Contracting for ADA compliance repairs at various locations in the Southeast District. | Adv. CN | 58 | 15 | 0 | 73 | 0 | AC-STBG |  | 0 | 1 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | VARIOUS | Various | SE0388 |  |  | 0 | Y |  | On-call work zone enforcement at various locations in the Southeast District. | Federal | 39 | 4 | 0 | 43 | 0 | SAFETY |  | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | VARIOUS | Various | SE0389 | 0 | 0 | 0 | Y |  | Job Order Contracting for guard cable and guardrail repair for St. Francois, Ste. Genevieve, Madison, Perry, Cape Girardeau, Wayne, Bollinger, Stoddard, Scott, Butler, New Madrid, Mississippi, Pemiscot, and Dunklin Counties. | Adv. CN | 2049 | 512 | 0 | 2561 | 0 | AC-STBG |  | 0 | 2 | 4 | 168 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2387 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | VARIOUS | Various | SE0390 | 0 | 0 | 0 | N |  | Job Order Contracting for guard cable and guardrail repair for Wright, Douglas, Ozark, Texas, Howell, Shannon, Reynolds, Iron, Carter, Oregon, and Ripley Counties. | Adv. CN | 455 | 114 | 0 | 569 | 0 | AC-STBG |  | 0 | 1 | 1 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | VARIOUS | Various | SE0391 | 0 | 0 | 0 | Y |  | Job Order Contracting for concrete pavement repair at various locations on all highways except interstates in the Southeast District. | Adv. CN | 442 | 110 | 0 | 552 | 0 | AC-STBG |  | 0 | 1 | 1 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | VARIOUS | Various | SE0393 |  |  | 0 | Y |  | Job Order Contracting for erosion control repairs at various locations. | Adv. CN | 238 | 60 | 0 | 298 | 0 | AC-STBG |  | 0 | 5 | 5 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | VARIOUS | Various | SE0394 | 0 | 0 | 0 | Y |  | Job Order Contracting to replace signage on major highways in St. Francois, Ste. Genevieve, Madison, Perry, Cape Girardeau, Wayne, Bollinger, Stoddard, Scott, Butler, New Madrid, Mississippi, Pemiscot, and Dunklin Counties. | Federal | 460 | 115 | 0 | 575 | 0 | NHPP |  | 0 | 75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | VARIOUS | Various | SE0396 | 0 | 0 | 0 | Y |  | Job Order Contracting to replace signage on major highways in St. Francois, Ste. Genevieve, Madison, Perry, Cape Girardeau, Wayne, Bollinger, Stoddard, Scott, Butler, New Madrid, Mississippi, Pemiscot, and Dunklin Counties. | Federal | 484 | 121 | 0 | 605 | 0 | NHPP |  | 0 | 5 | 10 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 530 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WAYNE | MO 34 E | SE0049 | 12.245 | 24.49 | 0 | N |  | Pavement resurfacing from Wayne County line to Rte. 49 north. | Federal | 2667 | 667 | 0 | 3368 | 0 | NHPP |  | 34 | 16 | 50 | 264 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WAYNE | MO 34 E | SE0417 | 0.548 | 1.096 | 0 | N |  | Safety improvements from 2.5 miles east of Rte. 67 to 3 miles east of Rte. 67. | Federal | 224 | 25 | 0 | 249 | 0 | SAFETY |  | 0 | 5 | 5 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WAYNE | US 67 S | 9P3822 | 7.42 | 29.04 | 0 | N |  | Pavement preservation treatment in the southbound lane from 0.2 mile south of Rte. A to 0.9 mile north of Rte. F, from 0.4 mile north of Rte. 49 to 0.3 mile south of County Road 521, and in the northbound lane from 0.7 mile north of Rte. 172 to 0.2 mile south of Rte. F. | Federal | 5316 | 1329 | 0 | 6748 | 0 | NHPP |  | 103 | 366 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WAYNE | RT A E | 9S3815 | 0.2 | 0.4 | 1 | N |  | Bridge rehabilitation over Otter Creek. Project involves bridge A0518. | Federal | 759 | 190 | 0 | 1047 | 0 | NHPP | SE0147 | 98 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 846 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WAYNE | RT A E | SE0147 | 0.087 | 0.174 | 1 | N |  | Culvert replacement over Small Creek. Project involves culvert S0497. | Adv. CN | 670 | 168 | 0 | 981 | 0 | AC-STBG | 9S3815 | 143 | 122 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 710 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WAYNE | RT A E | SE0378 | 0.2 | 0.4 | 1 | N |  | Bridge painting over Otter Creek. Project involves bridge A0518. | Adv. CN | 188 | 47 | 0 | 235 | 0 | AC-STBG |  | 0 | 2 | 2 | 2 | 10 | 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WAYNE | RT B E | SE0341 | 7.599 | 15.198 | 0 | N |  | Pavement preservation treatment from Rte. 34 to Rte. U. | Adv. CN | 366 | 92 | 0 | 458 | 0 | AC-STBG |  | 0 | 10 | 15 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 393 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WAYNE | RT C S | SE0373 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Bear Creek. Project involves bridge X0774. | Federal | 3312 | 828 | 0 | 4140 | 0 | NHPP |  | 0 | 30 | 30 | 60 | 120 | 274 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 3506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WAYNE | RT V E | SE0342 | 12.048 | 24.096 | 0 | N |  | Pavement preservation treatment from Rte. 34 to Rte. A. | Adv. CN | 561 | 140 | 0 | 701 | 0 | AC-STBG |  | 0 | 10 | 20 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 611 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WAYNE | RT Z W | SE0343 | 13.903 | 27.806 | 0 | N |  | Pavemenet preservation treatment from Rte. D to Rte. P. | Adv. CN | 645 | 161 | 0 | 806 | 0 | AC-STBG |  | 0 | 20 | 20 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 701 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WRIGHT | MO 38 E | SE0237 | 0.2 | 0.4 | 1 | N |  | Bridge improvement over Whetstone Creek. Project involves bridge A2360. | Federal | 1406 | 351 | 0 | 1772 | 0 | NHPP | CD0217 | 15 | 10 | 30 | 191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WRIGHT | MO 5 S | SE0291 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over BNSF Railway. Project involves bridge A0327. | Federal | 1989 | 497 | 0 | 2506 | 0 | NHPP |  | 20 | 20 | 40 | 45 | 215 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 2138 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WRIGHT | MO 5 S | SE0292 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Woods Fork. Project involves bridge J0754. | Federal | 3494 | 874 | 0 | 4428 | 0 | NHPP |  | 60 | 60 | 60 | 70 | 390 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 3736 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WRIGHT | BU 60 W | SE0377 | 0.1 | 0.2 | 1 | N |  | Bridge rehabilitation over Rte. 60. Project involves bridge A3835. | Adv. CN | 2293 | 573 | 0 | 2866 | 0 | AC-STBG |  | 0 | 1 | 2 | 9 | 23 | 332 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2498 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WRIGHT | US 60 E | SE0023 | 20.001 | 40.305 | 1 | N |  | Pavement and bridge resurfacing on the eastbound lane east of Rte. C to east of Cabool. Project involves bridge A2647. | Federal | 6870 | 1718 | 0 | 8670 | 0 | NHPP | SE0315 | 82 | 55 | 824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7709 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WRIGHT | US 60 W | SE0024 | 23.619 | 47.238 | 0 | N |  | Pavement resurfacing on the westbound lane from Rte. 95 to Webster County line. | Federal | 9130 | 2283 | 0 | 11517 | 0 | NHPP |  | 104 | 65 | 86 | 988 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WRIGHT | MO 95 S | SE0145 | 1.622 | 3.488 | 1 | N |  | Add intersection turn lanes and improvements. Project involves bridge A3457. | Adv. CN | 12937 | 3234 | 0 | 17270 | 0 | AC-STBG |  | 1099 | 200 | 1250 | 0 | 0 | 0 | 0 | 2874 | 0 | 0 | 0 | 0 | 0 | 0 | 11847 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WRIGHT | RT AM E | SE0312 | 4.037 | 8.074 | 0 | N |  | Pavement preservation treatment from Rte. 95 to the end of state maintenance. | Federal | 0 | 213 | 0 | 218 | 0 | STATE |  | 5 | 10 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WRIGHT | RT C S | SE0313 | 17.376 | 34.752 | 0 | N |  | Pavement preservation treatment from Rte. 60 to Rte. 14. | Adv. CN | 602 | 151 | 0 | 758 | 0 | AC-STBG |  | 5 | 10 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 678 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WRIGHT | RT N E | SE0374 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over Whetstone Creek. Project involves bridge A1974. | Federal | 3514 | 879 | 0 | 4393 | 0 | NHPP |  | 0 | 50 | 50 | 100 | 150 | 638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3405 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | WRIGHT | RT U S | 9S3818 | 0.2 | 0.4 | 1 | N |  | Bridge replacement over BNSF Railway. Project involves bridge H0290. | Adv. CN | 2120 | 530 | 0 | 2954 | 0 | AC-STBG | 9S3801 | 304 | 332 | 0 | 0 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 2296 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | VARIOUS | VARIOUS | ST0140B |  |  | 0 | N |  | Guardrail improvements at various locations in the rural Kansas City District. $1,423,000 private entity funds. | Federal | 108 | 0 | 1423 | 1581 | 0 | SAFETY |  | 50 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1423 | 0 | 0 | 0 | 0 | 0 | 1423 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | VARIOUS | Various | ST0141 |  |  | 0 | Y |  | Guardrail improvements at various locations in the southern portion of Central District. $1,148,000 Private Entity Funds | Federal | 0 | 353 | 1148 | 1510 | 0 | STATE |  | 9 | 353 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1148 | 0 | 0 | 0 | 0 | 0 | 1148 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | VARIOUS | Various | ST0141B |  |  | 0 | Y |  | Guardrail improvements at various locations in the northern portion of Central District. $1,506,000 Private Entity Funds | Federal | 0 | 475 | 1506 | 1981 | 0 | STATE |  | 0 | 475 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1506 | 0 | 0 | 0 | 0 | 0 | 1506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | VARIOUS | Various | ST0144 |  |  | 1 | Y |  | Guardrail improvements at various locations in the Southeast District in Bollinger, Cape Girardeau, Iron, Madison, Mississippi, New Madrid, Perry, St. Francois, Ste. Genevieve, and Scott Counties. $ 182,000 private entity funds. | Federal | 0 | 2512 | 182 | 2701 | 0 | STATE |  | 7 | 215 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2479 | 0 | 0 | 0 | 0 | 0 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | VARIOUS | Various | ST0144B |  |  | 1 | N |  | Guardrail improvements at various locations in the Southeast District in Butler, Carter, Douglas, Dunklin, Howell, Oregon, Ozark, Pemiscot, Reynolds, Ripley, Shannon, Stoddard, Texas, Wayne, and Wright Counties. $172,000 private entity funds. | Federal | 0 | 2328 | 172 | 2503 | 0 | STATE |  | 3 | 203 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2297 | 0 | 0 | 0 | 0 | 0 | 172 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | VARIOUS | Various | ST0177 |  |  | 0 | N |  | Safety Circuit Rider statewide liaison for state fiscal year 2027. | Federal | 63 | 7 | 0 | 70 | 0 | SAFETY |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | VARIOUS | Various | ST0140 |  |  | 0 | Y |  | Guardrail improvements at various locations in the Kansas City District Urban Area. $1,744,000 private entity funds. | Federal | 0 | 125 | 1744 | 1924 | 0 | STATE |  | 55 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1744 | 0 | 0 | 0 | 0 | 0 | 1744 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | VARIOUS | Various | ST0142 |  |  | 0 | Y | 7565K-27 | Guardrail improvements at various locations in the St. Louis District. $2,550,000 private entity funds. | Federal | 0 | 225 | 2550 | 2785 | 0 | STATE |  | 10 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2550 | 0 | 0 | 0 | 0 | 0 | 2550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
99 | CALLAWAY | IS 70 E | ST0018 | 45.378 | 188.935 | 2 | N |  | Safety and capacity improvements from Kingdom City to Warrenton. Design-Build project. Project involves bridges A0096 and A0865. | Federal | 0 | 569893 | 0 | 580393 | 0 | STATE |  | 10500 | 5300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 564593 | 0 | 0 | 0 | 0 | 10500 | 547047 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | LAFAYETTE | IS 70 E | ST0016 | 13.5 | 55.066 | 0 | N |  | Safety and capacity improvements from Rte. H east of Odessa to Concordia. | Federal | 0 | 153650 | 0 | 163000 | 0 | STATE |  | 9350 | 4550 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 149000 | 0 | 0 | 0 | 0 | 9350 | 153650 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | LAFAYETTE | IS 70 E | ST0016C | 42.689 | 173.581 | 1 | N |  | Safety and capacity improvements from Concordia to Boonville. Design-Build project. Project involves bridge L0945. $1,087,200 Congressionally Directed Spending Demo ID MO261. | Federal | 0 | 563668 | 0 | 565918 | 0 | STATE |  | 2250 | 8750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 554918 | 0 | 0 | 0 | 0 | 2250 | 555368 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | VARIOUS | IS 70 | ST0137 |  |  | 0 | Y |  | Solar panel installation at various locations. $9,571,000 other funds. | Federal | 9539 | 2385 | 0 | 13429 | 0 | OTHER |  | 1505 | 10 | 20 | 115 | 250 | 757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10772 | [5 empty] | 9571 | 0 | 0 | 0 | 0 | 0 | 0
99 | VARIOUS | IS 70 | ST0151 |  |  | 0 | Y |  | Scoping for traffic and safety management improvements related to traffic incident management, emergency response enhancements, work zone speed safety management, and data driven analysis for Improve I-70. $6,911,850 Infrastructure for Rebuilding America Grant. | Federal | 6912 | 0 | 0 | 5989 | 0 | OTHER |  | 2300 | 922 | 922 | 922 | 923 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2300 | 922 | 922 | 922 | 923 |  | 0 | 0 | 0 | 0 | 0 | 0
99 | BENTON | US 65 S | ST0093 | 45.073 | 92.363 | 0 | N |  | Add passing lanes at various locations from Warsaw to Buffalo. | Federal | 0 | 37162 | 0 | 38000 | 0 | STATE | SR0109 | 838 | 5274 | 0 | 0 | 0 | 0 | 0 | 9289 | 0 | 0 | 0 | 0 | 0 | 22599 | 0 | 0 | 0 | 0 | 838 | 37104 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | BOONE | US 63 S | ST0092 | 1.306 | 3.41 | 0 | Y | 2025-11 | Roadway improvements in Columbia. $4,200,000 SFY 2025 General Revenue. | Federal | 0 | 4495 | 0 | 4501 | 0 | STATE |  | 6 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4200 | 0 | 0 | 0 | 0 |  | 4200 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | BUTLER | US 67 S | ST0062 | 7.695 | 15.39 | 0 | N |  | Roadway improvements from County Road 352 to Arkansas State line. | Federal | 0 | 43865 | 7850 | 56717 | 0 | STATE |  | 2 | 4201 | 0 | 0 | 0 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 47514 | 0 | 0 | 0 | 0 | 5000 | 47514 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | CLINTON | RT BB S | ST0081 | 0.259 | 0.518 | 0 | N |  | Scoping and enginering study over I-35 in Cameron. | Federal | 0 | 10 | 0 | 1010 | 0 | STATE |  | 1000 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
99 | LACLEDE | IS 44 W | ST0119 | 4.681 | 9.606 | 0 | N |  | Rebuild pavement and resurfacing 3.7 miles west of Rte. 133 to 2.1 miles east of Rte. F. | Federal | 0 | 51709 | 0 | 52206 | 0 | STATE | CD0270 CD0343 CD0344 | 497 | 7084 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44625 | 0 | 0 | 0 | 0 |  | 44625 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | NEWTON | IS 44 E | ST0089B | 1.877 | 8.04 | 0 | Y |  | Add lanes from Rte. 43 (Main Street) to Loop 49 (Rangeline Road) in Joplin. | Federal | 0 | 23581 | 0 | 25141 | 0 | STATE |  | 1560 | 2560 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 21016 | 0 | 0 | 0 | 0 |  | 21021 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | PHELPS | IS 44 E | ST0122 | 0.636 | 1.947 | 0 | N |  | Capacity and safety improvements at Rte. V in Rolla. Potential Design-Build project. | Federal | 0 | 17806 | 0 | 17812 | 0 | STATE |  | 6 | 1166 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 16635 | 0 | 0 | 0 | 0 |  | 16640 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | PHELPS | IS 44 E | ST0123 | 0.377 | 1.516 | 0 | N |  | Capacity and safety improvements at Rte. 68 in St. James. Potential Design-Build project. | Federal | 0 | 3950 | 0 | 4501 | 0 | STATE |  | 551 | 461 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 3289 | 0 | 0 | 0 | 0 |  | 3489 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | PHELPS | IS 44 W | ST0121 | 10.4 | 24.445 | 0 | N |  | Rebuild pavement on westbound lanes from east of Rte. 63 to Sugar Tree Road. Potential Design-Build project. | Federal | 0 | 54719 | 0 | 55595 | 0 | STATE |  | 876 | 3074 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51645 | 0 | 0 | 0 | 0 |  | 51645 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | CASS | IS 49 S | ST0091 | 0.83 | 3.745 | 1 | Y |  | Interchange and roadway improvements at Rte. 58 in Belton. Project involves bridge A2094. | Federal | 0 | 23851 | 0 | 24851 | 0 | STATE | 4I3494 KU0028 | 1000 | 1250 | 2601 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20000 | 0 | 0 | 0 |  |  | 20000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | CLAY | IS 35 N | ST0094 | 1.308 | 5.523 | 0 | Y |  | Rebuild pavement from North Antioch Road to Northeast Parvin Road and on I-29 from Northeast Parvin Road to North Davidson Road. | Federal | 0 | 32646 | 0 | 34896 | 0 | STATE | KU0025 KU0061 | 2250 | 500 | 2146 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30000 | 0 | 0 | 0 |  |  | 30000 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | FRANKLIN | IS 44 E | ST0115 | 0.481 | 2.146 | 0 | Y | 7380A-25 | Interchange and pavement improvements at Rte. 50. Design-Build project. | Federal | 0 | 63295 | 0 | 65300 | 0 | STATE |  | 2005 | 5075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 58220 | 0 | 0 | 0 | 0 |  | 58220 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | ST. LOUIS | IS 44 E | ST0117 | 7.937 | 49.904 | 0 | Y | 7380B-25 | Pavement resurfacing, pavement repair, pavement rebuild and median barrier replacement from Rte. 109 to Rte. 141, and upgrade signage at Antire Hill. | Federal | 0 | 44446 | 0 | 48481 | 0 | STATE | SL0277 | 4035 | 3375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41071 | 0 | 0 | 0 | 0 | 530 | 40320 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | CAMDEN | US 54 E | ST0156 | 4.109 | 11.816 | 0 | N |  | Intersection improvements at Rte. 54 and Rte. 5. Funding currently restricted. Contingent upon release of funds. | Federal | 0 | 4000 | 0 | 4000 | 0 | STATE |  | 0 | 944 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 2856 | 0 | 0 | 0 | 0 |  | 4000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | JASPER | RT N E | ST0083 | 9.993 | 19.986 | 0 | N |  | Road improvements on Baseline Road. Funding currently restricted. Contingent upon release of funds. | Federal | 0 | 2697 | 0 | 2697 | 0 | STATE |  | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 1997 | 0 | 0 | 0 | 0 |  | 2197 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | LEWIS | CRD 524 (250TH ST) E | ST0064 | 1.395 | 2.79 | 0 | N |  | Pavement resurfacing on 250th Street and Heritage Avenue near Highland High School in Lewis County. $2,366,000 Lewis County funds. Funding currently restricted. Contingent upon release of funds. | Federal | 0 | 2493 | 2047 | 4742 | 0 | STATE |  | 202 | 298 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 4240 | 0 | 0 | 0 | 0 | 490 | 4242 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | NEW MADRID | US 60 E | ST0160 | 0.589 | 2.176 | 0 | N |  | Add roundabouts and connections for future outer road and on and off ramps at the intersection of Ingram Road. Funding currently restricted. Contingent upon release of funds. | Federal | 0 | 5000 | 0 | 5000 | 0 | STATE |  | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 4350 | 0 | 0 | 0 | 0 |  | 5000 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | NEWTON | IS 44 W | ST0157 | 2.481 | 2.481 | 0 | Y |  | Add westbound climbing lane at Rte. 43. Funding currently restricted. Contingent upon release of funds. | Federal | 0 | 11915 | 0 | 11915 | 0 | STATE |  | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9915 | 0 | 0 | 0 | 0 |  | 11915 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | RANDOLPH | BU 63 S | ST0155 | 1.564 | 3.128 | 0 | N |  | Intersection improvements between East Burkhart Street and Rte. M in Moberly. Funding currently restricted. Contingent upon release of funds. | Federal | 0 | 1900 | 0 | 2100 | 0 | STATE |  | 200 | 152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1748 | 0 | 0 | 0 | 0 | 200 | 1900 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
99 | PLATTE | CST NW LP COOKINGHAM DR W | ST0159 | 0.388 | 1.846 | 0 | Y |  | Payment to Ambassador Building Community Improvement District to add roundabouts at I-29. $4,500,000 General Revenue funds. | Federal | 0 | 4500 | 0 | 4500 | 0 | STATE |  | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4498 | 0 | 0 | 0 | 0 |  | 4500 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0